|  |  |  |
| --- | --- | --- |
| **Type of Meeting: Videoconference** | | **Subject:** Item L.8.7 **of Appendix L to the Contract** |
| **Meeting secretary:-** | | **Meeting Head: Mr. Alidadi** |
| **Attachment: ✓ No ❒ Yes (…. Pages)** | **Date:02.09.2020** | **Code:** |
| **Location: NPPD Office** | **Finish time: 14:00** | **Start time: 10:30** |
|  | | **Participants:** |
| **The Principal: Mr. Alidadi, Mr. Safarpour, Mr. Zandbasiri**  **The Consulting: Mr. Laloei**  **The Contractor: Mr. Fadeev, Ms. Kozhina, Ms. Mitina, Mr. Shapkin, Ms. Buguorskaya** | | |

|  |  |  |
| --- | --- | --- |
| **Proposed by** | **Discussed issues** | **No.** |
| Principal (through letter No. 4300-99136046 dated 18.08.2020) | Process of implementation of Item L.8.7 of Appendix L | 1 |

|  |  |  |  |
| --- | --- | --- | --- |
| Responsible | Deadline | Decision made | No. |
| The Parties agreed on the execution of a.m. subject as followings: | | | |
| The Contractor | 30.09.2020 | ~~Scope of item L.8.7: For the Principal’s consideration, the Contractor will submit its opinions related to supplies and services for which the provisions of item L.8.7 shall be fulfilled.~~  پیشنهاد مشاور:  In order to fulfilment item L.8.7 of Appendix L by the Parties, the Contractor shall firstly send for the Principal’s consideration, respective list (specification) of main or important equipment/ components related to supplies or services for which are effective for safety and availability of the Units.  Based on the approved list (specification), the Contractor shall obtain the Principal’s approval prior the conclude the sub-contracts for these supplies and services. | 1 |
| The Contractor | - | ~~List of the information and documents which shall be submitted with Contractor’s letter via the Contractor on request for approval of proposed sub-contractors:~~  پیشنهاد مشاور:  In order to approval of the proposed sub-contractors by the Principal, the Contractor shall provide and submit to the Principal, the following documents:   * All documentation ~~in~~ based on Attachment L.J to Appendix L for which have not been ~~submitted~~ provided by the Contractor, previously. * To fulfil required document for which their comments have been issued by the Principal. Or, a.m. document based on Att.L.J have not been completed. * Also the Contractor ~~should do~~ shall consider its contractual obligations according to item 5.4 of the Contract.   Note: For Iranian companies and manufacturers which have already been ~~approved~~ audited and provided technical decisions by LJWG group, the respective decisions ~~of LJWG on agreement regarding the relevant company~~ shall ~~delivered~~ be submitted by the Contractor to the Principal. Therefore, the submission of information based of Attachment L.J to Appendix L is not mandatory for such companies. | 2 |
| The Principal | 15 days | ~~Responding the Contractor’s official request~~  By 15 calendar days, the Principal shall reply its opinion on sub-contractors document received via the Contractor. | 4 |
| The Contractor | 10 days | ~~The removing of the Principal’s probable comments and official submission of the modified request to the Principal.~~  After receiving the Principal's comments, the Contractor shall modify and complete a.m. document by 10 calendar days. | 5 |
| The Principal | 7 days | ~~Declaring its final opinion.~~  Finally, the Principal will issue its opinion on sub-contractors by 7 calendar days and inform the Contractor. | 6 |

|  |  |  |
| --- | --- | --- |
| **The Principal** | **The Consultant** | **The Contractor** |