## PCMFExport
IRA/2/011: Action Plan for Implementation of | [7 empty] | 2014-02-14
Workplan activities in 2012-2013 |  | and 2014-2015
Activity | Implementing Officers/ Input | Venue | Type | Funding | Budget | Budget Year | Date | Comments
1.1 Safety Training through a Visit to an Incident Emergency Center | IAEA: Lipar, NPPD: Abbaspour | [6 empty] | BNPP-1 requested to be replaced with SVs on operation, RP, technical support and emergency preprdness.
| 1.1.1-1.1.5 SV1-5 for one week | TBD | 5 SVs | FootNote | 3,095 | 2012 | TBD | Pending. Final decision at the Annual Meeting in March 2014
1.2 Training to strengthen the capability of BNPP personnel on routine Core analysis for safe operation. | IAEA: Poulat, NPPD: Abbaspour | [6 empty] | Expectations provided
| 1.2.1 One week EM with 1 Agency Expert and 2 External Experts | Bushehr | EM | HardCore | 15,678 | 2012 | Nov. 2013 | Postponed to 27-30 April 2014
1.5 Training to assist BNPP-1 security procedures including operation of physical protection system | IAEA: Ubeev, NPPD: Amini
| 1.5.1 One week Meeting with 1 Agency Expert and 3 External Experts | Bushehr | WS | FootNote | 21,800 | 2012 | 1-4 Dec 2013 | Completed
1.6 Evaluation of BNPP-1 physical protection system effectiveness | IAEA: Ubeev, NPPD: Amini
| 1.6.1 One week Meeting with 1 Agency Expert and 3 External Experts | Bushehr | WS | FootNote | 21,800 | 2012 | 18-21 Aug. 2013 | Completed
1.10 Workshop in security procedures at utility level | IAEA: Ubeev, NPPD: Amini | [6 empty] | Security procedures incorporated in 1.5.
| 1.10.1 Enhancement of BNPP-1 Nuclear Safety and Security Synergy (1 IAEA staff and 2 EX) | Bushehr | WS | HardCore | 13,065 | 2012 | 18-22 May 2014 | Focus changed on the BNPP-1 request
| 1.10.2 Strengthening Nuclear Security Culture (1 IAEA + 2 EX) | Bushehr | WS |  |  |  | 24-26 Nov.2014 | Focus changed on the BNPP-1 request
1.22 WWER core management calculations for safe operation of BNPP-1 | IAEA: M. Lipar, NPPD: Sheikholeslami/Ghods | [6 empty] | Topic refocusssed on the request
| 1.22.1 1 2 Agency Expert and 2 External Experts | Tehran | WS | HardCore | 16,780 | 2012 | Sept/Oct 2014
1.23 Thermal-hydraulics analysis for safe operation of BNPP-1 | IAEA: M. Lipar, NPPD: Sheikholeslami/Ghods | [6 empty] | Topic refocusssed on the request
| 1.23.1 2 Agency Expert and 2 External Experts | Tehran | WS | FootNote | 13,065 | 2012 | Q1/2015
3.1 Training on outage management with focus on organization, implementation and supporting. | IAEA: Kang/Shouler, BNPP-1: Banazadeh/Deylami/Roshankar
| 3.1.1 one week WS with 1 Agency Expert and 2 External Experts | Paks NPP | WS | FootNote | 21,000 | 2012 | 27-30 Nov.2012 | Completed
| 3.1.2 To support development of statement of Work (SoW) to comuterize BNPP-1 outage management activities with focus on safety aspects (one wek EM with1 IAEA staff and 2 IEX) | TBD | EM |  |  |  | Q3/2014 | Requested follow-up assistance
3.5 To strengthen the capability of BNPP personnel in establishment of Safety Performance Indicators in compliance with the latest IAEA guidance and best world practices. | IAEA: Yllera, Mandula; BNPP-1: Deylami
| 3.5.1 one week WS with 1 Agency Expert and 3 External Experts practices. | Bushehr | WS | FootNote | 21,800 | 2012 | 1-5 Dec.2012 | Completed
3.7 Modern methods of maintenance and repair of rotating/turbomachinery equipment | IAEA: Kang/Eiler/Mandula; BNPP-1: Roshankar/Deylami | [6 empty] | The title changed on the request of BNPP-1.
| 3.7.1 One week WS with 1 IAEA and 5 national experts (NEX) | Hungary, Paks | WS | HardCore | 13,065 | 2012 | 12-15 Nov. 2013 | Completed
| 3.7.2 Training on methods of vibration monitoring of rotating machines including reactor cooling pomp (RCP) and turbogenerator | Hungary, Paks NPP | WS |  |  |  | 30 June-3 July 2014 | Requested follow-up assistance
| 3.7.3 Assistance on computer based management if safety related operational and ispection procedures/documents | TBD | WS/EM |  |  |  | Q4/2014 | Additional (NEW-3) request
5.1 1.5.1 Building in safety requirements/considerations in contractual arrangements between NPPD and BNPP-1 | IAEA: Vincze, NPPD: Tajbakhsh
| 5.1.1 Short EM with 1 Agency Expert , 2 External Experts + 3-4 National Experts | Vienna | HBA +EM | FootNote | 16,350 | 2012 | 3-6 Sept.2012 | Completed
5.2 1.5.2 Building in safety requirements/considerations in contractual arrangements for repair and/or maintenance of BNPP-1 | IAEA: Kang, NPPD: Tajbakhsh
| 5.2.1 One week WS with 1 Agency Expert, 2 External Experts + 4-5 National Experts | Vienna | WS | HardCore | 16,350 | 2012 | 24-26 Feb.2014 | In progress
8.2 Proactive safety management during operation and outage, operational safety indicators | IAEA: Gest, BNPP-1: Abbaspour
| 8.2.1 One week WS with 1 Agency Expert and 2 External Experts | Bushehr | WS | HardCore | 21,000 | 2012 | 25-29 May'13 | Completed
8.3 Enhancement on NPPD safety performance control (oversight) | IAEA: Lipar, NPPD: Sheikholeslami
| 8.3.1 One week Meeting with 1 Agency Expert and 2 External Experts | Tehran | WS | FootNote | 16,350 | 2012 | 3-6 Feb. 2013 | Completed
8.1. Assist NPPD nuclear oversight team to conduct safety oversight activity at BNPP-1 | IAEA: Lipar, NPPD: Sheikholeslami
| 8.1.1 Four days EM with 1 IAEA staff and 1 External Expert) | Tehran and Bushehr | EM |  |  |  | I half of May 2014 | follow-up on 8.3.1
8.4 Maintenance strategy: predictive, preventive maintenance programme development | IAEA: K.S. Kang, BNPP-1: Banazadeh | [6 empty] | Follow-up in 2014 to be considered
| 8.4.1 One week WS with 2-3 External Experts | Vienna | WS | FootNote | 21,000 | 2012 | 3-6 July 2012 | Completed
1.3 Training to strengthen the capability of BNPP Personnel on using the practical application of Living Probabilistic Safety Assessment for safe operation | IAEA: M. Lipar/B. Poulat, NPPD: Abbaspour/Ghods
| 1.3.1 one week TC with 1 Agency Expert + External Experts +5 NEX | Vienna | WS | FootNote | 17,820 | 2013 | 28 Oct -1 Nov 2013 | Completed
| 1.3.2 Asistance in the purchase and application of RISK SPECTRUM software | TBD | TBD |  |  |  | TBD
1.4 Training (Scientific Visits) on methods for reduction of personnel dose during operation, routine maintenance and outage | IAEA: Lipar, BNPP-1: Abbaspour | [6 empty] | BNPP-1 request to refocus on: supervision of operation, technical service, event evaluation, near miss, low level events, etc.
| 1.4.1-1.4.5 SV 1-5 for one week | TBD | 5 SVs | FootNote | 3,155 | 2013 | TBD | Pending. Final decision at the Annual Meeting in March 2014
1.9 Implementation of OSART Mission | IAEA: Lipar, BNPP-1: Derakhshandeh
| 1.9.1 Three weeks Expert Mission with 2 Agency staff and 10 international experts | Busher | EM | HardCore | 83,625 | 2013 | February-March 2015 | To be confirmed
1.11 Preparatory mission for OSART mission | IAEA: Lipar, BNPP-1: Derakhshandeh
| 1.11.1 Three days EM with one Agency staff and tow external experts | Bushehr | EM | HardCore | 8,019 | 2013 | 3-4 Feb.2013 | Completed
1.12 Good practices in implemnentation of stress test in IAEA Member States and identificastion of potential areas for improvement in BNPP-1 | IAEA: Yllera, NPPD: Sheikholeslami
| 1.12.1 One week EM with 1 IAEA staff and 3 external experts | Tehran or Vienna | EM | FootNote | 17,820 | 2013 | 9-13 Dec.2012 | Completed
3.2 To strengthen the capability of BNPP personnel in methods and procedures for Plant life management program. | IAEA: Kang, BNPP-1: Deylami
| 3.2.1 One week WS with 1 IAEA staff + 2 external experts + 4 NEX | Vienna | WS |  |  |  | 22-24 Oct. 2013 | Completed
1.13 To support BNPP-1 Senior Management for assessment and improvement of safety culture in BNPP-1 | IAEA: M. Haage, BNPP-1: Abbaspour
| 1.13.1 One week WS with 1 IAEA and 3 external experts | Busher or Tehran | WS | HardCore | 14,256 | 2013 | 19-21 Aug. 2013 | Completed
1.16 To support NPPD/BNPP-1 in strengthening routine and post accident environmental monitoring | IAEA: Polyakov, NPPD: Sheikoleslami
| 1.16.1 One week WS with1 IAEA staff and 2 external experts | Tehran | WS | FootNote | 13,365 | 2013 | 17-20 Feb.2013 | Completed
2.1 Scientific visit on spare part management including warehouse | IAEA: Kang, BNPP-1: Roshankar
| 2.1.1-2.1.5 SV1-5 for one week | Paks NPP, Hungary | 5 SVs | FootNote | 3,155 | 2013 | 12-15 Nov.2013 | Completed jointly with 3.7
3.3 To strengthen the capability of BNPP personnel in using advanced Ultrasonic Test methods, standards, evaluation and techniques. | IAEA: Kang, BNPP-1: Deylami
| 3.3.1 One EM with 2 External Experts | Bushehr | EM | FootNote | 13,365 | 2013 | 6-8 July 2013 | Completed
| 3.3.2 Training (Fellowships) on advanced non-destructive methods and techniques for enhancement of safety of BNPP-1 reactor equipment (4 FSs for two weeks) | HRID, Croatia | 4 FSs |  |  |  | 2014-04-01 | reguest for follow-up activity
| 3.3.3 Scientific visits on proven methods for safety analysis of BNPP-1 equipment reliability (SV 1-4 for one week) | TBD | SV/or WS in Vienna |  |  |  | Q4/2014 | additional input requested
3.4 To strengthen the capability of BNPP personnel in application of best practices in water chemistry for Primary and Secondary circuit with focus on erosion corrosion. | IAEA: Kim, BNPP-1: Deylami
| 3.4.1 One week EM with and 3 External Experts corrosion. | Bushehr | EM | FootNote | 22,300 | 2013 | 23-26 Nov.2013 | Postponed to 2014
4.1 Assessment of BNPP-1 selected operational training program and procedures, assistance in the development of corrective action plan. | IAEA: Molloy, BNPP-1: Talebianzadeh | [6 empty] | BNPP-1 submitted 2 JTA - comments provided and proposal how to proceed further
| 4.1.1 one week EM with 1 Agency and 2 External Experts | Bushehr | EM+ HBA? | FootNote | 13,365 | 2013 | Q4/2013 | Further assistance in review of selected documents in 2014
6.1 To evaluate BNPP HRM system and to provide recommendations for improvement | IAEA: Molloy, NPPD: Rahnama, BNPP-1: Talebianzadeh | [6 empty] | Link with new-9 for 2014?
| 6.1.1 One week EM with 1 Agency Expert and 2 External Experts | Merge with IRA4038, 4.1 | HBA +EM | FootNote | 13,365 | 2013 | 2014-04-01 | Seif-assessment by December 2013
additional requested input | 6.1.2 Assistance to enhance performance of BNPP-1 Psychlogical Laboratory | Vienna | HBA + CM |  |  |  | 2014 | Draft SoW reviewed in 2013. Further assistance to be clarified
6.2 To assist NPPD/BNPP-1 on improvement of knowledge management system | IAEA: Pasztory, NPPD: Rahnama
| 6.2.1 One week EM with 1 Agency Expert and 2 External Experts | Tehran | EM | FootNote | 13,365 | 2013 | 8-10 December 2013 | Completed
7.1 To assist in review of procedure for evaluation and in development of an action plan for modification of BNPP-1 FSS | IAEA: Molloy NPPD: Rahnama | [6 empty] | Link with new-10 in 2014?
| 7.1.1 One week EM with 1 Agency Expert and 3 External Experts | TBD | EM/HBA | FootNote | 17,820 | 2013 | Q4/2015 | BNPP to provide draft report on planned modifications of the training programs, scenarios, procedures, and lessons learned from commissioning
8.5 Radioactive waste management programme improvements | IAEA: Ormai, BNPP-1: Abbaspour
| 8.5.1 One week EM with 1 Agency Expert and 2 External Expert | Bushehr | WS | FootNote | 21,500 | 2013 | 14-18 September 2013 | Completed
8.7 To assist in practical application of technical support of utility/operating organization | IAEA: Kang, NPPD: M. Sheikholeslami | Busher/Tehran WS 4-6 May 2013 Completed
9.1 To support BNPP-1 in the development of the strategy for continuous improvement of the BNPP Training Centre | IAEA: Molloy BNPP-1: Talebianzadeh | In partnership with WANO,
| 9.1.2 EM with I external expert | Balakovo | EM |  |  |  | 2013-05-01 | Completed
| 9.1.1 SV1-5 for one week | Balakovo | 5 SVs | FootNote | 3,155 | 2013 | 20-25 May 2013 | Completed
| 9.1.3 Assistance in T&Q of maintenance personnel using BTC | TBD | TBD |  |  |  | TBD
3.6 Scientific Visit on PSI application and evaluation of PSI | IAEA: Mandula NPPD: Deylami | Czech Republic | SV |  |  |  | 2014 | In progress. Change the venue to the IAEA to be considered
2.2 To strengthen the capability of BNPP in advanced maintenance methods, techniques, materials and tools | IAEA: Kang, BNPP-1: Roshankar
| 2.2.1 One week WS with 1 IAEA staff and 3 IEX | TBD | WS |  |  |  | Q3/2014
| 2.2.2 Training of BNPP-1 personnel on surveillance spesiments management of main safety equipment (one week WS with 1 IAEA staff and 2 IEX) | TBD | WS |  |  |  | Q3-4/2014 | additional input requested
2.3 Scientific visits on outage management with focus on organization, implementation and supporting | IAEA: Kang, BNPP-1: Roshankar
| 2.3.1-5 SV1-5 for one week | TBD | SV |  |  |  | Q3/2014
| 2.3.2 Scientific visits on advanced equipment and techniques for In-Service Inspection (ISI) of BNPP-1 primary circuit equipment (SV 1-4 for one week) | TBD | SV |  |  |  | Q4/2014 | additional input requested
2.4 Introduction of modern methods of outage management | IAEA: Kang/Kilic; BNPP-1: Roshankar/Deylami
| 2.4.1 One week EM with 1 IAEA staff and 3 IEX | TBD | EM |  |  |  | Q3/2014
| 2.4.2 To support development of statement of Work (SoW) to comuterize BNPP-1 outage management activities with focus on safety aspects (one wek EM with 1 IAEA staff and 2 IEX) | TBD | EM |  |  |  | Q4/2014 | additional input requested
1.21 Scientific visits on safety management systems with focus on radioactive waste management, radiation monitoring, core calculation and emergency preparedness | IAEA: Lipar, BNPP-1: Abbaspour
| 1.21.1-5 SV1-5 for one week | TBD | SV |  |  |  | Q4/2014
1.18 To support NPPD/BNPP-1 in enhancement of on-site and of-site emergency preparedness and response | IAEA: Lipar, BNPP-1: Abbaspour
| 1.18.1 One week EM with 1 IAEA staff and 3 IEX | TBD | EM |  |  |  | Q3/2015
1.17 To advice BNPP-1 on proven approaches in radioactive waste management | IAEA: Ormai and Lipar, BNPP-1: Abbaspour
| 1.17.1 To strengthen BNPP-1 capability on practical experience in decontamination related activties (one week EM with 2 IAEA staff and 2 IEX) | Bushehr | EM |  |  |  | Q4/2014 | focus changed on the BNPP-1 request
1.20 Assistance in organization of BNPP emergency repairs team | IAEA: Lipar/Vincze; NPPD/BNPP: Roshankar | [6 empty] | focus changed on the BNPP-1 request
| 1.20.1 One week WS with 2 IAEA staff + 2 IEX | TBD | TBD |  |  |  | TBD | focus changed on the BNPP-1 request
1.8 Advanced training on effective nuclear accountancy and control (STAR software) | IAEA: Lipar, NPPD: Amini
| 1.8.1 One week training by software developer | Tehran | EM |  |  |  | Q1/2014 | In progress
Legend:
New request - needs confirmation
Needs further clarification
Completed