## Лист1
Sсhedule-report of equipment localization for 2019 year
Performed
Control points
Not manufactures in accordance with LJWG Decision
[12 empty] | No answer |  |  |  | Stage 1 | [22 empty] | Stage 2
№ | Name of procurement task | Safety class | HLC availability LTSD | Дата начала работ по локализации (УЛиТП) |  | Дата направления проектной потребности (по аналогу) Заказчику (УЛиТП) |  | Дата проведения аудитов (УЛиТП) |  | Дата передачи информации о локализации в УК (УЛиТП) |  | Date of PT submission | Date of PT submission (PPD-SIO) | Number of PT | Name of PT | Results of localization/ Number of LJWG decision | Submission of specification+ITR to the Primcipal Responsible |  |  | Technical proposal from IPM |  |  | Submission of technical proposal of IPM to PD |  |  | Submisson of PD comments to the Primcipal |  |  | Submission of PD conclusion to the Principal |  |  | Received technical proposals | Determination of names of local manufacturers ready to participate in the competition |  |  | Date | Lot number | Name of lot | Notes
|  |  |  | План | Факт | План | Факт | План | Факт | План | Факт | [5 empty] | Plan | Fact | Document | Plan | Fact | Document | Plan | Fact | Document | Plan | Fact | Document | Plan | Fact | Document |  | Plan | Fact | Name
2 | Supply of turbine hall crane 220+220/32 t, 32/5 t and 15 t | 4 | no | 2018-06-17 | выполнено | 2018-07-07 | выполнено | 2018-08-16 | выполнено | 2018-09-15 | выполнено | 2018-09-15 | 2018-02-16 | ЗЗ-Бшр2-П-012-2016 | Supply of turbine hall crane 220+220/32 t, 32/5 t and 15 t | BU2-LJWG-2018-04-85-89 | 2018-09-30 | 2019-01-31 | BU2-ASEM-NPPD-PSE-007/ULTP/00057 | 2018-11-09 | 2019-03-13 | 1000-250597 | 2018-11-19 | 2019-03-13 | 40-304-2/21152-ВК | 2018-12-04 | 2019-03-19 | 40-40-2/22945-ВК | 2018-12-14 | 2019-03-27 | BU2-ASEM-NPPD-PSE-007/ULTP/00083 | Firouza | 2018-12-24 | 2018-12-13 | 1 Firouza Engineering Co. - NDA подписан 02.04.19 2 Farabar Sanate Vazin Co. - офиц отказ (10.04.19) 3 Iran Sakht Ind. Co. - NDA подписан 09.04.19 4 Telfer - офиц отказ (07.04.19) 5 Fassan Cranes - офиц отказ (07.04.19) | 2019-01-31 | 9358/54 | Supply of turbine hall crane 220+220/32 t, 32/5 t and 15 t | Tender is completed
9 | Inverters and rectifiers | 4 | no | 2018-06-26 | выполнено | 2018-07-16 | выполнено | 2018-08-25 | выполнено | 2018-09-24 | выполнено | 2018-09-24 | 2018-09-24 | ЗЗ-Бшр2-2-П-094-2017 | Inverters and rectifiers | BU2-LJWG-2018-02-D049-51 | 2018-10-09 | 2018-09-28 | BU2-ASEM-NPPD-PSE-007/ULTP/00021 | 2018-11-18 | 2019-03-13 | 10020-249095 | 2018-11-28 | 2019-03-13 | 40-304-2/21154-ВК | 2018-12-13 | 2019-03-26 | 02-47/3272-ВК | 2018-12-23 | completed | BU2-ASEM-NPPD-PSE-007/ULTP/00105 | 1 PSP 2 Borna Electronic 3 Satna 4 Poyeh Electronics | 2019-01-02 | 2019-03-13 | 1 PSP (Tolid Manabe Taghzien Electronic) - NDA подписан 16.04.19 - офиц отказ 18.05.19 2 Borna Electronic - NDA подписан 08.04.19 3 Satna - NDA подписан 13.04.19 4 Porsoo Electronic - офиц отказ (20.04.19) 5 Poyeh Electronics - офиц отказ (17.04.19) | 2019-02-18 | 13996/510 | Inverters and rectifiers | Expertise of participants
17 | Welding equipment | 4 | no | 2017-12-15 | выполнено | 2018-01-04 | выполнено | 2018-02-13 | выполнено | 2018-03-15 | выполнено | 2018-03-15 | 2018-11-23 | ЗЗ-Бшр2-2-П-091/05-2017 | Welding equipment | BU2-LJWG-2018-03-81 | 2018-03-30 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | [13 empty] | 2019-04-22 | 2019-04-22 | 1 Kara Sazeh 2 Mashinsazi Tabriz 3 GAAM Electric Arc | 2019-02-21 | 12375/1086 | Welding equipment | Tender is completed
23 | Static equipment | 4 | no | 2018-07-09 | выполнено | 2018-07-29 | выполнено | 2018-09-07 | выполнено | 2018-10-07 | выполнено | 2018-10-07 | 2018-10-07 | ЗЗ-Бшр2-П-020/08-2018 | Static equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-10-22 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | no | - | - | Mashin sazi Arak Hesar Sanat Arak Asas Sanat Pars - отказ тел. Masnuat Felezi Sangin Azarab | 2019-07-15 | 12375/1024 | Static equipment | Expertise of participants
27 | Plate heatexchangers | 2 | no | 2018-06-14 | выполнено | 2018-07-04 | выполнено | 2018-08-13 | выполнено | 2018-09-12 | выполнено | 2018-09-12 | 2018-09-12 | ЗЗ-Бшр2-П-267/00-2018 | Plate heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-27 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-06 | - | - | 2018-11-16 | - | - | 2018-12-01 | - | - | 2018-12-11 | - | - | no | - | - | Taha Ghaleb Toos Co. | 2019-05-31 | 12375/1264 | Plate heatexchangers | Retender
31 | Supply of pumps КВА, JМN, JND | 2, 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/01-2017 | Supply of pumps КВА, JМN, JND | BU2-LJWG-2017-12-D014-23 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Arya Sepehr Kayhan - Khavar Eng. Co. - Petro Hirad - Pumpiran - Navid Sahand | 2019-02-27 | 12375/895 | Supply of pumps КВА, JМN, JND | Expertise of participants
33 | Evaporator equipment | 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/06-2017 | Evaporator equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman | 2019-03-31 | 12375/923 | Evaporator equipment | Retender
35 | CIE Tanks | 4 | no | 2018-07-19 | выполнено | 2018-08-08 | выполнено | 2018-09-17 | выполнено | 2018-10-17 | выполнено | 2018-10-17 | 2018-10-17 | ЗЗ-Бшр2-П-020/08-2018 | CIE Tanks | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-11-01 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-11 | - | - | 2018-12-21 | - | - | 2019-01-05 | - | - | 2019-01-15 | - | - | no | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman | 2019-03-30 | 12375/936 | CIE Tanks | Retender
36 | CIE Tanks | 2, 3 | no | 2018-07-19 | выполнено | 2018-08-08 | выполнено | 2018-09-17 | выполнено | 2018-10-17 | выполнено | 2018-10-17 | 2018-10-17 | ЗЗ-Бшр2-П-020/08-2018 | CIE Tanks | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-11-01 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-11 | - | - | 2018-12-21 | - | - | 2019-01-05 | - | - | 2019-01-15 | - | - | no | - | - | Azar Ab Ind. Co. - NDA подписан 15.06.19 Machine Sazi Arak Co. | 2019-05-06 | 12375/937 | CIE Tanks | Expertise of participants
37 | Emergency cooling and organized leakage heat exchangers | 2, 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/02-2018 | Emergency cooling and organized leakage heat exchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Azarab Mashin sazi Arak Asas Sanat Pars Atlas Epco Masnuat Felezi Sangin Packman | 2019-03-30 | 12375/942 | Emergency cooling and organized leakage heat exchangers | Tender is completed
39 | Plate heatexchangers | 2, 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/02-2017 | Plate heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Taha Ghaleb Toos Co. - NDA подписан 11.06.19 | 2019-03-31 | 12375/945 | Plate heatexchangers | Expertise of participants
69 | Supply of decontaminating solution pumps | 4 | no | [8 empty] | 2019-09-11 | 2018-09-11 | ЗЗ-Бшр2-П-217/03-2018 | Supply of decontaminating solution pumps | BU2-LJWG-2017-12-D014-23 | 2019-09-26 | 2019-06-21 | BU2-ASEM-NPPD-PSE-007/ULTP/00139 | 2019-11-05 | - | - | 2019-11-15 | - | - | 2019-11-30 | - | - | 2019-12-10 | - | - | - | - | - | Arya Sepehr Kayhan - отказ по тел Khavar Eng. Co. - отказ по тел Petro Hirad Pumpiran Navid Sahand | - | 13996/1417 | Supply of decontaminating solution pumps | Retender
76 | Supply of filters for UKC, UJA building | 2, 3, 4 | no | [8 empty] | 2019-05-11 | 2019-05-11 | ЗЗ-Бшр2-П-020/03-2017 | Supply of filters for UKC, UJA building | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-05-26 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00144 | 2019-07-05 | - | - | 2019-07-15 | - | - | 2019-07-30 | - | - | 2019-08-09 | - | - | - | - | - | 1. PSI (Parsian Sazeh Sepahan) 2. Hesar Sanat Arak 3. Pacman Co 4. Asas Sanat Pars 5. Mashin sazi Arak | 2019-07-09 | 13996/1554 | Fiters | Tender in progress
| Lead stationary batteries | 4 | no | [8 empty] | 2019-02-19 | 2019-02-12 | ЗЗ-Бшр2-П-032/00-2017 | Lead stationary batteries | 4 safety class Manufactured 2,3 Not manufactured BU2/LJWG-2018/11-D119 | 2019-03-06 | 22.02.2019 15.03.2019 | BU2-ASEM-NPPD-PSE-007/ULTP/00063 BU2-ASEM-NPPD-PSE-007/ULTP/00073 | 2019-04-15 | - | - | 2019-04-25 | - | - | 2019-05-10 | - | - | 2019-05-20 | - | - | - | - | - | Sabba Batary (TAVAN ENERGYSOURS DEVELOPMENT COMPANY) | 2019-07-17 | 13996/1602 | Lead stationary batteries | Expertise of participants
81 | Pumps | 2 | no | [8 empty] | 2019-06-11 | 2019-06-11 | ЗЗ-Бшр2-П-217/04-2018 | Pumps | BU2-LJWG-2017-12-D014-23 | 2019-06-26 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00146 | 2019-08-05 | - | - | 2019-08-15 | - | - | 2019-08-30 | - | - | 2019-09-09 | - | - | - | - | - | Arya Sepehr Kaehan Khavar Engeeniring Company Navid Sahand Co Petro Hirad PUMPIRAN |  | 13996/414 | Pumps | Retender
85 | Seal doors | 3, 4 | yes | 2018-11-18 | выполнено | 2018-12-08 | выполнено | 2019-01-17 | выполнено | 2019-02-16 | выполнено | 2019-02-16 | 2019-02-12 | ЗЗ-О53-2-П-452/00-2019 | Seal doors | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | In accordance with the individual HLC schedule | [17 empty] | 1 G.M.P. 2 Parsian Sazeh Sepahan 3 Imen Sakht Pasargad 4 Ganj Cham Arman Co | 2019-06-26 | 13996/1463 | Seal doors | Tender is completed
92 | Boron concentrate, distillate pump | 3 | no | [8 empty] | 2018-09-11 | 2018-09-11 | ЗЗ-Бшр2-П-217/10-2018 | Boron concentrate, distillate pump | BU2-LJWG-2017-12-D014-23 | 2018-09-26 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-05 | - | - | 2018-11-15 | - | - | 2018-11-30 | - | - | 2018-12-10 | - | - | - | - | - | Pumpiran Navid Sahand Iran Industrial Pumps (IIP Co.) - отказ по тел Petro Hirad | не передано | 13996/1416 | Boron concentrate, distillate pump | Retender
| Supply of electric heaters | 3 | no | [8 empty] | 2018-10-17 | 2018-10-17 | ЗЗ-Бшр2-2-П-264/04-2018 | Supply of electric heaters | [19 empty] | Sabalan Gostar Tahvieh Omran Tahvieh Inustrial Co Damavand Air Cond/Co Tahvieh Air Conditioning SARAVEL - отказ по тел. | 2019-07-16 | 13996/140 | Supply of electric heaters | Tender is completed
1 | Stationary lead batteries | 2, 3, 4 | no | 2018-11-21 | выполнено | 2018-12-11 | выполнено | 2019-01-20 | выполнено | 2019-02-19 | выполнено | 2019-02-19 | 2019-02-12 | ЗЗ-Бшр2-П-032/00-2017 | Stationary lead batteries | 4 Производится 2,3 Не производится BU2/LJWG-2018/11-D119 | 2019-03-06 | 22.02.2019 15.03.2019 | BU2-ASEM-NPPD-PSE-007/ULTP/00063 BU2-ASEM-NPPD-PSE-007/ULTP/00073 | 2019-04-15 | - | - | 2019-04-25 | - | - | 2019-05-10 | - | - | 2019-05-20 | - | - | no | 2019-05-30 | 2018-02-01 | Sabba Batary | 2019-07-17 | 13996/337 | Stationary lead batteries | Expertise of participants
77 | Supply of distillate feed pumps | 3 | no | [8 empty] | 2019-06-10 | 2019-06-10 | ЗЗ-Бшр2-П-217/09-2018 | Supply of distillate feed pumps | BU2-LJWG-2017-12-D014-23 | 2019-06-25 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00140 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - | Arya Sepehr Kaehan - отказ по тел Iran Industrial Pump Khavar Engineering Company - отказ по тел Petro Rahan pump Petro Hirad Co | 2019-07-17 | 13996/395 | Supply of distillate feed pumps | Expertise of participants
| Supply of special water treatment system coolers | 3, 4 | no | [8 empty] | 2018-10-18 | 2018-10-18 | ЗЗ-Бшр2-2-П-264/05-2018 | Supply of special water treatment system coolers | [19 empty] | Taha Ghaleb Toos Co. | 2019-07-24 | 13996/367 | Supply of special water treatment system coolers | Retender
52 | Filtering equipment | 4 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/03-2017 | Filtering equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2019-03-05 | BU2-ASEM-NPPD-PSE-007/ULTP/00069 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Machine Sazi Arak Asas sanat Pars Parsian Sazeh Sepahan Packman Hesar Sanat Arak | 2019-02-27 | 13996/648 | Filtering equipment | Tender is completed
| Aerosol filters | 3 | no | [8 empty] | 2018-09-14 | 2018-09-14 | ЗЗ-Бшр2-П-219/05-2018 | Aerosol filters | [19 empty] | Azarab Masmuat Fellezi Sangin (MFS) Pacman Atlas Energy FinRotakSanat Garma gostar Industrie Hesar Sanat Arak Mahdin Industial Company Mobaddel Tank Assa Sanat Pars Mashine Sazi Arak Taha Ghaleb Toos | 2019-07-16 | 13996/1441 | Aerosol filters | Retender
8 | General transformers | 3 | no | 2018-08-25 | выполнено | 2018-09-14 | выполнено | 2018-10-24 | выполнено | 2018-11-23 | выполнено | 2018-11-23 | 2018-11-23 | ЗЗ-Бшр2-2-П-204-00-2018 | General transformers | BU2-LJWG-2017-10-D001-002 | 2018-12-08 | 2018-11-28 | BU2-ASEM-NPPD-PSE-007/ULTP/00035 | 2019-01-17 | 2019-02-10 | 10020-249096 | 2019-01-27 | 2019-03-07 | 40-304-1/19752-ВК | 2019-02-11 | 2019-03-20 | 40-47-2/23648 | 2019-02-21 | 2019-03-22 | BU2-ASEM-NPPD-PSE-007/ULTP/00080 | 1 Iran Transfo | 2019-03-03 | 2017-10-01 | IranTransfo | 2019-05-22 | 13996/1494 | General transformers | Tender in progress
| Vacuum pumps | 3 | no | [8 empty] | 2018-10-01 | 2019-06-03 | ЗЗ-Бшр2-П-217/16-2018 | Vacuum pumps | [19 empty] | Iran Industrial pumps Khavar Navid Sahan Petro Hirad PUMPIRAN | 2019-07-17 | 13996/1732 | Vacuum pumps | Tender is completed
95 | Switchgear 6,6 kV | 2.3 | no | [8 empty] | 2019-01-29 | 2019-01-29 | ЗЗ-Бшр2-2-П-084-2017 | Switchgear 6,6 kV | BU2-LJWG-2018-02-D049-51 | 2019-02-13 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00160 | 2019-08-17 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-21 | [5 empty] | Tabesh Taliran Ashtian Tablo Jabon Pars Tableau Tabarestan SATNA | не передано | 13996/544 | Switchgear 6,6 kV | Expertise of participants
96 | Switchgear 6,6 kV | 4 | no | [8 empty] | 2019-01-29 | 2019-01-29 | ЗЗ-Бшр2-2-П-084-2017 | Switchgear 6,6 kV | BU2-LJWG-2018-02-D049-51 | 2019-02-13 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00160 | 2019-08-17 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-21 | [5 empty] | Taliran Pars Tableau SATNA | не передано | 13996/1629 | Switchgear 6,6 kV | Expertise of participants
21 | Supply of pump units for cooling system of responsible consumers | 2 | no | [8 empty] | 2018-08-30 | 2018-08-30 | ЗЗ-Бшр2-П-216/04-2018 | Supply of pump units for cooling system of responsible consumers | BU2-LJWG-2017-12-D014-23 | 2018-09-14 | 2019-04-04 | BU2-ASEM-NPPD-PSE-007/ULTP/00089 | 2019-05-14 | - | - | 2019-05-24 | - | - | 2019-06-08 | - | - | 2019-06-18 | - | - | no | - | - | 1 Arya Sepehr Kaehan - офиц. отказ 28.04.19 2 Bohlul Pumps 3 Khavar Engineering Company - офиц. отказ 08.05.19 4 Navid Sahand Co - NDA подписан 18.05.19 5 Petro Hirad Co 6 Petro Pedam - NDA подписан 20.04.19 - офиц. отказ 12.06.19 7 PUMPIRAN 8 Rayan Electro Pump Ind. Co. - офиц. отказ 18.05.19 9 Tolombeh Toos | 2019-03-29 | 13996/368 Об53 2,3/П-19 | Supply of pump units for cooling system of responsible consumers | Tender in progress
40 | Sampling heatexchangers | 4 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/02-2017 | Sampling heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | no | - | - | Azar Ab Ind. Co. - NDA подписан 15.06.19 Machine Sazi Arak Co. Taha Ghaleb Toos Co. - NDA подписан 24.06.19 | 2019-03-31 | 12375/970 | Sampling heatexchangers | Retender
51 | CIE Filtering equipment | 2, 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/03-2017 | CIE Filtering equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2019-03-05 | BU2-ASEM-NPPD-PSE-007/ULTP/00069 | 2019-04-14 | - | - | 2019-04-24 | - | - | 2019-05-09 | - | - | 2019-05-19 | - | - | no | - | - | Azar Ab Ind. Co. NDA подписано 21.05.2019 -Atlas Energy Process Co. -Garma Gostar Industry -Hesar Sonat Arak - Masnouat Felezi Sangin (MFS) -Mahdin Industrial Company -Mobaddel Tank -Pacman Co. -Asas Sanat Pars - NDA подписан 21.05.2019 -Taha Ghaleb Toos Co | 2019-02-28 | 13996/647 | CIE Filtering equipment | Retender
25 | First circuit pumps | 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/01-2017 | First circuit pumps | BU2-LJWG-2017-12-D014-23 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | no | - | - | Pelro Hirad Со (NDA подписан 15.06.19) Petro Pedam - отказ 12.06.2019 | 2019-03-07 | 12375/1244 | First circuit pumps | Retender
44 | Heatexchangers | 2 | no | 2018-06-14 | выполнено | 2018-07-04 | выполнено | 2018-08-13 | выполнено | 2018-09-12 | выполнено | 2018-09-12 | 2018-09-12 | ЗЗ-Бшр2-П-265/00-2018 | Heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-27 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | no | - | - | Azarab - NDA подп. 11.06.2019 Mashin sazi Arak - NDA подп. 20.06.2019 Asas Sanat Pars - NDA подп. 22.06.2019 Atlas Epco - NDA подп. 09.06.2019 Masnuat Felezi Sangin | 2019-05-15 | 13996/518 | Heatexchangers | Tender is completed
7 | Radioactive air filtration plants | 2, 3 | no | 2018-06-14 | выполнено | 2018-07-04 | выполнено | 2018-08-13 | выполнено | 2018-09-12 | выполнено | 2018-09-12 | 2018-09-12 | ЗЗ-Бшр2-П-271/00-2018 | Radioactive air filtration plants | BU2-LJWG-2018-03-62-79 | 2018-09-27 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | нет | - | - | Tahvieh air conditions system - Sabalan gostr Tahvieh - Omran Tahvieh industries - Saravel - Damavand air conditions | 2019-02-24 | 13996/154 | Radioactive air filtration plants | Retender
60 | Supply of boron water pumps | 3 | no | [8 empty] | 2019-03-29 | 2019-03-29 | ЗЗ-Бшр2-П-217/14-2018 | Supply of boron water pumps | BU2-LJWG-2017-12-D014-23 | 2019-04-05 | 2019-04-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00093 | 2019-05-18 | - | - | 2019-05-28 | - | - | 2019-06-12 | - | - | 2019-06-22 | - | - | - | - | - | Arya Sepehr Kaehan Bohlul Pumps Khavar Engineering Company Navid Sahand Co Petro Hirad Co Petro Pedam PUMPIRAN Rayan Electro Pump Ind. Co. Tolombeh Toos | 2019-05-06 | 13996/1516 | Supply of boron water pumps | Tender is completed
10 | Inverters and rectifiers | 2, 3 | no | 2018-06-26 | выполнено | 2018-07-16 | выполнено | 2018-08-25 | выполнено | 2018-09-24 | выполнено | 2018-09-24 | 2018-09-28 | ЗЗ-Бшр2-2-П-094-2017 | Inverters and rectifiers | BU2-LJWG-2018-02-D049-51 | 2018-10-09 | 2018-09-28 | BU2-ASEM-NPPD-PSE-007/ULTP/00021 | 2018-11-18 | 2019-03-13 | 10020-249095 | 2018-11-28 | 2019-03-13 | 40-304-2/21154-ВК | 2018-12-13 | 2019-03-26 | 02-47/3272-ВК | 2018-12-23 | выполнено | BU2-ASEM-NPPD-PSE-007/ULTP/00105 | 1 PSP 2 Borna Electronic 3 Satna 4 Poyeh Electronics | 2019-01-02 | 2019-03-13 | 1 PSP (Tolid Manabe Taghzien Electronic) 2 Borna Electronic 3 Satna 4 Porsoo Electronic 5 Poyeh Electronics | 2019-04-25 | 13996/513 | Inverters and rectifiers | Expertise of participants
97 | Supply of purge deaerators | 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/04-2017 | Supply of purge deaerators | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007/ULTP/00024 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Azar Ab Ind. Co. -Atlas Energy Process Co. -Finrotak Sanat Co. -Garma Gostar Industry -Hesar Sonat Arak - Masnouat Felezi Sangin (MFS) -Mahdin Industrial Company -Mobaddel Tank -Pacman Co. -Asas Sanat Pars -Machine sazi Arak Co. -Taha Ghaleb Toos Co | 2019-03-22 | 12375/925 | Supply of purge deaerators | Tender is completed
8 | Supply of submersible electric pump units | 3 | no | 2018-12-05 | выполнено | 2018-12-25 | выполнено | 2019-02-03 | выполнено | 2019-03-05 | выполнено | 2019-03-05 | 2019-02-06 | ЗЗ-Бшр2-П-92/0-2017 | Supply of submersible electric pump units | BU2-LJWG-2017-12-D014-23 | 2019-02-21 | 2019-02-22 | BU2-ASEM-NPPD-PSE-007/ULTP/00065 | 2019-04-02 | - | - | 2019-04-12 | - | - | 2019-04-27 | - | - | 2019-05-07 | - | - | no | - | - | 1 Arya Sepehr Kaehan - устный отказ на основе письма по предыдущ конкурсу 2 Khavar Engineering Company - офиц. отказ 08.05.19 3 Navid Sahand Co - ? 4 Petro Pedam - NDA подписан 07.05.19 - офиц. отказ 12.06.19 5 Rayan Electro Pump Ind. Co. - офиц. отказ 18.05.19 6 Tolombeh Toos - NDA подписан 12.06.19 | 2019-04-11 | 13996/1189 | Supply of submersible electric pump units | Tender is completed
7 | Supply of electric pump units for boron water collection | 3 | no | 2018-12-05 | выполнено | 2018-12-25 | выполнено | 2019-02-03 | выполнено | 2019-03-05 | выполнено | 2019-03-05 | 2019-02-06 | ЗЗ-Бшр2-П-092/00-2017 | Supply of electric pump units for boron water collection | BU2-LJWG-2017-12-D014-23 | 2019-02-21 | 2019-02-22 | BU2-ASEM-NPPD-PSE-007/ULTP/00065 | 2019-04-02 | - | - | 2019-04-12 |  |  | 2019-04-27 | - | - | 2019-05-07 | - | - | no | 2019-05-17 | - | Arya Sepehr Kaehan - устный отказ на основе письма по предыдущ конкурсу Bohlul Pumps Khavar Engineering Co. - устный отказ на основе письма по предыдуш конкурсу; Navid Sahand Co. Petro Hirad Co. - NDA подписан 15.06.19 Petro Pedam - NDA подписан 27.05.19 - офиц. отказ 12.06.19 PUMPIRAN Electro Pump Ind. Co. Tolombeh Toos - NDA подписан 08.06.19 | 2019-04-09 | 13996/1090 | Supply of electric pump units for boron water collection | Tender is completed
32 | Pump equipment (Pump of hydraulic tests of ECCS tanks, Electric pump set for SG hydraulic testing on Secondary side) | 4 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/01-2017 | Pump equipment (Pump of hydraulic tests of ECCS tanks, Electric pump set for SG hydraulic testing on Secondary side) | BU2-LJWG-2017-12-D014-23 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Pelro Hirad Со (NDA подписан 15.06.19) Petro Pedam - отказ 12.06.2019 | 2019-02-27 | 12375/896 | Pump equipment (Pump of hydraulic tests of ECCS tanks, Electric pump set for SG hydraulic testing on Secondary side) | Tender is completed
55 | Vertical traverse | 2 | no | [8 empty] | 2018-09-17 | 2018-09-17 | ЗЗ-Бшр2-2-П-275/00-2018 | Vertical traverse | BU2-LJWG-2018-04-85-89 | 2018-10-02 | 2018-11-20 | BU2-ASEM-NPPD-PSE-007/ULTP/00030 | 2018-11-11 |  |  | 2018-11-21 |  |  | 2018-12-06 |  |  | 2018-12-16 | - | - | no | - | - | 1 Firouza Engineering Co NDA подп. 25.06.2019 2 Iran Sakht Ind. Co. 3 Farabar Sanate Vazin Co 4 Telfer 5 Fassan Cranes | 2019-05-31 | 13996/348 | Vertical traverse | Tender is completed
14 | Test equipment | 4 | no | #VALUE! | выполнено | #VALUE! | выполнено | Московский АЭП, БКП-3 Мовчан Андрей | выполнено | 2019-03-13 | выполнено | 2019-03-13 | 2018-03-28 | ЗЗ-Бшр2-П-091/06-2017 | Test equipment | BU2-LJWG-2018-03-D081 | 2019-03-28 | 2019-03-15 | BU2-ASEM-NPPD-PSE-007/ULTP/00074 | [13 empty] | 2019-04-22 | 2019-04-22 | There’s no complete suppliers in IRI | 2019-02-22 | 12375/1072 | Test equipment | Tender is completed
16 | Supply of machine tools | 4 | no | #REF! | выполнено | #REF! | выполнено | #REF! | выполнено | #REF! | выполнено | #REF! | 2018-11-24 | ЗЗ-Бшр2-2-П-091/04-2017 | Supply of machine tools | BU2-LJWG-2018-05-105 | #REF! | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | [13 empty] | 2019-04-22 | 2019-04-22 | 1 Kara Sazeh 2 Mashinsazi-ye Tabriz - офиц отказ (11.03.19) 3 GAAM Electric Arc | 2019-02-22 | 12375/869 | Supply of machine tools | Tender is completed
1 | Supply of concrete plants | 4 | no | [11 empty] | Supply of concrete plants | [19 empty] | Omran Azeristan | 2019-02-22 | 12375/704 | Supply of concrete plants | Tender is completed
2 | 3rd stages tank of passive filling system | 2 | yes | 2018-09-06 | выполнено | 2018-09-26 | выполнено | 2018-11-05 | выполнено | 2018-12-05 | выполнено | 2018-12-05 | 2018-12-05 | ЗЗ-Бшр2-2-П-052/00-2017 | 3rd stages tank of passive filling system | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | In accordance with the individual HLC schedule | [17 empty] | 1. АМЭ* (совместно с AZARAB) 2 Azar Ab Ind. Co (совместно с АМЭ) 3 Machine Sazi Arak Co. | 2019-03-05 | 13996/651 | 3rd stages tank of passive filling system | Tender is completed
3 | Seal doors | 3 | yes | 2018-08-29 | выполнено | 2018-09-18 | выполнено | 2018-10-28 | выполнено | 2018-11-27 | выполнено | 2018-11-27 | 2018-12-03 | ЗЗ-Бшр2-П-245/01-2018 | Seal doors | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | In accordance with the individual HLC schedule | [17 empty] | 1. АМЭ* (совместно с Imen Sakht Pasargad Co.); 2. Ganj Cham Arman Co (NDA подп 13.01.19) 3. Parsian Sazeh Sepahan (NDA подп 14.01.19) 4. G.M.P (NDA подп 14.01.19) 5. Imen Sakht Passargat (NDA подп 13.01.19) | 2018-12-27 | 13996/608 | Seal doors | Tender is completed
5 | Welding reinforcement equipment | 4 | no | 2018-08-26 | выполнено | 2018-09-15 | выполнено | 2018-10-25 | выполнено | 2018-11-24 | выполнено | 2018-11-24 | 2018-11-24 | ЗЗ-Бшр2-2-054/01-2017 | Welding reinforcement equipment | BU2-LJWG-2018-05-105 | 2018-12-09 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | [13 empty] | 2019-04-22 | 2019-04-22 | 1 Kara Sazeh | 2019-05-29 | 12375/716 | Welding reinforcement equipment | Tender is completed
11 | Rod penetrations | 4 | no | 2018-08-18 | выполнено | 2018-09-07 | выполнено | 2018-10-17 | выполнено | 2018-11-16 | выполнено | 2018-11-16 | 2019-01-24 | ЗЗ-Бшр2-2-П-041/00-2017 | Rod penetrations | BU2-LJWG-2017-12-D028 | 2019-02-08 | 2018-11-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00027 | 2019-03-20 | 2019-02-27 | 1000-250017 | 2019-03-30 | 2019-02-28 | 40-304-2/17343-ВК | 2019-04-14 | 2019-03-15 | 02-42/1827-ВК | 2019-04-24 | 2019-03-26 | BU2-ASEM-NPPD-PSE-007/ULTP/00082 | Shakhes Behbod Sanat - Tesa Co | 2019-05-04 | 2019-04-20 | 1 Shakhes Behbod Sanat - Tesa Co 2 Parsian Sazeh Sepahan 3 Godakhtar | 2019-01-24 | 13996/300 | Rod penetrations | Tender is completed
13 | Road train for fresh nuclear fuel | 4 | no | 2018-08-08 | выполнено | 2018-09-05 | выполнено | 2018-10-15 | выполнено | 2018-11-14 | выполнено | 2018-11-14 | 2018-09-18 | ЗЗ-Бшр2-2-П-275/01-2018 | Road train for fresh nuclear fuel | Производится. Поступило тех. предложение производителя ИРИ. | 2018-11-29 | 2018-11-20 | BU2-ASEM-NPPD-PSE-007/ULTP/00031 | 2019-01-08 | 2019-01-09 | 4300-104436 | 2019-01-18 | 2019-02-06 | № 4300-104436 | 2019-02-02 | 2019-02-06 | 02-42/1176-ВК | 2019-02-10 | 2019-02-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00060 | yes | 2019-02-20 | 2019-02-20 | 1 PSI 2 Mummut – official refusal (24.02.19) | 2019-05-07 | 13996/421 | Road train for fresh nuclear fuel | Tender is completed
38 | Sampling heatexchangers | 3 | no | 2018-02-09 | выполнено | 2018-03-01 | выполнено | 2018-04-10 | выполнено | 2018-05-10 | выполнено | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/02-2017 | Sampling heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-07-04 | - | - | 2018-07-14 | - | - | 2018-07-29 | - | - | 2018-08-08 | - | - | no | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman | 2019-03-31 | 12375/944 | Sampling heatexchangers | Retender
56 | The mixing pump for sprinkler solution | 4 | no | 2019-02-05 |  | 2019-02-25 |  | 2019-04-06 |  | 2019-05-06 |  | 2019-05-06 | 2019-05-06 | ЗЗ-Бшр2-П-217/06-2018 | The mixing pump for sprinkler solution | BU2-LJWG-2017-12-D014-23 | 2019-05-21 | 2019-05-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00112 | 2019-06-30 | - | - | 2019-07-10 | - | - | 2019-07-25 | - | - | 2019-08-04 | - | - | no | - | - | Pumpiran Navid Sahand Petro Hirad RAYAN electro pump Ind. Co Tolombeh Toos Bohlul pumpl | 2019-07-10 | 13996/394 | The mixing pump for sprinkler solution | Retender
26 | Tanks for decontaminating acid solution | 4 | no | 2018-06-13 | выполнено | 2018-07-03 | выполнено | 2018-08-12 | выполнено | 2018-09-11 | выполнено | 2018-09-11 | 2018-09-11 | ЗЗ-Бшр2-П-020/09-2018 | Tanks for decontaminating acid solution | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-26 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-05 | - | - | 2018-11-15 | - | - | 2018-11-30 | - | - | 2018-12-10 | - | - | no | - | - | Mashin sazi Arak - Atlas Epco - Masnuat Felezi Sangin - Azarab - Parsian Sazeh Sepahan |  |  |  | Lot is not prepared
28 | Supply of plate heatexchangers | 3 | no | 2018-06-09 | выполнено | 2018-06-29 | выполнено | 2018-08-08 | выполнено | 2018-09-07 | выполнено | 2018-09-07 | 2018-09-07 | ЗЗ-Бшр2-П-258/00-2018 | Supply of plate heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-22 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-01 | - | - | 2018-11-11 | - | - | 2018-11-26 | - | - | 2018-12-06 | - | - | no | - | - | Taha Ghaleb Toos Co. | 2019-05-31 | 12375/1264 | Supply of plate heatexchangers | Retender
29 | Supply of plate heatexchangers | 3 | no | 2018-06-13 | выполнено | 2018-07-03 | выполнено | 2018-08-12 | выполнено | 2018-09-11 | выполнено | 2018-09-11 | 2018-09-11 | ЗЗ-Бшр2-П-258/01-2018 | Supply of plate heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-26 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-05 | - | - | 2018-11-15 | - | - | 2018-11-30 | - | - | 2018-12-10 | - | - | no | - | - | Taha Ghaleb Toos Co. | 2019-05-31 | 12375/1264 | Supply of plate heatexchangers | Retender
30 | Supply of plate heatexchangers | 4 | no | 2018-06-12 | выполнено | 2018-07-02 | выполнено | 2018-08-11 | выполнено | 2018-09-10 | выполнено | 2018-09-10 | 2018-09-10 | ЗЗ-Бшр2-П-269/00-2018 | Supply of plate heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-25 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-04 | - | - | 2018-11-14 | - | - | 2018-11-29 | - | - | 2018-12-09 | - | - | no | - | - | Taha Ghaleb Toos Co. | 2019-05-31 | 12375/1264 | Supply of plate heatexchangers | Retender
41 | Filter-adsorbers | 3 | no | 2018-06-09 | выполнено | 2018-06-29 | выполнено | 2018-08-08 | выполнено | 2018-09-07 | выполнено | 2018-09-07 | 2018-09-07 | ЗЗ-Бшр2-П-219/04-2018 | Filter-adsorbers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-22 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-01 | - | - | 2018-11-11 | - | - | 2018-11-26 | - | - | 2018-12-06 | - | - | no | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman | 2019-02-28 | 13996/145 | Filter-adsorbers | Retender
43 | Shut-off valves, reverse | 2, 3 | no | 2018-06-09 | выполнено | 2018-06-29 | выполнено | 2018-08-08 | выполнено | 2018-09-07 | выполнено | 2018-09-07 | 2018-09-07 | ЗЗ-Бшр2-П-272/00-2018 | Shut-off valves, reverse | BU2-LJWG-2017-11-D003-006 | 2018-09-22 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-01 | - | - | 2018-11-11 | - | - | 2018-11-26 | - | - | 2018-12-06 | - | - | no | - | - | 1 Shahrokhi Technical Institute 2 Tahvieh Hamoon Manufacturing Co. Ltd. 3 Tahviev Air Conditioning Systems 4 Saravel 5 Havasaz | 2019-02-28 | 13996/512 | Shut-off valves, reverse | Preparation for tender
48 | Sampling chambers | 3 | no | 2018-07-20 | выполнено | 2018-08-09 | выполнено | 2018-09-18 | выполнено | 2018-10-18 | выполнено | 2018-10-18 | 2018-10-18 | ЗЗ-Бшр2-П-256/02-2018 | Sampling chambers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-11-02 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-12 | - | - | 2018-12-22 | - | - | 2019-01-06 | - | - | 2019-01-16 | - | - | no | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman | 2019-04-14 | 13996/519 | Sampling chambers | Preparation for tender
49 | Sampling chambers | 4 | no | 2018-07-20 | выполнено | 2018-08-09 | выполнено | 2018-09-18 | выполнено | 2018-10-18 | выполнено | 2018-10-18 | 2018-10-18 | ЗЗ-Бшр2-П-256/03-2018 | Sampling chambers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-11-02 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-12 | - | - | 2018-12-22 | - | - | 2019-01-06 | - | - | 2019-01-16 | - | - | no | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman | 2019-04-14 | 13996/519 | Sampling chambers | Preparation for tender
50 | Gas blower | 3 | no | 2018-06-16 | выполнено | 2018-07-06 | выполнено | 2018-08-15 | выполнено | 2018-09-14 | выполнено | 2018-09-14 | 2018-09-14 | ЗЗ-Бшр2-П-264/01-2018 | Gas blower | BU2-LJWG-2017-12-D018 | 2018-09-29 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-11-08 | - | - | 2018-11-18 | - | - | 2018-12-03 | - | - | 2018-12-13 | - | - | no | - | - | Petro Hirad - Arya Sepehr Kayhan | 2019-02-26 | 13996/539 | Gas blower | Preparation for tender
54 | Pump of hydraulic tests of ECCS tanks of safety class 4 | 4 | no | [8 empty] | 2019-04-23 | 2019-04-23 | ЗЗ-Бшр2-2-П-20/1-2017 | Pump of hydraulic tests of ECCS tanks of safety class 4 | BU2-LJWG-2017-12-D014-23 | 2019-05-08 | 2019-02-22 | BU2-ASEM-NPPD-PSE-007/ULTP/00113 | 2019-06-17 | - | - | 2019-06-27 | - | - | 2019-07-12 | - | - | 2019-07-22 | - | - | no | - | - | Pumpiran Navid Sahand Petro Hirad Iran Industrial Pumps (IIP Co.) |  |  |  | Lot is not prepared
3 | Seal doors. Stage 2 | 3, 4 | yes | 2018-11-18 | выполнено | 2018-12-08 | выполнено | 2019-01-17 | выполнено | 2019-02-16 | выполнено | 2019-02-16 | 2019-02-12 | ЗЗ-Бшр2-3-П-262/01-2018 | Seal doors. Stage 2 | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | In accordance with the individual HLC schedule | [17 empty] | 1 G.M.P. 2 Parsian Sazeh Sepahan 3 Imen Sakht Pasargad |  |  |  | Lot is not prepared
8 | Transformers | 3 | no | 2018-08-25 | выполнено | 2018-09-14 | выполнено | 2018-10-24 | выполнено | 2018-11-23 | выполнено | 2018-11-23 | 2018-11-23 | ЗЗ-Бшр2-2-П-204-00-2018 | Transformers | BU2-LJWG-2017-10-D001-002 | 2018-12-08 | 2018-11-28 | BU2-ASEM-NPPD-PSE-007/ULTP/00035 | 2019-01-17 | 2019-02-10 | 10020-249096 | 2019-01-27 | 2019-03-07 | 40-304-1/19752-ВК | 2019-02-11 | 2019-03-20 | 40-47-2/23648 | 2019-02-21 | 2019-03-22 | BU2-ASEM-NPPD-PSE-007/ULTP/00080 | 1 Iran Transfo | 2019-03-03 | 2017-10-01 | 1 Iran Transfo 2. Arya Transfo |  |  |  | Lot is not prepared
12 | Rod penetrations | 4 | no | 2018-12-30 | выполнено | 2019-01-19 | выполнено | 2019-02-28 | выполнено | 2019-03-30 | выполнено | 2019-03-30 | 2019-02-21 | ЗЗ-Бшр2-П-042/00-2017 ЗЗ-Бшр3-П-042/00-2017 | Rod penetrations | BU2-LJWG-2017-12-D028 | 2019-03-08 | 2019-03-15 | BU2-ASEM-NPPD-PSE-007/ULTP/00076 | 2019-04-17 | 2019-02-27 | 1000-250017 | 2019-04-27 | 2019-02-28 | СЗ 40-304-2/17343-ВК | 2019-05-12 | 2019-03-15 | 02-42/1827-ВК | 2019-05-22 | 2019-03-26 | BU2-ASEM-NPPD-PSE-007/ULTP/00082 | Shakhes Behbod Sanat - Tesa Co | 2019-06-01 | 2019-04-20 | 1 Shakhes Behbod Sanat - Tesa Co 2 Parsian Sazeh Sepahan 3 Godakhtar | 2019-08-15 | 13996/1464 | Supply of rod penetrations | Tender is completed
18 | Hydraulic conveyor for loading ionexchange resins | 4 | no | 2018-11-24 | выполнено | 2018-12-14 | выполнено | 2019-01-23 | выполнено | 2019-02-22 | выполнено | 2019-02-22 | 2019-02-22 | ЗЗ-Бшр2-2-7704-201399460 | Hydraulic conveyor for loading ionexchange resins | BU2-LJWG-2017-12-D014-23 | 2019-03-09 | 2019-03-15 | BU2-ASEM-NPPD-PSE-007/ULTP/00077 | 2019-04-18 | 2019-06-16 | 9000-254550 | 2019-04-28 | - | - | 2019-05-13 | - | - | 2019-05-23 | - | - | no | - | - | 1 Masnouat Felezi Sangin 2 Mahdin 3 Asas Sanat Pars 4 Pacman 5 Mobaddel Tank |  |  |  | Lot is not prepared
19 | Supply of pumps filling 1st circuit | 3 | no | 2018-12-29 | выполнено | 2019-01-18 | выполнено | 2019-02-27 | выполнено | 2019-03-29 | выполнено | 2019-03-29 | 2019-03-29 | ЗЗ-Бшр2-П-217/13-2018 | Supply of pumps filling 1st circuit | BU2-LJWG-2017-12-D014-23 | 2019-04-13 | 2019-04-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00092 | 2019-05-23 | - | - | 2019-06-02 | - | - | 2019-06-17 | - | - | 2019-06-27 | - | - | no | - | - | Arya Sepehr Kayhan - Khavar Eng. Co. - Petro Hirad - Pumpiran - Navid Sahand | - | 13996/1673 | Supply of pumps filling 1st circuit | Expertise of participants
22 | Distillate pump | 3 | no | 2018-12-27 | выполнено | 2019-01-16 | выполнено | 2019-02-25 | выполнено | 2019-03-27 | выполнено | 2019-03-27 | 2019-03-27 | ЗЗ-Бшр3-П-217/08-2018 | Distillate pump | BU2-LJWG-2017-12-D014-23 | 2019-04-11 | 2019-04-12 | 007/ULTP/00094 | 2019-05-21 | - | - | 2019-05-31 | - | - | 2019-06-15 | - | - | 2019-06-25 | - | - | no | - | - |  | 2019-07-11 | 13996/1416 | Distillate pump | Retender
24 | Supply of static equipment (CIE) | 4 | no | 2018-07-20 | выполнено | 2018-08-09 | выполнено | 2018-09-18 | выполнено | 2018-10-18 | выполнено | 2018-10-18 | 2018-10-18 | ЗЗ-Бшр2-П-020/08-2018 | Supply of static equipment (CIE) | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-11-02 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-12 | - | - | 2018-12-22 | - | - | 2019-01-06 | - | - | 2019-01-16 | - | - | no | - | - |  | 2019-07-15 | 12375/1024 | Supply of static equipment (CIE) | Expertise of participants
79 | Technical-mechanical equipment UQA UQC UQN UQX | 2, 4 | no | [8 empty] | 2019-06-10 | 2019-06-10 | ЗЗ-Бшр2-2-П-243/01-2018 | Technical-mechanical equipment UQA UQC UQN UQX | No Decision | 2019-06-25 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00142 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - |  |  |  |  | Lot is not prepared
80 | Technical-mechanical equipment UQA UQC UQN UQX | 2, 4 | no | [8 empty] | 2019-06-10 | 2019-06-10 | ЗЗ-Бшр3-2-П-243/01-2018 | Technical-mechanical equipment UQA UQC UQN UQX | Нет Решения | 2019-06-25 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00142 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - |  |  |  |  | Lot is not prepared
70 | Small diameter valves | 2, 3, 4 | no | [8 empty] | 2019-06-03 | 2019-06-03 | ЗЗ-О53-2-П-233/01-2019 | Small diameter valves | BU2-LJWG-2017-11-D003-006 | 2019-06-18 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00143 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - | PEIC TESA (Shakhes) Godakhtar KIASA |  |  |  | Lot is not prepared
71 | Small diameter valves UJA UKC UKA | 2, 3, 4 | no | [8 empty] | 2019-06-03 | 2019-06-03 | ЗЗ-О53-2-П-302/03-2019 | Small diameter valves UJA UKC UKA | BU2-LJWG-2017-11-D003-006 | 2019-06-18 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00145 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - | PEIC TESA (Shakhes) Godakhtar KIASA |  |  |  | Lot is not prepared
72 | Box type installation valves | 2, 3, 4 | no | [8 empty] | 2019-06-03 | 2019-06-03 | ЗЗ-О53-3-П-095/00-2017 | Box type installation valves | BU2-LJWG-2017-11-D003-006 | 2019-06-18 | 2018-11-27 | BU2-ASEM-NPPD-PSE-007/ULTP/00033 | 2019-01-06 | - | - | 2019-01-16 | - | - | 2019-01-31 | - | - | 2019-02-10 | - | - | - | - | - | PEIC TESA (Shakhes) Godakhtar KIASA |  |  |  | Lot is not prepared
73 | Small diameter valves | 2, 3, 4 | no | [8 empty] | 2019-06-03 | 2019-06-03 | ЗЗ-О53-3-П-233/01-2019 | Small diameter valves | BU2-LJWG-2017-11-D003-006 | 2019-06-18 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00143 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - | PEIC TESA (Shakhes) Godakhtar KIASA |  |  |  | Lot is not prepared
74 | Small diameter valves UJA UKC UKA | 2, 3, 4 | no | [8 empty] | 2019-06-03 | 2019-06-03 | ЗЗ-О53-3-П-302/02-2019 | Small diameter valves UJA UKC UKA | BU2-LJWG-2017-11-D003-006 | 2019-06-18 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00145 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - | PEIC TESA (Shakhes) Godakhtar KIASA |  |  |  | Lot is not prepared
75 | LMCE Simulators | - | no | [8 empty] | 2019-06-05 | 2019-06-05 | ЗЗ-Бшр2-1-П-053/00-2017 | LMCE Simulators | [19 empty] | EDIS |  |  |  | Lot is not prepared
57 | Box type installation valves | 2,3,4 | yes | 2019-02-06 |  | 2019-02-26 |  | 2019-04-07 |  | 2019-05-07 |  | 2019-05-07 | 2019-05-07 | ЗЗ-О53-2-П-095/00-2017 | Box type installation valves | BU2-LJWG-2017-11-D003-006 | 2019-05-21 | 2019-05-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00110 | 2019-07-03 | - | - | 2019-07-13 | - | - | 2019-07-28 | - | - | 2019-08-07 | - | - | no | - | - | PEIC TESA (Shakhes) Godakhtar KIASA |  |  |  | Lot is not prepared
58 | Small diameter valves UJA UKC UKA | 2,3,4 | yes | 2019-02-07 |  | 2019-02-27 |  | 2019-04-08 |  | 2019-05-08 |  | 2019-05-08 | 2019-05-08 | ЗЗ-О53-2-П-141/02-2019 | Small diameter valves UJA UKC UKA | BU2-LJWG-2017-11-D003-006 | 2019-05-21 | 2019-05-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00110 | 2019-07-03 | - | - | 2019-07-13 | - | - | 2019-07-28 | - | - | 2019-08-07 | - | - | no | - | - | PEIC TESA (Shakhes) Godakhtar KIASA |  |  |  | Lot is not prepared
59 | LMCE Simulators | 4 | no | 2019-02-13 |  | 2019-03-05 |  | 2019-04-14 |  | 2019-05-14 |  | 2019-05-14 | 2019-05-14 | ЗЗ-Бшр2-2-П-149-2018 | LMCE Simulators | BU2-LJWG-2017-10-D001-002 | 2019-05-21 | 2019-05-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00111 | 2019-07-03 | - | - | 2019-07-13 | - | - | 2019-07-28 | - | - | 2019-08-07 | - | - | no | - | - | Iran Transfo |  |  |  | Lot is not prepared
61 | Metal hatches | 2 | no | [8 empty] | 2019-05-28 | 2019-05-28 | ЗЗ-Бшр2-2-П-263/00-2018 | Metal hatches | No Decision | 2019-06-12 | 2019-06-21 | BU2-ASEM-NPPD-PSE-007/ULTP/00134 | 2019-07-31 | - | - | 2019-08-10 | - | - | 2019-08-25 | - | - | 2019-09-04 | - | - | - | - | - | Ganj Cham Arman Ganjineh mehr Pars (GMP) Imen Sakht Pasargad |  |  |  | Lot is not prepared
62 | Floor water pump | 3 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-Бшр2-П-217/19-2018 | Floor water pump | BU2-LJWG-2017-12-D014-23 | 2019-06-14 | 2019-06-21 | BU2-ASEM-NPPD-PSE-007/ULTP/00135 | 2019-07-31 | - | - | 2019-08-10 | - | - | 2019-08-25 | - | - | 2019-09-04 | - | - | - | - | - | Pumpiran Navid Sahand Arya Sepehr Kayhan Petro Hirad Rayan Electro Pump | 2019-07-18 | 13996/1724 | Floor water pump | Tender is completed
64 | Supply of dosing pumps | 4 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-Бшр2-П-217/18-2018 | Supply of dosing pumps | BU2-LJWG-2017-12-D014-23 | 2019-06-14 | 2019-06-21 | BU2-ASEM-NPPD-PSE-007/ULTP/00136 | 2019-07-31 | - | - | 2019-08-10 | - | - | 2019-08-25 | - | - | 2019-09-04 | - | - | - | - | - | Petro Hirad Arya Sepehr Kayhan KEC Tolombeh Toos Tajhiz Gostar NoAndish |  | 13996/1756 | Supply of dosing pumps | Tender is completed
65 | Centrifugal pumps | 3.4 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-Бшр2-П-217/00-2018 | Centrifugal pumps | BU2-LJWG-2017-12-D014-23 | 2019-06-14 | 2019-08-14 | BU2-ASEM-NPPD-GEN-007/ULTP/00198 | 2019-09-23 | - | - | 2019-10-03 | - | - | 2019-10-18 | - | - | 2019-10-28 | - | - | - | - | - | Pumpiran Iran Industrial Pumps (IIP Co.) Arya Sepehr Kayhan Petro Pedam Rayan Electro Pump |  |  |  | Lot is not prepared
66 | The system of automated chemical control of the second circuit | 4 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-Бшр2-2-7704-201399462 | The system of automated chemical control of the second circuit | No Decision | 2019-06-14 | 2019-06-21 | BU2-ASEM-NPPD-PSE-007/ULTP/00137 | 2019-07-31 | - | - | 2019-08-10 | - | - | 2019-08-25 | - | - | 2019-09-04 | - | - | - | - | - |  |  |  |  | Lot is not prepared
67 | Washing solution heater | 4 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-О53-2-П-256/01-2018 | Washing solution heater | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-06-14 | 2019-06-21 | BU2-ASEM-NPPD-PSE-007/ULTP/00138 | 2019-07-31 | - | - | 2019-08-10 | - | - | 2019-08-25 | - | - | 2019-09-04 | - | - | - | - | - | 1. Mahdin 2. Atlas Epco, Finrotak sanat Co. 3. Mobaddel tank 4. Pacman 5. Parsian sazeh iranian |  |  |  | Lot is not prepared
68 | Dosing pumps | 4 | no | [8 empty] | 2019-05-31 | 2019-05-31 | ЗЗ-Бшр2-П-217/12-2018 | Dosing pumps | BU2-LJWG-2017-12-D014-23 | 2019-06-15 | 2019-06-21 | BU2-ASEM-NPPD-PSE-007/ULTP/00136 | 2019-07-31 | - | - | 2019-08-10 | - | - | 2019-08-25 | - | - | 2019-09-04 | - | - | - | - | - | Petro Hirad Arya Sepehr Kayhan KEC Tolombeh Toos Tajhiz Gostar NoAndish |  |  |  | Lot is not prepared
82 | Pumps | 2 | no | [8 empty] | 2019-06-11 | 2019-06-11 | ЗЗ-Бшр3-П-217/04-2018 | Pumps | BU2-LJWG-2017-12-D014-23 | 2019-06-26 | 2019-06-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00146 | 2019-08-04 | - | - | 2019-08-14 | - | - | 2019-08-29 | - | - | 2019-09-08 | - | - | - | - | - |  | 2019-07-17 | 13996/414 | Pumps | Retender
83 | Controlled leaks pumps | 2 | no | [8 empty] | 2019-06-19 | 2019-06-19 | ЗЗ-Бшр2-П-217/07-2018 | Controlled leaks pumps | BU2-LJWG-2017-12-D014-23 | 2019-07-04 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00156 | 2019-08-17 | - | - | 2019-08-27 | - | - | 2019-09-11 | - | - | 2019-09-21 | - | - | - | - | - | 1. PUMPIRAN 2. Navid Sahand Co 3. Petro Hirad Co 4. Petro Pedam | 2020-01-13 | 13996/2028 | Controlled leaks pumps | Expertise of participants
84 | Controlled leaks pumps | 2 | no | [8 empty] | 2019-06-19 | 2019-06-19 | ЗЗ-Бшр3-П-217/07-2018 | Controlled leaks pumps | BU2-LJWG-2017-12-D014-23 | 2019-07-04 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00156 | 2019-08-17 | - | - | 2019-08-27 | - | - | 2019-09-11 | - | - | 2019-09-21 | - | - | - | - | - |  |  |  |  | Lot is not prepared
86 | Seal doors UKC 2nd stage | 3 | yes | [8 empty] | 2019-06-21 | 2019-06-21 | ЗЗ-О53-2-П-453/00-2019 | Seal doors UKC 2nd stage | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | In accordance with the individual HLC schedule | [17 empty] | 1 G.M.P. 2 Parsian Sazeh Sepahan 3 Imen Sakht Pasargad 4 Ganj Cham Arman Co | 2019-06-26 | 13996/1463 | Seal doors | Tender is completed
87 | Seal doors UJA 2nd stage | 3, 4 | yes | [8 empty] | 2019-06-21 | 2019-06-21 | ЗЗ-О53-3-П-452/00-2019 | Seal doors UJA 2nd stage | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | In accordance with the individual HLC schedule | [17 empty] | 1 G.M.P. 2 Parsian Sazeh Sepahan 3 Imen Sakht Pasargad 4 Ganj Cham Arman Co | 2019-06-26 | 13996/1463 | Seal doors | Tender is completed
88 | Seal doors UKC 2nd stage | 3 | yes | [8 empty] | 2019-06-21 | 2019-06-21 | ЗЗ-О53-3-П-453/00-2019 | Seal doors UKC 2nd stage | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | In accordance with the individual HLC schedule | [17 empty] | 1 G.M.P. 2 Parsian Sazeh Sepahan 3 Imen Sakht Pasargad 4 Ganj Cham Arman Co | 2019-06-26 | 13996/1463 | Seal doors | Tender is completed
89 | Oil Tanks | 4 | no | [8 empty] | 2019-06-26 | 2019-06-26 | ЗЗ-О53-2-П-243/02-2018 | Oil Tanks | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-07-11 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00157 | 2019-08-17 | - | - | 2019-08-27 | - | - | 2019-09-11 | - | - | 2019-09-21 | - | - | - | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman |  |  |  | Lot is not prepared
90 | Oil Tanks | 4 | no | [8 empty] | 2019-06-26 | 2019-06-26 | ЗЗ-О53-3-П-243/02-2018 | Oil Tanks | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-07-11 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00157 | 2019-08-17 | - | - | 2019-08-27 | - | - | 2019-09-11 | - | - | 2019-09-21 | - | - | - | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman |  |  |  | Lot is not prepared
91 | System of automated chemical control of the primary circuit | 4 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-Бшр2-2-7704-201399459 | System of automated chemical control of the primary circuit | Нет Решения | 2019-06-14 | 2019-06-07 | BU2-ASEM-NPPD-PSE-007/ULTP/00131 | 2019-07-17 | - | - | 2019-07-27 | - | - | 2019-08-11 | - | - | 2019-08-21 | - | - | - | - | - | Pumpiran Navid Sahand Iran Industrial Pumps (IIP Co.) - отказ по тел Petro Hirad | 2019-07-11 | 13996/1416 | System of automated chemical control of the primary circuit | Retender
93 | Mix type filters | 2, 3, 4 | no | [8 empty] | 2018-05-11 | 2018-05-11 | ЗЗ-Бшр2-П-020/03-2017 | Mix type filters | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-26 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00158 | 2019-08-17 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-21 | [5 empty] | 1. PSI (Parsian Sazeh Sepahan) 2. Hesar Sanat Arak 3. Pacman Co 4. Asas Sanat Pars 5. Mashin sazi Arak | не передано | 13996/1554 | Mix type filters | Tender in progress
94 | High temperature filters | 2 | no | [8 empty] | 2018-10-01 | 2018-10-18 | ЗЗ-Бшр2-П-217/15-2018 | High temperature filters | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-10-16 | 2019-07-08 | BU2-ASEM-NPPD-PSE-007/ULTP/00159 | 2019-08-17 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-21 | [5 empty] | 1. PSI (Parsian Sazeh Sepahan) 2. Hesar Sanat Arak 3. Pacman Co 4. Asas Sanat Pars 5. Mashin sazi Arak | не передано | 13996/1554 | High temperature filters | Tender in progress
98 | Генераторное распределительное устройство | 3 | no | [8 empty] | 2019-07-10 | 2019-07-10 | ЗЗ-Бшр2-2-П-093-2017 | Generator circuit breaker | Нет Решения | 2019-07-25 | 2019-08-15 | BU2-ASEM-NPPD-GEN-007/ULTP/00202 | 2019-09-24 |  |  | 2019-10-04 |  |  | 2019-10-19 |  |  | 2019-10-29 | [9 empty] | Lot is not prepared
99 | The pump of emergency and planned cooling of the primary circuit | 2,3,4 | no | [8 empty] | 2018-05-10 | 2018-05-10 | ЗЗ-Бшр2-П-020/01-2017 | The pump equipment | BU2-LJWG-2017-12-D014-23 | 2018-05-25 | 2019-08-15 | BU2-ASEM-NPPD-GEN-007/ULTP/00200 | 2019-09-24 |  |  | 2019-10-04 |  |  | 2019-10-19 |  |  | 2019-10-29 | [6 empty] | 2019-06-21 | 12375/1198 | The pump of emergency and planned cooling of the primary circuit | Import
100 | Emergency boron injection pump | 2 | no | [8 empty] | 2017-09-28 | 2017-09-28 | ЗЗ-Бшр2-П-020/05-2017 | Emergency boron injection pump | BU2-LJWG-2017-12-D014-23 | 2017-10-13 | 2019-08-14 | BU2-ASEM-NPPD-GEN-007/ULTP/00199 | 2019-09-23 |  |  | 2019-10-03 |  |  | 2019-10-18 |  |  | 2019-10-28 | [6 empty] | 2017-12-29 | 12375/576 | Emergency boron injection pump | Preparation for tender
101 | Sampling heatexchangers | 3.4 | no | [8 empty] | 2018-10-18 | 2018-10-18 | ЗЗ-Бшр2-2-П-243/00-2018 | Sampling heatexchangers | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-11-02 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-12 |  |  | 2018-12-22 |  |  | 2019-01-06 |  |  | 2019-01-16 | [6 empty] | Не передано | 13996/520 | Sampling heatexchangers | Preparation for tender
102 | Оборудование установки цементирования | 3.4 | no | [8 empty] | 2018-05-15 | 2018-05-15 | ЗЗ-Бшр2-1-П-178/00-2018 | Cementing installation equipment | Нет Решения | 2018-05-30 | 2019-08-15 | BU2-ASEM-NPPD-GEN-007/ULTP/00205 | 2019-09-24 |  |  | 2019-10-04 |  |  | 2019-10-19 |  |  | 2019-10-29 | [9 empty] | Lot is not prepared
103 | ТТТ_п.137.1_Система автоматизированного химического контроля второго контура | 4 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-Бшр2-2-7704-201399458 | the system of automated chemical control of the second circuit | Нет Решения | 2019-06-14 | 2019-06-21 | BU2-ASEM-NPPD- GEN -007/ULTP/00137 | 2019-07-31 |  |  | 2019-08-10 |  |  | 2019-08-25 |  |  | 2019-09-04 | [9 empty] | Lot is not prepared
104 | Оборудование отбора проб UKC, UKA, UJA | 4 | no | [8 empty] | 2018-07-03 | 2018-07-03 | ЗЗ-Бшр2-2-П-256/00-2018 | Sampling equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-07-18 | 2019-08-15 | BU2-ASEM-NPPD-GEN-007/ULTP/00204 | 2019-09-24 |  |  | 2019-10-04 |  |  | 2019-10-19 |  |  | 2019-10-29 | [9 empty] | Lot is not prepared
105 | Емкостное оборудование свыше 80 куб. м | 3 | no | [8 empty] | 2018-05-15 | 2018-05-15 | ЗЗ-Бшр2-П-020/07-2018 | Static equipment over 80 m3 | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-30 | 2019-08-14 | BU2-ASEM-NPPD-GEN-007/ULTP/00196 | 2019-09-23 |  |  | 2019-10-03 |  |  | 2019-10-18 |  |  | 2019-10-28 | [9 empty] | Lot is not prepared
106 | Насосное оборудование - Большие ЦНА | 3.4 | no | [8 empty] | 2019-05-30 | 2019-05-30 | ЗЗ-Бшр2-П-217/17-2018 | Pumping equipment - big centrifugal pumps | BU2-LJWG-2017-12-D014-23 | 2019-06-14 | 2019-08-15 | BU2-ASEM-NPPD-GEN-007/ULTP/00203 | 2019-09-24 |  |  | 2019-10-04 |  |  | 2019-10-19 |  |  | 2019-10-29 | [9 empty] | Lot is not prepared
107 | Насосное оборудование АЭП БКП-6 | 4 | no | [8 empty] | 2018-05-16 | 2018-05-16 | ЗЗ-Бшр2-П-219/00-2018 | Pumping equipment | BU2-LJWG-2017-12-D014-23 | 2018-05-31 | 2019-08-27 | BU2-ASEM-NPPD-GEN-007/ULTP/00216 | 2019-10-06 |  |  | 2019-10-16 |  |  | 2019-10-31 |  |  | 2019-11-10 | [9 empty] | Lot is not prepared
108 | Фильтр самоочищающийся механический системы охлаждающей воды ответственных потребителей | 2 | no | [8 empty] | 2018-05-16 | 2018-05-16 | ЗЗ-Бшр2-П-221/00-2018 | Mechanical self-cleaning filter | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-05-31 | 2019-08-22 | BU2-ASEM-NPPD-GEN-007/ULTP/00213 | 2019-10-01 |  |  | 2019-10-11 |  |  | 2019-10-26 |  |  | 2019-11-05 | [9 empty] | Lot is not prepared
109 | Оборудование охлаждения пара UKC, UJA | 4 | no | [8 empty] | 2018-07-03 | 2018-07-03 | ЗЗ-О53-2-П-257/00-2018 | Steam cooling equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-07-18 | 2019-08-14 | BU2-ASEM-NPPD-GEN-007/ULTP/00197 | 2019-09-23 | 2019-08-14 | 9000-257688 | 2019-10-03 |  |  | 2019-10-18 |  |  | 2019-10-28 | [9 empty] | Lot is not prepared
45 | CIE regenerative heat exchanger blowdown steam generator | 2 | no | 2018-06-14 | выполнено | 2018-07-04 | выполнено | 2018-08-13 | выполнено | 2018-09-12 | выполнено | 2018-09-12 | 2018-09-12 | ЗЗ-Бшр2-П-266/00-2018 | CIE regenerative heat exchanger blowdown steam generator | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-27 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | no | - | - | Azarab - Mashin sazi Arak - Asas Sanat Pars - Atlas Epco - Masnuat Felezi Sangin - Packman | 2019-05-15 | 13996/518 | Supply of heatexchangers | Tender is completed
46 | CIE after-cooler purge | 2 | no | 2018-06-13 | выполнено | 2018-07-03 | выполнено | 2018-08-12 | выполнено | 2018-09-11 | выполнено | 2018-09-11 | 2018-09-11 | ЗЗ-Бшр2-П-274/00-2018 | CIE after-cooler purge | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-26 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | no | - | - | Masnouat Felezi Sangin Mahdin Asas Sanat Pars Atlas EPCO( Fin Rotak) Mashin sazi Arak | 2019-05-15 | 13996/518 | Supply of heatexchangers | Tender is completed
47 | Gas cooler | 3 | no | 2018-06-13 | выполнено | 2018-07-03 | выполнено | 2018-08-12 | выполнено | 2018-09-11 | выполнено | 2018-09-11 | 2018-09-11 | ЗЗ-Бшр2-П-264/02-2018 | Gas cooler | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2018-09-26 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00024 | 2018-12-01 | - | - | 2018-12-11 | - | - | 2018-12-26 | - | - | 2019-01-05 | - | - | no | - | - | Pacman Mobaddel Tank Asas Sanat Pars Atlas EPCO( Fin Rotak) Mashin sazi Arak | 2019-05-15 | 13996/518 | Supply of heatexchangers | Tender is completed
1 | Seal doors | 4 | no | [8 empty] | 2019-09-16 | 2019-09-16 | ЗЗ-О53-2-П-154/01-2018 ЗЗ-О53-3-П-154/01-2018 | Seal doors | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | 2019-10-01 | 2019-09-11 | BU2-ASEM-NPPD-GEN-007/ULTP/00227 | 2019-10-21 | - | - | 2019-10-31 | - | - | 2019-11-15 | - | - | 2019-11-25 | - | - | no | - | - | Pacman Mobaddel Tank Asas Sanat Pars Atlas EPCO( Fin Rotak) Mashin sazi Arak
2 | Rubber-cord compensator | 2,3,4 | no | [8 empty] | 2019-09-16 | 2019-09-16 | ЗЗ-О53-2-П-293/00-2018 ЗЗ-О53-3-П-293/00-2018 | Rubber-cord compensator | Нет Решения | 2019-10-01 | 2019-09-12 | BU2-ASEM-NPPD-GEN-007/ULTP/00230 | 2019-10-22 | - | - | 2019-11-01 | - | - | 2019-11-16 | - | - | 2019-11-26 | - | - | no | - | -
3 | CIE Static equipment over 75m3 | 3 | no | [8 empty] | 2019-07-12 | 2019-09-16 | ЗЗ-Бшр2-П-202/07-2018 ЗЗ-Бшр3-П-202/07-2018 | CIE Static equipment over 75m3 | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-10-01 | 2019-09-09 | BU2-ASEM-NPPD-GEN-007/ULTP/00221 | 2019-10-19 | - | - | 2019-10-29 | - | - | 2019-11-13 | - | - | 2019-11-23 | - | - | no | - | -
4 | Seal doors, hatches, gates | 4 | no | [8 empty] | 2019-09-17 | 2019-09-18 | ЗЗ-О53-2-П-470/00-2019 ЗЗ-О53-2-П-470/00-2019 | Seal doors, hatches, gates | BU2-LJWG-2017-11-D007-009 BU2-LJWG-2018-03-83 | 2019-10-03 | 2019-09-09 | BU2-ASEM-NPPD-GEN-007/ULTP/00225 | 2019-10-19 | - | - | 2019-10-29 | - | - | 2019-11-13 | - | - | 2019-11-23 | - | - | no | - | -
5 | special sewage system from lavatory equipment control tank pump | 4 | no | [8 empty] | 2019-09-17 | 2019-09-18 | ЗЗ-О53-2-П-219/06-2019 ЗЗ-О53-3-П-219/06-2019 | special sewage system from lavatory equipment control tank pump | BU2-LJWG-2017-12-D014-23 | 2019-10-03 | 2019-09-09 | BU2-ASEM-NPPD-GEN-007/ULTP/00222 | 2019-10-19 | - | - | 2019-10-29 | - | - | 2019-11-13 | - | - | 2019-11-23 | - | - | no | - | -
6 | Electric pump unit of a tank of water drain from steam | 4 | no | [8 empty] | 2019-05-16 | 2019-09-20 | ЗЗ-Бшр2-П-217/11-2018 | Electric pump unit of a tank of water drain from steam | BU2-LJWG-2017-12-D014-23 | 2019-10-05 | 2019-09-09 | BU2-ASEM-NPPD-GEN-007/ULTP/00224 | 2019-10-19 | - | - | 2019-10-29 | - | - | 2019-11-13 | - | - | 2019-11-23 | - | - | no | - | -
7 | Double check valves | 3 | no | [8 empty] | 2019-05-16 | 2019-09-23 | ЗЗ-О53-2-П-480/00-2019 | Double check valves | BU2-LJWG-2017-11-D003-006 | 2019-10-08 | 2019-09-09 | BU2-ASEM-NPPD-GEN-007/ULTP/00226 | 2019-10-19 | - | - | 2019-10-29 | - | - | 2019-11-13 | - | - | 2019-11-23 | - | - | no | - | -
8 | Distillate cooler | 4 | no | [8 empty] | 2019-05-16 | 2019-09-20 | ЗЗ-О533-П-256/00-2018 ЗЗ-О53-2-П-256/00-2018 | Distillate cooler | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-10-05 | 2019-09-12 | BU2-ASEM-NPPD-GEN-007/ULTP/00234 | 2019-10-22 | - | - | 2019-11-01 | - | - | 2019-11-16 | - | - | 2019-11-26 | - | - | no | - | -
9 | Component cooling circuit aftercooler | 4 | no | [8 empty] | 2019-05-16 | 2019-09-20 | ЗЗ-Бшр2-2-П-262/00-2018 ЗЗ-О53-3-П-262/00-2019 | Component cooling circuit aftercooler | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-10-05 | 2019-09-18 | BU2-ASEM-NPPD-GEN-007/ULTP/00239 | 2019-10-28 | - | - | 2019-11-07 | - | - | 2019-11-22 | - | - | 2019-12-02 | - | - | no | - | -
10 | Small diameter valves UJA UKC UKA | 4 | no | [8 empty] | 2019-05-16 | 2019-09-20 | ЗЗ-О53-2-П-302/02-2018 ЗЗ-О53-3-П-302/02-2018 ЗЗ-О53-3-П-302/04-2018 | Small diameter valves UJA UKC UKA | BU2-LJWG-2017-11-D003-006 | 2019-10-05 | 2019-09-18 | BU2-ASEM-NPPD-GEN-007/ULTP/00240 | 2019-10-28 | - | - | 2019-11-07 | - | - | 2019-11-22 | - | - | 2019-12-02 | - | - | no | - | -
11 | Airlock trolley with a rail track | 4 | no | [8 empty] | 2019-05-16 | 2019-09-20 | ЗЗ-О53-2-П-482/01-2019 | Airlock trolley with a rail track | BU2-LJWG-2018-04-85-89 | 2019-10-05 | 2019-09-18 | BU2-ASEM-NPPD-GEN-007/ULTP/00241 | 2019-10-28 | - | - | 2019-11-07 | - | - | 2019-11-22 | - | - | 2019-12-02 | - | - | no | - | -
12 | Steam cooling equipment | 4 | no | [8 empty] | 2019-05-16 | 2019-09-20 | ЗЗ-О53-2-П-257/02-2019 ЗЗ-О53-3-П-257/02-2019 | Steam cooling equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-05-31 | 2019-08-14 | BU2-ASEM-NPPD-GEN-007/ULTP/00197 | 2019-09-23 | - | - | 2019-10-03 | - | - | 2019-10-18 | - | - | 2019-10-28 | - | - | no | - | -
13 | Pressure-reducing and desuperheater plant | 4 | no | [8 empty] | 2019-05-16 | 2019-09-20 | ЗЗ-О53-2-П-257/01-2019 ЗЗ-О53-3-П-257/01-2019 | Pressure-reducing and desuperheater plant | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-05-31 | 2019-09-26 | BU2-ASEM-NPPD-GEN-007/ULTP/00258 | 2019-11-05 | - | - | 2019-11-15 | - | - | 2019-11-30 | - | - | 2019-12-10 | - | - | no | - | -
14 | Frames and gates | 4 | no | [8 empty] | 2019-05-16 | 2019-09-24 | ЗЗ-Бшр2-2-П-238/01-2018 ЗЗ-Бшр2-3-П-238/01-2018 | Frames and gates | Нет Решения | 2019-05-31 | 2019-09-23 | BU2-ASEM-NPPD-GEN-007/ULTP/00245 | 2019-11-02 | - | - | 2019-11-12 | - | - | 2019-11-27 | - | - | 2019-12-07 | - | - | no | - | -
15 | Heat exchanging equipment | 2 | no | [8 empty] | 2019-01-29 | 2019-09-23 | ЗЗ-О53-2-П-020/020-2019 ЗЗ-О53-3-П-020/020-2019 | Heat exchanging equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-05-31 | 2019-09-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00248 | 2019-11-03 | - | - | 2019-11-13 | - | - | 2019-11-28 | - | - | 2019-12-08 | - | - | no | - | -
16 | Pumping equipment | 3 | no | [8 empty] | 2019-09-30 | 2019-09-30 | ЗЗ-О53-2-П-216/00-2018 ЗЗ-О53-3-П-216/00-2018 | Pumping equipment | BU2-LJWG-2017-12-D014-23 | 2019-05-31 | 2019-10-22 | BU2-ASEM-NPPD-PSE-007ULTP00278 | 2019-12-01 | - | - | 2019-12-11 | - | - | 2019-12-26 | - | - | 2020-01-05 | - | - | no | - | -
17 | Pumping equipment (post-treatment units, tank units, sewage pump ) | 2.3 | no | [8 empty] | 2019-09-30 | 2019-09-30 | ЗЗ-О53-2-П-216/05-2018 | Pumping equipment (post-treatment units, tank units, sewage pump ) | BU2-LJWG-2017-12-D014-23 | 2019-05-31 | 2019-09-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00249 | 2019-11-03 | - | - | 2019-11-13 | - | - | 2019-11-28 | - | - | 2019-12-08 | - | - | no | - | -
18 | portable submersible pump semi-submersible pump, portable submersible centrifugal pump | 4 | no | [8 empty] | 2019-10-09 | 2019-10-09 | ЗЗ-О53-2-П-216/06-2018 ЗЗ-О53-3-П-216/06-2018 | portable submersible pump semi-submersible pump, portable submersible centrifugal pump | BU2-LJWG-2017-12-D014-23 | 2019-05-31 | 2019-09-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00250 | 2019-11-03 | - | - | 2019-11-13 | - | - | 2019-11-28 | - | - | 2019-12-08 | - | - | no | - | -
19 | Horizontal centrifugal pump | 4 | no | [8 empty] | 2019-10-10 | 2019-10-10 | ЗЗ-О53-2-П-216/07-2018 ЗЗ-О53-3-П-216/07-2018 | Horizontal centrifugal pump | BU2-LJWG-2017-12-D014-23 | 2019-05-31 | 2019-09-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00251 | 2019-11-03 | - | - | 2019-11-13 | - | - | 2019-11-28 | - | - | 2019-12-08 | - | - | no | - | -
20 | Gear-type pump | 4 | no | [8 empty] | 2019-05-15 | 2019-10-15 | ЗЗ-О53-2-П-216/08-2018 ЗЗ-О53-3-П-216/08-2018 | Gear-type pump | BU2-LJWG-2017-12-D014-23 | 2019-05-31 | 2019-09-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00252 | 2019-11-03 | - | - | 2019-11-13 | - | - | 2019-11-28 | - | - | 2019-12-08 | - | - | no | - | -
21 | Artesian pump | 2,3,4 | no | [8 empty] | 2018-12-13 | 2019-10-18 | ЗЗ-О53-2-П-216/09-2018 ЗЗ-О53-3-П-216/09-2018 | Artesian pump | BU2-LJWG-2017-12-D014-23 | 2019-05-31 | 2019-09-24 | BU2-ASEM-NPPD-GEN-007/ULTP/00253 | 2019-11-03 | - | - | 2019-11-13 | - | - | 2019-11-28 | - | - | 2019-12-08 | - | - | no | - | -
22 | Oil Tank | 2 | no | [8 empty] | 2019-06-11 | 2019-06-11 | ЗЗ-О53-2-П-256/05-2018 ЗЗ-О53-3-П-256/05-2018 | Oil Tank | BU2-LJWG-2017-12-D014-23 | 2019-05-31 | 2019-09-25 | BU2-ASEM-NPPD-GEN-007/ULTP/00257 | 2019-11-04 | - | - | 2019-11-14 | - | - | 2019-11-29 | - | - | 2019-12-09 | - | - | no | - | -
24 | Filtering equipment | 2,3,4 | no | [8 empty] | 2018-01-25 | 2019-10-24 | ЗЗ-О53-2-П-217/01-2018 ЗЗ-О53-3-П-217/01-2018 | Filtering equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-10-15 | 2019-10-03 | BU2-ASEM-NPPD-PSE-007ULTP00267 | 2019-11-12 | - | - | 2019-11-22 | - | - | 2019-12-07 | - | - | 2019-12-17 | - | - | no | - | -
25 | Dry transformers | 4 | no | [8 empty] | 2019-05-15 | 2019-10-24 | ЗЗ-Бшр2-3-П-145-2018 ЗЗ-Бшр2-П-145/00-2018 | Dry transformers | BU2-LJWG-2017-10-D001-002 | 2019-10-15 | 2019-10-03 | BU2-ASEM-NPPD-PSE-007ULTP00266 | 2019-11-12 | - | - | 2019-11-22 | - | - | 2019-12-07 | - | - | 2019-12-17 | - | - | no | - | -
26 | Filtering equipment | 4 | no | [8 empty] | 2019-08-16 | 2019-10-30 | ЗЗ-О53-2-П-220/01-2018 ЗЗ-О53-3-П-220/01-2018 | Filtering equipment | BU2-LJWG-2018-02-D038-47 BU2-LJWG-2018-03-84 | 2019-10-24 | 2019-10-18 | BU2-ASEM-NPPD-PSE-007ULTP00275 | 2019-11-27 | - | - | 2019-12-07 | - | - | 2019-12-22 | - | - | 2020-01-01 | - | - | no | - | -
27 | Mixers | 4 | no | [8 empty] | 2018-05-15 | 2019-10-30 | ЗЗ-О53-2-П-253/00-2019 ЗЗ-О53-3-П-253/00-2019 | Mixers | BU2-LJWG-2017-11-D003 BU2-LJWG-2017-11-D004 BU2-LJWG-2017-11-D005 BU2-LJWG-2017-11-D006 | 2019-10-25 | 2019-10-18 | BU2-ASEM-NPPD-PSE-007ULTP00276 | 2019-11-27 | - | - | 2019-12-07 | - | - | 2019-12-22 | - | - | 2020-01-01 | - | - | no | - | -
| Frequency converter | 4 | no | [8 empty] | 2019-05-15 | 2019-10-15 | ЗЗ-Бшр2-2-20910761-201396102 | Frequency converter | No Decision | 2018-05-15 | 2019-10-23 | BU2-ASEM-NPPD-GEN-007ULTP00285 | 2019-12-02 | - | - | 2019-12-12 | - | - | 2019-12-27 | - | - | 2020-01-06 | - | - | no | - | -
| Pipelines UJA UKC stage 2 (403 tones) | 2,3,4 | no | [8 empty] | 2018-12-13 | 2019-10-18 | ЗЗ-Бшр2-2-П-224/01-2018 ЗЗ-Бшр2-3-П-224/01-2018 | Pipelines UJA UKC stage 2 (403 tones) | BU2-LJWG-2019/06-D149 | 2019-11-01 | 2019-10-28 | BU2-ASEM-NPPD-PSE-007/ULTP/00288 | 2019-12-07 | - | - | 2019-12-17 | - | - | 2020-01-01 | - | - | 2020-01-11 | - | - | no | - | -
| SG emergency cooldown pump | 2 | no | [8 empty] | 2019-06-11 | 2019-06-11 | ЗЗ-Бшр2-П-217/05-2018 ЗЗ-Бшр3-П-217/05-2018 | SG emergency cooldown pump | BU2-LJWG-2017-12-D014-23 | 2019-08-15 | 2019-08-14 | BU2-ASEM-NPPD-PSE-007/ULTP/00140 | 2019-09-23 | - | - | 2019-10-03 | - | - | 2019-10-18 | - | - | 2019-10-28 | - | - | no | - | - | 1. PUMPIRAN 2. Navid Sahand Co 3. Petro Hirad Co 4. Petro Pedam | 2019-07-29 | 13996/2021 | SG emergency cooldown pump | Tender is completed
| Switchgear 0,4 kV | 2,3,4 | no | [8 empty] | 2018-01-25 | 2019-10-24 | ЗЗ-Бшр2-2-П-102-2018 ЗЗ-Бшр2-3-П-102-2018 | Switchgear 0,4 kV | BU2-LJWG-2018-02-D049-51 | 2019-11-08 | 2019-10-28 | BU2-ASEM-NPPD-PSE-007/ULTP/00287 | 2019-12-07 | - | - | 2019-12-17 | - | - | 2020-01-01 | - | - | 2020-01-11 | - | - | no | - | -
| Small diameter valves UJA UKC UKA | 4 | no | [8 empty] | 2019-05-15 | 2019-10-24 | ЗЗ-О53-2-П-148/00-2018 ЗЗ-О53-3-П-148/00-2018 | Small diameter valves UJA UKC UKA | BU2-LJWG-2017-11-D003-006 | 2019-11-08 | 2019-10-28 | BU2-ASEM-NPPD-PSE-007/ULTP/00289 | 2019-12-07 | - | - | 2019-12-17 | - | - | 2020-01-01 | - | - | 2020-01-11 | - | - | no | - | -
| Sand separator | 4 | no | [8 empty] | 2019-08-16 | 2019-10-30 | ЗЗ-О53-2-П-270/03-2018 | Sand separator | BU2-LJWG-2018-03-09 | 2019-11-14 | 2019-11-06 | BU2-ASEM-NPPD-GEN-007/ULTP/00298
| Stands, tools, laboratory equipment | 4 | no | [8 empty] | 2018-05-15 | 2019-10-30 | ЗЗ-Бшр2-2-П-169/00-2018 | Stands, tools, laboratory equipment | BU2-LJWG-2018-02-D058 BU2-LJWG-2018-03-81 BU2-LJWG-2018-03-82 BU2-LJWG-2018-05-105 BU2-LJWG-2018-05-106 | 2019-11-14 | 2019-11-11 | BU2-ASEM-NPPD-PSE-007/ULTP/00302
| GMM pumps | 4 | no | [8 empty] | 2019-10-18 | 2019-10-31 | ЗЗ-О53-2-П-216/11-2019 | GMM pumps | BU2-LJWG-2017-12-D014-23 | 2019-11-15 | 2019-11-11 | BU2-ASEM-NPPD-PSE-007/ULTP/00301
| Generator bus-bar system | 3 | no | [8 empty] | 2019-05-15 | 2019-05-15 | ЗЗ-Бшр2-2-20910761-201396120 | Generator bus-bar system | Нет Решения | 2019-05-30 | 2019-08-13 | BU2-ASEM-NPPD-GEN-007/ULTP/00195 | 2019-09-22 | 2019-11-07 | 10020-261998
1 | Filtering device | 2 | no | 2019-04-16 | выполнено | 2019-05-06 | выполнено | 2019-06-15 | выполнено | 2019-07-15 | выполнено | 2019-07-15 | 2019-02-06 | ЗЗ-Бшр2-2-20910761-201396102 | Filtering device | BU2-LJWG-2018-12-D144 | 2019-02-21 | 2018-10-22 | BU2-ASEM-NPPD-PSE-007/ULTP/00024 | 2019-04-02 | 2018-12-15 | 4300-103266 | Not manufactured. Decision BU2/LJWG-2019/04-D144 | [12 empty] | 2019-04-13 | 13996/390 | Filtering device | Tender is completed
2 | Main steam vavle unit | 2 | yes | Не производится BU2/LJWG-2018/09-D116 | [7 empty] | 2018-11-23 | 2018-11-23 | ЗЗ-Бшр2-2-П-224/01-2018 ЗЗ-Бшр2-3-П-224/01-2018 | Main steam vavle unit | Not manufactured. Decision BU2/LJWG-2018/09-D116 | [19 empty] | 2019-02-21 | 12375/858 | Main steam vavle unit | Import
3 | CIB. Measuring devices | 2 | yes | Не производится BU2/LJWG-2018/09-D116 | [7 empty] | 2018-11-23 | 2018-11-23 | ЗЗ-Бшр2-П-217/05-2018 ЗЗ-Бшр3-П-217/05-2018 | CIB. Measuring devices | Not manufactured. Decision BU2/LJWG-2018/09-D116 | [19 empty] | 2019-02-11 | 12375/806 | CIB. Measuring devices | Import
4 | CIB Equipment | 4 | no | Не производится. Решение BU2/LJWG-2018-03/D082 | [8 empty] | 2018-11-13 | ЗЗ-О53-2-agrechukhin-201404051 | CIB Equipment | Not manufactured. DecisionBU2/LJWG-2018-03/D082 | [21 empty] | CIB Equipment | Import
5 | Power supply unit | 4 | no | 2018-12-15 | выполнено | 2019-01-04 | выполнено | 2019-02-13 | выполнено | 2019-03-15 | выполнено | 2019-03-15 | 2019-03-15 | ЗЗ-Бшр2-2-П-102-2018 ЗЗ-Бшр2-3-П-102-2018 | Power supply unit | Not manufactured. Decision BU2/LJWG-2017/12-D023 | [19 empty] | 2019-02-25 | 10583/61 | Power supply unit | Import
6 | Manufacture and supply of equipment for the reactor concrete pit | 2 | no | Не производится. Решение BU2-LJWG-2017-12-D025 | [7 empty] | 2019-01-22 | 2019-01-22 | ЗЗ-О53-2-П-148/00-2018 ЗЗ-О53-3-П-148/00-2018 | Manufacture and supply of equipment for the reactor concrete pit | Not manufactured BU2-LJWG-2017-12-D025 | [19 empty] | 2019-02-20 | 10583/58 | Manufacture and supply of equipment for the reactor concrete pit | Import
7 | Supply and manufacturing equipment for reactor pit | 2 | no | Не производится. Решение BU2-LJWG-2017-12-D026 | [7 empty] | 2019-01-22 | 2019-01-22 | ЗЗ-О53-2-П-270/03-2018 | Supply and manufacturing equipment for reactor pit | Not manufactured. Decision BU2-LJWG-2017-12-D026 | [19 empty] | 2019-02-15 | 10583/45 | Supply and manufacturing equipment for reactor pit | Import
8 | LMCE equipment | 3, 4 | no | Не производится. Решение BU2-LJWG-2017-12-D026 | [7 empty] | 2019-01-22 | 2019-01-22 | ЗЗ-Бшр2-2-П-169/00-2018 | LMCE equipment | Not manufactured. Decision BU2-LJWG-2017-12-D026 | [19 empty] | 2019-04-16 | 13996/670 | LMCE equipment | Import
9 | Water jet pump | 2 | no | Не производится. Решение BU2/LJWG-2019/02-D138 | [7 empty] | 2018-09-11 | 2018-09-11 | ЗЗ-Бшр2-П-092/01-2018 | Water jet pump | Not manufactured. Decision BU2/LJWG-2019/02-D138 | [21 empty] | Water jet pump | Import
10 | LMCE equipment | 2 | no | 2019-02-21 |  | 2019-03-13 |  | 2019-04-22 |  | 2019-05-22 |  | 2019-05-22 | 2019-05-22 | ЗЗ-Бшр2-2-П-225/00-2018 | LMCE equipment | Not manufactured. DecisionBU2-LJWG-2017-12-D026 | [19 empty] | 2019-05-27 | 13996/297 | LMCE equipment | Import
11 | Supply of test equipment for laboratories | 2 | no | [8 empty] | 2018-09-24 | 2018-09-24 | ЗЗ-Бшр2-2-П-246/00-2018 | Supply of test equipment for laboratories | Not manufactured. DecisionBU2-LJWG-2018-11-D119 | [19 empty] | 2019-03-15 | 13996/1192 | Supply of test equipment for laboratories | Tender is completed
13 | Transportation cask shock absorber | 2 | no | [8 empty] | 2018-09-11 | 2018-09-11 | ЗЗ-Бшр2-2-П-268/00-2018 | Transportation cask shock absorber | Not manufactured. Decision BU2/LJWG-2018/12-D134 | [21 empty] | Transportation cask shock absorber | Import
14 | Condencer Vacuum tube | 3 | no | [8 empty] | 2019-06-03 | 2019-06-03 | ЗЗ-Бшр2-П-217/16-2018 | Condencer Vacuum tube | Not manufactured. Decision BU2/LJWG-2018/12-D137 | [21 empty] | Condencer Vacuum tube | Import
15 | Containment pre-stressing system | 2, 4 | no | [8 empty] | 2019-06-24 | 2019-06-24 | ЗЗ-Бшр2-П-030/00-2017 | Containment pre-stressing system | Not manufactured. Decision BU2/LJWG-2017/12-D029 | [21 empty] | Containment pre-stressing system | Import
16 | LMCE. Turbine hall | 3 | no | [8 empty] | 2019-05-28 | 2019-05-28 | ЗЗ-Бшр2-2-П-295/01-2019 | LMCE. Turbine hall | BU2-LJWG-2017-12-D014-23 | Not manufactured. Decision BU2-LJWG-2017-12-D024 | [20 empty] | LMCE. Turbine hall | Import
17 | Hermetic pipe penetrations | 3 | no | [8 empty] | 2019-05-15 | 2019-07-11 | ЗЗ-О53-3-П-454/00-2019 ЗЗ-О53-3-П-454/00-2019 | Hermetic pipe penetrations | Not manufactured. Decision BU2/LJWG-2018/02-D059 | [21 empty] | Hermetic pipe penetrations | Import
Formulas:
План = [План]-20
План = [No answer]
Plan = [План]+15
Plan = [Plan]+40
No answer = [План]
Note on AJ42: PSP (целевой) офиц. отказывалась от лота н инвертеры 4 класс