**Comments on:**

STSA Tasks and Gantt chart

1. **General comments:**
2. Topical meetings related to particular improvement measures should be placed and scheduled within T5 and T6. The detailed description of work stages and time schedule can be discussed during these meetings. A frequency and duration of those meetings would be specified when the Stress Tests Action Plan and the OSART Mission Action Plan are available.
3. Stress Tests Action Plan and the OSART Mission Action Plan should be part of the outcomes of task 5 and 6. An integrated plan for implementation of final safety improvements should also be considered as an outcome of task 6.
4. A final meeting is envisaged to be held in accordance with TOR requirements. It should be scheduled at the end of the project.
5. **Specific comments:**
6. **STSA Bushehr, Page 5, Gantt Chart:**

Two visits of End User’s experts to EU should be mentioned within the Task 1 and 5.

1. **STSA Bushehr, Page 5, Gantt Chart:**

There is a time gap between task 2 and 3. It should be checked. Task 2 is finished at 6/6/19 and task 3 will be started at 7/16/19.

1. **STSA Bushehr, Page 5, Gantt Chart:**

Beginning and end date of “selected OSART recommendations detailed review” and “Harmonization with ST recommendations” seems to be incorrect.

1. **STSA Bushehr, Page 5, Gantt Chart:**

If main topic of workshop-2 is methodology draft presentation and comments fixing, it should be placed and scheduled before STSA methodology report finalizing and if it is final report presentation, then the main topic shall be amended.