## PCMFExport
IRA2012: Action Pland for implementation of | [7 empty] | 2014-07-25
Workplan activties in 2012-2013for IRA/4/038 | in 2014-2017
Activity | Implementing Officers/Input | Venue | Type | Funding | Budget | Budget Year | Date | Comments
1.2 Conducting project review meetings | IAEA: Gueorguiev, NPPD: Fatourechian
| 1.2.1 - 1.2.4 Annual project review and planning meeting (3 IAEA staff for 3 days) | Tehran and Bushehr | Expert | FootNote | 39,195 | 2012 | Q1/2014-2017 | one meeting per year 1.2.1 Meeting in 2014 completed
1.5 IAEA field monitoring | IAEA: Gueorguiev, NPPD: Fatourechian
| 1.5.1 - 1.5.4 Reqular field monitoring and review missions (1 IAEA staff for 4 days) | Tehran and Bushehr | Meeting | FootNote | 21,000 | 2012 | 2014-2017 | 1-2 missions per quarter In progress
2.2 Spent fuel storage and waste management programs | IAEA:Ormai/Dyck, NPPD:Sheikholeslami
| 2.2.1 EM to assist in radioactive waste management programme, including scaling factor application (1 IAEA staff and 3 IEX) | Tehran | EM | FootNote | 3,095 | 2012 | 27 Sept - 1 Oct 2014 | Jointly with IRA2011/1.17.3 In progress
| 2.2.2 EM to assist in spent fuel storage (1 IAEA staff and 3 IEX) | TBD | EM |  |  |  | Q1/2017
3.1 Development of training materials for two new NPP projects | IAEA:Pal Vincze , NPPD: Fatourechian
| 3.1.1 EM to assist in review of selected/developed training materials for two new NPP units (1 IAEA staff and 3 IEX) | TBD | HBA/EM TBD | FootNote | 16,725 | 2012 | Q4/2015
| 3.1.2 EM to assist in review of selected/developed training materials for two new NPP units (1 IAEA staff and 3 IEX) | TBD | HBA/EM TBD |  |  |  | Q1/2017
3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant | IAEA: Kang, NPPD: Tajbakhsh
| 3.2.1. WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety (1 IAEA saff and 2 IEX for 4 days) | Tehran Bushehr | WS | HardCore | 21,000 | 2012 | 27-30 April 2014 | Completed
5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations | IAEA: Yagi/Lipar; NPPD: Sheikholeslami
| 5.1.1 WS to assist NPPD in addressing Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations (6 NEX and 3 IEX) | Tehran/Vienna | WS | FootNote | 21,000 | 2012 | Q3-4/2014 | Specific issues of interest to be provided by 15 March,2014
6.1 Public information and awareness programmes development | IAEA:B. Pagannone/Lipar , NPPD:Rahnama
| 6.1.1 WS on public information and awareness programmes (4-6 NEX and 2 IEX) | Tehran | WS | FootNote | 16,350 | 2012 | 28 Sept-1 Oct 2014 | In progress
| 6.1.2 EM to assist on the establishment of public information and awareness centre (1 IAEA staff and 2 IEX ) | Tehran/Bushehr | EM |  |  |  | Q4/2016
2.1 Seismic safety assessment | IAEA:O.Coman, NPPD:Sheikholeslami
| 2.1.1 EM to assist in seismic safety assessment (1 IAEA staff and 3 IEX) | Tehran/Vienna | EM | FootNote | 40,095 | 2013 | Q1/2015 | Specific interest to be provided by NPPD.
3.3 Corporate knowledge management | IAEA:J.de Grosbois /Kang NPPD:Rahnama/Sheikholeslami
| 3.3.1 EM on corporate knowledge management (1 IAEA staff and 3 IEX) | Tehran | EM | FootNote | 7,805 | 2013 | Q2/2015
| 3.3.2 EM on Maintenance of design basis information through life cycle | Tehran | EM |  |  |  | Q1/2015
3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr | IAEA: , NPPD:Amini
| 3.4.1 WS on nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr (1 IAEA staff and 2 IEX) | TBD | WS | FootNote | 22,275 | 2013 | Q2/2015
| 3.4.2 SV on nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr | TBD | SV |  |  |  | Q4/2015
4.1 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr | IAEA:Molloy/Kang/Lipar , NPPD: Rahnama/Fatourechian | [6 empty] | continuation of IRA4038
| 4.1.1 EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units (1 IAEA sraff and 3 IEX) | TBD | HBA/EM TBD | HardCore | 27,875 | 2013 | Q2/2015 | Specific needs to be provided by NPPD.
| 4.1.2 EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units (1 IAEA sraff and 3 IEX) | TBD | HBA/EM TBD |  |  |  | Q3/2016 | Specific needs to be provided by NPPD.
| 4.1.3 WS on project management with focus on safety requirements | ICTC in China | WS |  |  |  | Q4/2014 | IAEA provided information on ICTC. NPPD to submit request
4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units | IAEA: , NPPD: | [6 empty] | Jointly with 4.1.2
| 4.2.1 EM to assist in review and evaluation of the developed programme for upgrading owner's training system for thje two new PWR units (1 IAEA staff and # IEX) | TBD | EM and HBA | FootNote | 13,365 | 2013 | Q4/2015