## Sheet1
Project Objective
Logical Framework Matrix (LFM) for IRA………..
| Design Element | Indicator | Means of Verification | Assumptions
Outcome | Enhanced owner's capabilies towards safe and reliable operation and maintenance of BNPP-1. | Performance and safety indicators are assessed and in all areas improved by the end of 2018 in comparison with the baseline | Annual report of performance section in 2018 IAEA and NPPD assessment and project review meetings | Qualified external experts can be readily recruited for the implementation of planned activities and adequate progress is made in finding suitable institutes for hosting Scientific Visits and Fellowships. Adequate resources are available for providing laboratory equipment and improving access to proper computer codes necessary for nuclear safety.
Output | 1 Safety management is assessed and thoroughly improved | Safety performance indicators are collected and analyzed by the end of 2018,Capabilities for independent safety analysis | Annual report of performance section in 2018
| 2 Technical Support program is improved. | 20 staff of Technical support department capable of using the new methods in planning and implementation of new methods for modernization of equipment and inspection activities. | assessment report
| 3 Outage Management is optimized and updated. | 20 staff of M&R department capable of using the new methods in M&R process planning and implementation of procedures | assessment report
| 4 Human resources management system is improved. | All procedures and training plans are revised by the end of 2Q2018 | Revised procedures , docs. and training plans
| 5 Accident management includes severe accident management and nuclear emergency response improvement | procedures and accident management plans are revised by the end of 2Q2018. 20 staff of BNPP personel capable of using the new methods inaccident management | Annual report of safety manger
| 6 Health, environmental and ecological management improvement | procedures and their plans are revised by the end of 2Q2018 | Annual report of safety manger
Activity | 1.1 Safety training through a Visit on radioactive waste management, radiation monitoring, core calculation and emergency preparedness | Scientific visit completed, 5 staff participate in the SV by the end of Q2 2016 | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 1.2. Scientific visits on safety management in the field of operation, Radiation Protection, technical support and emergency preprdness. | Scientific visit completed, 3-4 BNPP-1 Managers participate in the SV by the end of Q2 2017 | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 1.3.1 Preparatory mission for OSART mission | Prepared action plan for implmentation OSART mission in Q1 2016 | Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 1.3.2. Implementation of OSART Mission | OSART mission completed by end of Q2 2017 | End of mission report | All planned inputs are timely available. Three weeks Expert Mission with 2 Agency staff and 10 international experts.
| 1.4.1 Implementation the Nuclear oversight function | Expert mission to assist NPPD for Implementation the Nuclear oversight function completed by the end of Q2 2016 & Q3 2017 | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 2.1..1 Training through a Visit on environmental qualification improvement | Scientific visit completed, 3-4 staff participate in the SV by the end of Q1 2016 | Technical Advise and providing "creating an anti-corrosion plan" in BNPP | All planned inputs are timely available.
| 2.1.2 Training on modern method for measuring hydrogen of aerosol, and corrosives chemical-physical cleaning of radioactive Power plant equipment | Training course completed, 20 staff of Technical support department are trained by the end of Q3 2016. | Technical Advise and preparation of relevant reports. | All planned inputs are timely available. One week Workshop with one Agency staff and 2 exernal Experts
| 2.2. Training to strengthen technical control section capabilities and qualification for supervision on repairs of NPPs | Training course completed, 20 staff of Technical support department are trained by the end of Q1 2016. | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week Workshop with one Agency staff and 2 exernal Experts
| 2.3 Training on failure analysis and necessary tests on equipment during operation | Training course completed, 20 staff of Technical support department are trained by the end of Q3 2016. | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week Workshop with one Agency staff and 2 exernal Experts
| 2.4 Training through a Visit on containment tests during outage calculations | Scientific visit completed onsample tests and analysis result of containment tests, 5 staff participate in the SV by the end of Q2 2016 | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week SV.
| 2.5.1. Scientific visit on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system; | Scientific visit completed on decreasing the time response of APCS system; 5 staff participate in the SV by the end of Q3 2016. | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week SV.
| 2.5.2. To strengthen the capability of BNPP personnel on application of new standards of IAEA in modification MCR (new TLSU system) | Training course completed, 20 staff of Technical support department are trained by the end of Q1 2016. | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week SV.
| 2.6 Training course on computer networks security | Training course completed, 10 staff are trained by the end of Q2 2016.10 personnel to be familiare with the subject “network security”. | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week Workshop with one Agency staff and 2 exernal Experts
| 2.7 Development of measures in case of proposal to change of BNPP-1 nuclear fuel for extention of refueling period | EM completed in Q3 2016 | Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 2.8 Reactor core operation in stationary and transient conditions | EM completed in Q3 2016. | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week Workshop with one Agency staff and 2 exernal Experts
| 3.1.1. Training course on Modern methods of CM (Condition Based Maintenance) at Nuclear Power Plants for Optimizing maintenance and repair programmes | EM completed in Q3 2016 | Technical Advise and preparation of relevant reports to Change the maintenance and repair Strategy from PM( preventive maintenance ) to CM(Condition Based Maintenance), Increase the reliability and efficiency of equipment,Reduction of labour, maintenance costs | All planned inputs are timely available. EM at BNPP ,one Agency staff and 2 exernal Experts
| 3.1.2.Scientific visit on implementation of strategies and advanced method tools for CM (Condition Based Maintenance) at NPPs. | Scientific visit completed on CM (Condition Based Maintenance) at NPPs.and Utilization new methods, techniques, materials and tools for it ; 5 staff participate in the SV in Q2 2017. | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week SV.
| 3.2.1. Training course on advance methods,new techniques and materials,modern tools for Maintenance and repair WWER-1000 Reactor , refuling machine ,equipment and pipelines at Nuclear Power Plants | Training course completed, 20 staff are trained by the end of Q3 2017. | Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 3.2.2. Scientific visit on NPPs for Optimizing overall WWER-1000 Reactor and refuling process with focus on new techniques and materials,modern tools and advance method to strengthen the capablity refuling machine operators | Scientific visit completed on outage duration such as :reduce refuling duration,the failure of refuling machine and time of uninstaliation and instaliation reactor ; 3-4 staff to be participated in the SV in Q3 2017. | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week SV.
| 3.3.1. Training to strengthen the capability on Reverse-design engineering of the repairing parts of the equipment and designing of special tools related to repairs activities at NPPs. | EM completed on Reverse-design engineering of the repairing parts and the structure of the engineering design management of repairs in Q3 2017. | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week EM one Agency staff and 2 exernal Experts .
| 3.3.2.Training through Scientific visit for Optimizing the Reverse-design engineering, Designing of special tools and optimizing the reverse design including special tools | SV completed on the structure of the engineering design management of repairs ,designing and providing the special tools engineering design, 5 staff participate in Q1 2018. | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week SV.
| 3.4. Training through Scientific visit on NPPs emergency repair team on enhancement of preparedness and responsibility of BNPP emergency repair teams. | SV completed by Q2 2017on enhancment on-site and off-site emergency preparedness and response. and emergency repairs. | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week SV.
| 3.5. Training course on development of a procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance | Training course completed, 20 staff are trained by the end of Q3 2016. | Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 4.1.1. Training on improvement of personnel performance , competency models, method / tools for their assessment | Training course completed, 20 staff are trained by Q2 2016 to strenghten capabilities for further improvement on the personnel performance assessment system | Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 4.1.2. Training through Scientific visit on Strengthening capabilities for assessing the personel performance process and its relationship to the other human resources sub- systems | Scientific visit completed on improvement of the personnel performance assessment system by the end of Q4 2016 | Technical Advise and preparation of relevant reports | All planned inputs are timely available.
| 4.1.3 Improvement the performance assessment system | EM completed by Q3 2017 to further improvement of personnel performance assessment system | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week EM with 1 Agency Expert and 3 External Experts
| 4.2.1. Improvement of job classifications plan and career development | WS/EM completed by the end of Q1 2017 on exchange of the worldwide experiences on its criteria, specification and methods in NPPs | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week WS /EM with 1 Agency Expert and 3 External Experts
| 4.2.2.Improvement of job work-paths document for Bushehr NPP | EM completed by Q1 2018 to further improvement of job work-paths document for Bushehr NPP | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week WS /EM with 1 Agency Expert and 3 External Experts
| 4.3.Development of selected training scenarios for severe accidents for training in FSS | EM completed by Q3 2016 on completion of the scenarios of FSS in severe accident area | Technical Advise and preparation of relevant reports | All planned inputs are timely available. One week WS /EM with 1 Agency Expert and 3 External Experts
| 4.4.Development & improvement training system of maintenance & repair personnel . | EMs completed in Q1 2016, 2017 & 2018 on assistance for improving the maintenance and repair training system | Technical Advise and preparation of relevant reports as well as supporting to provide necessary docs. , tools and equipments | All planned inputs are timely available.
| 5.1. Training on medical Response to Radiological Emergency Situation at nuclear instalations and NPPs. | Training course completed on preparation of BNPP and off-site organizations in Emergency situation , 20 staff are trained by the end of Q4 2016. | Technical Advise and preparation of relevant reports | All planned inputs are timely available for WS in 3 days at BNPP.
| 5.2. Review of BNPP on site Emergency Preparedness Program | EM completed in Q4 2018 , to assist on development new version of BNPP Emergency Documents. | Through Expert Mission, Training Course, Scientific Visit and Technical Advise and preparation of relevant reports | All planned inputs are timely available
| 6.1. Training on improving BNPP on Occupational health and safety management system including specifications and Methods for reducing the human errors and supervision on personnel performance. | Training course completed, 20 staff are trained by Q1 2017. | Technical Advise and preparation of relevant reports | All planned inputs are timely available
| 6.2. Training on assessing doses in normal Operation and radiological Emergency. | Training course completed, 20 staff are trained by Q4 2017.Focus on Running the dipersion model and participating in related proficiency tests. | Technical Advise and preparation of relevant reports. | All planned inputs are timely available for WS at BNPP. One Agency staff and 2 external experts.
| 6.3. Methods in the Alpha and beta-emitting radionuclides in high activity samples. | EM completed by Q1 2018 on achieved results by BNPP experts in Laboratory with use of reference materials as well as participating in proficiency tests | Technical Advise and preparation of relevant reports. | All planned inputs are timely available . One Agency staff and 2 external experts.The place is BNPP.
| 6.4. The methods for gamma spectrometry for high activity samples and counting devices in spectrometry Laboratories | EM completed in Q2 2016 , strenghten capabilities on New methods for analyzing and identifying Gamma-Emittig Radionuclides in smples. Counting devices in laboratories with high activity samples. | Technical Advise and preparation of relevant reports. | All planned inputs are timely available . One Agency staff and 2 external experts.The place is BNPP.
Input 1.1 | SV1 for one week
Input 1.2 | SV for one week
Input 1.3.1 | One week EM with 1 Agency Expert and 2 External Experts
Input 1.3.2 | Three weeks Expert Mission with 12 Agency Experts
Input 1.4.1 | Two weeks Expert Mission
Input 2.1.1 | SV for one week
Input 2.1.2 | One week Workshop with one Agency staff and 2 exernal Experts
Input 2.2. | One week Workshop with one Agency staff and 2 exernal Experts
Input 2.3. | One week Workshop with one Agency staff and 2 exernal Experts
Input 2.4. | SV for one week
Input 2.5.1. | SV for one week
Input 2.5.2. | One week Workshop with one Agency staff and 2 exernal Experts
Input 2.6. | One week Workshop with one Agency staff and 2 exernal Experts
Input 2.7 | One week EM with 1 Agency Expert and 3 External Experts
Input 2.8 | One week EM with 1 Agency Expert and 2 External Experts
Input 3.1.1 | One week EM with 1 Agency Expert and 2 External Experts
Input 3.1.2. | SV for one week
Input 3.2.1. | One week Workshop with one Agency staff and 2 exernal Experts
Input 3.2.2. | SV for one week
Input 3.3.1. | One week EM with 1 Agency Expert and 2 External Experts
Input 3.3.2. | SV for one week
Input 3.4. | SV for one week
Input 3.5 | One week Workshop with one Agency staff and 3 exernal Experts
Input 4.1.1 | One week Workshop with one Agency staff and 2 exernal Experts
Input 4.1.2 | SV for one week
Input 4.1.3 | One week EM with 1 Agency Expert and 3 External Experts
Input 4.2.1 | One week Workshop with one Agency staff and 3 exernal Experts
Input 4.2.2 | One week EM with 1 Agency Expert and 3 External Experts
Input 4.3 | One week EM with 1 Agency Expert and 3 External Experts
Input 4.4 | Three weeks EM with 1 Agency Expert and 2 External Experts
Input 5.1. | One week Workshop with one Agency staff and 2 exernal Experts
Input 5.2 | One week EM with 1 Agency Expert and 2 External Experts
Input 6.1. | One week Workshop with one Agency staff and 2 exernal Experts
Input 6.2. | One week Workshop with one Agency staff and 2 exernal Experts
Input 6.3. | One week EM with 1 Agency Expert and 2 External Experts
Input 6.4. | One week EM with 1 Agency Expert and 2 External Experts