## IRA2012_Nov_2016
IRA2012: Action Plan for implementation of Workplan activities in 2014-2017
as of 30.11.2016
Increasing NPPD's Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Funding | Budget | Budget Year | Date | Changed Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting 2014 | IAEA: Gueorguiev, NPPD: Fatourechian | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | FootNote | 39,195 | 2012 | Q1/2014 |  | Completed
2 | 1.2.2 | Annual project review and planning meeting 2015 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2015 |  | Completed, 15-17 February 2015 in Tehran
3 | 1.2.3 | Annual project review and planning meeting 2016 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2016 |  | Completed 29 February - 2 March
4 | 1.2.4 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | EM |  |  |  | Q1 2017 |  |  |  | 14-15 Feb 2017 as agreed date
1.5 IAEA field monitoring
5 | 1.5.1 | Reqular field monitoring and review missions | IAEA: Gueorguiev, NPPD: Fatourechian | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2014 |  | Completed
6 | 1.5.2 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2015 |  | Completed
7 | 1.5.3 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2016 |  |  |  | 1-2 missions per quarter jointly with IRA2013
8 | 1.5.4 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | FootNote | 21,000 | 2012 | 2017 |  |  |  | 1-2 missions per quarter jointly with IRA2013
2.2 Spent fuel storage and waste management programs
9 | 2.2.1 | EM to assist in radioactive waste management programme, including scaling factor application | IAEA:Ormai/Dyck, NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX |  | Tehran | EM | FootNote | 3,095 | 2012 | 27 Sept - 1 Oct 2014 |  | Jointly with IRA2011/1.17.3 Completed
10 | 2.2.2 | EM to assist in spent fuel storage | IAEA: C. Hill NPPD: Derakhahandeh | 1 IAEA staff and 3 IEX |  | TBD | EM |  |  |  | Q2/2018- Shifted to New Project |  |  | H | Follow-up mission under 2011. Postpone to New Project.NPPD will elaborate its need 2 months in advance.
3.1 Development of training materials for two new NPP projects
11 | 3.1.1 | EM to assist in review of selected/developed training materials for future operatorsfor two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | Q4/2017 |  | To be implemented on the developed materials provided by the supplier of two new units | H
12 | 3.1.2 | EM to assist in review of selected/developed training materials for future operators for two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | FootNote | 16,725 | 2012 | Q4/2017 |  | To be implemented on the developed materials provided by the supplier of two new units | H | merged with 3.1.1
3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant
13 | 3.2.1. | WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety | IAEA: Kang, NPPD: Tajbakhsh | 1 IAEA staff and 2 IEX for 4 days |  | Tehran Bushehr | WS | HardCore | 21,000 | 2012 | 27-30 April 2014 |  | Completed
5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations
14 | 5.1.1 | WS To assist in development of the Local Industry Utilization Plan | IAEA: Kang NPPD: Derakhshandeh | 1 IAEA staff and 2 IEX for 5 days |  | Tehran | WS | FootNote | 21,000 | 2012 | Q2/2017 |  | NPPD will provide the necessary inputs (expectation) by the end of Feb. | M | NPPD: Specific issues related to local industry will be sent to the IAEA two months before the WS
6.1 Public information and awareness programmes development
15 | 6.1.1 | WS on public information and awareness programmes | IAEA:B. Pagannone/ NPPD:Rahnama | 4-6 NEX and 2 IEX |  | Tehran | WS | FootNote | 16,350 | 2012 | 28 Sept-1 Oct 2014 |  | Completed
16 | 6.1.2 | EM to assist on the establishment of public information and awareness centre | IAEA: D. Drury NPPD: Rahnama | 1 IAEA staff and 2 IEX |  | Tehran/Bushehr | EM |  |  |  | Q3/2017 |  |  | M | NPPD is requested to send the IAEA two months before the draft plan/status description for the Centre.
17 | 6.1.3 | EM to review results of Stakeholder Involvement Plan | IAEA: D. Drury NPPD: Rahnama | TBD |  | Tehran | EM |  |  |  | 2017 |  | Based on the results of 6.1.2 | M | Additional request as follow-up of 6.1.1. New request
18 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: D. Drury NPPD: Rahnama | TBD |  | TBD | SV |  |  |  | 2017 |  |  | M | Additional request as follow-up of 6.1.1. New request. NFs will send 6 months before.
2.1 Seismic safety assessment
19 | 2.1.1 | EM to assist in seismic safety assessment | IAEA:Y.Fukushima, NPPD: Shirzadi/Derakhshandeh | 1 IAEA staff and 3 IEX |  | Tehran / Bushehr | EM | FootNote | 40,095 | 2013 | 1-4 october 2016 | 1-4 October, Planned Implementation | Completed | H
20 | 2.1.2 | WS/EM on seismic safety | IAEA:Y.Fukushima, NPPD: Shirzadi/Derakhshandeh | TBD ( 4 days) |  | TBD | WS/EM |  |  |  | Q2/2017 |  |  | M | Considering the EMR on 2.1.1, NPPD will define the scope of needs for further proceed.
3.3 Corporate knowledge management
21 | 3.3.1 | EM on corporate knowledge management for BNPP - 2&3 with focus on safety | IAEA:Z. Pasztory NPPD:Rahnama/Sheikholeslami | 1 IAEA staff and 3 IEX, 4 days |  | Tehran | EM | FootNote | 7,805 | 2013 | 15-18 Nov. 2015 |  | Completed
22 | 3.3.2 | EM on Management and maintaining design basis information through life cycle of BNPP-2&3 | IAEA:J. de Grosbois, Kolomiets 1 IAEA staff and 3IEX | I IAEA + 2 IEX |  | Tehran | EM |  |  |  | 21-25 April 2016 (3 days) |  | Completed
3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr
23 | 3.4.1 | WS on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (cancelled) | [5 empty] | FootNote | 22,275 | 2013 |  |  | NPPD does not need further assistance
24 | 3.4.2 | SV on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (SG) | IAEA: M. Mishar, SG NPPD: NPPD:Amini | 3NEX |  | TBD | SV |  |  |  | 2016 |  | Cancelled | H | NFs to be provided timely in advance
4.4 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr
25 | 4.1.1 | EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units | IAEA: Drury, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | HardCore | 27,875 | 2013 | Q2/2017 |  |  | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. Jointly with 4.2.1 New task (Possible home based assignment)
26 | 4.1.2 | EM to assist in evaluation of developed programmes to update owner's training system for the two new PWR units | IAEA: Drury, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | Q2/2017 |  | To be moved to 2018-2019, new project | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. New task
27 | 4.1.3 | Group Trainig programme on pre-construction management with focus on safety requirements | IAEA: Kang; NPPD: Fatourechian | 1 IAEA Staff, 20 NEX |  | ICTC, Beijing, China | WS |  |  |  | 24 Aug.-4 Sept. 2015 |  | Completed
28 | 4.1.4 | EM to assist in development of comprehensive model for effective project management of the two new NPP units (1 + 3 IEX) | IAEA: Pekka Pyy. NPPD: Rahnama | 1 IAEA Staff and 3 IEX |  | Tehran | EM |  |  |  | 8-11 Nov. 2015 |  | Completed
29 | 4.1.5 | Group Fellowship Trainig on construction and commissioning management with focus on safety requirements | IAEA: K. S. Kang NPPD: Fatourechian/Rahnama | 2 IAEA staff and 20 NEX. The cost for the WS is expected cca. 100 000 EURs. |  | S. Korea | Group fellowship training |  |  |  | Q4/2017 |  |  | H
30 | 4.1.6 | EM to assist in the review of the developed Project Management System for units 2 and 3 of the new project. | IAEA: Pekka Pyy. NPPD: Fatourechian/Rahnama | 1 IAEA/3 IEX 4 days. |  | Tehran | EM |  |  |  | Q3 /2017 |  |  | H | NPPD: To send the scope and focus and the related documents two months before the mission. New request
4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units
31 | 4.2.1 | EM to assist in review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | EM and HBA | FootNote | 13,365 | 2013 | Q2/2017 |  |  | H | Jointly with 4.1.1
Cancelled
Further clarifications needed
| Completed | [9 empty] | 10 active tasks
| Move to new project (2018-2019) |  |  |  | H=5,M=5
Note on L34: Akbari , Amir: It was planned on Sep.2016, Planned Implementation on 1-4 October

## IRA2013_Nov_2016
IRA2013: Action Plan for implementation of Workplan activties in 2016-2017
as of 30.11.2016
Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed
2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | PRM | 14-15 Feb. 2017 | In progress
1.5 IAEA Field Monitoring (once per quarther)
2.2 Preparatory visit for OSART mission
3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | 14-16 Nov 2016 | Completed | H | Planned for 14-16 November 2016.
2.4 Implementation the nuclear safety oversight function
4 | 2.4.1 | One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: Derakhshandeh | 1 IAEA+2IEX |  | Tehran | EM | Q1/2017 | Cancelled | M
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
5 | 3.1.1 | WS on "modern methods for measuring hydrogen concentration in containment " | IAEA: Song, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | 18-21 Feb 2017 | In progress | H
3.2 Training on environmental qualification of safety equipment of BNPP-1
6 | 3.2.1 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD | SV | Q2-Q3/2017 | Pending SV nomination. As agreed in the May coordination meeting,the SV to be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. This can be reflected in the SV nomination form. Review of the SV can only be done once we receive the SV nominations.NPPD will send 3 NFs by the mid of Dec 2016 through official channel. Considering above mentioned prerequisite, it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or Brazil
7 | 3.2.2 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q2-Q3/2017 | NPPD will send 3 NFs by the mid of Dec 2016 through official channel. Considering above mentioned necessary prerequisite, it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or Brazil
8 | 3.2.3 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q2-Q3/2017 | NPPD will send 3 NFs by the mid of Dec 2016 through official channel. Considering above mentioned necessary prerequisite, it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or Brazil
3.3 Training on equipment reliability assessment techniqes of equipment during operation
9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" | IAEA: K. Kang, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016 | TO is awaiting confirmation/response from the CP for this mission. We urgently need the confirmation of dated for this mission (possible to take place end of November and December if we receive the proposed dates by next week.) |  | Deleted
10 | 3.3.10 1 | SV on PSI and reliability application and evaluation | IAEA: K. Kang, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA 6 months before.
11 | 3.3.10 2 | SV on PSI and reliability application and evaluation | IAEA: K. Kang, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA 6 months before.
12 | 3.3.10 3 | SV on PSI and reliability application and evaluation | IAEA: K. Kang, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA 6 months before.
13 | 3.3.10 4 | SV on PSI and reliability application and evaluation | IAEA: K. Kang, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA 6 months before.
11 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | 11-13 Feb 2017 | In progress | H
12 | 3.8.2 | WS developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: J. Moore, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q2/2017 | IAEA recommended to combine with 3.1.1, NPPD will inform IAEA by the end of Dec. 2016. | H | New request , It is discussed and decided during the mission on 3.8.1
3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1
13 | 3.10.1 | EM on "Assistance on review of safety analysis model for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Ghods-Derakhshandeh | 1 IAEA+3IEX/5 days( HBA 5 days) |  | Tehran | EM | Q2 / 2017 | Pending information on models and any result of calculation-information needed one month prior to the mission date. Need confirmation on mission dates. | M | NPPD to provide one month before, information on modeles and any result of calculation. In progress.
14 | 3.10.2 | EM on independent analysis of root-cause results for BNPP-1 | IAEA: P. Tarren, NPPD: Abbaspour/Ghods | 1 IAEA+3IEX/5 days |  | Tehran | EM | Q2/2017 |  | H | NPPD to provide two month before information in English on the root cause analysis in the last two years.Dian Zahradka is the point of contact.
3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1
15 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q3-4 /2017 | In progress | M | IAEA request further clarification of what NPPD are seeking at least two months before.(availability of software and scope of the mission)
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
16 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: T. Ulses, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2018 |  |  | To move 2018-2019
17 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; C .Hill, NPPD: Ghods-Abbaspour | 1 IAEA+2 IEX |  | Tehran | EM | Q2/2017 |  | M
5.5 Assistance in development of selected training scenarios for severe accidents in FSS
18 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | Q2 /2018 |  |  | To be discussed afterimplementation of 6.3.1,
5.6 Assistance in development & improvement of training system of maintenance & repair personnel
19 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: D. Drury, J. Song NPPD: Rahnama-Talebianzadeh | 1IAEA+2IEX |  | Bushehr/Tehran | EM | Q3 /2017 | the technical officer is awaiting the scope/ToR for this mission. The tentative date is 5-9 November 2016. We would appreciate to receive soonest possible the ToR to compose the expert team for this mission. | H
6.1 Asistance in review of BNPP-1 off-site emergency preparedness and response
20 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA: P.Tarren, NPPD: Abbaspour | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 - 13-17 May 2017 | NPPD will send its expectations and scope 2 months in advance. In progress | M | NPPD: To send clarification on the focus: Training on off-site response to radiological emergency situation BNPP-1. Ramon De la Vega is the IEC Contact Point.
6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1
21 | 6.3.1 | EM to review progress in development of the severe accident analysis model (using computer code) for BNPP-1 | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | EM | Q2/2017 |  | H | Depending on availability computer code
22 | 6.3.2 | RM to review the progress in development of the severe accident managementguidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | TSR-AM | Q3/2017 |  | H | TSR-AM: Technical Safety Review- Accident Management
7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1
23 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening, NPPD: Abbaspour | 1IAEA+3IEX |  | Bushehr | EM | 3-7 Dec 2016 | In progress | H
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
24 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: D. Talleria, NPPD: Abbaspour | Procurement |  | Bushehr | Procurement | 2017-05-01 | IAEA had initiated the procurement process, GCS has been transferred into the project. The procurement process is in proceed . It is expected to install and operate in May 2017 at Bushehr. | H | IAEA is requested to provide the report on the last status of submitting ESTE to CP.
2.3 Implementation of OSART mission
25 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  | Bushehr | EM | 13-30 Jan. 2018 |  | H
2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers
26 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | Tehran | EM | 16-20 July 2016 | Completed | H
2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission
27 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q1 2017( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1-3NEX |  | TBD | FS | 2017 |  | H | NPPD requests to involve 3 NEXs.
#VALUE! | 2.7.2 | Asist visits on operation,Maintenance,technical support and HTO areas as preparation for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 1IAEA+4IEX |  | Q2 / 2017 , 5 working days | EM |  |  | H | New Request
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
28 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: B.Song, K.Makela, NPPD: Deylami | 1 IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | H | Deleted.
3.4 Training on containment leakage tests and calculations after outage
29 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
30 | 3.4.2 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
31 | 3.4.3 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
32 | 3.4.4 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system
33 | 3.5.1 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q3/2017 | NPPD will send 4 NFs by the end of Dec 2016 | M | NFs should be sent to IAEA at least 8 months before.
34 | 3.5.2 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q3/2017 | NPPD will send 4 NFs by the end of Dec 2016 | M | NFs should be sent to IAEA at least 8 months before.
35 | 3.5.3 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q3/2017 | NPPD will send 4 NFs by the end of Dec 2016 | M | NFs should be sent to IAEA at least 8 months before.
36 | 3.5.4 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | TBD | SV | Q3/2017 | NPPD will send 4 NFs by the end of Dec 2016 | M | NFs should be sent to IAEA at least 8 months before.
3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR
37 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1IAEA+3IEX |  |  | WS | Q1/2018 |  |  | Shifted to next cycle(2018-2019_
3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles
38 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  | Tehran | EM | Q1/2017 |  | H | Deleted
3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system
39 | 3.9.1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests, High and low cycle fatigue analysis for strength assessment of Reactor Coolant System | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  | Tehran | WS | Q3/2017 |  | M
3.12 Assistance in performing the living PSA of the BNPP-1
40 | 3.12.1 | EM to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: I Kuzmina, NPPD: Ghods | 1IAEA+2IEX |  |  | EM | Q1/2018 |  |  | NPPD: To send information on the scope and focus including utilization of risk spectrum softwarein two months before the mission.
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
41 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: C. Hill / T.Ulses, NPPD: Derakhshandeh | 1 IAEA+2 IEX |  | Tehran / Bushehr | EM | Q2/2017 |  | M
4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
42 | 4.1.1 | EM on "modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes " in Q1 2017, (1 IAEA +3 IEX ) | IAEA: H. Varjonen, NPPD: Roshankar | 1IAEA+3IEX |  | Bushehr | EM | Q3/2017 |  | H
4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
43 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:J. Moore, NPPD: Tajbakhsh | 1IAEA+3IEX+ 5 NEX |  | Vienna | EM/HBA | Q1 / 2017 | The date is under negotiation. IAEA :27 March , NPPD request to be held in end of Febraury. | H | NFs should be sent to IAEA at least 2 months before.
5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
44 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | M
5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
45 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before.
46 | 5.2.2 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before.
47 | 5.2.3 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before.
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
48 | 7.4.2 | EM on "Review and assesment of results of environmental monitoring programme using the software ESTE" | IAEA: D. Talleria, NPPD: Abbaspour | 1 IAEA+2IEX |  | Bushehr | EM | Q2/2018 |  | M | One year after installation of ESTE at BNPP-1.
4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators
49 | 4.4.1 1 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016.(Mress. Tahernia,Ansari&Sedaghat) | H | New request for 2016 NPPD: to send the scope and focus of this task two months before the mission. (Potential for UKR, Zhaporozhe)
50 | 4.4.1 2 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016.(Mress. Tahernia,Ansari&Sedaghat) | H | New request for 2016 NPPD: to send the scope and focus of this task two months before the mission. (Potential for UKR, Zhaporozhe)
51 | 4.4.1 3 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016.(Mress. Tahernia,Ansari&Sedaghat) | H | New request for 2016 NPPD: to send the scope and focus of this task two months before the mission. (Potential for UKR, Zhaporozhe)
4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs
52 | 4.3.1 | WS on outage optimization through advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs | IAEA: H. Varjonen NPPD:Roshankar | 1IAEA+3IEX | 4 days | Bushehr |  | WS | Q3/2017 | H | New for 2017. NPPD: to send the scope and focus of this task two months before the mission.
Cancelled
| Further clarifications needed | [6 empty] | 27 active tasks
| Completed | [6 empty] | H= 18,M=9
Move to the next cycle
Note on L17: Rahnama , Afshin: on email 06.April.2016,