|  | International Atomic Energy Agency |  |
| --- | --- | --- |

DRAFT MINUTES OF MEETING

Review of NPPD TC Projects: IRA2012 & IRA2013

2 – 4 May 2017

- Vienna, VIC, Room:  B0979

- NPPD:

- Mr. Saeed Fatourehchian

- Mr. Amir Rahnama

- Mr. Kazem Khezri

- IAEA:

- Ms Jane Gerardo-Abaya

- Mr. Pal Vincze

- Mr. Peter Tarren

- Mr. Diego Telleria

- Mr. David Drury

- Mr. Janos Eiler

- Mr. Matt Van Sickle

- Ms. Helen Rycraft

- Mr. Kang Ki-Sig

- Mr. Anthony Patrick Ulses

- Mr. Yoshimitsu Fukushima

- Ms. Marina Mishar

- Objectives:

- Update of Projects Work Plans IRA2012 & IRA2013

- Finalization of Draft Project Design of  IRA2016002

- Review of Technical Meeting/Workshops for participation

- Relevant TC Projects:

- IRA2012 Increasing NPPD’s Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety (ends 2017)

- IRA2013 Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1 (ends 2019)

- IRA201003 Further Increasing NPPD's Capability in Planning and Implementing Activities Related to Design, Construction and Commissioning of Two New NPP Units in Bushehr with Emphasis on Safety (new project for 2018 – 2021)

- 3. 	Work Done

- Agenda of the meeting was discussed and approved (Attachment 1)

- Update of the Agreed Actions of 14 – 15 February Meeting.

- Project Progress to date for both projects was presented by the Counterpart and PMO shared IAEA inputs in 2017. The meeting discussed on the lessons learnt towards improved implementation from both sides.

- Work plans of IRA2012 and IRA2013 were updated accordingly to the current progress and prioritization with focus on tasks planned for implementation during 2017 (Attachments 2 and 3)

- Discussions were held on the proposed new project for 2018/2019 of which the CP shared new updates of the project work plan.

- Discussions and agreement on international conferences to be participated by the CPs and funding support via IRA2012 or IRA2013 if no funding support from the event organizer.

- 4.	Conclusions

- Both projects are moving as planned with slight delay in the progress of IRA2012 due to issues related to contractual agreement.

- The work plans of IRA2012 and IRA2013 were updated and agreed. In total, 29 activities in the plan for implementation in 2017 under both projects. Available funding under both projects is adequate to support the implementation of all these planned activities.

- The status of the procurement and installation of the Environmental Monitoring Software were presented by the IAEA Technical Officer. Due to its delay (expected in May 2017), NPPD requested to speed-up the issue.

- The updated project design of IRA201003 was also reflected in the PCMF.

- List of possible conference/seminar, to be supported by IRA2012/IRA2013 if limited funding from the organizer as agreed is listed below. Nomination via TC Meeting Form, endorsed by the NLO should be attached during the nomination to participate in such events:

  - 4th International Conference on Plant Life Management (PLIM) – dealine for nomination is 19 May 2017 (http://www-pub.iaea.org/iaeameetings/50811/Fourth-International-Conference-on-Nuclear-Power-Plant-Life-Management)

  - TM for embarking countries on effective Operating Experience Programme and Lessons learned from Events that Shaped Nuclear Industry - date not confirmed; Scientific Secretary: Mr D. Zahradka

  - Participation in SALTO missions as observers – Scientific Secretary: Mr. R. Krivanek

- Follow-up Actions

- Recommendation for improved implementations and communications for the missions to Iran. Information sheets to be prepared and to be shared with CPs and experts by end of mid-June 2017:

  - Iran: Information sheet on contact persons and administrative procedures in Iran

  - IAEA: Information sheet on required information from the Counterpart for IAEA Security Clearance process

- IAEA to closely follow-up on the status of the Procurement of Environmental Monitoring Software which is currently waiting for offer to supplier. The new expected date for the procurement is September 2017 and installation of the software in Iran in November 2017.

- The next Review Meeting will be held in VIC in October 2017.

  - IAEA to provide the dates of the meeting by end of May 2017

  - IRA to provide meeting nomination forms by end of July 2017

- IAEA to provide additional information about the dates, location and nomination procedure for these events by end of May 2017:

  - TM for embarking countries on effective Operating Experience Programme and Lessons learned from Events that Shaped Nuclear Industry - date not confirmed; Scientific Secretary: Mr D. Zahradka

  - Participation in SALTO missions as observers – Scientific Secretary: Mr. R. Krivanek

- Attachments:

- Agenda of the meeting

- Updated Work Plan of IRA2012

- Updated Work Plan of IRA2013

Attachment 1

Agenda

Review Meeting on NPPD TC Projects: IRA2012 & IRA2013

2 – 4 May 2017

- Vienna, VIC, Room:  B0979

| Tuesday 2 May 2017 |  |  |
| --- | --- | --- |
| Time | Main Topic | Responsible |
| 09:00-09:15 | Introductions - Agenda Review & Meeting Deliverables - Review of status of actions as agreed in February 2017 Meeting Conclusions (Annex 1) | All |
| 09:15-10:15 | Session I : Review of Achievement & Progress - Presentation of Project progress (to date) - Presentation of IAEA inputs progress (to date) - Discussion on lessons’ learnt towards improved implementation | CPs PMO, Lead TO All |
| 10:15 – 10:30 | Coffee Break |  |
| 10:30 – 12:45 | Session 2: Clarification of scope and objectives for the activities scheduled for 2017: - Reference to IRA2012 and IRA2013 Work plan | TOs, CPs |
| 12:45-14:00 | Lunch |  |
| 14:00-15:30 | Session 2: Clarification of scope and objectives for the activities scheduled for 2017: Continue … | TOs, CPs |
| 15:30-15:50 | Coffee Break |  |
| 15:50-17:00 | Session 2: Clarification of scope and objectives for the activities scheduled for 2017: Continue … | TOs, CPs |

| Wednesday 3 May 2017 |  |  |
| --- | --- | --- |
| Time | Main Topic | Responsible |
| 09:00-10:30 | Session 2: Clarification of scope and objectives for the activities scheduled for 2017: Continue … | CPs All |
| 10:30-10:45 | Coffee Break |  |
| 10:45-12:45 | Presentation on Project Design IRA2016003 Q&A | CPs |
| 12:45-14:00 | Lunch |  |
| 14:00-15:30 | - Refinement of Project Design based on comments received - Clarification of other activities/inputs (Annex 2) | All |
| 15:30-15:50 | Coffee Break |  |
| 15:50-17:00 | - Finalization of project design - Review of Technical Meeting/Workshops for possible participation | CPs, TOs CPs, PMO |
| Thursday 4 May 2017 |  |  |
| Time | Main Topic | Responsible |
| 09:30-10:30 |  | CPs All |
| 10:30-10:45 | Coffee Break |  |
| 10:45-12:45 | Review of Technical Meeting/Workshops for possible participation | CPs |
| 12:45-14:00 | Lunch |  |
| 14:00-15:30 | Discussion on - meeting conclusions - agreed follow-up actions - agenda for 2017 Coordination Meeting in Tehran | All |

| IRA2012: Action Plan for implementation of Workplan activities in 2014-2017 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| as of 04.05.2017 |  |  |  |  |  |  |  |  |  |  |  |
| Increasing NPPD's Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety |  |  |  |  |  |  |  |  |  |  |  |
| No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments |
| 1.2 Conducting project review meetings |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 1.2.1 | Annual project review and planning meeting 2014 | IAEA: Gueorguiev, NPPD: Fatourechian | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | Q1/2014 | Completed |  |  |
| 2 | 1.2.2 | Annual project review and planning meeting 2015 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | Q1 2015 | Completed, 15-17 February 2015 in Tehran |  |  |
| 3 | 1.2.3 | Annual project review and planning meeting 2016 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | Q1 2016 | Completed 29 February - 2 March |  |  |
| 4 | 1.2.4 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | EM | Q1 2017 | Completed |  | 14-15 Feb 2017 as agreed date |
| 1.5 IAEA field monitoring |  |  |  |  |  |  |  |  |  |  |  |
| 5 | 1.5.1 | Reqular field monitoring and review missions | IAEA: Gueorguiev, NPPD: Fatourechian | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | 2014 | Completed |  |  |
| 6 | 1.5.2 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | 2015 | Completed |  |  |
| 7 | 1.5.3 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | 2016 | Completed |  | 1-2 missions per quarter jointly with IRA2013 |
| 8 | 1.5.4 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Vienna | Meeting | 2017 |  |  | 1-2 missions per quarter jointly with IRA2013 |
| 2.2 Spent fuel storage and waste management programs |  |  |  |  |  |  |  |  |  |  |  |
| 9 | 2.2.1 | EM to assist in radioactive waste management programme, including scaling factor application | IAEA:Ormai/Dyck, NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX |  | Tehran | EM | 27 Sept - 1 Oct 2014 | Jointly with IRA2011/1.17.3 Completed |  |  |
| 10 | 2.2.2 | EM to assist in spent fuel storage | IAEA: C. Hill NPPD: Derakhahandeh | 1 IAEA staff and 3 IEX |  | TBD | EM | Q2/2018- Shifted to New Project |  | H | Follow-up mission under 2011. Postpone to New Project.NPPD will elaborate its need 2 months in advance. |
| 3.1 Development of training materials for two new NPP projects |  |  |  |  |  |  |  |  |  |  |  |
| 11 | 3.1.1 | EM to assist in review of selected/developed training materials for future operatorsfor two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q4/2017 | To be implemented on the developed materials provided by the supplier of two new units | H | Move to the new Project 2018-2019 |
| 12 | 3.1.2 | EM to assist in review of selected/developed training materials for future operators for two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q4/2017 | To be implemented on the developed materials provided by the supplier of two new units | H | merged with 3.1.1, Move to the new Project 2018-2019 |
| 3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant |  |  |  |  |  |  |  |  |  |  |  |
| 13 | 3.2.1. | WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety | IAEA: Kang, NPPD: Tajbakhsh | 1 IAEA staff and 2 IEX for 4 days |  | Tehran Bushehr | WS | 27-30 April 2014 | Completed |  |  |
| 5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations |  |  |  |  |  |  |  |  |  |  |  |
| 14 | 5.1.1 | WS To assist in development of the Local Industry Utilization Plan | IAEA: Kang NPPD: Derakhshandeh | 1 IAEA staff and 2 IEX for 3 days |  | Tehran | WS | 25-27 Nov. 2017 | In progress | M |  |
| 6.1 Public information and awareness programmes development |  |  |  |  |  |  |  |  |  |  |  |
| 15 | 6.1.1 | WS on public information and awareness programmes | IAEA:B. Pagannone/ NPPD:Rahnama | 4-6 NEX and 2 IEX |  | Tehran | WS | 28 Sept-1 Oct 2014 | Completed |  |  |
| 16 | 6.1.2 | EM to assist on the establishment of public information and awareness centre | IAEA: M. Van Sickle, NPPD: Rahnama | 1 IAEA staff and 2 IEX |  | Tehran/Bushehr | EM | Q3/2017 |  | M | NPPD is requested to send the IAEA two months before the draft plan/status description for the Centre. |
| 17 | 6.1.3 | EM to review results of Stakeholder Involvement Plan | IAEA: M. Van Sickl, NPPD: Rahnama | TBD |  | Tehran | EM | Q3/2017 |  | M | Additional request as follow-up of 6.1.1. New request. Merged with 6.1.2 |
|  | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: M. Van Sickl, NPPD: Rahnama | 3NEX |  | TBD | SV | Q4/2017 |  | M | NFs will send by end of June. |
|  | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: M. Van Sickl, NPPD: Rahnama | 3NEX |  | TBD | SV | Q4/2017 |  | M | NFs will send by end of June. |
| 18 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: M. Van Sickl, NPPD: Rahnama | 3NEX |  | TBD | SV | Q4/2017 |  | M | NFs will send by end of June. |
| 2.1 Seismic safety assessment |  |  |  |  |  |  |  |  |  |  |  |
| 19 | 2.1.1 | EM to assist in seismic safety assessment | IAEA:Y.Fukushima, NPPD: Shirzadi/Derakhshandeh | 1 IAEA staff and 3 IEX |  | Tehran / Bushehr | EM | 1-4 october 2016 | Completed | H |  |
| 20 | 2.1.2 | WS/EM on seismic safety | IAEA:Y.Fukushima, NPPD: Tourafshan/Derakhshandeh | TBD ( 4 days) |  | Tehran | WS/EM | Q3/2017 |  | M | Considering the EMR on 2.1.1, NPPD will define the scope of needs for further proceed. |
| 3.3 Corporate knowledge management |  |  |  |  |  |  |  |  |  |  |  |
| 21 | 3.3.1 | EM on corporate knowledge management for BNPP - 2&3 with focus on safety | IAEA:Z. Pasztory NPPD:Rahnama/Sheikholeslami | 1 IAEA staff and 3 IEX, 4 days |  | Tehran | EM | 15-18 Nov. 2015 | Completed |  |  |
| 22 | 3.3.2 | EM on Management and maintaining design basis information through life cycle of BNPP-2&3 | IAEA:J. de Grosbois, Kolomiets 1 IAEA staff and 3IEX | I IAEA + 2 IEX |  | Tehran | EM | 21-25 April 2016 (3 days) | Completed |  |  |
| 3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr |  |  |  |  |  |  |  |  |  |  |  |
| 23 | 3.4.1 | WS on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (cancelled) |  |  |  |  |  |  | NPPD does not need further assistance |  |  |
| 24 | 3.4.2 | SV on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (SG) | IAEA: M. Mishar, SG NPPD: NPPD:Amini | 3NEX |  | TBD | SV | 2016 | Cancelled | H | NFs to be provided timely in advance |
| 4.4 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr |  |  |  |  |  |  |  |  |  |  |  |
| 25 | 4.1.1 | EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units | IAEA: Drury, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q2/2017 |  | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. Jointly with 4.2.1 New task (Possible home based assignment), Move to the new project 2018-2019 |
| 26 | 4.1.2 | EM to assist in evaluation of developed programmes to update owner's training system for the two new PWR units | IAEA: Drury, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q2/2017 | To be moved to 2018-2019, new project | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. New task |
| 27 | 4.1.3 | Group Trainig programme on pre-construction management with focus on safety requirements | IAEA: Kang; NPPD: Fatourechian | 1 IAEA Staff, 20 NEX |  | ICTC, Beijing, China | WS | 24 Aug.-4 Sept. 2015 | Completed |  |  |
| 28 | 4.1.4 | EM to assist in development of comprehensive model for effective project management of the two new NPP units (1 + 3 IEX) | IAEA: Pekka Pyy. NPPD: Rahnama | 1 IAEA Staff and 3 IEX |  | Tehran | EM | 8-11 Nov. 2015 | Completed |  |  |
| 29 | 4.1.5 | Group Fellowship Trainig on construction and commissioning management with focus on safety requirements | IAEA: K. S. Kang NPPD: Fatourechian/Rahnama | 2 IAEA staff and 20 NEX. The cost for the WS is expected cca. 100 000 EURs. |  | S. Korea | Group fellowship training | Q4/2017- Q1/2018 |  | H |  |
| 30 | 4.1.6 | EM to assist in the review of the developed Project Management System for units 2 and 3 of the new project. | IAEA: Pekka Pyy. NPPD: Fatourechian/Rahnama | 1 IAEA/3 IEX 4 days. |  | Tehran | EM | Q3 /2017 |  | H | NPPD combine it with 3.1.1 |
| 4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units |  |  |  |  |  |  |  |  |  |  |  |
| 31 | 4.2.1 | EM to assist in review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | EM and HBA | Q2/2017 |  | H | Jointly with 4.1.1 |
|  | Cancelled |  |  |  |  |  |  |  |  |  |  |
|  | Further clarifications needed |  |  |  |  |  |  |  |  |  |  |
|  | Completed |  |  |  |  |  |  | 10 active tasks |  |  |  |
|  | Move to new project (2018-2019) |  |  |  | H=5,M=5 |  |  |  |  |  |  |

| IRA2013: Action Plan for implementation of Workplan activties in 2016-2017 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| as of 04.05.2017 |  |  |  |  |  |  |  |  |  |  |  |
| Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1 |  |  |  |  |  |  |  |  |  |  |  |
| No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments |
| 1.2 Conducting project review meetings |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed |  |  |
| 2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | PRM | 14-15 Feb. 2017 | Completed |  |  |
| 1.5 IAEA Field Monitoring (once per quarther) |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Preparatory visit for OSART mission |  |  |  |  |  |  |  |  |  |  |  |
| 3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | 14-16 Nov 2016 | Completed | H |  |
| 2.4 Implementation the nuclear safety oversight function |  |  |  |  |  |  |  |  |  |  |  |
| 4 | 2.4.1 | One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: | 1 IAEA+2IEX |  | Tehran | EM | Q4/2017 |  | M | NPPD will send the expectations and scope by the end of July. |
| 3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment |  |  |  |  |  |  |  |  |  |  |  |
| 5 | 3.1.1 | WS on "modern methods for measuring hydrogen in primary loop and analysis | IAEA: Song, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | 18-21 Feb 2017 | Completed | H |  |
| 3.2 Training on environmental qualification of safety equipment of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |
| 6 | 3.2.1 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD | SV | Q4/2017 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or France |
| 7 | 3.2.2 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q4/2017 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or France |
| 8 | 3.2.3 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q4/2017 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or France |
| 3.3 Training on equipment reliability assessment techniqes of equipment during operation |  |  |  |  |  |  |  |  |  |  |  |
| 9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" | IAEA: K. Kang, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016 | TO is awaiting confirmation/response from the CP for this mission. We urgently need the confirmation of dated for this mission (possible to take place end of November and December if we receive the proposed dates by next week.) |  | Deleted |
| 10 | 3.3.10 1 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017. |
| 11 | 3.3.10 2 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017. |
| 12 | 3.3.10 3 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017. |
| 13 | 3.3.10 4 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017. |
| 14 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | 11-13 Feb 2017 | Completed | H |  |
| 15 | 3.8.1-1 | EM on review of BNPP-1 AMP | IAEA: K.Kang,Robert Krivanek, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | EM | Q2 / 2018 |  | H | New Request |
| 16 | 3.8.1-2 | SV on AMP | IAEA: K.Kang,Robert Krivanek, NPPD: Ghods | 4NEX |  | TBD | SV | Q4/2017 |  | H | NFs will send to IAEA 6 months before.It is prefer to France-Areva. |
| 17 | 3.8.1-3 | Procurement of FAC software , COMSY | IAEA: K.Kang, NPPD: Ghods |  |  |  | Procurement | TBD |  | M | New Request. IAEA will inform NPPD on its price by the end of Feb, 2017. |
| 18 | 3.8.2 | WS developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: K.Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q3/2018 |  | H |  |
| 3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |
| 19 | 3.10.1 | EM on "Assistance on review of safety analysis model for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Ghods-Derakhshandeh | 1 IAEA+3IEX/5 days( HBA 5 days) |  | Tehran | EM | Q3 / 2017 | Pending information on models and any result of calculation-information needed one month prior to the mission date. Need confirmation on mission dates. | M | NPPD to provide one month before, information on modeles and any result of calculation. In progress. |
| 20 | 3.10.2 | EM on independent analysis of root-cause results for BNPP-1 | IAEA: Dian Zahratka, P.Tarren, NPPD: Ghods/Derakhshandeh | 1 IAEA+3IEX/5 days |  | Tehran | EM | Q2/2017 19-23 August |  | H | NPPD to provide two month before information in English on the root cause analysis in the last two years.Dian Zahradka is the Implementing Officer from IAEA side. |
| 3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |
| 21 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q4 /2017 | In progress | M | IAEA request further clarification of what NPPD are seeking at least two months before.(availability of software and scope of the mission) |
| 3.14 Assistance on safety aspacts of fresh and spent fuel engineering |  |  |  |  |  |  |  |  |  |  |  |
| 22 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: T. Ulses, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2018 |  |  | NPPD Provide more information two months before. |
| 23 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; C .Hill, NPPD: Ghods-Abbaspour | 1 IAEA+2 IEX |  | Tehran | EM | Q4/2017 |  | M | NPPD Provide more information two months before. |
| 5.5 Assistance in development of selected training scenarios for severe accidents in FSS |  |  |  |  |  |  |  |  |  |  |  |
| 24 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | Q2 /2018 |  |  | To be discussed after implementation of 6.3.1, |
| 5.6 Assistance in development & improvement of training system of maintenance & repair personnel |  |  |  |  |  |  |  |  |  |  |  |
| 25 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: J. Song NPPD: Rahnama-Talebianzadeh | 1IAEA+2IEX |  | Bushehr/Tehran | EM | Oct. 2017 |  | H | NPPD will provide more information on area(s) two months before. |
| F |  |  |  |  |  |  |  |  |  |  |  |
| 26 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA:V.Welter, NPPD: Abbaspour | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 - 06-10 May 2017 | NPPD will send its expectations and scope 2 months in advance. In progress | M | NPPD: To send clarification on the focus: Training on off-site response to radiological emergency situation BNPP-1. Ramon De la Vega is the IEC Contact Point.BNPP will send off-site emergency prepardeness and response plan by the end of March, 2017. |
| 6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |
| 27 | 6.3.1 | EM to review progress in development of the severe accident analysis model for BNPP-1 | IAEA: T. Ulses, NPPD: Ghods/Derakhshandeh | 1IAEA+2IEX |  | Tehran | EM | Q4/2017 |  | H | IAEA will request more clarification of the mission and NPPD will reply by the end of June. |
| 28 | 6.3.2 | RM to review the progress in development of the severe accident managementguidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | TSR-AM | Q3/2017 |  | H | NPPD will provide additional information on statues of SAMG by the end of June. |
| 7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |
| 29 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening, NPPD: Abbaspour | 1IAEA+3IEX |  | Bushehr | EM | 3-7 Dec 2016 | Completed | H |  |
| 7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011) |  |  |  |  |  |  |  |  |  |  |  |
| 30 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: D. Talleria, NPPD: Abbaspour | Procurement |  | Bushehr | Procurement | May, 2017 | IAEA had initiated the procurement process, GCS has been transferred into the project. The procurement process is in proceed . It is expected to install and operate in November 2017 at Bushehr. | H | IAEA is requested to provide the report on the last status of submitting ESTE to CP. |
| 2.3 Implementation of OSART mission |  |  |  |  |  |  |  |  |  |  |  |
| 31 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  | Bushehr | EM | 29 Sep- 17 Oct. 2018 |  | H |  |
| 2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers |  |  |  |  |  |  |  |  |  |  |  |
| 32 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | Tehran | EM | 16-20 July 2016 | Completed | H |  |
| 2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission |  |  |  |  |  |  |  |  |  |  |  |
| 33 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q4 2018( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1-3NEX |  | TBD | FS | 2017 |  | H | NPPD requests to involve 3 NEXs.One place agreed for 13-30 November 2017 in Leningrad. |
| 34 | 2.7.2 | Asist visits on operation,Maintenance and technical support areas as preparation for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 1IAEA+4IEX |  | Q4 / 2017 , 5 working days/ Bushehr | EM |  |  | H |  |
| 35 | 2.7.3 | Asist visits on HTO and GSR-Part2 areas as preparation for OSART mission | IAEA: P. Tarren, NPPD: Khezri | 1IAEA+2IEX |  | 3 working days , Bushehr | EM | Nov. 2017 |  | H | Ms.Helen Rycraft is implementing officer from IAEA side. |
| 3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment |  |  |  |  |  |  |  |  |  |  |  |
| 36 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: B.Song, K.Makela, NPPD: Deylami | 1 IAEA+2IEX |  | Bushehr | WS | Q2/2017 | Deleted. | H |  |
| 3.4 Training on containment leakage tests and calculations after outage |  |  |  |  |  |  |  |  |  |  |  |
| 37 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019) |
| 38 | 3.4.2 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019) |
| 39 | 3.4.3 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019) |
| 40 | 3.4.4 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019) |
| 3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system |  |  |  |  |  |  |  |  |  |  |  |
| 41 | 3.5.1 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M |  |
| 42 | 3.5.2 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M |  |
| 43 | 3.5.3 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M |  |
| 44 | 3.5.4 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M |  |
| 3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR |  |  |  |  |  |  |  |  |  |  |  |
| 45 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1IAEA+3IEX |  | Bushehr | WS | Q1/2018 |  |  | NPPD requsted to provide more information to the content of the WS by the end of Sep. 2017. |
| 3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles |  |  |  |  |  |  |  |  |  |  |  |
| 46 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  | Tehran | EM | Q1/2017 | Deleted | H |  |
| 3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system |  |  |  |  |  |  |  |  |  |  |  |
| 47 | 3.9.1 -1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests. | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  | Tehran | WS | Dec,2017 |  | M |  |
| 48 | 3.9.1 -2 | WS on High and low cycle fatigue analysis for strength assessment of Reactor Coolant System | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  | Tehran | WS | TBD |  | M |  |
| 3.12 Assistance in performing the living PSA of the BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |
| 49 | 3.12.1 | EM to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: I Kuzmina, NPPD: Ghods | 1IAEA+2IEX |  |  | EM | Q1/2018 |  |  | NPPD: To send information on the scope and focus including utilization of risk spectrum software in two months before the mission. |
| 3.14 Assistance on safety aspacts of fresh and spent fuel engineering |  |  |  |  |  |  |  |  |  |  |  |
| 50 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: A. Gonzalez Espartero / T.Ulses, NPPD: Ghods | 1 IAEA+2 IEX |  | Tehran / Bushehr | EM | Q2/2017 | Dublicated with 3.14.2 | M | NPPD requested to provide information two months before. |
| 4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes |  |  |  |  |  |  |  |  |  |  |  |
| 51 | 4.1.1 | EM on modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes | IAEA: H. Varjonen, NPPD: Roshankar | 1IAEA+3IEX |  | Bushehr | EM | Q3/2017 |  | H | NPPD will provide more information on area(s) by the end of May. |
| 4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance |  |  |  |  |  |  |  |  |  |  |  |
| 52 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:Kang, NPPD: Mohebi/ | 1IAEA+3IEX |  | Tehran | EM/HBA | Q4/ 2017, |  | H | NPPD will update the expectations by the end of May,2017. |
| 5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel |  |  |  |  |  |  |  |  |  |  |  |
| 53 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  | Bushehr | WS | Q3/2017 |  | M | NPPD has been sent the expectation in 29.04.2017 |
| 5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel |  |  |  |  |  |  |  |  |  |  |  |
| 54 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before. |
| 55 | 5.2.2 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before. |
| 56 | 5.2.3 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before. |
| 7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011) |  |  |  |  |  |  |  |  |  |  |  |
| 57 | 7.4.2 | EM on "Review and assesment of results of environmental monitoring programme using the software ESTE" | IAEA: D. Talleria, NPPD: Abbaspour | 1 IAEA+2IEX |  | Bushehr | EM | Q2/2018 |  | M | One year after installation of ESTE at BNPP-1. |
| 4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators |  |  |  |  |  |  |  |  |  |  |  |
| 58 | 4.4.1 1 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016. | H | New request for 2016 NPPD, China |
| 59 | 4.4.1 2 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016. | H | New request for 2016 NPPD, China |
| 60 | 4.4.1 3 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016. | H | New request for 2016 NPPD, China |
| 4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs |  |  |  |  |  |  |  |  |  |  |  |
| 61 | 4.3.1 | WS on outage optimization through advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs | IAEA: H. Varjonen NPPD:Roshankar | 1IAEA+3IEX | 4 days | Bushehr |  | WS | Q3/2017 | H | NPPD will provide more information on area(s) by the end of May. ( NPPD will consider combining 4.1.1 and 4.3.1) |
|  | Cancelled |  |  |  |  |  |  |  |  |  |  |
|  | Further clarifications needed |  |  |  |  |  |  | 27 active tasks |  |  |  |
|  | Completed |  |  |  |  |  |  | H= 18,M=9 |  |  |  |
|  | Move to the next cycle |  |  |  |  |  |  |  |  |  |  |