## IRA2012_Sep_2016
IRA2012: Action Plan for implementation of Workplan activities in 2014-2017
as of 25.09.2016
Increasing NPPD's Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Funding | Budget | Budget Year | Date | Changed Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting 2014 | IAEA: Gueorguiev, NPPD: Fatourechian | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | FootNote | 39,195 | 2012 | Q1/2014 |  | Completed
2 | 1.2.2 | Annual project review and planning meeting 2015 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2015 |  | Completed, 15-17 February 2015 in Tehran
3 | 1.2.3 | Annual project review and planning meeting 2016 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2016 |  | Completed 29 February - 2 March
4 | 1.2.4 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Vienna | EM |  |  |  | Q1 2017
1.5 IAEA field monitoring
5 | 1.5.1 | Reqular field monitoring and review missions | IAEA: Gueorguiev, NPPD: Fatourechian | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2014 |  | Completed
6 | 1.5.2 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2015 |  | Completed
7 | 1.5.3 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2016 |  |  |  | 1-2 missions per quarter jointly with IRA2013
8 | 1.5.4 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | FootNote | 21,000 | 2012 | 2017 |  |  |  | 1-2 missions per quarter jointly with IRA2013
2.2 Spent fuel storage and waste management programs
9 | 2.2.1 | EM to assist in radioactive waste management programme, including scaling factor application | IAEA:Ormai/Dyck, NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX |  | Tehran | EM | FootNote | 3,095 | 2012 | 27 Sept - 1 Oct 2014 |  | Jointly with IRA2011/1.17.3 Completed
10 | 2.2.2 | EM to assist in spent fuel storage | IAEA: C. Hill NPPD: Derakhahandeh | 1 IAEA staff and 3 IEX |  | TBD | EM |  |  |  | Q1/2017 |  | NPPD will specify and send the needs and expectation in Q4 2016 | H | Follow-up mission under 2011
3.1 Development of training materials for two new NPP projects
11 | 3.1.1 | EM to assist in review of selected/developed training materials for future operatorsfor two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | Q4/2017 |  | To be implemented on the developed materials provided by the supplier of two new units | H
12 | 3.1.2 | EM to assist in review of selected/developed training materials for future operators for two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | FootNote | 16,725 | 2012 | Q4/2017 |  | To be implemented on the developed materials provided by the supplier of two new units | H | merged with 3.1.1
3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant
13 | 3.2.1. | WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety | IAEA: Kang, NPPD: Tajbakhsh | 1 IAEA staff and 2 IEX for 4 days |  | Tehran Bushehr | WS | HardCore | 21,000 | 2012 | 27-30 April 2014 |  | Completed
5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations
14 | 5.1.1 | EM To assist in development of the Local Industry Utilization Plan | IAEA: Kang NPPD: Derakhshandeh | 1 IAEA staff and 2 IEX for 3 days |  | Tehran | EM | FootNote | 21,000 | 2012 | Q4/2016 |  | NPPD will provide the necessary inputs (expectation) in the beginning of October 2016 | M | NPPD: Specific issues related to local industry will be sent to the IAEA two months before the WS
6.1 Public information and awareness programmes development
15 | 6.1.1 | WS on public information and awareness programmes | IAEA:B. Pagannone/ NPPD:Rahnama | 4-6 NEX and 2 IEX |  | Tehran | WS | FootNote | 16,350 | 2012 | 28 Sept-1 Oct 2014 |  | Completed
16 | 6.1.2 | EM to assist on the establishment of public information and awareness centre | IAEA: T, Tigerstedt NPPD: Rahnama | 1 IAEA staff and 2 IEX |  | Tehran/Bushehr | EM |  |  |  | Q4/2016 |  | NPPD request to be postponed to Q3 2017 | M | NPPD is requested to send the IAEA two months before the draft plan/status description for the Centre.
17 | 6.1.3 | EM to review results of Stakeholder Involvement Plan | IAEA: T, Tigerstedt NPPD: Rahnama | TBD |  | Tehran | EM |  |  |  | Q3/2017 |  |  | M | Additional request as follow-up of 6.1.1. New request
17 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: T, Tigerstedt NPPD:Rahnama | TBD |  | TBD | SV |  |  |  | 2017 |  |  | M | Additional request as follow-up of 6.1.1. New request
2.1 Seismic safety assessment
18 | 2.1.1 | EM to assist in seismic safety assessment | IAEA:Y.Fukushima, NPPD: Shirzadi/Derakhshandeh | 1 IAEA staff and 3 IEX |  | Tehran / Bushehr | EM | FootNote | 40,095 | 2013 | 1-4 october 2016 | 1-4 October, Planned Implementation | Ready for implementation-information for implementation of this mission was provided last week. Visa support number is pending. | H | Specific issues of interest for site data provided. NPPD to provide report on Seismic Hazard Evaluation in advance by end of june. In Progress
3.3 Corporate knowledge management
19 | 3.3.1 | EM on corporate knowledge management for BNPP - 2&3 with focus on safety | IAEA:Z. Pasztory NPPD:Rahnama/Sheikholeslami | 1 IAEA staff and 3 IEX, 4 days |  | Tehran | EM | FootNote | 7,805 | 2013 | 15-18 Nov. 2015 |  | Completed
20 | 3.3.2 | EM on Management and maintaining design basis information through life cycle of BNPP-2&3 | IAEA:J. de Grosbois, Kolomiets 1 IAEA staff and 3IEX | I IAEA + 2 IEX |  | Tehran | EM |  |  |  | 21-25 April 2016 (3 days) |  | Completed
3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr
21 | 3.4.1 | WS on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (cancelled) | [5 empty] | FootNote | 22,275 | 2013 |  |  | NPPD does not need further assistance
22 | 3.4.2 | SV on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (SG) | IAEA: M. Mishar, SG NPPD: NPPD:Amini | 3NEX |  | TBD | SV |  |  |  | 2016 |  |  | H | NFs to be provided timely in advance
4.4 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr
23 | 4.1.1 | EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units | IAEA: Drury/Tarren, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | HardCore | 27,875 | 2013 | Q2/2017 |  |  | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. Jointly with 4.2.1 New task (Possible home based assignment)
24 | 4.1.2 | EM to assist in evaluation of developed programmes to update owner's training system for the two new PWR units | IAEA: Drury/Tarren, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | Q2/2017 |  |  | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. New task
25 | 4.1.3 | Group Trainig programme on pre-construction management with focus on safety requirements | IAEA: Kang; NPPD: Fatourechian | 1 IAEA Staff, 20 NEX |  | ICTC, Beijing, China | WS |  |  |  | 24 Aug.-4 Sept. 2015 |  | Completed
26 | 4.1.4 | EM to assist in development of comprehensive model for effective project management of the two new NPP units (1 + 3 IEX) | IAEA: Pekka Pyy. NPPD: Rahnama | 1 IAEA Staff and 3 IEX |  | Tehran | EM |  |  |  | 8-11 Nov. 2015 |  | Completed
27 | 4.1.5 | Group Fellowship Trainig on construction and commissioning management with focus on safety requirements | IAEA: K. S. Kang NPPD: Fatourechian/Rahnama | 2 IAEA staff and 20 NEX. The cost for the WS is expected cca. 100 000 EURs. |  | S. Korea | Group fellowship training |  |  |  | Q3-Q4/2016 |  | NPPD request to be shifted to Q4 2017, | H
28 | 4.1.6 | EM to assist in the review of the developed Project Management System for units 2 and 3 of the new project. | IAEA: Pekka Pyy. NPPD: Fatourechian/Rahnama | 1 IAEA/3 IEX 4 days. |  | Tehran | EM |  |  |  | New date Q3 2017 |  | NPPD Requests to be postponed - we need the the new dates for this mission for preparation of the expert team and other necessary arrangements. As aggred during the May Coordination meeting, we need the scope and focus and the related documents two months before the mission. | H | NPPD: To send the scope and focus and the related documents two months before the mission. New request
4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units
29 | 4.2.1 | EM to assist in review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and # IEX |  | TBD | EM and HBA | FootNote | 13,365 | 2013 | Q2/2017 |  |  | H | Jointly with 4.1.1 and 4.1.2
Cancelled / shift to new project
Further clarifications needed
| Completed | [9 empty] | 11 active tasks ( 1 deleted and 3 merged) including 3 new request
| Changed Date |  |  |  | H=8,M=3
About to be held
Note on L34: Akbari , Amir: It was planned on Sep.2016, Planned Implementation on 1-4 October

## IRA2013_Sep_2016
IRA2013: Action Plan for implementation of Workplan activties in 2016-2017
as of 25.09.2016
Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed
2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Vienna | PRM | Q1/2017
1.5 IAEA Field Monitoring (once per quarther)
2.2 Preparatory visit for OSART mission
3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | Q4/2016 | Ready to be implemented on 14-16 November 2016. Official information will be submitted soon for visa support. | H | Planned for 14-16 November 2016
2.4 Implementation the nuclear safety oversight function
4 | 2.4.1 | One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: Derakhshandeh | 1 IAEA+2IEX |  | Tehran | EM | Q1/2017 |  | M | The need to be confirmed at March 2016 follow-up visit
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
5 | 3.1.1 | WS on "modern methods for measuring hydrogen concentration in containment " | IAEA: S. Monti, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q4/2016 | IAEA will arrange and organize team to be held this WS on Q4 2016 at Bushehr Site | H | The needs and expectation have been specified. To be composed the expert team for this mission by IAEA.
3.2 Training on environmental qualification of safety equipment of BNPP-1
6 | 3.2.1 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD | SV | Q3/2016 | Pending SV nomination. As agreed in the May coordination meeting,the SV to be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. This can be reflected in the SV nomination form. Review of the SV can only be done once we receive the SV nominations.NPPD will send 3 NFs by the end of october 2016. Considering above mentioned necessary prerequisite, it is expected to hold this task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or Brazil
7 | 3.2.2 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q3/2016 | NPPD will send 3 NFs by the end of october 2016. Considering above mentioned necessary prerequisite, it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or Brazil
8 | 3.2.3 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q3/2016 | NPPD will send 3 NFs by the end of october 2016. Considering above mentioned necessary prerequisite, it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or Brazil
3.3 Training on equipment reliability assessment techniqes of equipment during operation
9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" | IAEA: K. Kang, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016 | TO is awaiting confirmation/response from the CP for this mission. We urgently need the confirmation of dated for this mission (possible to take place end of November and December if we receive the proposed dates by next week.) |  | Deleted
3.8 Development of ageing management program for BNPP-1
10 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q3/2016 agreed on Feb 2017 as new date | NPPD requests to implement it on Feb 2017 | H | In progress
11 | 3.8.2 | WS developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: J. Moore, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q2/2017 |  | M | New request
3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1
12 | 3.10.1 | EM on "Assistance on review of safety analysis model for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Ghods-Derakhshandeh | 1 IAEA+3IEX/5 days( HBA 5 days) |  | Tehran | EM | Oct.2016 2017 | Pending information on models and any result of calculation-information needed one month prior to the mission date. Need confirmation on mission dates. | H | NPPD to provide one month before, information on modeles and any result of calculation. In Progress
13 | 3.10.2 | E M on independent analysis of root-cause results for BNPP-1 | IAEA: P. Tarren, NPPD: Abbaspour/Ghods | 1 IAEA+3IEX/5 days |  | Tehran | EM | Q2/2017 |  | H | NPPD to provide two month before information in English on the root cause analysis in the last two years.
3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1
14 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q4/2016 Q4/2017 | As agreed in the May coordination meeting, IAEA is awaiting further clarification of the TOR/Scope of the mission and dated for the mission. | H | IAEA request further clarification of what NPPD are seeking. In Progress
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
15 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: T. Ulses, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2018 |  |  | Move to the next cycle. (2018-2019)
16 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; C .Hill, NPPD: Ghods-Abbaspour | 1 IAEA+2 IEX |  | Tehran | EM | Q2/2017 |  | M
5.5 Assistance in development of selected training scenarios for severe accidents in FSS
17 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | Q2 /2018 |  |  | To be discussed afterimplementation of 6.3.1,
5.6 Assistance in development & improvement of training system of maintenance & repair personnel
18 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: D. Drury, J. Song NPPD: Rahnama-Talebianzadeh | 1IAEA+2IEX |  | Bushehr/Tehran | EM | Q4/2016 | the technical officer is awaiting the scope/ToR for this mission. The tentative date is 5-9 November 2016. We would appreciate to receive soonest possible the ToR to compose the expert team for this mission. | H
6.1 Asistance in review of BNPP-1 off-site emergency preparedness and response
19 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA: P. Salinas, NPPD: Abbaspour | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | M | NPPD: To send clarification on the focus: Training on off-site response to radiological emergency situation BNPP-1?
6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1
20 | 6.3.1 | EM to review progress in development of the severe accident analysis model (using computer code) for BNPP-1 | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | EM | Q2/2017 |  | H | Depending on availability computer code
21 | 6.3.2 | RM to review the progress in development of the severe accident managementguidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | TSR-AM | Q3/2017 |  | H | TSR-AM: Technical Safety Review- Accident Management
7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1
22 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening, NPPD: Abbaspour | 1IAEA+3IEX |  | Bushehr | EM | Oct.2016 | NPPD had shared the scope and potential dates (second half of october 2016) for this mission on 15 August 2016. TO is reviewing the composition/availability of the experts for the specific dates for the mission. | H | IAEA to confirm the date. BNPP-1 will provide tools for measurements.
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
23 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: D. Talleria, NPPD: Abbaspour | Procurement |  | Bushehr | Procurement | Oct.2016 | IAEA had initiated the procurement process. GCS has been transfeered to the project.The procurement process is in proceed . | H | NPPD: to clarify the scope and duration of maintenance period. The IAEA will inform anout the expected price. NPPD will proceed with the officils request. Timely payment of GCS is important.
2.3 Implementation of OSART mission
24 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  | Bushehr | EM | Q4/2017 |  | H | IAEA: November 2017 is recommended. An official request is needed untl the end of Q2 2016
2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers
25 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | Tehran | EM | 16-20 July 2016 | Completed | H
2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission
26 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q1 2017( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1-2 NEX |  | TBD | FS | 2017 |  | H
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
27 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: B.Song, K.Makela, NPPD: Deylami | 1 IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | H
3.4 Training on containment leakage tests and calculations after outage
28 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H
29 | 3.4.2 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H
30 | 3.4.3 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H
31 | 3.4.4 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H
3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system
32 | 3.5.1 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q1/2017 |  | M | NFs should be sent to IAEA at least 8 months before.
33 | 3.5.2 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q1/2017 |  | M | NFs should be sent to IAEA at least 8 months before.
34 | 3.5.3 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q1/2017 |  | M | NFs should be sent to IAEA at least 8 months before.
35 | 3.5.4 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | TBD | SV | Q1/2017 |  | M | NFs should be sent to IAEA at least 8 months before.
3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR
36 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1IAEA+3IEX |  |  | WS | Q1/2018 |  |  | Shifted to next cycle(2018-2019_
3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles
37 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  | Tehran | EM | Q1/2017 |  | H
3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system
38 | 3.9.1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests, High and low cycle fatigue analysis for strength assessment of Reactor Coolant System | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  | Tehran | WS | Q3/2017 |  | M | the IAEA will contact to NPPD by end of june 2016.
3.12 Assistance in performing the living PSA of the BNPP-1
39 | 3.12.1 | EM to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: I Kuzmina, NPPD: Ghods | 1IAEA+2IEX |  |  | EM | Q1/2018 |  |  | NPPD: To send information on the scope and focus including utilization of risk spectrum softwarein two months before the mission.
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
40 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: C. Hill / T.Ulses, NPPD: Derakhshandeh | 1 IAEA+2 IEX |  | Tehran / Bushehr | EM | Q2/2017 |  | M
4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
41 | 4.1.1 | EM on "modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes " in Q1 2017, (1 IAEA +3 IEX ) | IAEA: H. Varjonen, NPPD: Roshankar | 1IAEA+3IEX |  | Bushehr | EM | Q3/2017 |  | H
4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
42 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:J. Moore, NPPD: Tajbakhsh | 1IAEA+3IEX |  | Tehran | EM/HBA | Q4/2016 | As agreed in May coordination meeting, NPPD to provide expectations,focus and apprach by the end of june. Please advise if this was already provided for us to move to the next step for implementation. | H | NPPD to provide expectations,focus and approach by the beginning of October 2016.
5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
43 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | M
5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
44 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017
45 | 5.2.2 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017
46 | 5.2.3 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
47 | 7.4.2 | EM on "Review and assesment of results of environmental monitoring programme using the software ESTE" | IAEA: D. Talleria, NPPD: Abbaspour | 1 IAEA+2IEX |  | Bushehr | EM | Q4/2017 |  | M
4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators
48 | 4.4.1 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD |  | SV | 2017 | H | New request for 2016 NPPD: to send the scope and focus of this task two months before the mission. (Potential for UKR, Zhaporozhe)
4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs
49 | 4.3.1 | WS on outage optimization through advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs | IAEA: H. Varjonen NPPD:Roshankar | 1IAEA+3IEX(4 days) |  | Bushehr |  | WS | Q3/2017 | H | New for 2017. NPPD: to send the scope and focus of this task two months before the mission.
Deleted / shifted to 2018-2019
| Further clarifications needed | [6 empty] | 31 active tasks including 2 new request
| Completed | [6 empty] | H= 22,M=9
Note on L17: Rahnama , Afshin: on email 06.April.2016,