Delivery Contract

No. ____________________

between

Nuclear Power Production and Development Company of Iran

(Buyer)

and

ZAO DIAKONT

(Seller)

for SKGO-MP of Bushehr NPP

_______________ 2015

Nuclear Power Production and Development Company of Iran, established and existing under the law of the Islamic Republic of Iran, hereinafter called the BUYER, represented by _________________________, acting under the ________________, and ZAO DIAKONT, established and existing under the law of the Russian Federation, hereinafter called the SELLER, represented by the General Director Mikhail Fedosovsky, acting under the Charter, have entered into this contract, hereinafter called the Contract, as follows:

1. Subject of the Contract

1.1. The SELLER undertakes to produce and deliver to the BUYER, and the BUYER undertakes to pay for the equipment listed in the Specification (Appendix 1), hereinafter called the EQUIPMENT.

2. Contract Value

2.1. The value of this Contract is 560,000.00 (five hundred sixty thousand) EURO DAP Seaport __________________ under Incoterms 2010. The contract value includes the costs of the EQUIPMENT, export documentation issuance, transportation, packing, delivery, supervision of installation, EQUIPMENT setup and consulting services related to BUYER’s specialists training in operation of the EQUIPMENT on Bushehr NPP Unit 1.

2.2. The Contract Value shall not be revised.

2.3. All duty costs and banking expenses under this Contract which arise after EQUIPMENT arrival on the territory of the Islamic Republic of Iran shall be paid by the BUYER. All expenses which arise outside the territory of the Islamic Republic of Iran shall be paid by the SELLER.

3. Contract Dates

3.1. All EQUIPMENT under this Contract shall be delivered within 10 (ten) months from the date of this Contract (provided that clauses 15.4, 15.5 are observed by the Parties).

3.2. The shipment date of the EQUIPMENT is the date when the consignment was issued by the SELLER.

3.3. After EQUIPMENT arrival, the BUYER is responsible for transporting within the Islamic Republic of Iran, loading, unloading and storing the EQUIPMENT in accordance with the SELLER’s instructions.

3.4. The SELLER shall notify the BUYER 5 days before the shipment date of the EQUIPMENT as per the Contract. The notice shall contain the following information:

- Contract number;

- Planned shipment date;

- List of EQUIPMENT, quantity, weight (net/gross) and dimensions with package;

- Cost of EQUIPMENT shipped.

- Shipment marking.

3.5. Within 5 working days after the shipment date of the EQUIPMENT as per the Contract, the SELLER shall forward copies of the following documents to the BUYER by fax/email: consignment, packing list, proforma Invoice with the cost of EQUIPMENT and package type indicated.

At the same time, the SELLER shall send the following documents to the BUYER by express post:

- 1 duplicate copy of the consignment;

- 1 original copy of the proforma Invoice for the cost of delivered EQUIPMENT for customs clearance;

- 1 original and 2 duplicate copies of the detailed packing list;

- IPPC of the wooden package statement issued by the SELLER, or the wooden package statement issued by the beneficiary.

3.6. The SELLER has the right to deliver the EQUIPMENT ahead of time, having informed the BUYER about that beforehand. Ahead-of-time delivery of the EQUIPMENT will be a basis for ahead-of-time payment.

3.7. The proprietary right for the EQUIPMENT, and the accidental loss and/or damage of property risks are transferred to the BUYER from the time of EQUIPMENT delivery as per 2.1 of this Contract.

3.8. From the time of delivery and till payment, the EQUIPMENT transferred under this Contract is deemed to be pledged to the SELLER in order to provide that the BUYER fulfills its obligations regarding payment for the EQUIPMENT.

4. Payment Terms

4.1 The BUYER shall pay 168 000.00 (one hundred sixty eight thousand) EURO by bank transfer to the SELLER’s business account within 30 days from the date of this Contract after receiving the commercial invoice (1 original).

4.2. After receiving the payment as per 4.1 of this Contract, the SELLER shall ship the EQUIPMENT within the time stipulated in 3.1 of his Contract and, prior to the shipment, send to the BUYER the consignment (1 duplicate), proforma invoice for the full cost of delivered EQUIPMENT (1 original + 1 duplicate), IPPC of the wooden or not wooden package statement issued by the beneficiary (1 original + 1 duplicate), quality certificate (1 original + 1 duplicate), certificate of origin (1 original), packing certificate (1 duplicate), acceptance certificate (1 duplicate) (Supplement 1 to Appendix 3), packing list (1 original + 1 duplicate) and acceptance certificate (1 duplicate) and warranty letter (1 original) signed by the SELLER before the shipment.

4.3. The BUYER shall pay 364 000.00 (three hundred sixty four thousand) EURO by bank transfer to the SELLER’s business account within 30 days from the date of EQUIPMENT delivery after receiving the commercial invoice (1 original).

4.4. When the supervision of installation, EQUIPMENT setup and training of BUYER’s specialists on Bushehr NPP Unit 1 are completed, the BUYER shall pay 28 000.00 (twenty eight thousand) EURO by bank transfer to the SELLER’s business account within 20 days from the date of receiving the commercial invoice (2 originals) and Works Completion Certificate for Bushehr NPP Unit 1 (Supplement 2 to Appendix 3).

4.5. The payments shall be made to the SELLER using the following banking details:

MDM Bank (Public Joint Stock Company) ST.PETERSBURG BRANCH, 197022, Russia, Saint-Petersburg, Kamennostrovskiy pr. 53

SWIFT code: MOBWRUMM

№ 40702978100021003353

Correspondent bank:

Deutsche Bank AG 12, Taunusanlage 60262 Frankfurt/Main Germany

SWIFT code: DEUTDEFF

acc. 100947414900

4.6. Banking details of the BUYER:

5. Warranty

5.1. The warranty period of EQUIPMENT delivered under this Contract is 12 months from the date of EQUIPMENT commissioning, but not more than 18 months from the date of EQUIPMENT shipment. The BUYER hereunder undertakes to inform the SELLER of the date of EQUIPMENT commissioning.

5.2. Within the warranty period, the SELLER shall rectify the EQUIPMENT manufacturing defects which may occur on the BUYER’s territory or replace the faulty EQUIPMENT at its own expense, provided that the BUYER fulfills the rules of EQUIPMENT transportation, storage and operation. Should the EQUIPMENT be damaged due to negligent storage, transportation to Bushehr NPP, improper installation, maintenance, or should any changes be made by the BUYER to the EQUIPMENT structure during the warranty period without the presence of a SELLER’s representative or without its written agreement, or should the requirements of the SELLER’s technical documentation be fulfilled improperly by the BUYER, the SELLER shall not be responsible for the incurrence of such shortcomings/defects.

5.3. Should any defects of the EQUIPMENT be found, a Defect Detection Certificate shall be prepared in the presence of authorized representatives of the BUYER and SELLER. The Certificate shall be signed by the authorized representatives of the BUYER and SELLER. The Defect Detection Certificate shall contain the name of the defective EQUIPMENT, delivery date, and defects description sufficient for analyzing the reasons of the defects. If the SELLER is at fault, the BUYER sends a written reclamation containing a technical description of the defects, and the SELLER undertakes to consider the reclamation within 10 (ten) calendar days and to notify the SELLER of the acceptance of the reclamation or to give a reasoned refusal. Should any controversy regarding the nature of the defects arise between the Parties, they have the right to consult an expert organization in order to determine the reasons and/or the scope of the defects. If the reclamation is found reasonable, the SELLER undertakes to take, for its own expense, within the time period agreed between the Parties, all appropriate measures for rectification of the detected EQUIPMENT defects. The SELLER has the right to choose the defect rectification method, including EQUIPMENT delivery to the BUYER’s warehouse in St. Petersburg (repair, replacement, correction) and return of the rectified EQUIPMENT to Bushehr NPP, by informing the BUYER of its choice. Regardless of what method is chosen by the SELLER, the SELLER is responsible for rectifying the EQUIPMENT defect within the time limit agreed with the BUYER.

5.4. For the purpose of performing EQUIPMENT defect rectification works during the warranty period and other works, the BUYER undertakes to provide the SELLER, upon request, with the necessary equipment, lifting and hoisting mechanisms, workshops, decontamination equipment, energy resources, spare parts and expendables which are required and available on the site of Bushehr NPP. The SELLER undertakes to compensate the BUYER for the expendables and spare parts used within an agreed period, but not later than 3 (three) months from the date of completion of the defect rectification works. When required and possible, the BUYER will provide the SELLER with Bushehr NPP personnel to assist the SELLER in the repair works.

5.5. Where a reasoned refusal of the reclamation is given, the defect rectification works may be performed under a separate contract.

5.6. Within the warranty period, the SELLER provides the BUYER with spare parts for the EQUIPMENT. When the warranty period is over, the spare parts will be supplied under separate contracts.

6. Equipment Packing, Marking and Acceptance

6.1. The SELLER shall pack the EQUIPMENT and provide protection against exposure to natural phenomena, against damage and harmful effects during transportation and storage. Marking  shall be in English.

6.2. All wooden packing material sent to Iran shall be examined by a specialist of an authorized organization or an authorized representative of the quarantine center of the Russian Federation and provided with the special IPPC stamp.

6.3. Acceptance is performed at the SELLER’s factory in accordance with the test program developed by the SELLER and agreed with the BUYER. The SELLER undertakes to develop and send the test program to the BUYER for review at latest two months before the planned acceptance date, and the BUYER undertakes to review the test program at latest in 20 days following the date of its receipt from the SELLER.

6.4. Duration of the EQUIPMENT acceptance by the BUYER’s representatives at the SELLER’s factory shall not exceed 7 working days.

6.5. The BUYER’s representatives shall participate in acceptance of the manufactured EQUIPMENT at the SELLER’s factory and have the right to familiarize themselves with accompanying documentation and records during the acceptance.

6.6. The SELLER shall inform the BUYER about participation in the product acceptance at the SELLER’S premises 15 calendar days before the estimated date of acceptance. Upon receipt of the notification from the SELLER, the Parties shall agree and approve the final date and detailed timetable of the planned acceptance. However, the date of acceptance initially proposed by the SELLER may not be shifted by more than 7 days. Traveling, accommodation, dining and other costs shall be paid by the BUYER. If the BUYER or its representative cannot attend the acceptance commission, they must inform the SELLER thereof 10 days before the final date of the acceptance inspection. In this case, the SELLER shall not extend the delivery period and shall sign the Acceptance Certificate (Supplement №1 to Appendix №3) in absence of the BUYER’s representatives.

6.7. For more effective acceptance at the SELLER’S factory, the SELLER, upon the BUYER’S request, will assist in organization of respective services, such as transfer, accommodation, dining, etc. Costs of transfer, accommodation, dining, etc. shall be paid by the BUYER.

6.8. The SELLER shall inform the BUYER about the progress of works every 45 days within the period starting from the 3rd month of contract performance up to equipment delivery.

6.9. Representatives of the SELLER and the BUYER shall undertake to perform joint inspection of the EQUIPMENT at the seaport _______________ warehouse no later than 15 days after arrival of the EQUIPMENT to the seaport ______________. No later than in 3 calendar days after EQUIPMENT arrival to the seaport ______________, the BUYER shall call out the SELLER for participation in the inspection, make provisions for the inspection and assist representatives of the SELLER in obtaining visas. The inspection shall consist in examining the EQUIPMENT for external damage, availability of the complete technical documentation package, integrity, package, marking of products and package, availability of the full scope of supply and shipping documents. In case of conformity of the EQUIPMENT with requirements of the Contract, representatives of the SELLER and the BUYER shall jointly sign the Certificate of Equipment Inspection on Arrival to seaport ____________ (Appendix №4). Should any defects be found in the EQUIPMENT, representatives of the SELLER and the BUYER shall draw up the Defect Detection Certificate according to 5.3. In this case the BUYER shall undertake actions set forth in the International Convention for the Unification of Certain Rules of Law relating to Bills of Lading ("Hague Rules"), and Protocol of Signature (Brussels, 25 August 1924).

7. Liability of the Parties

7.1. Should the SELLER fail to ship the EQUIPMENT by the date stipulated in the Contract, except force-majeure for reasons set forth in Article 13 of this Contract, the SELLER shall pay penalty to the BUYER. The penalty shall amount to 0.05% of the total price of unshipped EQUIPMENT for every 7 days of delay (delay lasting for less than seven days shall be regarded as a seven days’ delay). However, the maximum penalty shall not exceed 10% of the total price of EQUIPMENT shipped late. Should the SELLER delay the shipment of the EQUIPMENT for more than 90 days after the date set in the contract, the BUYER shall reserve the right to terminate the contract.

7.2. Should the BUYER fail to effect payment in time set in the contract, except force-majeure for reasons set forth in Article 13 of this Contract, the BUYER shall pay penalty to the SELLER. The penalty shall amount to 0.05% of the total amount of each delayed payment for every 7 days of delay (delay lasting for less than seven days shall be regarded as a seven days’ delay). However, the maximum penalty shall not exceed 10% of the total amount of each delayed payment.

7.3. Should the payment period for the supplied EQUIPMENT be delayed for more than 90 (ninety) days, the SELLER shall be entitled to claim penalty for the entire payment period breached, return of the supplied EQUIPMENT, as well as indemnification of costs and damages incurred in connection with performance under this Contract.

7.4. Indemnification of damages shall not constitute a waiver of obligations under the Contract for the Parties.

8. Use of Equipment

The BUYER undertakes to:

8.1. Use the equipment received under this contract for inspection of tightness of fuel assemblies at Bushehr NPP.

8.2. Use the equipment received under this contract in accordance with laws of the Islamic Republic of Iran.

8.3. Use the equipment received under this contract only for the declared purposes not connected with activities relating to creation of nuclear explosive devices.

8.4. Prevent copying, modifying, re-exporting or transferring the Equipment received by the BUYER under this contract without written permission of ZAO Diakont endorsed by the Federal Service for Technical and Export Control of the Russian Federation.

8.5. Prevent using the Equipment received by the BUYER under this contract in activities of nuclear fuel cycle beyond IAEA guarantees.

9. Equipment Installation and Setup

9.1. The BUYER shall ensure installation of the EQUIPMENT and its connection in accordance with the SELLER’S recommendations. Installation of the EQUIPMENT at Bushehr NPP Unit №1 shall be performed by the BUYER or its representative in accordance with the Technical Requirements for Layout Plan, installation instruction and provisions of operating documentation supplied by the SELLER together with the EQUIPMENT. The Seller shall provide the Technical Requirements for Layout Plan before _________________.

9.2. Cabling necessary for connection of equipment at Bushehr NPP Unit 1 shall be performed by the BUYER or its representative in accordance with the Technical Requirements for Layout Plan provided by the SELLER.

9.3. Purchasing of cable products for establishing:

- communication line between the remote control equipment of SKGO MP and Technological equipment of SKGO MP (outside the containment from the connection box in the fuel-handling machine control room to penetrations; inside the containment: from penetrations to the fuel-handling machine cross-wiring cabinet, along the fuel-handling machine from the cross-wiring cabinet of the fuel-handling machine to the trolley cross-wiring cabinet);

- power line of the Technological equipment of SKGO MP (outside the containment from the power supply to penetrations; inside the containment: from penetrations to the fuel-handling machine cross-wiring cabinet, inside the containment: from penetrations to the fuel-handling machine cross-wiring cabinet, along the fuel-handling machine from the cross-wiring cabinet of the fuel-handling machine to the trolley cross-wiring cabinet);

- power line of the Remote control equipment of SKGO MP (outside the containment from the power supply to the Remote control equipment of SKGO MP);

shall be performed by the BUYER basing on requirements for cable products set forth by the SELLER in the Technical Requirements for Layout Plan.

9.4. Within 10 calendar days after receipt of the EQUIPMENT, the BUYER shall agree with the SELLER on the time schedule of installation supervision and EQUIPMENT setup works. The time schedule shall be feasible and shall not exceed 30 calendar days, whereas the supervision period according to this time schedule shall not exceed 3 months following the date of EQUIPMENT receipt by the BUYER.

9.5. The SELLER shall ensure supervision of the installation works performed by the BUYER, EQUIPMENT setup and instruction of the BUYER’S personnel in operating the equipment in accordance with the agreed time schedule.

9.6. Duration of installation supervision, EQUIPMENT setup and instruction of the BUYER’S personnel at the BUYER’S premises shall amount to no more than 30 calendar days. If the checkup time is extended at the BUYER’S initiative, additional expenses and costs incurred by the SELLER in that connection shall be subject to indemnification by the BUYER.

9.7. The SELLER shall provide installation of the EQUIPMENT and its connection in accordance with the SELLER’S recommendations.

9.8. All costs connected with detaching of the SELLER’S specialists to Bushehr NPP to supervise installation, setup and instruction of the BUYER’S specialists in operating the EQUIPMENT at Unit 1 shall be borne by the SELLER.

9.9. For more effective supervision of the installation, setup and instruction of the BUYER’S specialists at Bushehr NPP Unit 1, the BUYER, upon the SELLER’S request, will assist in organization of respective services, such as transfer, accommodation, dining, etc.

9.10. Two specialists will be sent by the SELLER to Bushehr NPP to supervise installation, setup and instruction of the BUYER’S specialists in operating the EQUIPMENT. Duration of the instruction is 4 days for 2 specialists of the BUYER.

9.11. Upon completion of supervision of EQUIPMENT installation and setup at Bushehr NPP Unit 1, the SELLER and the BUYER shall sign the Works Completion Certificate (Supplement №2 to Appendix №3) at latest in 10 days’ period following the completion of supervision at Bushehr NPP.

10. Period of Validity

This Contract shall be valid until December 31, 2016.

11. Disputes and Disagreements

11.1. Any disputes arising under this Contract or in connection thereof shall be settled by negotiation. Should settlement by negotiation be impossible, the disagreements shall be submitted and settled in accordance with the Rules of the Arbitration Institute of the Stockholm Chamber of Commerce by one arbitrator appointed in accordance with the said rules.

11.2. Arbitration shall be held in Stockholm, Sweden, unless otherwise agreed by the Parties. The language of the arbitration shall be English.

11.3. The decision taken by the Arbitration Commission shall be final and binding for both Parties. The decision taken by the Arbitration Commission shall be made in writing. Arbitration costs shall be borne by the defeated Party.

12. Force Majeure

12.1. The force majeure circumstances shall mean the circumstances which emerged after execution of the Contract as a result of events of extraordinary nature unforeseen and unavoidable by either Party, such as fire, flood, earthquake and other natural disasters, wars, military actions, mass riots, acts of state authorities, as well as other circumstances beyond the will and control of the Parties, resulting in the impossibility to perform under the Contract properly.

12.2. The SELLER shall not be liable for late shipment or failure to deliver the EQUIPMENT due to force-majeure circumstances which may arise during the production process or during loading and carriage. The SELLER shall immediately inform the BUYER about the above-mentioned occasions and, at latest in 14 days after the event, the SELLER shall provide the BUYER by air mail with a document issued by competent authorities in confirmation of the occurred event. Notwithstanding the above-mentioned circumstances, the SELLER shall be liable for taking any measures necessary for the delivery of the EQUIPMENT as soon as possible.

12.3. In the event if the emergency lasts for over ten weeks, the Parties shall settle further Contract performance procedure and come to an agreement as soon as possible.

13. Establishment of Communications

13.1. Communications between the BUYER and the SELLER shall be effected via separated channels, for instance, correspondence, letters, fax, e-mail, personal contacts, meetings, telephone, etc.

13.2. Any notification, consent, agreement or permission that may be provided by one Party to the other Party in accordance with the Contract shall be made in writing and signed by authorized representatives of the Parties, even though they may previously agree verbally or electronically, including e-mail, for convenience and to speed up the process.

13.3. Any documentation subject to exchange between the Parties shall be transferred in accordance with the rules established in Article 14.

14. Legal Addresses of the Parties

14.1. SELLER:

ZAO DIAKONT

4, Ropshinskoye shosse, 198903, Petrodvorets, Russia. Fax: +7 (812) 592-62-65. Electronic mail: sales@diakont.com

14.2. BUYER:

Nuclear Power Production and Development Company of Iran

15. Other Terms

15.1. Any additions and changes to this Contract shall be agreed by signing Addenda between the SELLER and the BUYER.

15.2. All correspondence important for performance of this Contract shall be made in English.

15.3. Facsimile copies of documents signed by authorized representatives have legal force.

15.4. After signing the Contract, the BUYER shall provide to the SELLER (at latest in 20 (twenty) days after Contract signing) the Obligation of the authorized body in the Islamic Republic of Iran that the EQUIPMENT:

- will not be used for production of nuclear weapons, other nuclear explosive devices, or for any military purpose;

- will be covered by IAEA guarantees for the entire period of their stay under jurisdiction of the Islamic Republic of Iran;

- will be provided with physical protection measures at least with IAEA-recommended levels;

- will be re-exported or passed from the jurisdiction of the Islamic Republic of Iran to any other country only on specified terms.

In the event of failure to provide the mentioned Obligation in due time, the delivery period (3.1) shall be extended to the commensurate number of days.

15.5. The SELLER shall undertake to apply for the export license to the Federal Service for Technical and Export Control within one week after receipt of the signed original of the Contract and the Obligation (15.4), whichever comes last.  This Contract shall be terminated without any liability incurred by either Party in the event of refusal of authorized bodies of the Russian Federation to issue the export license.

15.6. The Contract is drawn up in 3 (three) copies in English, one for each party.

15.7. Applicable law shall be the law of the Russian Federation.

15.8. All Appendices (1-3) to this Contract shall constitute inseparable parts of the Contract and shall have equal legal force. Any corrections, changes or additions to the Contract shall be executed in writing as Addenda to this Contract and signed by authorized representatives of both Parties. These Addenda shall constitute inseparable parts of the Contract and shall have equal legal force.

16. Appendices:

Appendix №1: Specification of Supply

Appendix №2: Technical Specifications of SKGO MP

Appendix №3: List of documents supplied with the shipped EQUIPMENT.

| On behalf of the SELLER (ZAO DIAKONT) | On behalf of the BUYER (Nuclear Power Production and Development Company of Iran) |
| --- | --- |
| __________________ Mikhail Fedosovsky General Director | __________________ |

Appendix №1: Specification of Supply

| № | Designation | Qty, pcs. | Price per item, EURO | Total price, EURO | Note |
| --- | --- | --- | --- | --- | --- |
| 1 | SKGO MP 1000 ITCYa.421457.071-XX.01, including: | 1 | 560 000,00 | 560 000,00 |  |
| 1.1 | Mechanical equipment of SKGO MP ITCYa.302542.YYY | 2 | - | - |  |
| 1.2 | Technological equipment of SKGO MP ITCYa.421415.004-ZZ | 1 | - | - |  |
| 1.3 | Remote control equipment of SKGO MP ITCYa.467617.050 | 1 | - | - |  |
| 1.4 | Connection box ITCYa.468354.046 | 2 | - | - |  |
| 1.5 | Set of mounting parts ITCYa.463961.557 | 2 | - | - | For installation of equipment inside the containment |
| 1.6 | Set of mounting parts ITCYa.463961.640 | 2 | - | - | For installation of equipment in the fuel-handling machine control room |
| 1.7 | Set of spare parts ITCYa.421943.011 | 1 | - | - | (see Supplement №1 to Appendix №1) |
| 1.8 | Set of tools and accessories ITCYa.421944.010 | 1 | - | - | ( see Supplement №1 to Appendix №1) |
| 1.9 | Set of operating documents | 1 | - | - | In accordance with ITCYa.421457.071 VE |
| 2 | Packing, customs clearance, transportation |  |  | - |  |
| TOTAL: |  |  |  | 560 000 |  |

Supplement 1 to Appendix №1:

1. Set of spare parts ITCYa.421943.011

| № | Name | Qty, pcs. |
| --- | --- | --- |
| 1 | Complete pilot light with integral LED XB4BVM1 "Schneider Electric" | 1 |
| 2 | Power supply S82K-5024; 627-460 "F" Omron | 1 |
| 3 | Pressure sensor PSE530M5-L "SMC" <Р><S> | 1 |
| 4 | Ring 006-010-25-2 GOST 9833/ В-14-1 RAD TU 38 1051325-2001 | 3 |
| 5 | Contactor LP1-K0610BD3 "Schneider Electric" | 2 |
| 6 | Filament lamp BA9s 24V/3W/0,125A 33-468-30 "E" "Bailey" | 4 |
| 7 | Relay 55.34.9.024.0040 "Finder" | 1 |
| 8 | Pneumatic connector KK130P-02M-XZ "SMC" | 1 |
| 9 | Filter element AFD20P-060AS "SMC" | 1 |
| 10 | Filter element AFM20P-060AS "SMC" | 1 |
| 11 | Filter element AMJ-EL3000 "SMC" | 1 |
| 12 | Filter element IDG-EL5 "SMC" | 1 |
| 13 | Filter element AF20P-060S "SMC" | 1 |

2.  Set of tools and accessories ITCYa.421944.010

| № | Name (of tool, accessory, material) | Qty, pcs. | Note |
| --- | --- | --- | --- |
| 1 | Maintenance cable К-Р47 ITCYa.685631.023 | 1 | For connecting power to IMSS TE for testing outside the containment |
| 2 | Power supply cable К-С-NGM2T ITCYa.685631.107-01 | 1 | For connecting power to beta-activity meter for testing outside the containment |
| 3 | Pressure hose d9 class 3 (20 atm) GOST 9356-75 | 2 m | For draining condensate. Connected to patch panel when necessary. |

Appendix №2:

Technical Specifications of SKGO MP

SKGO MP is intended for detecting leaking fuel assemblies on a shut-down reactor while transported by the fuel-handling machine (called FHM). SKGO MP is installed on fuel-handling machines of VVER reactors.

- Technical characteristics

Single fuel assembly inspection time, max.	180 s

Continuous operation time, at least	720 hours

- Operating conditions

Mechanical equipment of SKGO MP is mounted on the main mast of the fuel-handling machine and operates in the same conditions.

- Environment	water or water solution

(distilled water containing 16-20 g/dm3 of boric acid)

- Water temperature, С, max	+70

- Positive pressure, MPa, max	0,2

Technological equipment of SKGO MP is mounted on the trolley of the fuel-handling machine in reactor hall and operates in the following conditions:

- Environment	air

- Air temperature, С,	+15 to +40

- Absolute pressure, MPa	0,84 to 1,067

- Relative air humidity, %, max	90

- Detected activity 	β – emission

- Detected activity energy range, keV	80 to 2000

- Detected activity range of beta-emitting gases, Bq/m3	3,7104 to 3,7109

Remote control equipment of SKGO MP is installed in the fuel-handling machine control room and operates in the following conditions:

- Environment	air

- Operating air temperature, С,	+10 to +25

- Pressure	atmospheric

- Relative humidity at 25С,%, max	80

- SKGO MP quality category – QA4.

- SKGO MP safety class – 4.

Appendix № 3:

List of documents supplied with the shipped EQUIPMENT

| No. | Description |
| --- | --- |
| 1 | Shipping documents |
| 1.1 | # Packing list |
| 1.2 | Equipment acceptance certificate Form of the certificate is provided in supplement №1 to this Appendix |
| 1.3 | Equipment test report on the SELLER’S site |
| 1.4 | SELLER’S Packing Certificate |
| 2 | Technical documentation |
| 2.1 | Registration certificates for the supplied equipment |
| 2.2 | Installation instruction |
| 2.3 | Operating manual |
| 2.4 | Technical requirements for layout plan |

Requirements for the shipping documents supplied

Accompanying documentation shall be supplied in the following amount and form:

1. Accompanying documentation shall be in 2 copies in English and 1 copy in Russian, or in 2 bilingual copies.

2. Documents shall be grouped together in order of succession of spare parts and types of equipment in which these spare parts are to be installed.

3. Each complete set of documents shall be individually bound, the identification list of included documents enclosed. Description and type of equipment in which the spare parts will be installed shall be provided on the title page for each document set. Number of pages in the document shall be indicated on the first page; page numbers shall be provided at the bottom or in the bottom right corner of each page.

4. All accompanying documentation shall be packed in box №1 for each shipping lot and shall withstand handling operations, long-range transportation, and shall be protected against moisture, rain and mildew.

Supplement 1 to Appendix 3:

Acceptance Inspection Certificate Form

### CERTIFICATE of ACCEPTANCE INSPECTION № _____________ Seller name ______________ __________________________________________________ This is to certify that _______________________________________________________________ (product name, specification, drawing designation) _________________________________________________________________________________ in the amount of ______________________________________________________________________ (units, weight) Factory № _______________________________________________________________________ (product) _________________________________________________________________________________ _________________________________________________________________________________ was made in the Russian Federation. In the course of acceptance inspection this product was found to be in compliance with legislative, design, working documents and with the contract № _____________________ dated “ ___ ” _____________ _____ . The following was checked during acceptance inspection: - availability of a complete technical documentation package - integrity, package, marking of products and package - availability of a complete scope of supply and shipping documents compliant with requirements of contract № _____________________ dated “ __ ” ______ _____ . General statement on the items: The items in question passed all acceptance checks and are eligible for shipment to the Buyer. Representative of the Buyer (signature) (printed name) Stamp “_____ ” _________________ 201__ . (date) Representative of the Seller (signature) (printed name) Stamp “_____ ” _________________ 201__ . (date)

Supplement 2 to Appendix 3

Works Completion Certificate form

Works Completion Certificate No. ___ Seller’s name ____________________________________________________ Buyer’s name __________________________________________________ Bushehr NPP Unit 1. Representatives of the Seller and the Buyer hereby confirm that works at Bushehr NPP Unit 1 completed with successful installation and adjustment of Equipment supplied under contract №__________________________ dated “____” _____________ ______. Personnel of Bushehr NPP was instructed in operation the equipment in full scope. Representative of the Buyer (signature) (printed name) Stamp “_____ ” _________________ 201__ . (date) Representative of the Seller (signature) (printed name) Stamp “_____ ” _________________ 201__ . (date)

Appendix 4:

Form of Certificate of Equipment Inspection on Arrival to ______________

### CERTIFICATE of inspection on arrival to seaport ___________ № _____________ Seller’s name ______________ __________________________________________________ Buyer’s name ____________ __________________________________________________ This is to certify that ______________________________________________________ ( product name, specification, drawing designation ) _________________________________________________________________________________ in the amount of______________________________________________________________________ (units, weight) has arrived to the seaport ______________. In the course of acceptance inspection this product was found to be in compliance with quality requirements as per contract № _____________________ dated “ ___ ” _____________ _____ . The following was checked during on-arrival inspection: - availability of a complete technical documentation package - integrity, package, marking of products and package - availability of a complete scope of supply and shipping documents, no external damage, which is in compliance with requirements of contract № _____________________ dated “ __ ” ______ ____ . General statement on the products: The products in question passed the on-arrival inspection. Representative of the Buyer (signature) (printed name) Stamp “_____ ” _________________ 201__ . (date) Representative of the Seller (signature) (printed name) Stamp Seal “ _____ ” _________________ 201_ . (date of certificate issue)