**Tentative timetable of future activities**

|  |  |  |
| --- | --- | --- |
| Activity | Starting date | End date |
| Task 4 – Implementation of INRA comments to report | October 2020 (?) | December 2020 |
| Measures implementation breakdown and prioritization | November 2020 | February 2021 |
| Detailed measures implementation plan | February 2021 | April 2021 |
| General implementation strategy of selected measures | April 2021 | June 2021 |
| Detailed implementation strategy of selected measures | May 2021 | August 2021 |
| Direct analytical support in selected measures implementation | May 2021 | December 2021 |
| Existing procedures, guidelines and safety reports review and modification | May 2021 | January 2022 |
| Direct designing support in selected measures implementation | July 2021 | December 2021 |
| Support in procurement of external services and equipment acquisition (bid process) | July 2021 | December 2021 |
| Implementation status evaluation, outline of future steps (after concluding of project) | December 2021 | January 2022 |
| Finalizing of project, approval of final documents | February 2022 | March 2022 |