SUMMARY-REPORT

on  implementation of engineering survey

at the Bushehr-2 NPP site as of 23.06.2015

Progress in physical types of works within the Iranian Customer’s responsibilities

| № | Scope of works included in ES Program | Scope of works planned according to Schedule of ES Program as of 23.06.2015 | Actual completion of works according to Schedule of ES Program as of 23.06.2015 | Work Delay (-) % /Advance (+) % of Schedule |
| --- | --- | --- | --- | --- |
| - Engineering-geodetic survey |  |  |  |  |
| 1.1 | Laying reference points - 19 points | 19 reference points (100 %); | Accord changing the number of reference points from 19 to 16 points.(BNPP-2-50) (laid centers of 16 points, but without plates indicating point number)(90 %) | - 10 % (Customer manufactures platelets) |
| 1.2 | Topographic survey - 175,2 h | Topographic survey - 175,2h(100%) | Topographic survey - 175,2h (100%); | Field works completed |
| 1.3 | Laying geodetic chain (120 benchmarks; 14 points) | Laying geodetic chain 120 benchmarks; 14 points (100 %). | Laying geodetic chain – 63 benchmarks (not formalized completely), 0 points (42,2 %) | - 57,8 % (Works are in progress, delay due to additional agreements) |
| - Engineering-geological survey |  |  |  |  |
| 2.1 | Drilling - 9200 r.m. | Drilling–8483m (97 %) | Drilled –8500 m (92 %), 8 drilling rigs from 17 delivered to the site are involved | - 5 % (Delay in drilling at sea area due to weather conditions) |
| 2.2 | Fieldgeotechnical survey (sounding - 48 points, pressure metering - 130 tests, stamp test - 40 test) | Fieldgeotechnical survey (sounding – 48points(100%), pressure metering – 130tests (100 %); stamp testing40tests (100 %) | Field geodetic survey (sounding - 36 points (75%), pressure metering96test (74 %), stamp test 6(15 %) | -25%; -26%; -85 % Scheduled time of work completion: 10.07.2015 17.07.2015 |
| 2.3 | Hydro-geological studies (6 pump-outs, 6 fillingsв) | Hydro-geological studies – 6 pump-outs (100 %), 6 fillings (100 %) | Hydro-geological studies – 0 pump-(10%), 0fillings (10 %) | - 90%; - 90 % Scheduled time of work completion: 10.07.2015 05.07.2015 |
| 2.4 | Land geophysical studies: refraction method-5300 m, VES survey - 7600 m, electrotomography – 4000 m, natural field - 5 points; | Land geophysical studies: refraction method-5300 m (100 %), VES survey - 7600 m (100%), electrotomography– 4000 m (100 %), natural field - 5 points (100 %) | Land geophysical studies: refraction method -5300 m (100 %), VES survey - 7600 m (100 %), electrotomography - 0 %, natural field - 5 points (100 %) | completed; completed; completed (protocol BNPP-2-55 date 09.05.2015); completed |
| 2.5 | Geophysical studies in the wells: radio logging - 2625 m, Down-hole - 2625 m, Seismictomography600 m | Geophysical studies in the wells: radio logging - 2625m (100 %), Down-hole – 2625m (100 %), Seismictomography600m (100 %) | Geophysical studies in the wells: radio logging –1785m, 80 %, Down-hole –1665m (75%), Seismic tomography –600 m, 100 % | - 20% - 25% (Delay due to borehole drilling at sea area) completed |
| - Seismological and seismo-tectonic studies: |  |  |  |  |
| 3.1 | 12seismic stations are installed | 12seismic stations are installed (100 %) | 12 seismic stations are installed (100 %) | completed |
| 3.2 | Seismic hazard assessment | Seismic hazard assessment - 100 % | Seismic hazard assessment - 40 % | - 60 % (Customer informed about Report handover) |
| - Hydro-meteorological studies |  |  |  |  |
| 4.1 | Arrangement of 1 weather station | Arrangement of 1 weather station - 100 % | Arrangement of 1 weather station -100% | completed (Arranged 19.03.2015) Software adjustment is needed |
| 4.2 | Equipment of100 m of meteorological station; | Equipment of 100 m of meteorological station - 100 % | Equipment of 100 m of meteorological station - 100 % | completed (Arranged 19.03.2015) |
| 4.3 | Equipment of point for radioacoustic sounding of bottom atmospheric layer (SODAR) | Equipment of 1 point for radioacoustic sounding of bottom atmospheric layer (SODAR)- 100 % | Equipment of 1 point for radioacoustic sounding of bottom atmospheric layer (SODAR)– 50 % | SODAR system is installed, Software adjustment is needed; compensatory measures are required |
| 4.4 | Arrangement of 5 points to measure atmospheric pollution, dustiness and corrosiveness and atmospheric corrosion velocity of metal samples | Arrangement of 5 points tomeasure atmospheric pollution, dustiness and corrosiveness - 100 % atmospheric corrosion velocity of metal samples – 100% | Arrangement of 5 points tomeasure atmospheric pollution, dustiness and corrosiveness – 0%; atmospheric corrosion velocity of metal samples – 100% | not completed (Reason of non-fulfillment has not been informed by the Customer) completed Installed on 26.05.2015. |
| 4.5 | Organization of 3 water-metering posts and 3 water sections in temporary water flows; | Organization of 3 water-metering posts - 100 % and 3 hydrometric ranges at temporary watercourcess - 100 % | Changing of water metering posts from 3 to 1 is agreed. 1 water metering post (100 %) and one 1 hydrometric range at temporary watercources (100 %) | completed; completed |
| 4.6 | Performance of hydrographic survey of Persian Gulf of scales 1:25000 (500 km2), 1:10000 (80 km2), 1:1000 (16 km2) | Performance of hydrographic survey of Persian Gulf of scales1:25000 – 453km2(91%), 1:10000, 1:1000 – 14 km2 (91 %) | Performance of hydrographic survey of the Persian Gulf of scales: 1:25000 -400km2 (80 %), 1:10000 – 80 km2 (100 %), 1:1000 - 15,2 km2 (95 %) | -20 %; выполнено; -5 % (Map material requires a serious rework) |
| 4.7 | Arrangementof18 temporarystations (offshore points) to measure water temperature in various layers | Arrangementof18 temporarystations (offshore points) to measure water temperature in various layers - 100 % | 18temporarystationsarearranged (offshore points) to measure water temperature in various layers (100 %) | completed |
| 4.8 | Arrangementof6 water metering stations | Arrangementof6 water metering stations - 100 % | Arrangementof6 water metering stations - 100 % | completed |
| 4.9 | Arrangementof12 stationsformeasurementsofflowdirectionandspeed, 1 station formeasurements of water level, water temperature and water conductivity at marine basin | Arrangementof12 stationsformeasurementsofflowdirectionandspeed - 100 %, 1 station formeasurements of water level, water temperature and water conductivity at marine basin - 100 % | 12 stationsformeasurementsofflowdirectionandspeed - 100 %, 1 station formeasurements of water level, water temperature and water conductivity at marine basin - 100 % are installed | completed |
| - Engineering-ecological survey |  |  |  |  |
| 5.1 | Route observations (18 key points); | Route observations in 18 points (100 %) | Route observations in 16 points - 100 % | completed |
| 5.2 | Studies of ground air: air sampling to determine concentration of harmful chemical substances at 2 stationsonce a month for a year) | Studies of ground air: air sampling to determine concentration of harmful chemical substances once a month at 2 stations -42 % | Studies of ground air: air sampling to determine concentration of harmful chemical substances1 time at 2 station- 25 % | -75% |
| 5.3 | Determination of ground air radiological indices (monthly during a year) | Determination of radiological indices hourly during a year) –40 % | Equipment is installed and measurements are performed in a scheduled mode. (10%) | -90% (Preliminary materials on work progress are not submitted) |
| 5.4 | Studies of terrestrial eco-systems: testing of natural soils in 15 key points | Studies of terrestrial eco-systems: testing of natural soils in 15 key points - 100 % | Studies of terrestrial eco-systems: testing of natural soils in 15 key points 100 % | completed (Reports are not submitted) |
| 5.5 | Study of vegetation in 3 points, agricultural soil testing | Study of vegetation in 3 points - 100 %, agricultural soil testing - 100 % | Study of vegetation in 3 points - 100 %, agricultural soil testing – 0 % | completed; (Reports are not submitted) |
| 5.6 | Study of vegetation and soil cover in 15 key points | Studies ofvegetationin6points - 65 %, soil cover in 15 key points - 100 % | Study of vegetation in 1 points - 100%, soil cover in 15 key points– 100 % | completed; Reports are not submitted) |
| 5.7 | Studies of aquatic eco-systems: hydro-chemical-studies (at 15 stations 3 times a year), radiological studies (at 14 stations once a year), hydro-biological studies (at 15 stations 3 times a year) | Studies of aquatic eco-systems: hydro-chemical-studies at 15 stations 3 times a year – 33 %, radiological studies at 14 stations 1 time a year - 33 %, hydro-biological studies at 15 stations 3 times a year - 33 % | Study of water ecosystems: hydro-chemical studies - 0 %, radiological studies - 20 %, hydro-biological studies – 33 % | -100% (Not fulfilled: stage 1- 01.02.2015 stage 2 - 19.04.2015); Non-fulfillment of work due to sea weather conditions by explanations of the Customer. -80%; (Preliminary materials on work progress are not submitted) 0% ) |
| 5.8 | Performance of chemical-analytical and other laboratory studies (during the year) | Performance of chemical-analytical and other laboratory studies - 50 % | Performance of chemical-analytical and other laboratory studies - 50 % | -50 % |
| 6 | Experimental soil compaction works | Experimental soil compaction works– 40 % |  | Protocol No 61 dated 23.05.2015 the term of development of Program of experimental soil compaction (the first stage of works) has changed on 30.11.2015 |

For the period from 16.06.2015 to 23.06.2015:

The overall backlog from ES Schedule is noted.

1. No obligations are fulfilled within the frames of Iranian Contractor responsibility as per Appendix 2 to MoM dated 08.04.2015 at “Bushehr” NPP site, and in particular:

- no work is carried out  to correct the comments of topographical survey after field observations, deadline 06.05.2015;

work to install points of the geodynamic polygon is carried out much behind the ES Schedule (work completion on 21.04.2015 as per MoM № BNPP-2-20 dtd. 03.03.2015);

- number of simultaneously running rigs is 8 instead of 17, deadline on 11.04.2015;

- plate load tests commenced on 01.06.2015, deadline on 10.06.2015;

- operability of SODAR and 10-meter meteorological station is not provided, deadline on 15.04.2015;

- 5 benches are installed; each of them has got a required number of plates for monitoring corrosive activity, 26.05.2015;

-  no work has been started to measure atmospheric pollution, dustiness corrosiveness and detrimental substances, deadline of work commencement on 23.04.2015;

- ecological-engineering survey of sea-water and bottom sediments related to  sampling for hydro-chemical analysis has been stopped and not performed at present;

- hydro-geological survey has been started (pumping out – 12.06.2015, pouring – 14.06.2015;12 piesometers out of 12 are installed), deadline on 17.05.2015.

2. According to MoM dtd. 20.05.2015 held between the parties’ Management on issues related to BNPP-2 Project realization, the following has been agreed:

2.1 Parties have agreed to replace survey method of  PS-logging to Down-hole method, by 23.05.2015;

2.3 the Customer has not submitted to the Contractor materials of topographic survey related to underground communications, by  23.05.2015;

2.4 The MoM has related to expedition of plate load tests  has been signed, by  24.05.2015;

2.5 The Contractor has sent to the Customer the list of instruments   which have no calibration certificates, by 24.05.2015;

- The Customer has not submitted appropriate certificates for instruments by 02.06.2015.