## PCMFExport
IRA/2/011: Action Plan for Implementation of | [7 empty] | 2014-02-26
Workplan activities in 2012-2013 |  | and 2014-2015
Activity | Implementing Officers/ Input | Venue | Type | Funding | Budget | Budget Year | Date | Comments
1.1 Safety Training through a Visit to an Incident Emergency Center | IAEA: Lipar, NPPD: Abbaspour | [6 empty] | BNPP-1 requested to be replaced with SVs on operation, RP, technical support and emergency preprdness.
| 1.1.1-1.1.5 SV1-5 for one week | TBD | 5 SVs | FootNote | 3,095 | 2012 | TBD | Pending. Final decision at the Annual Meeting in March 2014
1.2 Training to strengthen the capability of BNPP personnel on routine Core analysis for safe operation. | IAEA: Poulat, NPPD: Abbaspour | [6 empty] | Expectations provided
| 1.2.1 One week EM with 1 Agency Expert and 2 External Experts | Bushehr | EM | HardCore | 15,678 | 2012 | Nov. 2013 | Postponed to 27-30 April 2014
1.5 Training to assist BNPP-1 in operation of physical protection sytem | IAEA: Ubeev, NPPD: Amini
| 1.5.1 WS on BNPP-1 security procedures including operation of physical protection system (1 IAEA staff and 3 IEX) | Bushehr | WS | FootNote | 21,800 | 2012 | 1-4 Dec 2013 | Completed
1.6 Training to assist NPPD for application of physical protection against insiders and sabotage at BNPP-1 | IAEA: Ubeev, NPPD: Amini
| 1.6.1 WS on Evaluation of BNPP-1 physical protection system effectiveness (1 IAEA staff and 3 IEX) | Bushehr | WS | FootNote | 21,800 | 2012 | 18-21 Aug. 2013 | Completed
1.10 Workshop in security procedures at utility level | IAEA: Ubeev, NPPD: Amini | [6 empty] | Security procedures incorporated in 1.5.
| 1.10.1 Enhancement of BNPP-1 Nuclear Safety and Security Synergy (1 IAEA staff and 2 EX) | Bushehr | WS | HardCore | 13,065 | 2012 | 18-22 May 2014 | Focus changed on the BNPP-1 request
| 1.10.2 Strengthening Nuclear Security Culture (1 IAEA + 2 EX) | Bushehr | WS |  |  |  | 24-26 Nov.2014 | Focus changed on the BNPP-1 request
1.22 WWER in Core Fuel Management activities including preparation of optimized core pattern configuration by applying an overall optimized model | IAEA: M. Lipar, NPPD: Sheikholeslami/Ghods | [6 empty] | Pending availability of computer codes
| 1.22.1 WS on WWER core management calculations for safe operation of BNPP-1 (2 Agency Expert and 2 External Experts) | Tehran | WS | HardCore | 16,780 | 2012 | Sept/Oct 2014 | Topic refocusssed on the request
1.23 Steady state thermal-hydraulics paramenters of WWER reactor including coupling thermal-hydraulic codes with neutronic | IAEA: M. Lipar, NPPD: Sheikholeslami/Ghods | [6 empty] | Pending availability of computer codes
| 1.23.1 WS on Thermal-hydraulics analysis for safe operation of BNPP-1 (2 Agency Expert and 2 External Experts) | Tehran | WS | FootNote | 13,065 | 2012 | Q1/2015 | Topic refocusssed on the request
3.1 Training on outage management with focus on organization, implementation and supporting. | IAEA: Kang/Shouler, BNPP-1: Banazadeh/Deylami/Roshankar
| 3.1.1 WS on Outage management with focus on organization (1 Agency Expert and 2 External Experts) | Paks NPP | WS | FootNote | 21,000 | 2012 | 27-30 Nov.2012 | Completed
| 3.1.2 To support development of statement of Work (SoW) to comuterize BNPP-1 outage management activities with focus on safety aspects (one wek EM with1 IAEA staff and 2 IEX) | TBD | EM |  |  |  | Q3/2014 | Requested follow-up assistance
3.5 To strengthen the capability of BNPP personnel in establishment of Safety Performance Indicators in compliance with the latest IAEA guidance and best world practices. | IAEA: Yllera, Mandula; BNPP-1: Deylami
| 3.5.1 one week WS with 1 Agency Expert and 3 External Experts practices. | Bushehr | WS | FootNote | 21,800 | 2012 | 1-5 Dec.2012 | Completed
3.7 Modern methods of maintenance and repair of rotating/turbomachinery equipment | IAEA: Kang; BNPP-1: Roshankar | [6 empty] | The title changed on the request of BNPP-1.
| 3.7.1 One week WS with 1 IAEA and 5 national experts (NEX) | Hungary, Paks | WS | HardCore | 13,065 | 2012 | 12-15 Nov. 2013 | Completed
5.1 To asist BNPP-1 legal, contractual and technical provisions in operation contract between owner and operator company | IAEA: Vincze, NPPD: Tajbakhsh
| 5.1.1 EM on Building in safety requirements/considerations in contractual arrangements between NPPD and BNPP-1 (1 Agency staff + 2 IEX + 3-4 NEX) | Vienna | HBA +EM | FootNote | 16,350 | 2012 | 3-6 Sept.2012 | Completed
5.2 To assist BNPP-1 on general structure and spacial provisions in contracts for repair and /or maintemance of NPPs | IAEA: Kang, NPPD: Tajbakhsh
| 5.2.1 WS on Building in safety requirements/considerations in contractual arrangements for repair and/or maintenance of BNPP-1 ( 2 IEX + 4-5 NEX) | Vienna | WS | HardCore | 16,350 | 2012 | 24-26 Feb.2014 | Completed
8.2 Guidance on development of international safety oversight obligation | IAEA: Gest, BNPP-1: Abbaspour
| 8.2.1 WS on Proactive safety management during operation and outage, operational safety indicators (1 Agency staff and 2 IEX) | Bushehr | WS | HardCore | 21,000 | 2012 | 25-29 May'13 | Completed
8.3 Enhancement on NPPD safety performance control | IAEA: Lipar, NPPD: Sheikholeslami
| 8.3.1 One week Meeting with 1 Agency Expert and 2 External Experts | Tehran | WS | FootNote | 16,350 | 2012 | 3-6 Feb. 2013 | Completed
8.1. Assist in development and establishment of NPPD nuclear oversight organization | IAEA: Lipar, NPPD: Sheikholeslami
| 8.1.1 EM to assist NPPD nuclear oversight team to conduct safety oversight activity at BNPP-1 (1 IAEA staff and 1 IEX) | Tehran and Bushehr | EM |  |  |  | I half of May 2014 | follow-up on 8.3.1
8.4 To assist and support NPPD on supervision and control of NPPs outage program | IAEA: K.S. Kang, BNPP-1: Banazadeh | [6 empty] | Follow-up in 2014 to be considered
| 8.4.1 WS on maintenance strategy: predictive, preventive maintenance programme development (2-3 IEX) | Vienna | WS | FootNote | 21,000 | 2012 | 3-6 July 2012 | Completed
1.3 Training to strengthen the capability of BNPP Personnel on using the practical application of Living Probabilistic Safety Assessment for safe operation | IAEA: M. Lipar/B. Poulat, NPPD: Abbaspour/Ghods
| 1.3.1 WS on practical application of LPSA for safe operation of BNPP-1 (3 IEX +5 NEX) | Vienna | WS | FootNote | 17,820 | 2013 | 28 Oct -1 Nov 2013 | Completed
| 1.3.2 Asistance in the purchase and application of RISK SPECTRUM software | TBD | TBD |  |  |  | TBD | Additional follow-up request
1.4 Training (Scientific Visits) on methods for reduction of personnel dose during operation, routine maintenance and outage | IAEA: Lipar, BNPP-1: Abbaspour | [6 empty] | BNPP-1 request to refocus on: supervision of operation, technical service, event evaluation, near miss, low level events, etc.
| 1.4.1-1.4.5 SV 1-5 for one week | TBD | 5 SVs | FootNote | 3,155 | 2013 | TBD | Pending. Final decision at the Annual Meeting in March 2014
1.9 Implementation of OSART Mission | IAEA: Lipar, BNPP-1: Derakhshandeh
| 1.9.1 Three weeks Expert Mission with 2 Agency staff and 10 international experts | Busher | EM | HardCore | 83,625 | 2013 | February-March 2015 | To be confirmed
1.11 Preparatory mission for OSART mission | IAEA: Lipar, BNPP-1: Derakhshandeh
| 1.11.1 Three days EM with one Agency staff and tow external experts | Bushehr | EM | HardCore | 8,019 | 2013 | 3-4 Feb.2013 | Completed
1.12 To assist BNPP-1 in analysis of recent events and operational experience and create action plan for implementation of lessons learned | IAEA: Yllera, NPPD: Sheikholeslami
| 1.12.1 EM on good practices in implemnentation of stress test in IAEA Member States and identification of potential areas for improvement in BNPP-1 (1 IAEA staff and 3 IEX) | Tehran or Vienna | EM | FootNote | 17,820 | 2013 | 9-13 Dec.2012 | Completed
3.2 To strengthen the capability of BNPP personnel in methods and procedures for Plant life management program. | IAEA: Kang, BNPP-1: Deylami
| 3.2.1 WS on methods and procedures for Plant life management program (1 IAEA staff + 2 IEX + 4 NEX) | Vienna | WS |  |  |  | 22-24 Oct. 2013 | Completed
1.13 To support in development of a proces for assessment and improvement of safety culture in BNPP-1 | IAEA: M. Haage, BNPP-1: Abbaspour
| 1.13.1 WS to support BNPP-1 Senior Management for assessment and improvement of safety culture in BNPP-1 (1 IAEA staff and 3 IEX) | Busher or Tehran | WS | HardCore | 14,256 | 2013 | 19-21 Aug. 2013 | Completed
1.16 To support NPPD/BNPP-1 in strengthening routine and post accident environmental monitoring | IAEA: Polyakov, NPPD: Sheikoleslami
| 1.16.1 WS on routine and post accident environmental monitoring (1 IAEA staff and 2 IEX) | Tehran | WS | FootNote | 13,365 | 2013 | 17-20 Feb.2013 | Completed
2.1 Scientific visit on spare part management including warehouse | IAEA: Kang, BNPP-1: Roshankar
| 2.1.1-2.1.5 SV1-5 for one week | Paks NPP, Hungary | 5 SVs | FootNote | 3,155 | 2013 | 12-15 Nov.2013 | Completed jointly with 3.7
3.3 To strengthen the capability of BNPP personnel in using advanced Ultrasonic Test methods, standards, evaluation and techniques. | IAEA: Kang, BNPP-1: Deylami
| 3.3.1 EM on advanced UT methods, standards and techniques (2 External Experts) | Bushehr | EM | FootNote | 13,365 | 2013 | 6-8 July 2013 | Completed
| 3.3.2 Training (Fellowships) on advanced non-destructive methods and techniques for enhancement of safety of BNPP-1 reactor equipment (4 FSs for two weeks) | HRID, Croatia | 4 FSs |  |  |  | 2014-04-01 | reguest for follow-up activity
| 3.3.3 Scientific visits on proven methods for safety analysis of BNPP-1 equipment reliability (SV 1-4 for one week) | TBD | SV/or WS in Vienna |  |  |  | Q4/2014 | additional input requested
3.4 To strengthen the capability of BNPP personnel in application of best practices in water chemistry for Primary and Secondary circuit with focus on erosion corrosion. | IAEA: Kim, BNPP-1: Deylami
| 3.4.1 EM on application of best practices in water chemistry for Primary and Secondary circuit with focus on erosion corrosion ( 1 IAEA staff and 3 IEX) | Bushehr | EM | FootNote | 22,300 | 2013 | 23-26 Nov.2013 | Postponed to 2014
4.1 Assessment of BNPP-1 selected operational training program and procedures, assistance in the development of corrective action plan. | IAEA: Molloy, BNPP-1: Talebianzadeh | [6 empty] | BNPP-1 submitted 2 JTA - comments provided and proposal how to proceed further
| 4.1.1 Asistance on assessment of BNPP-1 selected operational training program and procedures (EM or/and HBA) | Bushehr | EM+ HBA? | FootNote | 13,365 | 2013 | Q4/2013 | Further assistance in review of selected documents in 2014
6.1 To evaluate BNPP HRM system and to provide recommendations for improvement | IAEA: Molloy, NPPD: Rahnama, BNPP-1: Talebianzadeh
| 6.1.1 Assistance in evaluation of BNPP HRM system | Merge with IRA4038, 4.1 | HBA +EM | FootNote | 13,365 | 2013 | 2014-04-01 | Self-assessment by December 2013
| 6.1.2 Assistance to enhance performance of BNPP-1 Psychlogical Laboratory | Vienna | HBA + CM |  |  |  | 2014 | Additional request Draft SoW reviewed in 2013. Further assistance to be clarified
6.2 To assist NPPD/BNPP-1 on improvement of knowledge management system | IAEA: Pasztory, NPPD: Rahnama
| 6.2.1 EM on improvement of NPPD/BNPP-1 knowledge management system (1 IAEA staff and 2 IEX) | Tehran | EM | FootNote | 13,365 | 2013 | 8-10 December 2013 | Completed
7.1 To assist in evaluation of FSS performance | IAEA: Molloy NPPD: Rahnama | [6 empty] | Link with new-10 in 2014?
| 7.1.1 EM to assist in review of procedure for evaluation and in development of an action plan for modification of BNPP-1 FSS (1 IAEA staff and 3 IEX) | TBD | EM/HBA | FootNote | 17,820 | 2013 | Q4/2015 | BNPP to provide draft report on planned modifications of the training programs, scenarios, procedures, and lessons learned from commissioning
8.7 To familiarize NPP experts with structure, function and qualification requirement for technical support of utility/operation organization | IAEA: Kang, NPPD: M. Sheikholeslami
| 8.7.1 WS on practical application of technical support of utility/operating organization | Tehran | WS |  |  |  | 4-6 May 2013 | Completed
9.1 To support BNPP-1 in the development of the strategy for continuous improvement of the BNPP Training Centre | IAEA: Molloy BNPP-1: Talebianzadeh | In partnership with WANO,
| 9.1.2 EM with I external expert | Balakovo | EM |  |  |  | 2013-05-01 | Completed
| 9.1.1 SV1-5 for one week | Balakovo | 5 SVs | FootNote | 3,155 | 2013 | 20-25 May 2013 | Completed
| 9.1.3 Assistance in T&Q of maintenance personnel using BTC | TBD | TBD |  |  |  | TBD
3.6 Scientific Visit on PSI application and evaluation of PSI | IAEA: Mandula NPPD: Deylami |  | SV |  |  |  | 2014
| 3.6.1 Scientific Visits 1-5 | Czech Republic/ Vienna | SV |  |  |  | 2014 | In progress. Change the venue to the IAEA to be considered
2.2 To strengthen the capability of BNPP in advanced maintenance methods, techniques, materials and tools | IAEA: Kang/Eiler/Mandula, BNPP-1: Roshankar/Deylami
| 2.2.1 WS on Advanced maintenance methods (1 IAEA staff and 3 IEX) | TBD | WS |  |  |  | Q3/2014
| 2.2.2 Training of BNPP-1 personnel on surveillance spesiments management of main safety equipment (one week WS with 1 IAEA staff and 2 IEX) | TBD | WS |  |  |  | Q3-4/2014 | additional input requested
| 2.2.3 Training on methods of vibration monitoring of rotating machines including reactor cooling pomp (RCP) and turbogenerator | Hungary, Paks NPP | WS |  |  |  | 30 June-3 July 2014 | Requested follow-up assistance
| 2.2.4 Assistance on computer based management if safety related operational and ispection procedures/documents | TBD | WS/EM |  |  |  | Q4/2014 | Additional (NEW-3) request
2.3 Scientific visits on outage management with focus on organization, implementation and supporting | IAEA: Kang, BNPP-1: Roshankar
| 2.3.1 Scientific visits on outage management (SV 1-5 for one week) | TBD | SV |  |  |  | Q3/2014
| 2.3.2 Scientific visits on advanced equipment and techniques for In-Service Inspection (ISI) of BNPP-1 primary circuit equipment (SV 1-4 for one week) | TBD | SV |  |  |  | Q4/2014 | additional input requested
2.4 Introduction of modern methods of outage management | IAEA: Kang/Kilic; BNPP-1: Roshankar/Deylami
| 2.4.1 EM on modern methods of outage management (1 IAEA staff and 3 IEX) | TBD | EM |  |  |  | Q3/2014
1.21 To visit NPPs for safety management systems with focus on radioactive waste management, radiation monitoring, core calculation and emergency preparedness | IAEA: Lipar, BNPP-1: Abbaspour
| 1.21.1-5 SV1-5 for one week | TBD | SV |  |  |  | Q4/2014
1.18 To support NPPD/BNPP-1 in enhancement of on-site and of-site emergency preparedness and response | IAEA: Lipar/Vincze, NPPD/BNPP-1: Abbaspour/Roshankar
| 1.18.1 EM on enhancement of on-site and of-site emergency preparedness and response (1 IAEA staff and 3 IEX) | TBD | EM |  |  |  | Q3/2015
| 1.18.2 Assistance in organization of emergency repairs team (2 IAEA staff + 2 IEX) | TBD | WS |  |  |  | TBD | Additional input requested
1.17 To advice BNPP-1 on proven approaches in radioactive waste management | IAEA: Ormai and Lipar, BNPP-1: Abbaspour
| 1.17.1 EM on radioactive waste management programme improvements (1 IAEA staff and 2 IEX) | Bushehr | EM |  |  |  | 14-18 September 2013 | Completed
| 1.17.2 To strengthen BNPP-1 capability on practical experience in decontamination related activties ( 2 IAEA staff and 2 IEX) | Bushehr | EM |  |  |  | Q4/2014 | additional BNPP-1 request
1.8 To assist BNPP-1 for implementation of effective accountancy and control measures | IAEA: Lipar, NPPD: Amini
| 1.8.1 Advanced training on effective nuclear accountancy and control using STAR software (one week training by software developer) | Tehran | EM |  |  |  | Q1/2014 | In progress
Legend:
New request - needs confirmation
Needs further clarification
Completed