Report on MTD Development and Handover within the framework of Addendum 58 to the Contract (as on 26.11.2016)

| No. | Activity |  |  | Total number (in Addendum 58) | Planned according to Schedule | Developed / implemented | Under the Principal’s review | Under the implementation of Principal’s comments | Approved by the Principal |  | Submitted to Principal | Reasons for delay |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Russian | English |  |  |
|  | Development of training programmes for job positions (Expert way) | Initial |  | 315 | 315 | 315 | - | - | 315 | 315 | - |  |
|  |  | Continuing |  | 49 | 49 | 49 | 0 | - | 49 | 49 | - |  |
|  | Development of training programmes for job positions (based on SAT) | Initial | Task list | 6 | 6 | 6 | 0 | - | 6 | 6 | - |  |
|  |  |  | Training objective | 6 | 6 | 6 | 0 | - |  |  |  |  |
|  |  |  | Training program | 6 | 6 | 6 | 0 | - |  |  |  |  |
|  |  | Continuing |  | 6 | 6 | 6 | 0 | - | 6 | 6 | - |  |
|  | Methodological Training Materials |  |  | 272 | 272 | 272/272 | - | - | 272 | 272 | - |  |
|  | Development of test items | Entry level |  | 12 | 12 | 12 | 0 | - | 12 | 12 | - |  |
|  |  | Final exam |  | 12 | 12 | 12 | 0 | - | 12 | 12 | - |  |
|  | Implementation of on-the-job training (as per schedule) |  |  | 480 | 5 | OJT is conducted for 5 persons. OJT is completed by 441 persons |  |  |  |  |  |  |
|  | Implementation of theoretical training (as per schedule) |  |  | 493 | 51 | Training has been conducted for 423 persons. Certificates have been issued for 420 persons |  |  |  |  |  |  |
|  | Development of administrative/technical documents |  |  | 9 | 9 | 9 | - | - | 9 | 9 | - |  |

As on 26.11.2016, 6321 Trainee's Materials and Lesson Plans (as complete sets in Russian and in English) of 26 compulsory training courses have been transmitted to the Principal. 26 Trainee's Materials and Lesson Plans (as complete sets in in Russian and in English) of additional training course TC27 "Operator Fundamental Skills" have been transmitted to the Principal. 41 BNPP-1 FSS scenarios have been developed and transmitted to the Principal's for agreement.