## Финал
Разработка и внедрение ИСМ АЭС "Бушер-1". Расчет стоимости
Этап | Дата начала этапа, месяц (T0 - дата получения заказа-нряда) | Дата окончания этапа (месяц) | Наименование работы | Грейд | Кол-во специалистов | Место выполнения работ | Ставка возмещения, евро | Кол-во часов работы по теме | Кол-во месяцев работы по теме | Трудозатраты, чел.*мес | Стоимость, евро
2017
Этап 1 | T0 | T0+2 | Проведение семинара для персонала АЭС «Бушер-1» по разработке и внедрению ИСМ. | 6В | 1 | РФ | 19944 |  | 0.25 | 0.25 | 4986 | Подготовка учебных материалов семинара по ИСМ для руководителей АЭС "Бушер-1"
|  |  |  | 7В | 1 | РФ | 17211 |  | 0.25 | 0.25 | 4302.75 | Подготовка учебных материалов семинара по ИСМ для руководителей АЭС "Бушер-1"
|  |  |  | 6В | 1 | АЭС "Бушер" | 22589 | 27 | 0.17 | 0.17 | 3840.13 | Проведение семинара для руководителей АЭС "Бушер-1" (3 дня).
|  |  |  | 7В | 1 | АЭС "Бушер" | 19692 | 27 | 0.17 | 0.17 | 3347.64 | Проведение семинара для руководителей АЭС "Бушер-1" (3 дня).
Итого по этапу 1 | [9 empty] | 0.84 | 16476.52
Этап 2 | T0 | T0+2 | Проведение аудита состояния текущего состояния документированной системы управления, процессов, KPIs. Подготовка детального совместного плана работ по внедрению ИСМ. | 6В | 1 | РФ | 19944 |  | 0.15 | 0.15 | 2991.6 | Подготовка к проведению аудита
|  |  |  | 7В | 1 | РФ | 17211 |  | 0.15 | 0.15 | 2581.65 | Подготовка к проведению аудита
|  |  |  | 6В | 1 | АЭС "Бушер" | 22589 | 88 | 0.54 | 0.54 | 12198.06 | Проведение аудита на площадке АЭС "Бушер-1". Подготовка детального совместного плана работ по внедрению ИСМ (10 дней)
|  |  |  | 7В | 1 | АЭС "Бушер" | 19692 | 88 | 0.54 | 0.54 | 10633.68 | Проведение аудита на площадке АЭС "Бушер-1". Подготовка детального совместного плана работ по внедрению ИСМ (10 дней)
Итого по этапу 2 | [9 empty] | 1.38 | 28404.99
2018
Этап 3 | T0 | T0+6 | Проектирование ИСМ.
| T0 | T0+5 | 3.1. Разработка и внедрение интегрированной политики, интегрированного руководства по ИСМ, интегрированных аудитов. Разработка/доработка описаний и моделей процессов. Направление проектов описаний процессов Заказчику. | 6В | 1 | РФ | 20942 |  | 0.25 | 0.25 | 5235.5 | Разработка описаний и моделей процессов в офисе Подрядчика.
|  |  |  | 7В | 3 | РФ | 18072 |  | 1.5 | 4.5 | 81324 | Разработка описаний и моделей процессов в офисе Подрядчика.
|  |  |  | 8В | 4 | РФ | 15102 |  | 2 | 8 | 120816 | Разработка описаний и моделей процессов в офисе Подрядчика.
| T0+5 | T0+6 | 3.2. Привязка разработанных описаний процессов на месте. Консультирование по адаптации документации ИСМ. | 6В | 1 | АЭС "Бушер" | 23719 | 88 | 0.54 | 0.54 | 12808.26 | Привязка разработанных описаний процессов на месте. Консультирование по разработке документации ИСМ (10 дней)
|  |  |  | 7В | 1 | АЭС "Бушер" | 20676 | 88 | 0.54 | 0.54 | 11165.04 | Привязка разработанных описаний процессов на месте. Консультирование по разработке документации ИСМ (10 дней)
|  |  |  | 7В | 1 | РФ | 18072 |  | 0.5 | 0.5 | 9036 | Подготовка Отчета по привязке разработанных описаний процессов на АЭС, отчета по консультированию по разработке документации
Итого по этапу 3 | [9 empty] | 14.33 | 240384.8
Этап 4 | T0 | T0+9 | Документирование ИСМ.
| T0 | T0+8 | 4.1. Разработка и настройка процессной модели ИСМ на принципах МАГАТЭ с учетом национального законодательства ИРИ. | 6В | 1 | РФ | 20942 |  | 0.25 | 0.25 | 5235.5 | Разработка и настройка процессной модели ИСМ в офисе Подрядчика
|  |  |  | 7В | 2 | РФ | 18072 |  | 1.5 | 3 | 54216 | Разработка и настройка процессной модели ИСМ в офисе Подрядчика
|  |  |  | 8В | 6 | РФ | 15102 |  | 1 | 6 | 90612 | Разработка и настройка процессной модели ИСМ в офисе Подрядчика
| T0+8 | T0+9 | 4.2. Консультирование по выбору и интеграции процессной модели в информационные системы АЭС для поддержки процессов и их показателей на уровне АЭС в идеологии МАГАТЭ (GSR Part2). Настройка KPIs процессов. Настройка KPIs, важных для безопасности. | 6В | 1 | АЭС "Бушер" | 23719 | 88 | 0.54 | 0.54 | 12808.26 | Консультирование по выбору и интеграции процессной модели в информационные системы АЭС для поддержки процессов и их показателей на уровне АЭС в идеологии МАГАТЭ (GSR Part2). Настройка KPIs процессов. Настройка KPIs, важных для безопасности (10 дней)
|  |  |  | 7В | 1 | АЭС "Бушер" | 20676 | 88 | 0.54 | 0.54 | 11165.04 | Консультирование по выбору и интеграции процессной модели в информационные системы АЭС для поддержки процессов и их показателей на уровне АЭС в идеологии МАГАТЭ (GSR Part2). Настройка KPIs процессов. Настройка KPIs, важных для безопасности (10 дней)
|  |  |  | 7В | 1 | РФ | 18072 |  | 0.5 | 0.5 | 9036 | Подготовка отчета по консультированию по выбору и интеграции процессной модели в информационные системы АЭС
Итого по этапу 4 | [9 empty] | 10.83 | 183072.8
Этап 5 | T0+9 | T0+10 | Внедрение ИСМ. Обучение внутренних аудиторов проведению интегрированных аудитов системы менеджмента. Консультирование, доработка документации ИСМ АЭС «Бушер-1». | 6В | 1 | РФ | 20942 |  | 0.25 | 0.25 | 5235.5 | Подготовка учебных материалов семинара для внутренних аудиторов ИСМ АЭС "Бушер-1". Подготовка к аудиту ИСМ.
|  |  |  | 7В | 1 | РФ | 18072 |  | 0.25 | 0.25 | 4518 | Подготовка учебных материалов семинара для внутренних аудиторов ИСМ АЭС "Бушер-1". Подготовка к аудиту ИСМ.
|  |  |  | 6В | 1 | АЭС "Бушер" | 23719 | 88 | 0.54 | 0.54 | 12808.26 | Проведение семинара для внутренних аудиторов ИСМ (3 дня). Консультирование, доработка документации ИСМ на площадке АЭС "Бушер-1" (7 дней).
|  |  |  | 7В | 1 | АЭС "Бушер" | 20676 | 88 | 0.54 | 0.54 | 11165.04 | Проведение семинара для внутренних аудиторов ИСМ (3 дня). Консультирование, доработка документации ИСМ на площадке АЭС "Бушер-1" (7 дней).
|  |  |  | 7В | 2 | РФ | 18072 |  | 1 | 2 | 36144 | Подготовка комплекта доработанных описаний процессов ИСМ АЭС "Бушер-1".
Итого по этапу 5 | [9 empty] | 3.58 | 69870.8
Этап 6 | T0+13 | T0+14 | Второй надзорный аудит функционирования ИСМ АЭС «Бушер-1». Определение областей для улучшений. | 6В | 1 | РФ | 20942 |  | 0.15 | 0.15 | 3141.3 | Подготовка ко 2-му надзорному аудиту ИСМ
|  |  |  | 7В | 1 | РФ | 18072 |  | 0.15 | 0.15 | 2710.8 | Подготовка ко 2-му надзорному аудиту ИСМ
|  |  |  | 6В | 1 | АЭС "Бушер" | 23719 | 44 | 0.27 | 0.27 | 6404.13 | Проведение 2-го совместного надзорного аудита ИСМ. Определение областей для улучшения (5 дней).
|  |  |  | 7В | 1 | АЭС "Бушер" | 20676 | 44 | 0.27 | 0.27 | 5582.52 | Проведение 2-го совместного надзорного аудита ИСМ. Определение областей для улучшения (5 дней).
|  |  |  | 7В | 1 | РФ | 18072 |  | 0.5 | 0.5 | 9036 | Подготовка отчета по 2-му надзорному аудиту
Итого по этапу 6 | [9 empty] | 1.34 | 26874.75
2019
Этап 7 | T0+14 | T0+18 | Оценка результативности ИСМ. Консультирование персонала АЭС «Бушер-1» по ИСМ.
| T0+14 | T0+17 | 7.1. Корректировка окончательной редакции документации ИСМ для АЭС «Бушер-1», направленной Заказчиком в адрес Подрядчика. | 6В | 1 | РФ | 22198 |  | 0.25 | 0.25 | 5549.5 | Корректировка окончательной редакции документации ИСМ для АЭС «Бушер-1», направленной Заказчиком в адрес Подрядчика
|  |  |  | 7В | 1 | РФ | 19156 |  | 0.5 | 0.5 | 9578 | Корректировка окончательной редакции документации ИСМ для АЭС «Бушер-1», направленной Заказчиком в адрес Подрядчика
|  |  |  | 8В | 1 | РФ | 16008 |  | 1 | 1 | 16008 | Корректировка окончательной редакции документации ИСМ для АЭС «Бушер-1», направленной Заказчиком в адрес Подрядчика
| T0+17 | T0+18 | 7.2. Оценка результативности ИСМ. Консультирование персонала АЭС «Бушер-1» по ИСМ. | 6В | 1 | АЭС "Бушер" | 25142 | 88 | 0.54 | 0.54 | 13576.68 | Консультирование персонала АЭС "Бушер-1" по работе с документацией ИСМ. Оценка результативности ИСМ и степени интеграции подсистем менеджмента (10 дней)
|  |  |  | 7В | 1 | АЭС "Бушер" | 21916 | 88 | 0.54 | 0.54 | 11834.64 | Консультирование персонала АЭС "Бушер-1" по работе с документацией ИСМ. Оценка результативности ИСМ и степени интеграции подсистем менеджмента (10 дней)
|  |  |  | 7В | 1 | РФ | 19156 |  | 0.5 | 0.5 | 9578 | Подготовка отчета по оценке результативности ИСМ с планом корректирующих действий
Итого по этапу 7 | [9 empty] | 3.33 | 66124.82
Итого | [9 empty] | 35.63 | 631209.48
Расчет рабочего времени (часов в мес.)
[12 empty] | 2017 | принято | 163

## Англ
Elaboration and implementation of Bushehr NPP-1 Integrated Management system. Cost calculation
Stage | Stage starting date, month (T0 - work order receipt date) | Stage expiration date, month | Work description | Grade of specialists | Number of specialists | Services rendering | Rate, Euro | Labour expenditures per one specialist, man*hours | Labour expenditures per one specialist, man*months | Labour expenditures, man*months | Cost calculation by rate, Euro
2017
Stage 1 | T0 | T0+2 | Holding of a workshop for Bushehr NPP-1 personnel on elaboration and implementation of the IMS. | 6В | 1 | RF | 19944 |  | 0.25 | 0.25 | 4986 | IMS workshop training matetials preparation for Bushehr NPP-1 managers
|  |  |  | 7В | 1 | RF | 17211 |  | 0.25 | 0.25 | 4302.75 | IMS workshop training matetials preparation for Bushehr NPP-1 managers
|  |  |  | 6В | 1 | Bushehr NPP-1 | 22589 | 27 | 0.17 | 0.17 | 3840.13 | Holding of a workshop for Bushehr NPP-1 personnel (3 working days).
|  |  |  | 7В | 1 | Bushehr NPP-1 | 19692 | 27 | 0.17 | 0.17 | 3347.64 | Holding of a workshop for Bushehr NPP-1 personnel (3 working days).
Total Stage 1 | [9 empty] | 0.84 | 16476.52
Stage 2 | T0 | T0+2 | Holding of an audit of documented control system, processes, KPI current state. Preparation of a joint detailed work schedule of IMS implementation operations. | 6В | 1 | RF | 19944 |  | 0.15 | 0.15 | 2991.6 | Arrangements to audit performance
|  |  |  | 7В | 1 | RF | 17211 |  | 0.15 | 0.15 | 2581.65 | Arrangements to audit performance
|  |  |  | 6В | 1 | Bushehr NPP-1 | 22589 | 88 | 0.54 | 0.54 | 12198.06 | Holding of an audit. Preparation of a joint detailed work schedule (10 working days)
|  |  |  | 7В | 1 | Bushehr NPP-1 | 19692 | 88 | 0.54 | 0.54 | 10633.68 | Holding of an audit. Preparation of a joint detailed work schedule (10 working days)
Total Stage 2 | [9 empty] | 1.38 | 28404.99
2018
Stage 3 | T0 | T0+6 | IMS designing.
| T0 | T0+5 | 3.1. Elaboration and implementation of integrated policy, integrated IMS management, integrated audits. Elaboration/improvement of the processes descriptions and models. Delivery of the processes draft descriptions to the Principal. | 6В | 1 | RF | 20942 |  | 0.25 | 0.25 | 5235.5 | Elaboration/improvement of the processes descriptions and models.
|  |  |  | 7В | 3 | RF | 18072 |  | 1.5 | 4.5 | 81324 | Elaboration/improvement of the processes descriptions and models.
|  |  |  | 8В | 4 | RF | 15102 |  | 2 | 8 | 120816 | Elaboration/improvement of the processes descriptions and models.
| T0+5 | T0+6 | 3.2. Customizing of the elaborated processes description in situ. Consultations on IMS documentation adaptation. | 6В | 1 | Bushehr NPP-1 | 23719 | 88 | 0.54 | 0.54 | 12808.26 | Customizing of the elaborated processes description in situ. Consultations on IMS documentation adaptation (10 working days)
|  |  |  | 7В | 1 | Bushehr NPP-1 | 20676 | 88 | 0.54 | 0.54 | 11165.04 | Customizing of the elaborated processes description in situ. Consultations on IMS documentation adaptation (10 working days)
|  |  |  | 7В | 1 | RF | 18072 |  | 0.5 | 0.5 | 9036 | Development of Report on the processes elaborated descriptions customizing in situ and IMS documentation elaboration consultations provision
Total Stage 3 | [9 empty] | 14.33 | 240384.8
Stage 4 | T0 | T0+9 | IMS documenting.
| T0 | T0+8 | 4.1. Elaboration and debugging of IMS process model according to IAEA principles based on the National IRI legislation. | 6В | 1 | RF | 20942 |  | 0.25 | 0.25 | 5235.5 | Elaboration and debugging of IMS process model
|  |  |  | 7В | 2 | RF | 18072 |  | 1.5 | 3 | 54216 | Elaboration and debugging of IMS process model
|  |  |  | 8В | 6 | RF | 15102 |  | 1 | 6 | 90612 | Elaboration and debugging of IMS process model
| T0+8 | T0+9 | 4.2. Consultations in the process model selection and integration into NPP information systems to maintain processes and their indices at the NPP level within IAEA ideology (GSR Part2). KPIs processes debugging. Debugging of safety related KPIs. | 6В | 1 | Bushehr NPP-1 | 23719 | 88 | 0.54 | 0.54 | 12808.26 | Consultations in the process model selection and integration into NPP information systems. KPIs processes debugging. Debugging of safety related KPIs (10 working days)
|  |  |  | 7В | 1 | Bushehr NPP-1 | 20676 | 88 | 0.54 | 0.54 | 11165.04 | Consultations in the process model selection and integration into NPP information systems. KPIs processes debugging. Debugging of safety related KPIs (10 working days)
|  |  |  | 7В | 1 | RF | 18072 |  | 0.5 | 0.5 | 9036 | Development of Report on consultations in the process model selection and integration into NPP information systems
Total Stage 4 | [9 empty] | 10.83 | 183072.8
Stage 5 | T0+9 | T0+10 | IMS implementation. Internal auditors training to holding of management system integrated audits. Consultations, modification of Bushehr NPP-1 IMS documentation. | 6В | 1 | RF | 20942 |  | 0.25 | 0.25 | 5235.5 | Workshop training materials perparation for Bushehr NPP-1 IMS internal auditors. Arrangements to IMS audit performance.
|  |  |  | 7В | 1 | RF | 18072 |  | 0.25 | 0.25 | 4518 | Workshop training materials perparation for Bushehr NPP-1 IMS internal auditors. Arrangements to IMS audit performance.
|  |  |  | 6В | 1 | Bushehr NPP-1 | 23719 | 88 | 0.54 | 0.54 | 12808.26 | Internal auditors training to holding of management system integrated audits (3 working days). Consultations, modification of Bushehr NPP-1 IMS documentation (7 working days).
|  |  |  | 7В | 1 | Bushehr NPP-1 | 20676 | 88 | 0.54 | 0.54 | 11165.04 | Internal auditors training to holding of management system integrated audits (3 working days). Consultations, modification of Bushehr NPP-1 IMS documentation (7 working days).
|  |  |  | 7В | 2 | RF | 18072 |  | 1 | 2 | 36144 | Development of Package of Bushehr NPP-1 IMS processes completed and modified descriptions.
Total Stage 5 | [9 empty] | 3.58 | 69870.8
Stage 6 | T0+13 | T0+14 | The second Bushehr NPP-1 IMS functioning supervisory audit. Specifying of areas for improvements. | 6В | 1 | RF | 20942 |  | 0.15 | 0.15 | 3141.3 | Arrangements to the 2-nd IMS supervisory audit.
|  |  |  | 7В | 1 | RF | 18072 |  | 0.15 | 0.15 | 2710.8 | Arrangements to the 2-nd IMS supervisory audit.
|  |  |  | 6В | 1 | Bushehr NPP-1 | 23719 | 44 | 0.27 | 0.27 | 6404.13 | The second Bushehr NPP-1 IMS functioning supervisory audit (5 working days).
|  |  |  | 7В | 1 | Bushehr NPP-1 | 20676 | 44 | 0.27 | 0.27 | 5582.52 | The second Bushehr NPP-1 IMS functioning supervisory audit (5 working days).
|  |  |  | 7В | 1 | RF | 18072 |  | 0.5 | 0.5 | 9036 | Development of Report on the second Bushehr NPP-1 IMS functioning supervisory audit
Total Stage 6 | [9 empty] | 1.34 | 26874.75
2019
Stage 7 | T0+14 | T0+18 | IMS effectiveness assessment. Bushehr NPP-1 personnel consultations on IMS.
| T0+14 | T0+17 | 7.1. Amendment of IMS documentation final revision for Bushehr NPP-1, submitted by the Principal to the Contractor. | 6В | 1 | РФ | 22198 |  | 0.25 | 0.25 | 5549.5 | Amendment of IMS documentation final revision for Bushehr NPP-1
|  |  |  | 7В | 1 | РФ | 19156 |  | 0.5 | 0.5 | 9578 | Amendment of IMS documentation final revision for Bushehr NPP-1
|  |  |  | 8В | 1 | РФ | 16008 |  | 1 | 1 | 16008 | Amendment of IMS documentation final revision for Bushehr NPP-1
| T0+17 | T0+18 | 7.2. IMS effectiveness assessment. Bushehr NPP-1 personnel consultations on IMS. | 6В | 1 | Bushehr NPP-1 | 25142 | 88 | 0.54 | 0.54 | 13576.68 | IMS effectiveness assessment. Bushehr NPP-1 personnel consultations on IMS (10 working days)
|  |  |  | 7В | 1 | Bushehr NPP-1 | 21916 | 88 | 0.54 | 0.54 | 11834.64 | IMS effectiveness assessment. Bushehr NPP-1 personnel consultations on IMS (10 working days)
|  |  |  | 7В | 1 | РФ | 19156 |  | 0.5 | 0.5 | 9578 | Development of IMS effectiveness assessment report
Total Stage 7 | [9 empty] | 3.33 | 66124.82
Total | [9 empty] | 35.63 | 631209.48
labour time calculation (hours per month)
[12 empty] | 2017 | taken | 163