Minutes of Meeting

of 6th Joint Training Advisory Commission Meeting on Bushehr NPP Repair Personnel Training

Under Contract No. PPM/T-4100 dd September 2017

(hereafter – "Contract")

Tehran									September 24-25, 2019

| Principal Representatives Mr. A. Rahnama (NPPD) Mr. M. Yadollahi (BNPP) Mr. A. Basri (BNPP) Mr. A. Seyedhosseini (TAPNA) Mr. F. Sadeghi (NPPD) Mr. A. Ahangarian (NPPD) | Contractor Representatives Mr. S. Sharabanov (RusAS) Mr. S. Sheptunov (RusAS) Mr. P. Ferreyro Fernandes (RusAS) Mr. O. Shmakov (REA) Mr. A. Kachaev (REA) Mr. A. Solntsev (RTA) |
| --- | --- |

- Issues considered

- Implementation of the decisions made at the previous meeting.

- Organization of the theoretical training (TT) and development of documentation.

- Organization and provision of the on-the-job training (OJT).

- Organization and provision of the initial training.

- General issues.

2.	Information Mentioned:

- With regard to the decisions made at the previous meeting:

    - All decision made at the previous meeting have been reviewed and discussed.

    - The Principal did not submit information required in item 3.4.2. of the Minutes of the 5th JTAC Meeting held on 01-02.07.2019 on time.

    - The Contractor informed the Principal that he has to bear additional significant costs due to changes in the beginning dates of the OJT.

With regard to subgroup No. 7A, the information about changes in the date of their arrival at Russia was communicated 10 (ten) days before the beginning of their OJT.

With regard to subgroups Nos. 1В, 2В, 4В, 5А, 5В, 6А, and 6В, the information about changes in the date of their arrival at Russia was communicated 4 (four) days before the beginning of their OJT.

A lot of personnel and subcontractors are involved in meeting and housing trainees, as well as in their briefing. The NPP issues written orders with specific dates during which foreign specialists will be allowed at the NPP site. When time frames are changed at the last minute, a lot of written documents and terms of contracts with subcontractors have to be changed.

- With regard to the organization of the Group A TT and development of documentation:

- The implementation of the TT of group No. 7A was completed according to the approved schedule. The Contractor informed the Principal that the methodological training documents (MTDs) for the advanced professional training program (APTP) of group No. 7A were developed and submitted in electronic format to Bushehr NPP and TAPNA representatives during the meeting. The MTDs previously handed over to the Principal as hardcopy were not in the QAP format. Appendix No. 1 to these Minutes of Meeting (M. O. M.) contains the list of the developed MTDs for the APTP.

- The Contractor informed the Principal that the training programs for the continuing training program (CTP) for all 12 (twelve) groups were reviewed and agreed by Bushehr NPP and TAPNA representatives (Appendix No. 2 to these M. O. M.).

- The Contractor informed the Principal that the MTDs for the CTP of groups Nos. 5, 9, 10, 11, and 12 were reviewed and agreed by Bushehr NPP and TAPNA representatives. Appendix No. 3 to these M. O. M. contains the list of the developed MTDs for the CTP.

- The Contractor informed the Principal that subgroups Nos. 7А and 1В-12В went through their TT for their APTP. Appendix No. 4 to these M. O. M. contains the list of the subgroups that went through their TT for their APTP.

- The Contractor informed the Principal that subgroups Nos. 3А and 5А went through their TT for their CTP. Appendix No. 5 to these M. O. M. contains the list of the subgroups that went through their TT for their CTP.

- With regard to the organization of the OJT at Russian NPPs.

- The Contractor informed the Principal that subgroups Nos. 1А and 12А went through their OJT for their APTP at the Novovoronezh NPP. Appendix No. 6 to these M. O. M. contains the list of the subgroups that went through their OJT for their APTP in Russia.

- The Contractor informed the Principal that the Contactor cannot arrange access into the controlled access area (CAA) for subgroups 1B, 2B, 5A, 5B, 6A, and 6B until the necessary information is received. However, the Contractor will do their best to speed up the CAA entry permit issuing process. Both parties agreed that the trainees shall train overtime to compensate for this delay, if possible; the scope of such overtime training may be considered as the compensation for the lack of the amount of the previously provided training, if the parties mutually agree to that. However, the Principal mentioned having sent a letter to the Contractor on 23.09.2019; it contained results of physical examination of all trainees. The Principal confirmed that this information should be sufficient for arranging their access into the CAA. However, the Principal agrees that the date of this examination shall be sent to the Contractor before 27.09.2019.

- The Contractor informed the Principal that the information about specialists of subgroups Nos. 8В-11В and 7В was still not received. The Principal will send the necessary information by 02.10.2019. However, the Contractor emphasized that it takes 45 days to obtain an entry permit to the NPP; the Contractor has to get the approval of the NPP's security service for late submission of the documents. There is a risk of not getting such approval for the training to begin on 01.11.2019. The Contractor shall keep the Principal informed about the progress.

- With regard to the IT organization:

- The Contractor informed the Principal that the training for the risk analysis program was conducted according to requirements of item 3.3.3 of the minutes of the 5th JTAC meeting held on July 01-02, 2019. However, no MTDs were submitted to the Principal.

- All 11 (eleven) subgroups went through their initial training programs (ITPs) (Appendix No. 7 to these M. O. M.).

- The calculation of the actual labor costs spent on the development of the MTMs for the ITP of groups Nos. 7 and 11 were discussed during this JTAC meeting.

  - With regard to the general issues:

- The Contractor emphasized the importance of submitting information about specialists who are going to go through their OJT at Russian NPPs on time. It takes at least 45 days to obtain both a permit to enter an NPP and to enter Russia, but it is much more reliable if the information is received 60 days in advance.

- The Contractor informed the Principal that it is necessary to make changes to the 2020 training and OJT schedule due to changes in the outage schedules of the Russian NPPs.

3. Decisions Taken:

- With regard to the organization of the Group A TT and development of documentation:

- The JTAC approved the 11 (eleven) MTDs for the APTP (Appendix No. 1 to these M. O. M.).

- The JTAC approved the 12 (twelve) training programs for the CTP (Appendix No. 2 to these M. O. M.). The Contractor confirmed that if necessary, they will adjust this CTP for group B before the start of group B training.

- The JTAC approved the 5 (five) MTDs for the CTP (Appendix No. 3 to these M. O. M.).

- The JTAC confirmed that all 12 (twelve) subgroups of groups A and B went through their TT for their APTP (Appendix No. 4 to these M. O. M.). The Contractor should submit all necessary documents in compliance with QAP in order to be approved by the Principal.

- The JTAC confirmed that the 2 (two) subgroups of group A went through their TT for their CTP (Appendix No. 5 to these M. O. M.). The Contractor should submit all necessary documents in compliance with QAP in order to be approved by the Principal.

- As for the organization of the OJT for the APTP of group A:

- The JTAC confirmed that the 10 (ten) subgroups of group A went through their OJT for their APTP (Appendix No. 6 to these M. O. M.). The Contractor should submit all necessary documents in compliance with item 3.2.1 of JTAC-4 M.O.M. in order to be approved by the Principal.

- The Contractor shall provide 80 hours of additional TT to subgroups Nos. 8A-11A at the Bushehr Training Center. The Parties shall additionally agree the program of this training before it starts.

- The Principal shall review training materials for group No. 7A that were mentioned in item 2.2.1 of this M. O. M. and send their comments to the Contractor. The Parties agreed that if the Principal does not send their comments to the Contractor before 10.10.2019, these training materials shall be considered as agreed by the Principal.

- The Parties agreed the training start dates for subgroups No. 3А (starts 06.11.2019), No. 7А (starts 06.10.2019), and No. 7В (starts 02.12.2019).

- With regard to the initial training organization:

    - The Contractor provided the Principal with the Calculation of Actual Labor Costs Spent on Development of Methodological Training Documents for Initial Training of Groups Nos. C7 and C11 (Appendix No. 8 to these M. O. M.) according to item. 3.3.5 of the minutes of the 5th JTAC meeting. The parties agreed that based on the Contract, the Contractor should develop training materials for 400 hours of TT for the ITP of Groups Nos. C7 and C11. The actual scope of the developed Training documentation covers 102 hours (i.e. 77 hours for Group C7 and 25 hours for Group C11). The Principal emphasized the need for development of the remaining Training materials which will cover 298 hours of TT (which requires 10 579 man-hours of the Contractor’s labor costs). The Contractor shall analyze the remaining scope of obligations and provide their suggestions on the development of the remaining Training Materials to compensate for the lack of documentation. The contractor shall submit this information to the Principal 10 (ten) days before the next JTAC meeting.

    - The Contractor submitted their offer for the "Organization and Management of Maintenance and Repair" topic to the Bushehr NPP representatives. The Principal will review the abovementioned offer and send their comments to the Contractor by 02.10.2019.

    - The JTAC agreed that the Contractor conducted TT on the topic of “Risk analysis focused on maintenance and repair works” with duration of 8 work days (40 hours of training and 24 hours of self-study) including development of MTMs for the training (in the amount specified in the Contract, excluding individual training programs development). This training was conducted instead of the training for the ITP of group C.10 (mechanical maintenance shop). The Contractor shall hand over the set of documents for the “Risk analysis focused on maintenance and repair works” group to the Principal before 31.10.2019, as stipulated by the Contract.

    - The JTAC confirmed that all 11 (eleven) groups went through their ITPs (Appendix No. 7 to these M. O. M.). The Contractor should submit all necessary documents in order to be approved by the Principal.

- With regard to the general issues:

- The JTAC approved the 2019 TT and OJT schedule. The Principal shall review the changes to the 2020 TT and OJT schedule suggested by the Contractor and inform the Contractor about their decision before 31.10.2019. The Parties shall approve the final schedule at the next JTAC meeting. Appendix No. 9 to these M. O. M. contains the schedule.

- The next JTAC meeting will be held either in Tehran or Moscow on
07-09.12.2019; the Parties will mutually agree the city later.

Appendices:

- List of Approved Methodological Training Documents for Advanced Professional Training Program

- List of Approved Training Programs for Continuing Training Program

- List of Approved Methodological Training Documents for Continuing Training Program

- List of Subgroups that Went Through Their Theoretical Training for Their Advanced Professional Training Program

- List of Subgroups that Went Though Their Theoretical Training for Their Continuing Training Program

- List of Subgroups that Went Through Their On-the-Job Training for Their Advanced Professional Training Program in Russia

- List of Subgroups that Went Through Their Initial Training Program

- Calculation of Actual Labor Costs Spent on Development of Methodological Training Documents for Initial Training of Groups Nos. 7 and 11.

- Advanced Professional Training and Continuing Training Schedule for 2019-2020 (Ver. 5)

Principal                                                                                     Contractor

| Mr. A. Rahnama (NPPD) Mr. M. Yadollahi (BNPP) Mr. A. Basri (BNPP) Mr. A. Seyedhosseini (TAPNA) Mr. F. Sadeghi (NPPD) Mr. A. Ahangarian (NPPD) | Mr. S. Sharabanov (RusAS) Mr. S. Sheptunov (RusAS) Mr. P. Ferreyro Fernandes (RusAS) Mr. A. Solntsev (RTA) Mr. O. Shmakov (REA) Mr. A. Kachaev (REA) |
| --- | --- |

Appendix No. 1

List of Approved Methodological Training Documents

for Advanced Professional Training Program

| Group No. 1 | Reactor repair |
| --- | --- |
| Group No. 2 | Operation and repair of refueling machines |
| Group No. 3 | Maintenance and repair of reactor compartment main equipment hydraulic snubbers and gates of localizing safety systems |
| Group No. 4 | Turbine set repair |
| Group No. 5 | Repair of RCPs and main rotating machines |
| Group No. 6 | Repair of valves of main process systems |
| Group No. 8 | Design engineers |
| Group No. 9 | Process engineers specializing in reactor maintenance and repair |
| Group No. 10 | Process engineers specializing in maintenance and repair of rotating machines and turbine sets |
| Group No. 11 | Process engineers specializing in maintenance and repair of pipelines and heat exchangers |
| Group No. 12 | Repair Preparations and Performance Departments (engineers of Repair Preparations and Performance Departments and engineers of Repair Management Departments) |

Appendix No. 2

List of Approved Training Programs

for Continuing Training Program

| Group No. 1 | Reactor repair |
| --- | --- |
| Group No. 2 | Operation and repair of refueling machines |
| Group No. 3 | Maintenance and repair of reactor compartment main equipment hydraulic snubbers and gates of localizing safety systems |
| Group No. 4 | Turbine set repair |
| Group No. 5 | Repair of RCPs and main rotating machines |
| Group No. 6 | Repair of valves of main process systems |
| Group No. 7 | Diesel Generator Overhaul |
| Group No. 8 | Design engineers |
| Group No. 9 | Process engineers specializing in reactor maintenance and repair |
| Group No. 10 | Process engineers specializing in maintenance and repair of rotating machines and turbine sets |
| Group No. 11 | Process engineers specializing in maintenance and repair of pipelines and heat exchangers |
| Group No. 12 | Repair Preparations and Performance Departments (engineers of Repair Preparations and Performance Departments and engineers of Repair Management Departments) |

Appendix No. 3

List of Approved Methodological Training Documents

for Continuing Training Program

| Group No. 5 | Repair of RCPs and main rotating machines |
| --- | --- |
| Group No. 9 | Process engineers specializing in reactor maintenance and repair |
| Group No. 10 | Process engineers specializing in maintenance and repair of rotating machines and turbine sets |
| Group No. 11 | Process engineers specializing in maintenance and repair of pipelines and heat exchangers |
| Group No. 12 | Repair Preparations and Performance Departments (engineers of Repair Preparations and Performance Departments and engineers of Repair Management Departments) |

Appendix No. 4

List of Subgroups

that Went Through Their Theoretical Training

for Their Advanced Professional Training Program

| Group A |  |
| --- | --- |
| Group No. 1 | Reactor repair |
| Group No. 2 | Operation and repair of refueling machines |
| Group No. 3 | Maintenance and repair of reactor compartment main equipment hydraulic snubbers and gates of localizing safety systems |
| Group No. 4 | Turbine set repair |
| Group No. 5 | Repair of RCPs and main rotating machines |
| Group No. 6 | Repair of valves of main process systems |
| Group No. 7 | Diesel generator repair |
| Group No. 8 | Design engineers |
| Group No. 9 | Process engineers specializing in reactor maintenance and repair |
| Group No. 10 | Process engineers specializing in maintenance and repair of rotating machines and turbine sets |
| Group No. 11 | Process engineers specializing in maintenance and repair of pipelines and heat exchangers |
| Group No. 12 | Repair Preparations and Performance Departments (engineers of Repair Preparations and Performance Departments and engineers of Repair Management Departments) |
| Group B |  |
| Group No. 1 | Reactor repair |
| Group No. 2 | Operation and repair of refueling machines |
| Group No. 3 | Maintenance and repair of reactor compartment main equipment hydraulic snubbers and gates of localizing safety systems |
| Group No. 4 | Turbine set repair |
| Group No. 5 | Repair of RCPs and main rotating machines |
| Group No. 6 | Repair of valves of main process systems |
| Group No. 7 | Diesel generator repair |
| Group No. 8 | Design engineers |
| Group No. 9 | Process engineers specializing in reactor maintenance and repair |
| Group No. 10 | Process engineers specializing in maintenance and repair of rotating machines and turbine sets |
| Group No. 11 | Process engineers specializing in maintenance and repair of pipelines and heat exchangers |
| Group No. 12 | Repair Preparations and Performance Departments (engineers of Repair Preparations and Performance Departments and engineers of Repair Management Departments) |

Appendix No. 5

List of Subgroups

that Went Through Their Theoretical Training

for Their Continuing Training Program

| Group A |  |
| --- | --- |
| Group No. 3 | Maintenance and repair of reactor compartment main equipment hydraulic snubbers and gates of localizing safety systems |
| Group No. 5 | Repair of RCPs and main rotating machines |

Appendix No. 6

List of Subgroups that Went Through Their On-the-Job Training

for Their Advanced Professional Training Program in Russia

| Group A |  |
| --- | --- |
| Group No. 1 | Reactor repair |
| Group No. 2 | Operation and repair of refueling machines |
| Group No. 3 | Maintenance and repair of reactor compartment main equipment hydraulic snubbers and gates of localizing safety systems |
| Group No. 4 | Turbine set repair |
| Group No. 5 | Repair of RCPs and main rotating machines |
| Group No. 8 | Design engineers |
| Group No. 9 | Process engineers specializing in reactor maintenance and repair |
| Group No. 10 | Process engineers specializing in maintenance and repair of rotating machines and turbine sets |
| Group No. 11 | Process engineers specializing in maintenance and repair of pipelines and heat exchangers |
| Group No. 12 | Repair Preparations and Performance Departments (engineers of Repair Preparations and Performance Departments and engineers of Repair Management Departments) |

Appendix No. 7

List of Groups that Completed

Their Initial Training Program

| Group No. 1 | Reactor maintenance |
| --- | --- |
| Group No. 2 | Controlled Access Area rotary equipment |
| Group No. 3 | Controlled Access Area static equipment |
| Group No. 4 | Free Access Area rotary equipment |
| Group No. 5 | Free Access Area static equipment |
| Group No. 6 | Diesel Generator |
| Group No. 7 | Engineering maintenance |
| Group No. 8 | Design engineering |
| Group No. 9 | Preparation and planning |
| Group No. 10 | Mechanical maintenance shop (Risk analysis focused on maintenance and repair works) |
| Group No. 11 | Quality Control |