| Participants |  |  |
| --- | --- | --- |
| The Principal's | The Consultant's | The Contractor's |
| Mr. M. Nasouri | Mr. A.R. Moradian | Mr. V.N. Pavlov |
| Mr. B. Mohammadhosseini | Mr. E. Deylami | Mr. S.A. Ambartsumyan |
| Mr. R. Alidadi | Mr. M. Evazi | Mr. S.A. Streltsov |
| Mr. Sh. Shareghi | Mr. H.R. Ahmadian | Mr. A.A. Shevyrev |
| Mr. P. Toorafshan | Mr. M. Ahmadi (OSEMM) | Mr. A.I. Skorobogatov |
| Mr. G. Dashti | Mr. M. Moghadam | Mr. Yu.O. Mikhashula |
| Mr. S. Ataei-Ashtiani | Mr. M.H. Fayyaz | Mr. M.O. Chernyshev |
| Mr. A. Rahnama | Mr. R. Esmaeilifar | Mr. A.A. Nerovnov |
| Mr. Gh. ZandBasiri | Mr. N. Bazargan | Mr. A.I. Ilchuk |
| Mr. S. Vahdanifar | Mr. M.R. Tahaeifard | Mr. K.V. Mityurev |
| Mr. K. Keshtakar |  | Mr. V.E. Lobovich |
|  |  | Mr. S.V. Seliverstov |
|  |  | Mr. L.A. Stoletov |
|  |  | Mr. A.N. Troshin |
|  |  | Ms. E.A. Mitiukhina |
|  |  | Mr. D.E. Avdoshin |
|  |  | Mr. A.V. Victorov |
|  |  | Mr. K.L. Rodin |
|  |  | Mr. N.V. Shemiakin |
|  |  | Ms. M.V. Neskashina |

| № | Issues Discussed & Decisions Made | Discussed | Decisions | Deadline | Responsible |
| --- | --- | --- | --- | --- | --- |
| 1 | Fulfilling item № 7 of MOM dd. 02~03.02.2020 attached hereto (Attachment # 2), taking into account the seismic design of buildings and structures, the Contractor undertakes to revise the respective BDDs and submit, by 30.03.2020, the revised version thereof. The Contractor shall, by 15.02.2020, submit a document on feasibility of applying SP 14.13330.2014 in design of nuclear power buildings and structures, upon obtaining the required authorization from the RF Regulatory Authority (Rostekhnadzor). | Y | Y | 15.02.2020 & 30.03.2020 | Contractor |
| 2 | The Plan submitted by the Contractor via 007/BU2/40-41/00388 dd. 19.12.2019 for settlement of the comments raised by the Principal on BDDs shall be jointly discussed and finalized by WG-1. By 15.02.2020, the Principal will convey their comments on the referred Plan. Subsequently, starting from 23.02.2020, the Parties will convene joint meetings on BDDs. For re-scheduling of the Plan for development, consideration, and approval of DDDs, the Parties (WG-1 & WG-6) will hold joint meetings starting from 29.02.2020. The Parties will continue discussions on list of prioritization of DDDs for the year 2020 and the 1st quarter of 2020, in meetings starting from 09.02.2020. | Y | Y | As Stated | Parties |
| 3 | Further to PMM-21 item 1, aimed at optimizing the design of water intake, the Parties' experts shall convene, on 09~13.02.2020, meetings wherein the Principal's comments on water intake will be conveyed over to ASE, to be forwarded over to VNIIG. The Parties will then convene another meeting, to be also attended by VNIIG and Darya-Bandar companies, the date of which will be declared by the Contractor in the a.m. meeting of 09~13.02.2020. | Y | Y | 09-13.02.2020 | Parties |
| 4 | With reference to letter № 4300-116214 dd. 28.09.2019, the Contractor shall by 29.02.2020 consider Attachment S.B. to Appendix S to the Contract and convey its comments thereon. | Y | Y | 29.02.2020 | Contractor |
| 5 | The Contractor shall, by the 27th of each month, submit to the Principal its HSE Monthly Plan for the upcoming month, based on the risks; the Contractor also undertakes to submit, by the 30th of each month, its Monthly HSE Report for the same month. | Y | Y | Periodically | Contractor |
| 6 | The Contractor undertakes to monthly submit results of its survey over HSE quantitative goals discussed through PMM № 22; the concerned goals are as below: Zero LTI (Lost Time Incident); Zero Occupational Illnesses; Zero Environmental Damages. | Y | Y | Monthly | Contractor |
| 7 | Basing on the compensatory measures earlier undertaken, HMS as the manufacturer of AFW and MFWP pumps will establish a Design Center at Tehran; ASE declares its agreement with the referred arrangement. Details of the tasks to be discharged through the referred Design Center will be finalized in a meeting among the Parties, attended by HMS. | Y | Y | Under Control | Contractor/ HMS |
| 8 | LJWG will by 14.02.2020 issue the permit for import of Condensate Electrical Pumps (CEP-1, 2). | Y | Y | 14.02.2020 | Parties (LJWG) |
| 9 | The Parties agreed on IEC60076 or GOST as reference standard for the design, manufacture, and test of BNPP-2,3 transformers, for IRI and RF manufacturers, respectively (letter # 4300-121982 dd. 13.01.2020). Decision on the test requirements to be stipulated for IRI manufacturers in case IEC60076 is selected as reference will be taken in a joint meeting also attended by Trans Post Pars. | Y | Y | UC | Parties |
| 10 | As for Conformity Assessment: - The Parties underline that in BNPP-2,3 Project, Conformity Assessment shall be done based on NP-071-06 and all the respective requirements (Orders, Decisions, and related Standards and Procedures). - The Contractor will submit a procedure on implementation of form of mandatory certificates under NP-071-06. - The Contractor shall submit by 15.02.2020 for the Principal's information the Procedure on implementation of State Control Form, as implemented in RF by Regulatory Body, Rostekhnadzor. - Upon receiving the Procedure on NNSD License Issuance, the Principal will forward the same for the Contractor's information. - In the scope of Authorized Organization for Conformity Assessment purposes, in all cases where VO 'Safety' is not involved, ZAES, as the Contractor's Authorized Organization, shall take action. - Other outstanding issues of Conformity Assessment shall be discussed and settled in a joint meeting on 03.03.2020. | Y | Y | UC & 15.02.2020 & 03.03.2020 | Parties |
| 11 | As concerns Power Machines' issues, including using mineral oil in TP systems, reliability of Turbine Blades, and Condenser Tube Cleaning System (CTCS) and Debris Filtration System (DFS); the Parties signed a protocol which is attached hereto (Attach. # 3) | Y | Y | UC | Parties |
| 12 | Replying the Principal's inquiry concerning the Contractor's delay in submission of the revised documents on water chemistry, BDD, Section 3.4, the Contractor undertakes to submit the documents not later than 30.03.2020. | Y | Y | 30.03.2020 | Contractor |
| 13 | The Principal agrees to conditionally accept by 08.02.2020 those QPs that had been submitted Izhora via letter № 007/UKS-07/09/00433 dd. 28.01.2020 enlisted under "List of QPs with No Comments" provided that the same will also be approved by ZAES as Authorized Organization. While the referred conditional acceptance authorizes Izhora to start execution of activities, it is underlined that the concerned QPs will be considered as finalized only after being signed and stamped by ZAES not later than 15.02.2020. | Y | Y | 08.02.2020 | Principal |
| 14 | The Parties will convene a series of meetings starting from 15.02.2020 to discuss and finalize TA for BNPP-2 Training Center and ITR to FSS/AS. | Y | Y | Starting from 15.02.2020 | Parties |
| 15 | The Principal will reply letter № 007/73/02/00104 dd. 20.01.2020 on establishment of Operating Subdivision. | Y | Y | UC | Principal |
| 16 | As for operation of BNPP-2&3 based on 18-month fuel cycle, the Principal will consider and reply the Contractor's letter № 007/BU2/541-1/00018 dd. 17.12.2019. | Y | Y | UC | Principal |
| 17 | As for design level of seawater, in the meeting, the Contractor submitted to the Principal a copy of their letter № 007/BU2/40-41/00373 dd. 10.12.2019 (which had not been formally received). The Principal will consider and reply the letter. | Y | Y | UC | Principal |
| 18 | Basing on letter № 007/40/433/BUSH-2/00052 dated 31.01.2020, the Principal will declare a date for convening a meeting on the Procedure on 3D model (received via letter № 007/40/433/BUSH-2/00041 dated 27.06.2019). | Y | Y | UC | Principal |
| 19 | Whereas in their letter № 007/70/08/00220 dd. 21.01.2020, the Contractor replied only one set of comments on IOTS forwarded via letter № 4300-121807 dd. 09.01.2020, the Contractor undertakes to (a) provide full feedback to the raised comments and (b) arrange for holding a joint meeting, not later than 02.03.2020, on finalization of the referred comments. Each of the Parties will assign new authorized representatives to the task of IOTS finalization and implementation of App. G to the Contract. | Y | Y | 02.03.2020 & UC | Contractor & Parties |
| 20 | In order for WG-4 to decide, on 08.02.2020, on the outstanding issues of environmental air temperature and humidity of BNPP-2, each of the Parties shall develop and submit their justification report and respective computational details justifying the values presented by each Party. | Y | Y | 08.02.2020 | Parties |
| 21 | In a joint meeting among the Parties, also attended by AZARAB, AME, and IRI Taxation Administration; the financial aspects of AZARAB-AME contract, including the issue of Value Added Tax (VAT), shall be settled through signing an Agreement. The Contractor's authorized representative to the said meeting is Mr. Sheveryov. The Principal will make the required arrangements for convening of the said meeting. | Y | Y | UC | Parties |
| 22 | As a part of participation of IRI bidders, the Principal sent to the Contractor the list of the banks authorized by the Central Bank of Iran (CBI). By 19.02.2020, the Contractor will formally declare their stance. | Y | Y | 19.02.2020 | Contractor |
| 23 | To accelerate consideration and finalization of DDDs at the Site, the Contractor/Designer shall establish their Design Office with an organizational structure similar to the one used in BNPP-1 Project and also strengthen number of their skillful experts at the Site. By 05.03.2020, the Contractor will submit their Plan for dispatching of 5 experts as Site residents. | Y | Y | 05.03.2020 | Contractor |
| 24 | As concerns the Contractor's contractual obligation of reaching Availability Factor of 93%, the Contractor shall primarily reply letter № 4300-121525 dd. 01.01.2020 wherein comments were raised on the earlier-submitted formula and then demonstrate to the Principal in a joint meeting that the claimed AF of 93% is achievable for BNPP-2,3. | Y | Y | UC | Contractor & Parties |
| 25 | As for FBB and FBC (i.e. FAs cleaning and repair) Systems, the Principal will give their feedback to the Contractor's reply sent via letter № 007/BU2/02-01/01098 dd. 27.01.2020. | Y | Y | UC | Principal |
| 26 | As for IMS, The Contractor shall, by 20.02.2020, submit: (A) a comparative analysis of ENOVIA and T-FLEX software; (B) an analysis of T-FLEX software basing on Technical Assignment of IMS. | Y | Y | 20.02.2020 | Contractor |
| 27 | As for the issues on selection of Upper Level Control System software (either Portal or Operator), the Contractor shall reply letter № LTR-4300-98132326 dd. 28.01.2020. | Y | Y | UC | Contractor |
| 28 | Further to the stipulations of the M.O.M communicated via letter № 4300-120338 dd. 12.12.2019, the Contractor sent the Principal (via letter # 007/BU2/02-01/01080 dd. 13.01.2020) the revised version of the technical documents on KLM Passive Filtration System. Afterwards, the Parties shall hold a joint meeting on finalization of the said document. | Y | Y | UC | Parties |
| 29 | In meetings on 25~26.02.2020 in Tehran, the Parties shall finalize Attach. L.A to App. L to the Contract. | Y | Y | 25~26.02.2020 | Parties |
| 30 | The Parties' next PM Meeting will be held on 03~04.03.2020. | Y | Y | 03~04.03.2020 | Parties |

Enclosure(s):

- MOMs of Workgroups №№ 1, 3, 4, 6

- MOM dd. 02~03.02.2020 on taking into account the seismic design of buildings and structures, in the respective BDDs

- M.O.M of 04~05.02.2020 on Power Machines Co.

| Signed by |  |  |
| --- | --- | --- |
| The Principal | The Consultant | The Contractor |
| Mr. M. Nasouri | Mr. A.R. Moradian | Mr. V.N. Pavlov |
| Mr. B. Mohammadhosseini | Mr. E. Deylami | Mr. S.A. Streltsov |
| Mr. R. Alidadi | Mr. M. Evazi | Mr. S.A. Ambartsumyan |
| Mr. Sh. Shareghi | Mr. H.R. Ahmadian | Mr. A.A. Shevyrev |
| Mr. P. Toorafshan | Mr. M. Ahmadi (OSEMM) | Mr. Yu.O. Mikhashula |
| Mr. G. Dashti | Mr. M. Moghadam | Mr. A.I. Skorobogatov |
| Mr. S. Ataei-Ashtiani | Mr. M.H. Fayyaz | Mr. A.A. Nerovnov |
| Mr. A. Rahnama | Mr. R. Esmaeilifar | Mr. A.I. Ilchuk |
| Mr. Gh. ZandBasiri | Mr. N. Bazargan | Mr. V.E. Lobovich |
| Mr. S. Vahdanifar | Mr. M.R. Tahaeifard | Mr. A.N. Troshin |
| Mr. K. Keshtakar |  | Mr. K.V. Mityurev |
|  |  | Mr. K.L. Rodin |