Attachment No.1 to the Supplement No.10 to the Fuel Contract No.08843672 / 50293-09D    08.08.1995

The list of documentation, technical support and advice.

| No | Procedure | Provided by |  | Term of procedure performance |  | men/ months | Brief description of provided procedures |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0 | Making of Contract (or Supplement) |  |  | Т0= 31.05.2016 |  |  |  |  |  |
| 1 | Description of FA and core | JSC PFC OKB GP - VNIINM |  | Т0+3 months 31.08.2016 |  | 12 men/ months |  |  |  |
| - 1.1 | - Topical report on the project of TVS-2М and core, compatibility TVS-2M with AFA, RCCA and the reactors equipment. | - OKB GP |  | - Т0+3 months |  | 12 men/ months | - Description of the construction and main technical characteristics of TVS-2M, AFA, fuel rods, RCCA. The basic characteristics of a fuel cycle. The list, the description and the maintenance of documents and services in a substantiation of use ТВС-2М and modernisations of equipment Busher-1. Operating conditions, handling requirements. Analysis of mechanical and hydraulic compatibility TVS-2M with AFA. The indications of settlement codes and the standard documentation on which basis are carried out a substantiation. |  |  |
| 2 | Neutron-physical calculations | JSC PFC OKB GP |  | Т0+7 months 31.12.2016 |  | 31 men/ months | Development the in core NPhC (transitive loads from UTVS_TVS-2М with blankets_TVS-2M without blankets and equilibrium TVS-2M without blankets). Elaboration of initial data for neutron-physical and thermal-hydraulic calculations. |  |  |
| - 2.1 | - Calculation of neutron-physical characteristics of transitive fuel cycles starting from the 7-th loading, with outlet to equilibrium fuel cycle of Unit 1 of "Bushehr" NPP | - JSC PFC |  | - Т0+7 months |  | - 18 men/ months | Work purpose — determination of make-up fuel nomenclature for transitive and equilibrium fuel cycles, selection of "Bushehr" NPP reactor core arrangement and calculation of neutron-physical characteristics. Determination and coordination with the Customer of TVS-2M core specifications, nomenclature and work schedule. Elaboration of the initial data to provide NPhC. Elaboration of input data for neutron-physical characteristics (transitive and equilibrium cycles), for safety analyses of RIA type, for thermo-mechanical calculations. |  |  |
| - 2.2 | - Verification of engineering safety factors for transition from UTVS to TVS-2M | - JSC PFC |  | - Т0+7 months |  | - 3 men/ months | - The procedure will be presented considering FA¦ structure and dimensions (with tolerances) and numerical values of heat flux and coolant heating engineering safety factors, which shall be used in the calculation analysis of transfer to and further operation of TVS-2M in "Bushehr" NPP. |  |  |
| - 2.3 | - Calculation of decay heat for spent TVS-2M in spent fuel pool (in shutdown reactor and removed top head) | - OKB GP |  | - Т0+7 months |  | - 4 men/ months | - Calculation of core and spent fuel decay heat is provided using the procedure of international standard - ISO-10645-92, Calculation of the decay heat power in nuclear fuels in light water reactors. The events of reactor scheduled shutdown for refuelling with FA partial and complete unloading from the core are considered. The data are presented for whole core powers in various states, average and maximum powers of FA unloaded into a spent fuel pool. The results obtained are use in thermal-hydraulic calculations of shutdown reactor and fuel pool cooling. The composition of spend fuel in the spend fuel pool, with design conservatism and emergency fuel unloading from the reactor. |  |  |
| - 2.4 | - Development and justification of the format of Refuelling safety evaluation report (RSER) considering application in the design justification of spatial kinetics codes | - OKB GP |  | - Т0+7 months |  | - 6 men/ months | - New format of refuelling safety evaluation report (RSER) will be developed considering application in the design justification of the codes with core spatial kinetics. Limitations allowing to evaluate fuel cycle safety under deviations from the design refuelling pattern on the basis of neutron-physical characteristics calculations will be presented in RSER updated format. - Safety analysis of the conditions with core spatial kinetics for various versions of fuel cycle arrangements will be provided as a verification of the report new format. - Input data, necessary for calculation performance of AEP |  |  |
| 3 | Thermal-hydraulic design of the core (transitive cycles from UTVS to TVS-2M with blankets, and then to TVS-2M without blankets and equilibrium TVS-2M without blankets) | OKB GP |  | То+9 months 28.02.2017 |  | 23 men/ months |  |  |  |
| - 3.1 | Thermal hydraulic parameters under normal operating conditions with a different number of operating RCP (four, three, two). | - OKB GP |  | - Т0+9 months |  | - 11 men/ months | - RP steady-state conditions of operation with four, three and two working RCP set in the first transitive and subsequent cycle, including equilibrium fuel cycles with core arrangement of UTVS and TVS-2M type FA will be considered in the calculations. - Thermal-hydraulic characteristics in RP steady-state operating conditions with four, three and to two RCP in operation will be determined for nominal parameters and considering parameter possible deviations from nominal values within the limits of design tolerances. |  |  |
| - 3.2 | - Stop of spent fuel pool cooling | - OKB GP |  | - Т0+9 months |  | - 5 men/ months | - Calculation purpose - to determine the time before fuel damage in the SFP for considered initiating event with stop of cooling water supply into the cooling pool. Make-up flowrate required for SFP evaporated water compensation is also determined in the calculation. |  |  |
| - 3.3 | - Spent fuel pool leak or pipeline break resulting in spent fuel pool water level decrease | - OKB GP |  | - Т0+9 months |  | - 7 men/ months | - The calculation is provided for cooling pool spent FA for the initiating event with water leak through spent fuel pool (SFP) bottom lining under flowrate equal to the capacity of cooling pool standard system make-up pumps for the initiating event with guillotine break of the pipeline for water supply into a spent fuel pool cooling system. Thus SFP water make-up is not provided. The calculation purpose - to determine the time before SFP fuel damage in considered initiating events with SFP water leak. |  |  |
| I | The reports transfer on Stages 1, 2, 3 | TVEL | 30.05. 2017 |  |  | 66 men/ months |  |  |  |
| 4 | Strength and thermal mechanics of FA, RCCA and reactor core (loadings of transfer from UTVS to TVS-2M with blankets, and then to TVS-2M without blankets and equilibrium TVS-2M without blankets) | OKB GP |  | Т0+12 months 31.05.2017 |  | 113 men/ months |  |  |  |
| - 4.1 | - Elaboration of calculations of reactor internals temperatures and heat exchange boundary conditions for strain determination of reactor internals affecting FA compression | - OKB GP |  | - Т0+6 months |  | - 3 men/ months | - Determination of coolant flowrates and heating in core baffle channels and gaps for various versions of fuel loadings. Calculation of temperature fields in core baffle and core barrel under normal operation at different versions of fuel loading. Calculation of core barrel temperature fields in for the version with wall maximum power for the conditions of anticipated operational occurrences and main coolant pipeline breaks. |  |  |
| - 4.2 | - Substantiation of TVS-2M thermo-mechanical stability and strength | - OKB GP |  | - Т0+9 months |  | - 39 men/ months |  |  |  |
| - 4.2.1 | - Calculations for determination of the parameters of fuel rods and guiding channels interaction with FA spacing grid | - OKB GP |  | - Т0+9 months |  | 7 men/ months | - The calculations determine local parameters of fuel rod and guiding channel (GCh) interaction with spacing grid (SG) of UTVS and TVS-2M: SG rigidity for turn of fuel rods and GCh depending of current elastic tightness in contact pairs “fuel rod – SG cell” and coefficient of friction in contacting surfaces; radial rigidity of SG cells; parameters describing fuel rod and GCh deformations in the flights between SG considering radiation creeping of structural materials; parameters describing SG deformation considering radiation creeping of structural materials (variation of SG cell internal inscribed diameter, SG deformation under fuel rod and GCh turnings in the grid). Сalculation results will be used as input data for simulation of UTVS and TVS-2M thermo-mechanical behavior during operation. Two calculations are scheduled using code package ANSYS |  |  |
| - 4.2.2 | - Calculation of FA operation longitudinal strain and rigidity | - OKB GP |  | - Т0+9 months |  | 3 men/ months | - Bend and longitudinal rigidity of UTVS and TVS-2M, both UTVS and TVS-2M GCh in-service length variation will be determined in the calculation. Work results are required for calculation of FA compression forces during operation and determination of permissible range for PTU axial position during preventive maintenance. FA various states will be considered in the calculation. Calculations will be provided using specialized certificated code FAME_N1simulating FA thermo-mechanical behavior during operation |  |  |
| - 4.2.3 | - Calculation of FA components shape variation in loss of coolant accidents | - OKB GP |  | - Т0+12 months |  | 3 men/ months | - Analysis of UTVS and TVS-2M SG straining resulted from interactions with fuel rod ballooned claddings, including variation of SG wrench dimension in the course of loss of coolant accident will be provided in the calculation. Evaluation of the conservatism for UTVS and TVS-2M loss of stability under longitudinal compression in the course of loss of coolant accident will be provided in the calculation. Conclusions of FA thermo-mechanical stability in the loss of coolant accident and of the possibility of core unloading after the accident will be made on the basis of the results obtained. Code package ANSYS and code FAME_N1 will be used in the calculation. |  |  |
| - 4.2.4 | - Calculation analysis of FA frame strength during operation | - OKB GP |  | - Т0+9 months |  | 8 men/ months | - Two calculations are scheduled. Forces in UTVS and TVS-2M components during operation, considering radiation increase and creeping of zirconium alloys will be determined in the first calculation using code FAME_N1. Calculation analysis of UTVS and TVS-2M component strength considering most loaded structure units will be provided in the second calculation on the basis of the forces obtained using code package ANSYS. Non-elastic analysis methods will be used providing more exact safety margins for composite units using finite-element code packages. |  |  |
| - 4.2.5 | - Calculations of FA and inter-assembly space deflections in NOC. Preparation of reference data generated for calculation of Keng. | - OKB GP |  | - Т0+12 months |  | 8 men/ months | - Two calculations will be provided. Calculation evaluations of UTVS and TVS-2M possible deflections during operation will be provided in the first calculation using specialized code FAME_N1. Single FA will be conservatively assumed not considering supporting effects of adjacent FA. Specified calculation results will be used in the calculation analysis of UTVS and TVS-2M strength. Evaluation of FA compression maximum forces providing FA thermo-mechanical stability during operation will be also made within the framework of specified work. Simulation of thermo-mechanical behavior of all FA in the core using probabilistic methods will be provided in the second calculation. The calculation will be provided using specialized code developed on the basis of certificated code FAME_N1. The gaps between FA depending time will be determined in the calculation for the whole core at different axial levels. |  |  |
| - 4.2.6 | - Calculation of FA compression parameters for NOC conditions | - OKB GP |  | - Т0+11 months |  | 3 men/ months | - The ranges of top nozzle displacements for UTVS and TVS-2M, both the ranges of specified FA compression forces during operation will be determined in the calculation for RP in which PTU projection completions were not provided. All main factors defining FA compression during operation, including relaxation of FA spring unit preliminary compression forces and GCh length variation during operation will be considered in the calculation. Solution of the necessity to provide activities on FA compression forces optimisation during operation can be assumed by work results. Substantiation of absence of need for the revision of PTU in the implementation of TVS-2M |  |  |
| - 4.2.7 | - Calculation of the permissible range of PTU axial position during scheduled preventive maintenance | - OKB GP |  | - Т0+11 months |  | 6 men/ months | - Permissible range of PTU axial position during scheduled preventive maintenance (PM) will be determined in the calculation for each PM up to reactor brining to equilibrium fuel cycle. - The calculation will consider all main factors, which determine PTU axial position in open reactor, including core current cycle, PTU weight in water, variation of FA GCh length, relaxation of the forces of FA spring units preliminary compression. Specified work results are required to control the forces of FA compression during operation. |  |  |
| - 4.3 | - Calculations of CPS CR dynamic characteristics for NOC, AOO and DBA | - OKB GP |  | - Т0+12 months |  | - 7 men/ months | - Calculation of CPS CR dynamic characteristics for normal operation and anticipated operational occurrences. The calculation is provided to determine CPS CR dynamic characteristics under the conditions of their displacement in case of reactor scram at NOC and AOO. CPS CR dynamic characteristics (drop time, displacement velocities, overloads during drop and damping) are determined for various number of working RCP sets and various primary coolant temperatures typical for conditions NOC and AOO. Influence of geometrical and operating conditions parameter deviations (within the ranges of design tolerances) onto CPS CR dynamic characteristics is considered in the calculation. Calculation of CPS CR dynamic characteristics for design basis accidents. The calculation is provided to determine CPS CR dynamic characteristics in accident conditions with breaks of MCP and other pipelines, both with CPS drive housing break. CPS CR dynamic characteristics (drop time, displacement speeds, forces and overloads during drop and damping under scram, during emersion from bottom position (accidents with pipeline breaks) and withdrawal from the core (in the accident with drive housing break) are determined considering influence of CPS CR pressure differentials realized in considered accident conditions. Calculation results are used in RP safety analysis and as input data for strength calculations. |  |  |
| - 4.4 | - Calculation of core hydro-dynamical conditions for DBA | - OKB GP |  | - Т0+10 months |  | - 6 men/ months | - VVER-1000 reactor coolant parameters are determined for the accidents with: - - break of ECCS pipeline connected to MCP "cold" or "hot" leg; - - break of "hot" and "cold" MCP Dnom 850 (design criteria of the time for CPS CR insertion in the core is checked for specified conditions in the calculation of CPS CR dynamic characteristics). - Accident conditions are considered for two initial states: - - for reactor operation at nominal; - - at operation at zero power, in "hot" state of the reactor. - Calculations of accident operating conditions at nominal power are required for determination of CPS CR dynamic characteristics for drop time computation and strength calculation analysis. - Calculations of accident operating conditions at zero power are required for determination of RCCA extension shaft dynamic characteristics for emersion from bottom position. |  |  |
| - 4.5 | - Calculation of TVS-2M dynamic characteristics for DBA | - OKB GP |  | - Т0+10 months |  | - 18 men/ months |  |  |  |
| - 4.5.1 | - Dynamic characteristics of TVS-2M under "cold" and "hot" pipeline breaks for which LBB concept is not used | - OKB GP |  | - Т0+10 months |  | 6 men/ months | - Dynamic characteristics, axial and lateral loads to TVS-2M are determined for the process of RP reactor coolant system emergency de-pressurization at nominal power resulted from break of the pipeline with maximum diameter connected to MCP for which "leak before break" concept is not considered. Loads to TVS-2M are calculated for minimum and maximum compression of spring units in TVS-2M top nozzle. Calculation results are used as reference data in TVS-2M and reactor internals strength calculations. |  |  |
| - 4.6 | - Calculation of dynamic loads on reactor internals in DBA | - OKB GP |  | - Т0+10 months |  | - 17 men/ months |  |  |  |
| - 4.6.1 | - Forces to reactor internals under "cold" and "hot" pipeline breaks for which LBB concept is not used | - OKB GP |  | - Т0+10 months |  | 6 men/ months | - Work purpose is to determine pressure differentials and the forces affecting reactor internals at nominal power for the process of RP reactor coolant system emergency de-pressurization resulted from the break of maximum diameter pipeline connected to MCP, for which " leak before break " concept is not considered, for the first time moments characterized by maximum dynamic loads. Calculation results are used as reference data in TVS-2M and reactor internals strength calculations. |  |  |
| - 4.7 | - Strength calculations | - OKB GP |  | - Т0+12 months |  | - 23 men/ months |  |  |  |
| - 4.7.1 | - TVS-2M strength calculations for NOC, AOO and DBA, external dynamic loads and various combinations of conditions and loads | - OKB GP |  | - Т0+12 months |  | 10 men/ months | - Analysis of FA components static and cyclic strength, both stability during RP operation in the conditions NOC, AOO and combinations of loads is provided in TVS-2M strength calculations. Analysis of FA components safety is provided for the load combinations NOC+DBA and NOC+DBA+OBE: FA components deformation shall not prevent RCCA drop by reactor scram signal and core unloading. |  |  |
| - 4.7.2 | - Internals strength calculations for NOC, AOO and DBA, external dynamic loads and various combinations of conditions and loads | - OKB GP |  | - Т0+12 months |  | 13 men/ months | - Analysis of internals static and cyclic strength, both stability during RP operation in the conditions NOC, AOO and combinations of loads is provided in internals strength calculations. Analysis of internals components safety is provided for the load combinations NOC+DBA and NOC+DBA+OBE: internals components deformation shall not prevent RCCA drop by reactor scram signal and core unloading. |  |  |
| II | The reports transfer on Stage 4 | TVEL |  | 30.09. 2017 |  | 113 men/ months |  |  |  |
| 5 | - Development of justification of operability of fuel rod and gadolinium fuel rod under the steady-state operation conditions, NOC and AOO transients, analyses of behaviour during DBA | VNIINM |  | Т0+18 months 30.11.2017 |  | 35 men/ months |  |  |  |
| - 5.1 | - Justification of operability of fuel rods and gadolinium fuel rods under the steady-state operation condition at "Bushehr" NPP, Unit 1 during TVS-2М implementation | - VNIINM |  | - Т0+12 months |  | 11 men/ months | - The paper analyzes the initial data with the results of neutronics calculations of BNPP-1 fuel loadings and selects a representative array of FAs and fuel rods, Gd-fuel rods in them. Thermophysical and thermomechanical characteristics of fuel rods and Gd-fuel rods are calculated using the code START-3А and meeting of the design criteria is checked to justify operability of fuel rods and Gd-fuel rods under steady-state operating conditions at BNPP-1. |  |  |
| - 5.2 | - Justification of operability of fuel rods and gadolinium fuel rods during the transients with NOC, AOO at "Bushehr" NPP, Unit 1 during TVS-2М implementation | - VNIINM |  | - Т0+14 months |  | 9 men/ months | - The paper analyzes the results of neutronics calculations of governing transients of NOC, AOO at the beginning and the end of the transient and the steady-state fuel loading of BNPP-1. Thermophysical and thermomechanical characteristics of fuel rods and Gd-fuel rods are calculated using the code START-3А and meeting of the design criteria is checked to justify operability of fuel rods and Gd-fuel rods under transients of NOC, AOO at BNPP-1. |  |  |
| - 5.3 | - Justification of safety behavior of fuel rods and gadolinium fuel rods during the design basis accidents LOCA and RIA at "Bushehr" NPP, Unit 1 during TVS-2М implementation | - VNIINM |  | - Т0+18 months |  | 7 men/ months | - The paper analyzes the initial data for justification of a safe behavior of fuel rods and Gd-fuel rods under design LOCA and RIA for BNPP-1. Thermomechanical and corrosion characteristics of fuel rods and Gd-fuel rods are calculated using the code RAPTA-5.2 and meeting of the criteria is checked to justify a safe behavior of fuel rods and Gd-fuel rods under design LOCA and RIA at BNPP-1. |  |  |
| - 5.4 | - Determination and justification of design criteria of VVER-1000 fuel rods under NOC and AOO | - VNIINM |  | - Т0+12 months |  | 3 men/ months | - The objective of the paper is: to determine the design criteria applied in development of engineering material to justify the operability of fuel rods and Gd-fuel rods under NOC, AOO for licensing the uranium-gadolinium fuel for WWER-1000; to describe the reasons (causes) for introduction of an appropriate design criterion of fuel rod; to perform calculation-experimental justification of the magnitudes of the limiting values and dependencies for the criteria of operability of WWER-1000 fuel rods under NOC, AOO. |  |  |
| - 5.5 | - Determination and justification of criteria of safe behaviour of VVER-1000 fuel rods during the design basis accidents | - VNIINM |  | - Т0+18 months |  | 4 men/ months | - The objective of the paper is: to perform experimental justification of the criteria of a safe behavior of WWER fuel rods under design basis accidents with coolant loss (LOCA) and reactivity-initiated accidents (RIA); to evaluate the properties of alloy Э110 (E110) as material for WWER fuel rod claddings within the context of fuel system coolability criteria and fuel rod damage criteria whose meeting is necessary for safety assurance of the reactor plant with WWER. |  |  |
| 6 | Justification of RCCA operability and service life characteristics | OKB GP JSC PFC |  | Т0+20 months 31.01.2018 |  | 50 men/ months |  |  |  |
| - 6.1 | - Calculation of the limiting deviations of relative position of fuel stack and absorber in the absorbing rod of the control and protection system | - OKB GP |  | - Т0+4 months |  | 2 men/ months | - Considered two options RCCA – base and elongated. In the calculation it is determined the high-altitude position of the absorber with respect to the fuel stack with the various RCCA positions in the core. We consider the RCCA position on upper limit switch, lower rigid stop, lower limit switch, and also several different positions along the core height. The results of the calculation are required for elaboration and justification of the core reactivity control algorithms and for the calculated analysis of RCCA strength and serviceability. |  |  |
| - 6.2 | - Justification of RCCA service life. Determination of the radiation loads acting on the RCCA structural and absorbing materials during NOC | - OKB GP |  | - Т0+10 months |  | 3 men/ months | - For option base RCCA is considered its operation for the first 10 fuel loading of Bushehr-1. For option extended RCCA examines its operation from 11 fuel loading of Bushehr-1. To justify the radiation stability of the AE structural materials it is checked the meeting of the acceptance criteria of CPS CR to be spent during the automatic control and EP conditions. As a result of the analysis made considering the fuel cycle characteristics we determine the burn-ups of boron-10, dysprosium isotopes and neutron fluences onto the absorbing materials and AR end piece during CPS CR operation over an adjusting range with the various high-altitude positions from the core bottom followed by the operation in the EP to confirm the RCCA operability during the assigned service life. The calculation results are the initial data for calculations of change in the worth of the separate CPS CR groups and emergency protection considering the absorber burn-up during the fuel cycle operation. |  |  |
| - 6.3 | - Calculation of RCCA worth considering the absorber burn-up during operation | - OKB GP |  | - Т0+10 months |  | 3 men/ months | - Considered two options RCCA – base and elongated. The worth of the CPS CR emergency protection and working group is calculated considering a change in the isotope composition of boron carbide and dysprosium titanate during an irradiation for the AE assigned service life. The worth values are calculated for the chosen reactor fuel cycles. To confirm the frame values of the emergency protection worth it is chosen a conservative version of positioning the burnt CPS CRs considering the sticking of one CPS CR of the maximum worth. It is evaluated a decrease in the emergency protection worth during operation caused by a change in isotope composition of boron and dysprosium in the AE of CPS CR. |  |  |
| - 6.4 | - Calculation of power distribution in the RCCA absorbing and structural materials | - OKB GP |  | - Т0+10 months |  | 3 men/ months | - Considered two options RCCA – base and elongated. The calculation is carried out to obtain the initial data on power distribution in the AE structural materials for the analyses of AE cooling under the NOC and AOO including DBA. The conditions are broken down into the groups in which the CPS CR motion is initiated in addition to the EP signal, and the CPS CR motion occurs only by the EP signal. The relative local power distributions in the structural materials of AE and GCh, and also the fuel rods, surrounding the GCh, corresponding to the different CPS CR group positions are calculated for two groups of conditions. |  |  |
| - 6.5 | - Analysis of RCCA thermal state during NOC, AOO and DBA | - OKB GP |  | - Т0+13 months |  | 2 men/ months | - Considered two options RCCA – base and elongated. The analysis is performed to determine the data on the temperature state of AE of CPS CR under the steady-state conditions of NOC. The document deals with the calculation results of velocities, coolant flowrates in GCh, coolant temperatures in GCh, temperatures of GCh wall and temperatures of AE cladding for the various positions of absorbing element in the reactor core and with the various power profiles along the core height. The concentric and eccentric positions of AE in the GCh are considered. The analysis results are used for RP safety analysis. |  |  |
| - 6.6 | - Strength analysis of RCCA under NOC, AOO and DBA | - OKB GP |  | - Т0+17 months |  | 6 men/ months | - Considered two options RCCA – base and elongated. In the calculation analysis the strength analysis of RCCA under NOC and AOO and during DBA as well will be performed. |  |  |
| - 6.7 | - Upgrading of software of the software-hardware complex (SHC) in a set of the control and protection system (CPS) electrical equipment complex | - OKB GP |  | - Т0+14 months |  | 14 men/ months | - The following activities will be performed: - - upgrading of software of SHSR cabinet in a set of SHC of the information and diagnostic system (IDS); - - installation of the upgraded software (SHSR cabinets), testing of the upgraded software; - - upgrading of software of PKU1M cabinet, stationary building console PSS; - - installation of the upgraded software (PKU1M cabinets, stationary building console PSS), testing of the upgraded software. - For option base RCCA adjusts the display of the display position of fuel - absorber on unit control panel in PM, which are the first TVS-2M without blanket. For option extended RCCA is an increase in the magnitude of the stroke, ensuring the extracting of the elongated RCCA out of the fuel in the PM, which establishes elongated RCCA. Work on practical modernization SGI on the Busher-1 is carried out by the Corporation VNIIEM. |  |  |
| - 6.8 | - Analysis of RP dynamic stability | - OKB GP |  | - Т0+12 months |  | 6 men/ months | - Thermohydraulic calculation of normal operation conditions and several conditions with the anticipated operational occurrences in a realistic approach with simulation of operation of the main controllers, interlockings, EP-PP. The calculation is performed to confirm an absence of automatic unscheduled decrease in power, automatic unscheduled reactor shutdowns or actuation of control safety systems under the considered conditions without the failures of systems, equipment and personnel’s erroneous actions in addition to the initiating event or transient condition. |  |  |
| - 6.9 | - Topical report on the projects of AE and RCCA. | - OKB GP |  | - Т0+20 months |  | 11 men/ months | - Development of the report on the basis of the documentation of AE and RCCA projects (drawings, explanatory reports, project of technical specifications, specification for structural materials, patent forms). |  |  |
| 7 | Safety analyses (loads of transfer from UTVS to TVS-2M with blankets and then to TVS-2M without blankets and equilibrium TVS-2M without blankets) | OKB GP |  | Т0+20 months 31.01.2018 |  | 174 men/ months |  |  |  |
| - 7.1 | - Topical report. - Part 1. Safety analyses for AOO conditions | - OKB GP |  | - Т0+12 months |  | 52 men/ months | - Perform for the conservative option RCCA providing minimum headroom for acceptance criteria security analysis. |  |  |
| - 7.2 | - Topical report. - Part 1. Safety analyses in DBA conditions | - OKB GP |  | - Т0+18 months |  | 49 men/ months | - Perform for the conservative option RCCA providing minimum headroom for acceptance criteria security analysis. |  |  |
| - 7.3 | - Topical report. - Part 1. Safety analyses for BDBA conditions | - OKB GP |  | - Т0+20 months |  | 72 men/ months | - Perform for the conservative option RCCA providing minimum headroom for acceptance criteria security analysis. |  |  |
| 8 | Nuclear safety, releases, doses | JSC PFC OKB GP |  | Т0+20 months 31.01.2018 |  | 76 men/ months |  |  |  |
| - 8.1 | - Calculation of radiation characteristics of spent fuel during long-term storage (residual heat, activity and nuclide composition of spent fuel) | - JSC PFC |  | - Т0+17 months |  | 2 men/ months |  |  |  |
| - 8.2 | - Justification of nuclear safety when handling TVS-2M at the NPP | JSC PFC OKB GP |  | - Т0+17 months |  | 4 men/ months |  |  |  |
| - 8.2.1 | - Development of justification of nuclear safety when handling with TVS-2M at the NPP | - JSC PFC - OKB GP |  | - Т0+17 months |  | - 4 men/ months | - The nuclear safety analysis will be carried out on the basis of the results of neutron-and-physical calculations for the normal operation conditions and accident situations through the whole path of transportation and fuel storage at the NPP (before and after the reactor). - Agreement of nuclear safety analysis when handling with TVS-2М at the NPP. |  |  |
| - 8.3 | - Calculations of fission product accumulation within the claddings and in the primary coolant | JSC PFC |  | - Т0+10 months |  | 2 men/ months |  |  |  |
| - 8.3.1 | - Development of the calculations of fission product accumulation under the fuel rod claddings and in the primary coolant | - JSC PFC |  | - Т0+10 months |  | 2 men/ months | - In these calculation we shall determine the values of activity of the main fission products under the claddings of the leak-tight fuel rods and in the primary coolant with the assigned number of leaky fuel rods in the core. The results of these calculations are required as the initial data to calculate the radiation protection (item 8.4), and also to compile chapters FSAR. |  |  |
| - 8.4 | - Development of calculations of the radiation load on the reactor equipment | - OKB GP |  | - Т0+17 months |  | 32 men/ months |  |  |  |
| - 8.4.1 | - Topical report “Radiation load onto the reactor equipment” | - OKB GP |  | - Т0+17 months |  | 32 men/ months | Is determined by the intensity of the main sources of neutron and gamma radiation acting on the equipment of the reactor, the radiation energy of reactor internals and the reactor vessel, the parameters of fast neutron flux on the reactor vessel and internals (fluence, damaging dose, neutron spectrum). The results are used as input data when calculating the strength of the internals, preload TVs-2M and brittle failure resistance of the reactor vessel. |  |  |
| - 8.5 | - Development of the reactor vessel calculation for brittle failure resistance considering a changed neutron fluence | - OKB GP |  | - Т0+17 months |  | 27 men/ months | - We shall perform the calculations of temperature fields, stressed-strained state and fracture mechanics parameters in the reactor vessel for the design operation conditions including the accident conditions with a thermal shock. By the results of the calculations the reactor vessel service life will be evaluated by the brittle failure resistance criterion considering the new values of the neutron fluence. The “temperature - permissible pressure” (P-T curve) dependences will be developed for the normal operation conditions and the minimum permissible temperatures of hydrotests will be determined. |  |  |
| - 8.6 | - Elaboration of justification of NPP radiation safety, including radiologic safety under NOC, AOO and accident conditions | - OKB GP |  | - Т0+20 months |  | 9 men/ months |  |  |  |
| - 8.6.1 | - Topical report. - Part 1. Radiation consequences during AOO | - OKB GP |  | - Т0+20 months |  | 3 men/ months |  |  |  |
| - 8.6.2 | - Topical report. - Part 2. Radiation consequences under DBA conditions | - OKB GP |  | - Т0+20 months |  | 7 men/ months |  |  |  |
| 9 | ICIS Justification | OKB GP JSC PFC |  |  | Т0+20 months 31.01.2018 | 36 men/ months |  |  |  |
| - 9.1 | - Topical report.“ICIS constants prepare for FA which will be use during implementation TVS-2M” | - JSC PFC |  |  | - Т0+18 months | 5 men/ months | - In report “ICIS constants prepare for FA which will be use during implementation TVS-2M” will be offer ICIS constants wich need for functioning of ICIS and the method using of constants. The introduction of new constants into the database ICIS by the JSC "PFC", is carried out in the framework contract for support of nuclear fuel. Adjustment of setpoint for local power at SHC-P in PM when install the TVS-2M without blanket forces SNIIP-Askur. |  |  |
| - 9.2 | - Topical report. “Metrology evaluation of ICIS parameters of the power field obtained by SHC TL ICIS during implementation TVS-2M” | - JSC PFC |  |  | - Т0+18 months | 5 men/ months | - In report “Metrology evaluation of ICIS parameters of the power field obtained by SHC TL ICIS during implementation TVS-2M” will be offer metrology characteristics of ICIS parameters of the power field which will be obtaine by compare of ICIS power fields and power fields obtained by project code. |  |  |
| - 9.3 | - Topical report. “Metrology evaluation of complex SHC-P ICIS, which performs a protection function on the basis of the local parameters during implementation TVS-2M” | - JSC PFC |  |  | - Т0+18 months | 5 men/ months | - In report “Metrology evaluation of complex SHC-P ICIS, which performs a protection function on the basis of the local parameters during implementation TVS-2M” will be offer metrology characteristics of a protection function on the basis of the local parameters (rod linear power, DNBR) for the fuel cycle with TVS-2M of the Bushehr NPP Unit 1. |  |  |
| - 9.4 | - Justification of representativeness of temperature control at the core outlet and determination of operational temperature restrictions | - JSC PFC - OKB GP |  |  | - Т0+18 months | - 10 men/ months | To assure thermal-technical reliability of fuel rods in the core (DNBR > 1,0 under NOC and AOO), the coolant thermal inspection representativeness is performed. NTMC is applied to assure accuracy of heat rate inspection and to improve reliability of thermal control. Development of technical requirements to the NTMC, ensuring the representativeness of thermal control at the exit of the fuel assemblies. |  |  |
| - 9.5 | - Procedure of determination of operational safety factors for local power distribution and permissible volume power peaking factors | - OKB GP |  |  | - Т0+20 months | 1 men/ months | - The report deals with the procedure of determination of the permissible volume power peaking factors considering the operational safety factors, and also the setpoint values of the preventive and emergency protection by the linear power rating in the cores of "Bushehr" NPP, Unit 1 when changing over to TVS-2M operation are determined |  |  |
| - 9.6 | - Cross-verification of the ICIS software as regards realization of protection by DNBR | - OKB GP |  |  | - Т0+20 months | 10 men/ months | - Cross-verification of the ICIS software as regards realization of protection by DNBR is performed by comparing the calculation results obtained in the ICIS SW with the results of the safety analyses. The aim of the ICIS cross-verification is to verify that the functional requirements imposed on the function of DNBR determination are met. |  |  |
| III | The reports transfer on Stages 5, 6, 7, 8, 9 | TVEL |  |  | 31.05. 2018 | 370 men/ months |  |  |  |
| 10 | Development of justification of operability of the process equipment and systems of the Unit | OKB GP JSC PFC |  |  | Т0+24 months 31.05.2018 | 68 men/ months |  |  |  |
| - 10.1 | - Development of justification of operability of the process equipment of the Unit (DADS, fuel handling procedures, systems of storage of fresh and spent fuel) | OKB GP JSC PFC |  |  | - Т0+24 months | - 43 men/ months |  |  |  |
| - 10.1.1 | - Development of the Manual on LCC of the fuel rods at the RP being in operation and shutdown for "Bushehr" NPP during transition to TVS-2M new fuel (considering the LCC up-to-date requirements and procedures) | - JSC PFC - OKB GP |  |  | - Т0+19 months | - 3 men/ months | - Development of the documents (criteria, procedures and requirements) on LCC of the fuel rods at the RP being in operation and shutdown for new fuel (TVS-2M) and considering the up-to-date approaches and requirements. - Development of manual on LCC of the fuel rods at the RP being in operation and shutdown for "Bushehr" NPP when using TVS-2М (on the basis of JSC PFC documents). |  |  |
| - 10.1.2 | - Justification of operability of FHE with fuel, system of storage of fresh and spent fuel | - OKB GP |  |  | - Т0+24 months | 40 men/ months |  |  |  |
|  | - Calculations for strength of the packed fuel storage racks (PFSR) during normal operation and external dynamic impacts | - OKB GP |  |  | - Т0+15 months | 2 men/ months | - Evaluation of strength of PFSR during the normal operation and seismic impacts considering an increase in the loaded fuel mass |  |  |
|  | - Analysis of drop of heavy objects into spent fuel pool | - OKB GP |  |  | - Т0+15 months | 1 men/ months | - Evaluation of PFSR distortion during the accidents connected to the heavy object drop |  |  |
|  | - Thermohydraulic calculation. Cooling of SFA during storage in spent fuel pool | - OKB GP |  |  | - Т0+16 months | 3 men/ months | - The calculation is aimed at determining the cooling conditions of the spent FA located in the racks of the spent fuel pool during NOC; AOO; DBA; BDBA. |  |  |
|  | - Strength calculation of the rack in FFS | - OKB GP |  |  | - Т0+20 months | 3 men/ months | - In the calculation it will be considered the strength of the structural components of the rack for TVS-2M fresh fuel assemblies under the normal operation conditions, and also due to the external dynamic impacts: safe shutdown earthquake and crash of the middle class airplane onto the reactor building. |  |  |
|  | - Pattern of loading the SFP embedded components due to PFSR | - OKB GP |  |  | - Т0+15 months | 1 men/ months | - The loads onto the SFP civil structures are given on the basis of the strength calculations. |  |  |
|  | - Pattern of loading the FFS embedded components due to PFSR | - OKB GP |  |  | - Т0+16 months | 1 men/ months | - The loads onto the FFS civil structures are given on the basis of the strength calculations |  |  |
|  | - Modification of FHM | - OKB GP |  |  | - Т0+24 months | 28 men/ months |  |  |  |
| - 10.1.2.7.1 | - FHM control system caused by a change in the FA shuffling velocities and mass. | - OKB GP |  |  | - Т0+24 months | 9 men/ months | - Change in FHMCS (fuel handling machine control system) due to increase in the FA motion velocities and mass in FHM before 7th fuel loading.. Adjustment of the elevations of the extended transport position RCCA. |  |  |
| - 10.1.2.7.2 | - Implementation of LCC in FHM working shaft | - OKB GP |  |  | - Т0+24 months | 19 men/ months | - The fuel handling machine mast is additionally equipped with the leak detection system in fuel rod claddings. Supply, installation, commissioning of equipment and training of personnel BNPP-1 holding sipping control in PM before 5th fuel loading |  |  |
| - 10.1.3 | - Justification of DADS operability | - OKB GP |  |  | - Т0+18 months |  |  |  |  |
| - 10.1.3.1 | - Thermohydraulic calculation of DADS | - OKB GP |  |  | - Т0+18 months |  | - Determination of sufficiency of DADS heat exchanger surface for heat removal and non-exceeding of temperature in the DADS circuit above 90oC when carrying out the LCC (for the most-powered TVS-2M) |  |  |
| - 10.1.3.2 | - Calculation for determination of the permissible time of water circulation termination in the DADS circuit | - OKB GP |  |  | - Т0+18 months |  | - Determination of the permissible time of termination of water circulation in the DADS circuit (pump trip in the infusion mode) when performing the LCC of TVS-2М based on the condition of non-exceeding of the water saturation temperature in the circuit at the pressure in the infusion mode (for the most-powered TVS-2M) |  |  |
| - 10.2 | - Analysis of NPP systems and buildings during utilization of TVS-2M in 12-month cycle | - OKB GP |  |  | - Т0+24 months | 25 men/ months | - The following procedures will be performed: - - capability analysis of SFP constructions; - - capability analysis of fresh fuel storage constructions of the reactor building; - - the analysis of the applicability of safety systems - - calculations of coolant system under SFP cooling conditions (at annual fuel unloading, total fuel unloading, accidental fuel unloading) |  |  |
| - 10.3 | The development of programs to confirm design characteristics of TVS-2M at the BNPP-1 | - OKB GP |  |  | - Т0+24 months |  | The definition of operating States and the monitored parameters of operation of the reactor and the active zone during the introduction of TVs-2M. Data analysis and report design are performed within the framework of the contract accompany the operation of nuclear fuel. |  |  |
| - 10.4 | Change of operational documentations in connection with the introduction of TVS-2M | - TVEL - OKB GP - JSC PFC - VNIINM |  |  | - Т0+24 months |  | Analysis of the list of operational documentations BNPP-1 for the develoment and delivering of Principal proposals for necessary adjustments in connection with the introduction of TVS-2M. The Principal corrects the required documentations. The Contractor will obtain necessary agreements on modified documentations from related Russian organizations as well as NNSD with the support of the Principal. |  |  |
| IV | The reports transfer on Stage 10 | TVEL |  |  | 30.09. 2018 | 68 men/ months |  |  |  |
| 11 | Licensing | OKB GP JSC PFC VNIINM |  |  | Т0+30 months 30.11.2018 | 88 men/ months |  |  |  |
| - 11.1 | - Revision of FSAR by the results of the justification performed. | - OKB GP - JSC PFC VNIINM |  |  | - Т0+24 months | - 30 men/ months | - Results of justification are entered into the corresponding FSAR sections. Agreement with the Executors. |  |  |
| - 11.2 | - Revision of FSAR by the results of the justification performed and the agreement with NPPD (Customer). - Revision of FSAR by the results of agreement with NPPD. | - JSC TVEL - OKB GP |  |  | - Т0+27 months | - 32 men/ months | - Results of justification are entered into the corresponding FSAR sections. Agreement with the Customer. |  |  |
| - 11.3 | - Cooperation with NNSD. - Revision of FSAR by the results of agreement with NNSD and cooperation with the IAEA experts | - TVEL - OKB GP - JSC PFC - VNIINM |  |  | - Т0+30 months | - 25 men/ months | - Rendering the consulting services during cooperation with IAEA. |  |  |
| V | The reports transfer on Stage 11 | ТВЭЛ |  | 30.03. 2019 |  | 88 men/ months |  |  |  |
| 12 | Revision of FSAR by the results of experimental operation of TVS-2М at “Bushehr”NPP | OKB GP |  | Т0+60 months 31.05.2021 |  | 16 men/ months | The corresponding FSAR sections are corrected by the results of experimental operation. Agreement with the Iranian Regulatory Authorities and IAEA. |  |  |
| VI | Передача отчетов по этапу 12 | ТВЭЛ |  | 30.09. 2021 |  | 16 men/ months |  |  |  |
| THE TOTAL MEN/ MONTHS FOR THE WORKS IS |  |  |  |  |  | 720 men/ months |  |  | 18000,00 |