## IRA2010
Activity | Input | Input Type | Sub Type | Funding | Budget | Budget Year | Start | End
1.1 Confirming/Setting-up project team (CP, CP team in MS, PMO/TO) | [6 empty] | / | /
0
1.3 Updating project work plan | [6 empty] | / | /
0
1.4 Preparing and submitting PPARs (every six months) | [6 empty] | / | /
0
1.2 Conducting project review meetings | [6 empty] | Q1/2014 | Q1/2014
| 1.2.1 Annual project review and planning meeting | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2014 | Q1/2014 | Q1/2014
1.5 IAEA Field Monitoring | [6 empty] | Q1/2014 | Q4/2014
| 1.5.1 Regular [Quarterly] field monitoring and review missions | Government Cost Sharing (footnote-a/) | Expert | FootNote | 16,000 | 2014 | Q1/2014 | Q4/2014
2.2 Spent fuel storage and waste management programs | [6 empty] | Q2/2014 | Q2/2014
| 2.2.1 Expert Mission to assist in spent fuel storage and radioactive waste management programme [1 IAEA staff and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2014 | Q2/2014 | Q2/2014
3.1 Development of training materials for two new NPP projects | [6 empty] | Q4/2014 | Q4/2014
| 3.1.2 Expert Mission to assist in review of developed training materials for two new NPP units [1 IAEA staff and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2014 | Q4/2014 | Q4/2014
3.2 Risk management during preconstruction and construction phases of an actual nuclear power plant | [6 empty] | Q3/2014 | Q3/2014
| 3.2.1 WS on risk management during preconstruction and construction phases of the two new PWR units [6 NEX and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 45,000 | 2014 | Q3/2014 | Q3/2014
5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations | [6 empty] | Q3/2014 | Q3/2014
| 5.1.1 WS on safety and quality requirements in construction of the two new PWR units at Bushehr for local participating organizations [6 NEX and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 30,000 | 2014 | Q3/2014 | Q3/2014
6.1 Public information and awareness programmes development | [6 empty] | Q2/2014 | Q2/2014
| 6.1.1 WS on public information and awareness programmes [ 6 NEX and 2 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 32,000 | 2014 | Q2/2014 | Q2/2014
Sub-Total for 2014 |  |  |  |  | 183,000
1.2 Conducting project review meetings | [6 empty] | Q1/2015 | Q1/2015
| 1.2.2 Annual project review and planning meeting | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2015 | Q1/2015 | Q1/2015
1.5 IAEA Field Monitoring | [6 empty] | Q1/2015 | Q4/2015
| 1.5.2 Regular [Quarterly] field monitoring and review missions | Government Cost Sharing (footnote-a/) | Expert | FootNote | 16,000 | 2015 | Q1/2015 | Q4/2015
2.1 Seismic safety assessment | [6 empty] | Q1/2015 | Q1/2015
| 2.1.1 Expert Mission to assist in seismic safety assessments [1 IAEA staff and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2015 | Q1/2015 | Q1/2015
3.3 Corporate knowledge management | [6 empty] | Q2/2015 | Q2/2015
| 3.3.1 EM on corporate knowledge management [1 IAEA and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2015 | Q2/2015 | Q2/2015
3.4 Nuclear material accounting and control during pre operational phases of two new PWR units in Bushehr | [6 empty] | Q2/2015 | Q2/2015
| 3.4.1 WS on nuclear material accounting and control during pre operational phase of two new PWR units in Bushehr [1 IAEA and 2 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 15,000 | 2015 | Q2/2015 | Q2/2015
| 3.4.2 SV on nuclear material accounting and control during pre operational phase of two new PWR units in Bushehr | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 3,000 | 2015 | Q4/2015 | Q4/2015
4.1 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr | [6 empty] | Q2/2015 | Q2/2015
| 4.1.1 EM to assist in evaluation of developed programmes for updating owner's training system for the two new PWR units [1 IAEA and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 16,000 | 2015 | Q2/2015 | Q2/2015
4.2 Review and evaluation of the developed programme for upgrading owner’s training system for the new NPP units | [6 empty] | Q4/2015 | Q4/2015
| 4.2.1 EM to assist to review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units [1 IAEA and 3IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 16,000 | 2015 | Q4/2015 | Q4/2015
6.1 Public information and awareness programmes development | [6 empty] | Q4/2015 | Q4/2015
| 6.1.2 EM on public information and awareness programmes [ 1 IAEA and 2 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 12,000 | 2015 | Q4/2015 | Q4/2015
Sub-Total for 2015 |  |  |  |  | 138,000
1.2 Conducting project review meetings | [6 empty] | Q1/2016 | Q1/2016
| 1.2.3 Annual project review and planning meeting | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2016 | Q1/2016 | Q1/2016
1.5 IAEA Field Monitoring | [6 empty] | Q1/2016 | Q4/2016
| 1.5.3 Regular [Quarterly] field monitoring and review missions | Government Cost Sharing (footnote-a/) | Expert | FootNote | 16,000 | 2016 | Q1/2016 | Q4/2016
4.1 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr | [6 empty] | Q3/2016 | Q3/2016
| 4.1.2 EM to assist in evaluation of Developed programmes for updating owner's training system for the two new PWR units [1 IAEA and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 16,000 | 2016 | Q3/2016 | Q3/2016
Sub-Total for 2016 |  |  |  |  | 52,000
1.2 Conducting project review meetings | [6 empty] | Q1/2017 | Q1/2017
| 1.2.4 Annual project review and planning meeting | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2017 | Q1/2017 | Q1/2017
1.5 IAEA Field Monitoring | [6 empty] | Q1/2017 | Q4/2017
| 1.5.4 Regular [Quarterly] field monitoring and review missions | Government Cost Sharing (footnote-a/) | Expert | FootNote | 16,000 | 2017 | Q1/2017 | Q4/2017
2.2 Spent fuel storage and waste management programs | [6 empty] | Q1/2017 | Q1/2017
| 2.2.2 Expert Mission to assist in spent fuel storage and radioactive waste management programme [1 IAEA staff and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2017 | Q1/2017 | Q1/2017
3.1 Development of training materials for two new NPP projects | [6 empty] | Q1/2017 | Q1/2017
| 3.1.1 Expert Mission to assist in review of developed training materials for two new NPP units [1 IAEA staff and 3 IEX] | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 20,000 | 2017 | Q1/2017 | Q1/2017
Sub-Total for 2017 |  |  |  |  | 76,000

## IRA2011
Activity | Input | Input Type | Sub Type | Funding | Budget | Budget Year | Start | End
1.1 1.1.1 Safety Training through a Visit to an Incident Emergency Center | [6 empty] | Q3/2012 | Q3/2012
| 1.1.1 SV1 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,095 | 2012 | Q3/2012 | Q3/2012
| 1.1.2 SV2 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,095 | 2012 | Q3/2012 | Q3/2012
| 1.1.3 SV3 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,095 | 2012 | Q3/2012 | Q3/2012
| 1.1.4 SV4 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,095 | 2012 | Q3/2012 | Q3/2012
| 1.1.5 SV5 for one week | Agency | Scientific Visit | HardCore | 3,095 | 2012 | Q3/2012 | Q3/2012
1.2 1.1.2 Training to strengthen the capability of BNPP personnel on routine Core analysis for safe operation. | [6 empty] | Q4/2012 | Q4/2012
| 1.2.1 EM: Expert mission (with 1 Agency Expert and 2 External Experts) to support a one week national training course on core analysis and safety operation | Agency | Expert | HardCore | 15,678 | 2012 | Q4/2012 | Q4/2012
1.5 1.1.5 Training to assist BNPP-1 in operation of physical protection system at BNPP-1 | [6 empty] | Q2/2012 | Q2/2012
| 1.5.1 One week Meeting with 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 21,800 | 2012 | Q2/2012 | Q2/2012
1.6 1.1.6 Training to assist NPPD for application of physical protection against insiders and sabotage at BNPP-1 | [6 empty] | Q4/2012 | Q4/2012
| 1.6.1 One week Meeting with 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 21,800 | 2012 | Q4/2012 | Q4/2012
1.10 1.1.10 Workshop in security procedures at utility level | [6 empty] | Q2/2012 | Q2/2012
| 1.10.1 One week Workshop with one Agency staff and 2 exernal Experts | Agency | Expert | HardCore | 13,065 | 2012 | Q2/2012 | Q2/2012
1.22 1.1.22 WWER In Core Fuel Management activities including preparation of optimized core pattern configuration by applying an overall optimization model | [6 empty] | Q3/2012 | Q3/2012
| 1.22.1 1 Agency Expert and 2 External Experts | Agency | Meeting | HardCore | 16,780 | 2012 | Q3/2012 | Q3/2012
1.23 1.1.23 Steady state thermal-hydraulics parameters of WWER reactor including coupling thermal-hydraulic codes with neutronic | [6 empty] | Q4/2012 | Q4/2012
| 1.23.1 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,065 | 2012 | Q4/2012 | Q4/2012
3.1 1.3.1 Training course on outage management with focus on organization, implementation and supporting. | [6 empty] | Q3/2012 | Q3/2012
| 3.1.1 one week TC with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 21,000 | 2012 | Q3/2012 | Q3/2012
3.5 1.3.5 To strengthen the capability of BNPP personnel in establishment of Safety Performance Indicators in compliance with the latest IAEA guidance and best world practices. | [6 empty] | Q2/2012 | Q2/2012
| 3.5.1 one week TC with 1 Agency Expert and 3 External Experts practices. | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 21,800 | 2012 | Q2/2012 | Q2/2012
3.7 1.3.7 Establish the configuration management process, including its interfaces with other BNPP-1 processes | [6 empty] | Q1/2012 | Q1/2012
| 3.7.1 1 IAEA 3 experts | Agency | Expert | HardCore | 13,065 | 2012 | Q1/2012 | Q1/2012
5.1 1.5.1 To assist BNPP-1 legal , contractual and technical provisions in operation contract between owner and operator company | [6 empty] | Q2/2012 | Q2/2012
| 5.1.1 One week EM with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 16,350 | 2012 | Q2/2012 | Q2/2012
5.2 1.5.2 To assist BNPP-1 on general structure and special provisions in contracts for repair and/or maintenance of NPPs. | [6 empty] | Q3/2012 | Q3/2012
| 5.2.1 One week EM with 1 Agency Expert and 2 External Experts | Agency | Expert | HardCore | 16,350 | 2012 | Q3/2012 | Q3/2012
8.2 1.8.2 Guidance on development of international safety oversight obligation | [6 empty] | Q2/2012 | Q2/2012
| 8.2.1 One week Meeting with 1 Agency Expert and 2 External Experts | Agency | Meeting | HardCore | 21,000 | 2012 | Q2/2012 | Q2/2012
8.3 1.8.3 Enhancement on NPPD safety performance control | [6 empty] | Q3/2012 | Q3/2012
| 8.3.1 One week Meeting with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 16,350 | 2012 | Q3/2012 | Q3/2012
8.4 1.8.4 To assist and support NPPD on supervision and control of NPP’s outage program | [6 empty] | Q4/2012 | Q4/2012
| 8.4.1 One week Meeting with 1 Agency Expert and 2 External Expe | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 21,000 | 2012 | Q4/2012 | Q4/2012
Sub-Total for 2012 |  |  |  |  | 264,578
1.3 1.1.3 Training to strengthen the capability of BNPP Personnel on using the practical application of Living Probabilistic Safety Assessment for safe operation | [6 empty] | Q2/2013 | Q2/2013
| 1.3.1 one week TC with 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 17,820 | 2013 | Q2/2013 | Q2/2013
1.4 1.1.4 Training (Scientific visit) on methods for reduction of personnel dose during operation, routine maintenance and outage. | [6 empty] | Q3/2013 | Q3/2013
| 1.4.1 SV1 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q3/2013 | Q3/2013
| 1.4.2 SV2 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q3/2013 | Q3/2013
| 1.4.3 SV3 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q2/2013 | Q2/2013
| 1.4.4 SV4 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q3/2013 | Q3/2013
| 1.4.5 SV5 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q2/2013 | Q2/2013
1.9 1.1.9 Implementation of OSART Mission | [6 empty] | Q4/2013 | Q4/2013
| 1.9.1 Three weeks Expert Mission with 12 Agency Experts | Agency | Expert | HardCore | 83,625 | 2013 | Q4/2013 | Q4/2013
1.11 1.1.11 Preparatory mission for OSART mission | [6 empty] | Q1/2013 | Q1/2013
| 1.11.1 Three days EM with one Agency staff and tow external experts | Agency | Expert | HardCore | 8,019 | 2013 | Q1/2013 | Q1/2013
1.12 1.1.12 To assist BNPP-1 in analysis of recent events and operational experience and create action plan for implementation of lessons learned | [6 empty] | Q1/2013 | Q2/2013
| 1.12.1 1 IAEA and 3 external experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 17,820 | 2013 | Q1/2013 | Q2/2013
1.13 1.1.13 To support in development of a process for assessment and improvement of safety culture in BNPP-1 | [6 empty] | Q4/2013 | Q4/2013
| 1.13.1 EM: Expert Mission (1 IAEA and 3 external experts) to support the development of a process for assessment and improvement of safety cultutre in BNPP-1 | Agency | Expert | HardCore | 14,256 | 2013 | Q4/2013 | Q4/2013
1.15 1.1.15 To assist BNPP-1 in severe accident analysis, emergency preparedness and responses, including spent fuel storage | [6 empty] | Q2/2013 | Q2/2013
| 1.15.1 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 17,820 | 2013 | Q2/2013 | Q2/2013
1.16 1.1.16 To support NPPD/BNPP-1 in strengthening routine and post accident environmental monitoring | [6 empty] | Q1/2013 | Q1/2013
| 1.16.1 1 IAEA and 2 external experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,365 | 2013 | Q1/2013 | Q1/2013
1.20 1.1.20 To assist NPPD/BNPP-1 on incorporation of results from commissioning and trial operation into the Final Safety Analysis Report | [6 empty] | Q2/2013 | Q2/2013
| 1.20.1 1 IAEA and 2 external experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 17,180 | 2013 | Q2/2013 | Q2/2013
2.1 1.2.1 Scientific visit on spare part management including warehouse | [6 empty] | / | /
| 2.1.1 SV1 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
| 2.1.2 SV2 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
| 2.1.3 SV3 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
| 2.1.4 SV4 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
| 2.1.5 SV5 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
3.3 1.3.3 To strengthen the capability of BNPP personnel in using advanced Ultrasonic Test methods, standards, evaluation and techniques. | [6 empty] | Q4/2013 | Q4/2013
| 3.3.1 One week EM with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,365 | 2013 | Q4/2013 | Q4/2013
3.4 1.3.4 To strengthen the capability of BNPP personnel in application of best practices in water chemistry for Primary and Secondary circuit with focus on erosion corrosion. | [6 empty] | Q4/2013 | Q4/2013
| 3.4.1 One week TC with 1 Agency Expert and 3 External Experts corrosion. | Government Cost Sharing (footnote-a/) | Expert | FootNote | 22,300 | 2013 | Q4/2013 | Q4/2013
4.1 1.4.1 Assessment of BNPP training program and procedures, assistance in the development of corrective action plan. | [6 empty] | Q2/2013 | Q2/2013
| 4.1.1 one week EM with 1 Agency and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,365 | 2013 | Q2/2013 | Q2/2013
6.1 1.6.1 To evaluate BNPP HRM system and to provide recommendations for improvement | [6 empty] | / | /
| 6.1.1 One week EM with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,365 | 2013
6.2 1.6.2 To assist BNPP-1 on improvement of knowledge management system | [6 empty] | / | /
| 6.2.1 One week EM with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,365 | 2013
7.1 1.7.1 To assist in evaluation of FSS performance | [6 empty] | Q1/2013 | Q1/2013
| 7.1.1 One week EM with 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 17,820 | 2013 | Q1/2013 | Q1/2013
8.1 1.8.1 Assist in development and establishment of NPPD nuclear oversight organization | [6 empty] | Q1/2013 | Q1/2013
| 8.1.1 One week Meeting with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 17,180 | 2013 | Q1/2013 | Q1/2013
8.5 1.8.5 To Assist NPPD in development and implementation of regulatory requirements for the oversight of licensees’ Management System | [6 empty] | Q1/2013 | Q1/2013
| 8.5.1 One week Meeting with 1 Agency Expert and 2 External Expert | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 21,500 | 2013 | Q1/2013 | Q1/2013
8.7 1.8.7 To familiarize NPPD experts with structure, function and qualification requirement of technical support of utility/operating organization | [6 empty] | Q1/2013 | Q1/2013
| 8.7.1 SV1 for one week | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q1/2013 | Q1/2013
| 8.7.2 SV2 for one week | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q1/2013 | Q1/2013
| 8.7.3 SV3 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
| 8.7.4 SV4 for one week | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q1/2013 | Q1/2013
| 8.7.5 SV5 for one week | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q1/2013 | Q1/2013
9.1 1.9.1 To support BNPP-1 in the development of the strategy for continuous improvement of the BNPP Training Centre | [6 empty] | / | /
| 9.1.1 SV1 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
| 9.1.2 SV2 for one week | Donor extrabudgetary contribution (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013
| 9.1.3 SV3 for one week | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 3,155 | 2013 | Q1/2013 | Q1/2013
| 9.1.4 SV4 for one week | Agency | Scientific Visit | HardCore | 3,155 | 2013 | Q1/2013 | Q1/2013
| 9.1.5 SV5 for one week | Agency | Scientific Visit | HardCore | 3,155 | 2013 | Q1/2013 | Q1/2013
Sub-Total for 2013 |  |  |  |  | 385,265
1.7 1.1.7 To asist BNPP-1 in Safeguards and additional protocol | [6 empty] | / | /
| 1.7.1 One week Meeting with 1 Agency Expert and 2 External Experts | Agency | Meeting | HardCore | 17,579 | 2014
1.8 1.1.8 To assist BNPP-1 for Implementation of effective accountancy and control measures | [6 empty] | Q3/2014 | Q3/2014
| 1.8.1 One week Meeting with 1 Agency Expert and 2 External Experts | Agency | Meeting | HardCore | 17,579 | 2014 | Q3/2014 | Q3/2014
1.24 Ensuring timely technical support to the implementation of project activities | [6 empty] | / | /
| 1.24.1 Expert/consultant assistance (for six months) to ensure technical support and timely delivery of project outputs | Government Cost Sharing (footnote-a/) | Expert | FootNote | 50,000 | 2014
2.2 1.2.2 To strengthen the capability of BNPP in application of advanced maintenance methods, techniques, materials and tools | [6 empty] | Q2/2014 | Q2/2014
| 2.2.1 one week TC with 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 53,936 | 2014 | Q2/2014 | Q2/2014
2.3 1.2.3 Scientific visit on outage management with focus on organization, implementation and supporting. | [6 empty] | Q3/2014 | Q3/2014
| 2.3.1 SV1 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014 | Q3/2014 | Q3/2014
| 2.3.2 SV2 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014 | Q3/2014 | Q3/2014
| 2.3.3 SV3 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014 | Q1/2014 | Q1/2014
| 2.3.4 SV4 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014 | Q3/2014 | Q3/2014
| 2.3.5 SV5 for one week | Agency | Expert | HardCore | 4,655 | 2014 | Q3/2014 | Q3/2014
2.4 1.2.4 Introduction of modern methods of outage management | [6 empty] | Q3/2014 | Q3/2014
| 2.4.1 1 IAEA and 3 external experts | Agency | Expert | HardCore | 18,620 | 2014 | Q3/2014 | Q3/2014
3.2 1.3.2 To strengthen the capability of BNPP personnel in methods and procedures for Plant life management program. | [6 empty] | Q2/2014 | Q2/2014
| 3.2.1 one week TC with 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 53,936 | 2014 | Q2/2014 | Q2/2014
3.6 1.3.6 Scientific Visit on PSI application and evaluation of PSI | [6 empty] | / | /
| 3.6.1 SV1 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014
| 3.6.2 SV2 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014
| 3.6.3 SV3 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014
| 3.6.4 SV4 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014
| 3.6.5 SV5 for one week | Agency | Scientific Visit | HardCore | 3,235 | 2014 | Q1/2014 | Q1/2014
4.2 1.4.2 To assist BNPP-1 in updating the strategic plan for development of training programme | [6 empty] | Q1/2014 | Q1/2014
| 4.2.1 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 18,620 | 2014 | Q1/2014 | Q1/2014
4.3 1.4.3 To assist BNPP-1 in identification of new training needs | [6 empty] | Q2/2014 | Q2/2014
| 4.3.1 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,965 | 2014 | Q2/2014 | Q2/2014
7.2 1.7.2 To support BNPP-1 in updating the documentation of FSS | [6 empty] | / | /
| 7.2.1 1 Agency Expert and 2 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 13,965 | 2014
8.6 1.8.6 To assist NPPD on Strengthening Capabilities for NPP Safety, Performance, Learning from Korea's Experience | [6 empty] | Q2/2014 | Q2/2014
| 8.6.1 One week Meeting with 1 Agency Expert and 2 External Expert | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 17,579 | 2014 | Q2/2014 | Q2/2014
Sub-Total for 2014 |  |  |  |  | 309,549
1.14 1.1.14 Methods of supervision over exploitation of NPP buildings and structures, effects of earthquake on safe operation of NPPs | [6 empty] | Q4/2015 | Q4/2015
| 1.14.1 1 IAEA and 3 external experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 17,979 | 2015 | Q4/2015 | Q4/2015
1.17 1.1.17 To advise BNPP-1 on proven approaches in radioactiove waste management | [6 empty] | Q4/2015 | Q4/2015
| 1.17.1 1 IAEA and 3 external experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 18,620 | 2015 | Q4/2015 | Q4/2015
1.18 1.1.18 To support NPPD/BNPP-1 in Enhancement of on-site and off-site emergency preparedness and response | [6 empty] | / | /
| 1.18.1 1 IAEA and 3 external experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 17,979 | 2015
1.19 1.1.19 To assist BNPP in inspection and Supervision over operation in NPPs and NPP relationship with independent supervisory organizations | [6 empty] | Q2/2015 | Q2/2015
| 1.19.1 1 IAEA and 3 external experts | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 18,620 | 2015 | Q2/2015 | Q2/2015
1.21 1.1.21 To visit NPPs for safety management systems with focus on Rad Waste Management, Radiation Monitoring, Core Calculation and Emergency Preparedness | [6 empty] | Q4/2015 | Q4/2015
| 1.21.1 SV1 for one week | Agency | Scientific Visit | HardCore | 3,315 | 2015 | Q4/2015 | Q4/2015
| 1.21.2 SV2 for one week | Agency | Scientific Visit | HardCore | 3,315 | 2015 | Q4/2015 | Q4/2015
| 1.21.3 SV3 for one week | Agency | Scientific Visit | HardCore | 3,315 | 2015 | Q4/2015 | Q4/2015
| 1.21.4 SV4 for one week | Agency | Scientific Visit | HardCore | 3,315 | 2015 | Q4/2015 | Q4/2015
| 1.21.5 SV5 for one week | Agency | Scientific Visit | HardCore | 3,315 | 2015 | Q4/2015 | Q4/2015
1.24 Ensuring timely technical support to the implementation of project activities | [6 empty] | / | /
| 1.24.2 Expert/consultant assistance (for six months) to ensure technical support and timely delivery of project outputs | Government Cost Sharing (footnote-a/) | Expert | FootNote | 50,000 | 2015
4.4 1.4.4 To support BNPP-1 in updating the BNPP training programmes including initial and continuing training | [6 empty] | Q1/2015 | Q1/2015
| 4.4.1 1 Agency Expert and 3 External Experts | Agency | Expert | HardCore | 18,620 | 2015 | Q1/2015 | Q1/2015
4.5 1.4.5 To support BNPP-1 for updating the BNPP training programmes including initial and continuing training | [6 empty] | / | /
| 4.5.1 1 Agency Expert and 3 External Experts | Agency | Expert | HardCore | 18,620 | 2015
6.3 1.6.3 To assist BNPP-1 in updating the BNPP HRM systems including development necessary documents | [6 empty] | / | /
| 6.3.1 1 Agency Expert and 3 External Experts | Agency | Expert | HardCore | 18,620 | 2015
7.3 1.7.3 To support BNPP-1 for updating the documentation of FSS | [6 empty] | Q1/2015 | Q2/2015
| 7.3.1 1 Agency Expert and 3 External Experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 18,620 | 2015 | Q1/2015 | Q2/2015
Sub-Total for 2015 |  |  |  |  | 214,253
This report was generated on 2016-01-07 10:46:48 by MISHAR, Marina Binti Binti

## IRA2013
15-01-2016
IRA2013: Action Plan for implementation of Workplan activties in 2016-2017
Activity | Input | Implementing Officers | Resoutces | Venue | Type | Date | Status | Comments
1.1 Confirming/Setting-up project team (CP, CP team in MS, PMO/TO)
1.3 Updating project work plan
1.4 Preparing and submitting PPARs (every year end)
1.2 Conducting project review meetings
| 1.2.1 Annual project review and planning meeting will be joint with IRA/2/012 Annual meeting. |  | I IAEA staff for 4 days | Tehran | Meeting | Q1/2016
1.5 IAEA Field Monitoring (once per quarther)
2.2 Preparatory visit for OSART mission
| 2.2.1 Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA | Bushehr | WS | Q4/2016 |  | Need to confirm dates at Annual review meeting Feb 2016
2.4 Implementation the nuclear safety oversight function
| 2.4.1 One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: Derakhshandeh | 1 IAEA+2IEX | Tehran | EM | Q1/2017 |  | NPPD to confrm the need after previous expert mission plus March 2016 follow-up visit
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
| 3.1.1 WS on "modern methods for measuring hydrogen concentration in containment " | IAEA: S. Monti, P. Vincze, NPPD: Deilami | 1 IAEA+3IEX | Bushehr | WS | Q3/2016 |  | NPPD: Q2/2016
3.2 Training on environmental qualification of safety equipment of BNPP-1
| 3.2.1 3 SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Deilami | 1 NEX | TBD | SV | Q3/2016 |  | NPPD: Q4/2016
| 3.2.2 3 SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Deilami | 1 NEX | TBD | SV | Q3/2016 |  | NPPD: Q4/2016
| 3.2.3 3 SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Deilami | 1 NEX | TBD | SV | Q3/2016 |  | NPPD: Q4/2016
3.3 Training on equipment reliability assessment techniqes of equipment during operation
| 3.3.1 WS on "Equipment reliablity assessment techniqes of equipment during operation" | IAEA: K. Kang, NPPD: Deilami | 1 IAEA+3IEX | Bushehr | WS | Q3/2016
3.8 Development of ageing management program for BNPP-1
| 3.8.1 EM on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Tavana? | 1 IAEA+3IEX | Tehran | EM | Q3/2016
3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1
| 3.10.1 WS on "Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Tavana? | 1 IAEA+2IEX | Tehran | WS | Q3/2016 |  | IAEA request further clarification of what NPPD are seeking . NPPD: Q2/2016?
3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1
| 3.13.1 EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Tavana? | 1 IAEA+2IEX | Tehran | EM | Q1/2017 |  | IAEA request further clarification of what NPPD are seeking. NPPD: Q4/2016?
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
| 3.14.1 EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted in project IRA 2 011) | IAEA: P. Vincze, P. Tarren, NPPD: Tavana? | 1 IAEA+2IEX | Tehran | EM | Q4/2016
| 3.14.2 EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; C.Hill, , NPPD: Tavana? | 1 IAEA+2 IEX | Tehran | EM | Q2/2017
5.5 Assistance in development of selected training scenarios for severe accidents in FSS
| 5.5.1 EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: Vincze, NPPD: Talebianzadeh | 1 IAEA+2IEX | Bushehr | EM | Q3/2016 |  | NPPD: to be implemented after 6.3.1
5.6 Assistance in development & improvement of training system of maintenance & repair personnel
| 5.6.1 EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: Vincze, NPPD: Talebianzadeh | 1IAEA+2IEX |  | EM | Q4/2016
6.1 Asistance in review of BNPP-1 off-site emergency preparedness and response
| 6.1.1 WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA: P. Salinas, NPPD: Abbaspour | 1IAEA+2IEX |  | WS | Q4/2016 |  | NPPD: Training on off-site response to radiological emergency situation BNPP-1?
6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1
| 6.3.1 WS on Severe Accident (SA) Analysis of BNPP-1 | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | WS | Q4/2016 |  | IAEA: Q1/2017. New date assumes NPPD want computer code based activity. If theoretical presentation is sufficient IAEA is already running a WS in Feb 2016 for INRA that NPPD may be able to attend.
7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1
| 7.3.1 EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening?, NPPD: Abbaspour | 1IAEA+3IEX |  | EM | Q2/2016 |  | IAEA: who will provide tools for measurements?, are the high activity sources gamma sources?
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
| 7.4.1 Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: D. Talleria, NPPD: | Procurement |  | 100,000 | 2016
2.3 Implementation of OSART mission
| 2.3.1 15 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour | 3IAEA+12IEX for 15 days |  | 90,000 | Q4/2017 |  | IAEA: Confirmation at the meeting in February 2016
2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers
| 2.5.1 EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | EM | Q1/2017 |  | NPPD: Q2/2016
2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission
| 2.7.1 Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q1 2017( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1-2 NEX |  | FS | 2017
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
| 3.1.2 WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: P. Vincze, P. Tarren, NPPD: | 1 IAEA+2IEX |  | WS | Q2/2017
3.4 Training on containment leakage tests and calculations after outage
| 3.4.1 4 SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: | 1NEX |  | SV | Q2/2017
| 3.4.2 4 SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: | 1NEX |  | SV | Q2/2017
| 3.4.3 4 SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: | 1NEX |  | SV | Q2/2017
| 3.4.4 4 SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: | 1NEX |  | SV | Q2/2017
3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system
| 3.5.1 4 SV on "Decreasing the time response of APCS system" | IAEA; J. Eiler, NPPD: | 1 NEX |  | SV | Q1/2017
| 3.5.2 4 SV on "Decreasing the time response of APCS system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | SV | Q1/2017
| 3.5.3 4 SV on "Decreasing the time response of APCS system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | SV | Q1/2017
| 3.5.4 4 SV on "Decreasing the time response of APCS system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | SV | Q1/2017
3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR
| 3.6.1 WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: | 1IAEA+3IEX |  | WS | Q1/2017
3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles
| 3.7.1 EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: C. Hill, NPPD: | 1IAEA+2IEX |  | EM | Q1/2017
3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system
| 3.9.1 WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests, High and low cycle fatigue analysis for strength assessment of Reactor Coolant System | IAEA: K. Kang, NPPD: | 1IAEA+2IEX |  | WS | Q3/2017
3.12 Assistance in performing the living PSA of the BNPP-1
| 3.12.1 EM to review the progress in development the data bank for living PSA of the BNPP-1 | IAEA: I Kuzmina, NPPD: | 1IAEA+2IEX |  | EM | Q1/2017
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
| 3.14.2 EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel, ( 1 IAEA + 2 IEX) | IAEA: C. Hill, NPPD: | 1IAEA+2IEX |  | EM | Q2/2017
4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
| 4.1.1 EM on "modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes " in Q1 2017, (1 IAEA +3 IEX ) | IAEA: H. Varjonen, NPPD: | 1IAEA+3IEX |  | EM | Q1/2017
4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
| 4.6.1 EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" ( 1 IAEA + 3 IEX) | IAEA:H. Varjonen, NPPD: | 1IAEA+3IEX |  | EM | Q2/2017
5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
| 5.1.1 WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: P. Vincze?, NPPD: | 1IAEA+2IEX |  | WS | Q1/2017
5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
| 5.2.1 3 Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: P. Vincze?, NPPD: | 1 NEX |  | SV | Q2/2017
| 5.2.2 3 Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: P. Vincze?, NPPD: | 1 NEX |  | SV | Q2/2017
| 5.2.3 3 Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: P. Vincze?, NPPD: | 1 NEX |  | SV | Q2/2017
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
| 7.4.2 EM on "Review and assesment of results of environmental monitoring programme using the software ESTE" | IAEA: D. Talleria, NPPD: | 1 IAEA+2IEX |  | EM | Q4/2017

## IRA9023
Activity | Input | Input Type | Sub Type | Funding | Budget | Budget Year | Start | End
1.1 Confirming/Setting-up project team (CP, CP team in MS, PMO/TO) | [6 empty] | / | /
0
1.2 Conducting project review meetings | [6 empty] | / | /
0
1.5 IAEA Field Monitoring | [6 empty] | / | /
0
1.4 Preparing and submitting PPARs (every six months) | [6 empty] | Q2/2016 | Q2/2016
| 1.4.1 PPAR from 1/1/2016 to 30/6/2016 | Local Cost (MS) | Subcontract |  | 500 | 2016 | Q2/2016 | Q2/2016
| 1.4.2 PPAR from 30/6/2016 to 30/12/2016 | Local Cost (MS) | Subcontract |  | 500 | 2016 | Q4/2016 | Q4/2016
| 1.4.9 Counterpart review with Agency team regarding TC project and its progress | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 3,000 | 2016 | Q2/2016 | Q2/2016
2.1 Development of commissioning and operation schedules. | [6 empty] | Q4/2016 | Q4/2016
| 2.1.1 Development of commissioning and operation schedules | Local Cost (MS) | Subcontract |  | 3,600 | 2016 | Q4/2016 | Q4/2016
2.2 Development of final site characterization report | [6 empty] | Q2/2016 | Q1/2017
| 2.2.1 Development of final site characterization report by member state team | Local Cost (MS) | Subcontract |  | 7,200 | 2016 | Q2/2016 | Q1/2017
| 2.2.2 Review and assistances for activity's No.: 2.2-2.8-2.9 | Agency | Expert | HardCore | 5,000 | 2016 | Q3/2016 | Q4/2016
2.3 Development of QAP for Operation | [6 empty] | Q2/2016 | Q1/2017
| 2.3.1 Development of QAP for Operation(record keeping included) | Local Cost (MS) | Subcontract |  | 7,200 | 2016 | Q2/2016 | Q1/2017
| 2.3.2 Training/Assistances through scientific visit for the Development of QAP Operation | Agency | Scientific Visit | HardCore | 3,000 | 2016 | Q3/2016 | Q4/2016
2.4 Development of all operational procedures | [6 empty] | Q2/2016 | Q1/2017
| 2.4.1 Development of all operational procedures | Local Cost (MS) | Subcontract |  | 28,800 | 2016 | Q2/2016 | Q1/2017
| 2.4.2 Training/Assistances through scientific visit for Development of all operational procedures including those related to waste handling and placing, crane and vehicle normal and accident procedures | Agency | Scientific Visit | HardCore | 3,000 | 2016 | Q3/2016 | Q4/2016
2.5 Development of training and qualification program | [6 empty] | Q2/2016 | Q1/2017
| 2.5.1 Development of training and qualification program | Local Cost (MS) | Subcontract |  | 7,200 | 2016 | Q2/2016 | Q1/2017
2.6 Development of emergency preparedness program | [6 empty] | Q2/2016 | Q1/2017
| 2.6.1 Development of emergency preparedness program | Local Cost (MS) | Subcontract |  | 7,200 | 2016 | Q2/2016 | Q1/2017
| 2.6.2 Training/Assistances through scientific visit for the development of the emergency preparedness program | Agency | Scientific Visit | HardCore | 3,000 | 2016 | Q3/2016 | Q4/2016
2.7 Development of radiation protection program | [6 empty] | Q2/2016 | Q1/2017
| 2.7.1 Development of radiation protection program and its related procedures, checklists and forms | Local Cost (MS) | Subcontract |  | 14,400 | 2016 | Q2/2016 | Q1/2017
| 2.7.2 Training/Assistances through scientific visit for the development of the radiation protection program and its related procedures, checklists and forms | Agency | Scientific Visit | HardCore | 3,000 | 2016 | Q3/2016 | Q4/2016
2.8 Development of the Final Safety Assessment report (safety case) | [6 empty] | Q2/2016 | Q1/2017
| 2.8.1 Development of final safety assessment report(safety case) | Local Cost (MS) | Subcontract |  | 7,200 | 2016 | Q2/2016 | Q1/2017
| 2.8.2 Review and assistances for activity's No.: 2.2-2.8-2.9 (This input is the same as input No: 2.2.2 that is meant 1 expert for each activity (3 expert total)at the same time) | Agency | Expert | HardCore | 5,000 | 2016 | Q3/2016 | Q4/2016
2.9 Development of Environmental Impact Assessment | [6 empty] | Q2/2016 | Q1/2017
| 2.9.1 Development of environmental impact assessment | Local Cost (MS) | Subcontract |  | 7,200 | 2016 | Q2/2016 | Q1/2017
| 2.9.2 Expert mission to support the Review of the environmental impact assessment | Agency | Expert | HardCore | 5,000 | 2016 | Q3/2016 | Q4/2016
2.10 Trench operation | [6 empty] | Q3/2016 | Q4/2016
| 2.10.2 Training/Assistances through scientific visit for the Trench Operation | Agency | Scientific Visit | HardCore | 3,000 | 2016 | Q3/2016 | Q4/2016
3.1 Borehole concept phase | [6 empty] | Q2/2016 | Q2/2016
| 3.1.1 Development of borehole concept phase documents including schedule, WAC for borehole, techno-economic study and inventory | Local Cost (MS) | Subcontract |  | 27,000 | 2016 | Q2/2016 | Q2/2016
| 3.1.2 Review of documents prepared for concept phase | Agency | Meeting | HardCore | 16,000 | 2016 | Q3/2016 | Q3/2016
3.2 Borehole siting phase | [6 empty] | Q1/2016 | Q1/2016
| 3.2.1 development of planning document | Local Cost (MS) | Subcontract |  | 1,800 | 2016 | Q1/2016 | Q1/2016
| 3.2.2 Geography, Demography and Socioeconomically properties of TALMESI Site | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q2/2016 | Q2/2016
| 3.2.3 Topography and Geomorphology of TALMESI Site | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q2/2016 | Q2/2016
| 3.2.4 Surface and Subsurface Geology of TALMESI and evaluation of geological stability | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q2/2016 | Q2/2016
| 3.2.5 Tectonic, Seismicity and seismic hazard analysis | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q2/2016 | Q2/2016
| 3.2.6 Meteorological data based on TALMESI weather station | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q3/2016 | Q3/2016
| 3.2.7 Geophysical Investigations | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q3/2016 | Q3/2016
| 3.2.8 Geochemistry and Radionuclide Transport Capability of TALMESI Soil and Rocks | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q3/2016 | Q3/2016
| 3.2.9 Hydrology(surface water resources , Runoff and Floodwater) | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q4/2016 | Q4/2016
| 3.2.10 Hydrogeology and evaluation of subsurface streams and Aquifers | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q4/2016 | Q4/2016
| 3.2.11 Borehole Drilling for detailed information | Local Cost (MS) | Subcontract |  | 50,000 | 2016 | Q4/2016 | Q4/2016
| 3.2.12 Evaluation Geo mechanical properties of rocks | Local Cost (MS) | Subcontract |  | 4,200 | 2016 | Q4/2016 | Q4/2016
| 3.2.13 Assessment of erosion rate | Local Cost (MS) | Subcontract |  | 14,400 | 2016 | Q2/2016 | Q4/2016
| 3.2.14 Land Usage and Environmental Data | Local Cost (MS) | Subcontract |  | 9,600 | 2016 | Q2/2016 | Q4/2016
| 3.2.15 Preparation of Thematic Maps as GIS layers and Integration to Select the Best Location for Borehole Disposal | Local Cost (MS) | Subcontract |  | 9,600 | 2016 | Q2/2016 | Q4/2016
3.3 Borehole Basic design phase | [6 empty] | Q2/2016 | Q4/2016
| 3.3.1 Safety Requirements and Acceptance Criteria for Engineering Design of the Borehole Disposal | Local Cost (MS) | Subcontract |  | 4,800 | 2016 | Q2/2016 | Q4/2016
| 3.3.2 Safety Requirements and Acceptance Criteria for Hazard and accident Analysis;Fire Fighting Safety Philosophy in the Borehole Disposal | Local Cost (MS) | Subcontract |  | 4,800 | 2016 | Q2/2016 | Q4/2016
| 3.3.3 Non- Radiological Safety of Waste Container(cask/pipe) Transportation | Local Cost (MS) | Subcontract |  | 4,800 | 2016 | Q2/2016 | Q4/2016
| 3.3.4 Radioactive Waste Transportation Safety Requirement and Regulations;Radioactive Sources List;Radiological Design Report of Waste Container for Transportation | Local Cost (MS) | Subcontract |  | 4,800 | 2016 | Q2/2016 | Q4/2016
| 3.3.5 Radiation Protection Codes, Standards and Regulation;Consideration of Radiation Protection Principles;Radioactivity Releases: Regulations, Design Criteria;Radiation Protection and Shielding Requirements | Local Cost (MS) | Subcontract |  | 4,800 | 2016 | Q2/2016 | Q4/2016
| 3.3.6 Preparation of a Shielding Database;Hazardous Area Classification;Radiation Protection Program | Local Cost (MS) | Subcontract |  | 4,800 | 2016 | Q2/2016 | Q4/2016
4.1 Surveillance and Environmental Monitoring of Repository Site | [6 empty] | Q1/2016 | Q4/2016
| 4.1.4 Environmental Sample Analysis: Purchasing of an Alpha Spectrometer in addition to standard calibration sources and Tracers, sample preparation equipment (including of microwave digestion ovens and electro deposition installations) | Donor extrabudgetary contribution (footnote-a/) | Procurement | FootNote | 35,000 | 2016 | Q1/2016 | Q4/2016
| 4.1.5 Training on Gamma Spectroscopy for 2 persons. | Government Cost Sharing (footnote-a/) | Fellowship | FootNote | 8,100 | 2016 | Q2/2016 | Q2/2016
| 4.1.6 Training course of Alpha-Beta Spectroscopy for 2 persons. | Government Cost Sharing (footnote-a/) | Fellowship | FootNote | 8,100 | 2016 | Q2/2016 | Q3/2016
| 4.1.8 Training/Assistance through scientific visit for surveillance and environmental monitoring of the Repository site | Agency | Scientific Visit | HardCore | 3,000 | 2016 | Q1/2016 | Q3/2016
| 4.1.10 Training/Assistance through scientific visit of Individual and Environmental Monitoring procedure and equipment of a near surface repository site. | Agency | Scientific Visit | HardCore | 3,000 | 2016 | Q3/2016 | Q3/2016
| 4.1.11 Development of On-line and Off-Line Air (Gases-Aerosols) Monitoring Document | Local Cost (MS) | Subcontract |  | 600 | 2016 | Q1/2016 | Q1/2016
| 4.1.12 Development of a comprehensive monitoring program (including water, air, vegetation, soil, etc...) | Local Cost (MS) | Subcontract |  | 2,000 | 2016 | Q1/2016 | Q2/2016
| 4.1.13 Development of a comprehensive monitoring program including environmental dose rate measurements (online or/and offline) | Local Cost (MS) | Subcontract |  | 600 | 2016 | Q1/2016 | Q1/2016
| 4.1.14 Review of On-Line and Off-Line External Radiation Dosimetry, Air (Gases-Aerosols) Monitoring And Environmental Sample Analysis (Food and Feedstuffs, Terrestrial and Aquatic media) Documents | Agency | Meeting | HardCore | 10,000 | 2016 | Q1/2016 | Q1/2016
4.2 Surveillance and Individual Monitoring at Repository Site | [6 empty] | Q2/2016 | Q3/2016
| 4.2.1 Development of Individual Monitoring of Internal and External Exposure Documents. | Local Cost (MS) | Subcontract |  | 1,200 | 2016 | Q2/2016 | Q3/2016
| 4.2.2 Review of Individual Monitoring of Internal and External Exposure Documents. | Agency | Expert | HardCore | 5,000 | 2016 | Q2/2016 | Q4/2016
Sub-Total for 2016 |  |  |  |  | 399,800
1.3 Updating project work plan | [6 empty] | Q1/2017 | Q1/2017
| 1.3.1 TO's mission to Iran for updating the workplan | Agency | Expert | HardCore | 3,000 | 2017 | Q1/2017 | Q1/2017
| 1.3.2 Expert from agency travel to Iran for updating the workplan | Government Cost Sharing (footnote-a/) | Expert | FootNote | 3,000 | 2017 | Q1/2017 | Q1/2017
1.4 Preparing and submitting PPARs (every six months) | [6 empty] | Q2/2017 | Q2/2017
| 1.4.3 PPAR from 1/1/2017 to 30/6/2017 | Local Cost (MS) | Subcontract |  | 500 | 2017 | Q2/2017 | Q2/2017
| 1.4.4 PPAR from 30/6/2017 to 30/12/2017 | Local Cost (MS) | Subcontract |  | 500 | 2017 | Q4/2017 | Q4/2017
2.10 Trench operation | [6 empty] | Q4/2017 | Q4/2017
| 2.10.1 Disposal operation including trench preparation, waste emplacement, backfilling and capping | Local Cost (MS) | Subcontract |  | 300,000 | 2017 | Q4/2017 | Q4/2017
2.11 International Peer Review of the disposal programme | [6 empty] | Q3/2016 | Q3/2016
| 2.11.1 International peer review of all documents for trench operational phase | Agency | Meeting | HardCore | 20,000 | 2017 | Q3/2016 | Q3/2016
3.2 Borehole siting phase | [6 empty] | Q1/2017 | Q1/2017
| 3.2.16 Preliminary Safety assessment for Selected Borehole | Local Cost (MS) | Subcontract |  | 5,400 | 2017 | Q1/2017 | Q1/2017
| 3.2.17 Fellowship Training for Preliminary Safety assessment for Selected Borehole (software training) | Agency | Fellowship | HardCore | 5,400 | 2017 | Q1/2017 | Q1/2017
| 3.2.18 Document submitting for siting license | Local Cost (MS) | Subcontract |  | 5,400 | 2017 | Q2/2017 | Q2/2017
| 3.2.19 Meeting to review documents for sitting license | Government Cost Sharing (footnote-a/) | Meeting | FootNote | 10,000 | 2017 | Q1/2017 | Q2/2017
3.3 Borehole Basic design phase | [6 empty] | Q1/2017 | Q2/2017
| 3.3.7 Review of basic design documents | Agency | Meeting | HardCore | 10,000 | 2017 | Q1/2017 | Q2/2017
3.4 Borehole design phase | [6 empty] | Q1/2017 | Q3/2017
| 3.4.1 Ecology;Regional Historic, Archaeological, Architectural, Scenic, Cultural, and Natural Landmarks;Socioeconomics | Local Cost (MS) | Subcontract |  | 16,200 | 2017 | Q1/2017 | Q3/2017
| 3.4.2 Transportation and handling(including transportation safety assessment, radiation program, quality assurance and emergency program) | Local Cost (MS) | Subcontract |  | 5,400 | 2017 | Q1/2017 | Q3/2017
| 3.4.3 EIA Development;Short-term and Long-Term Environmental Effects;Environmental Effects of Accidents;Environmental Measurements and Monitoring Programs;Prevention, Mitigation and control methods for each of environmental negative consequences | Local Cost (MS) | Subcontract |  | 16,200 | 2017 | Q1/2017 | Q3/2017
| 3.4.4 Temporary Storage Building and Borehole Disposal Preliminary Safety Assessment Report (PSAR) | Local Cost (MS) | Subcontract |  | 10,800 | 2017 | Q1/2017 | Q3/2017
| 3.4.5 Temporary Storage Building and Borehole Disposal Radiation Protection Program (RPP) | Local Cost (MS) | Subcontract |  | 10,800 | 2017 | Q1/2017 | Q3/2017
| 3.4.6 Temporary Storage Building and Borehole Disposal Emergency Preparedness;Decommissioning Strategy; | Local Cost (MS) | Subcontract |  | 10,800 | 2017 | Q1/2017 | Q3/2017
| 3.4.7 Borehole disposal post closure safety assessment | Local Cost (MS) | Subcontract |  | 10,800 | 2017 | Q1/2017 | Q3/2017
| 3.4.8 Design of temporary storage of spent radioactive sources;Design of capsules and containers for spent radioactive sources;Design of the conditioning area for spent radioactive sources;Design of welding system and hotcell; | Local Cost (MS) | Subcontract |  | 27,000 | 2017 | Q1/2017 | Q3/2017
| 3.4.9 Evaluation of host layer and determination of dimensions (depth, thickness and diameter) of boreholes;Design of repository area and spacing, number and other requirements;Backfill materials and Engineering barrier System and suitable casing | Local Cost (MS) | Subcontract |  | 27,000 | 2017 | Q1/2017 | Q3/2017
| 3.4.10 review of Final Borehole Design and document submit for design license | Agency | Meeting | HardCore | 16,000 | 2017 | Q4/2017 | Q4/2017
4.1 Surveillance and Environmental Monitoring of Repository Site | [6 empty] | Q1/2017 | Q2/2017
| 4.1.16 To purchase On-Line and Off-Line Air (Gases-Aerosols) Monitoring Instruments and Equipment in addition to their related Software including of a network of online Air Monitoring (Air Sampling Station) and portable volume Air Sampler Pomp+Filters. | Donor extrabudgetary contribution (footnote-a/) | Procurement | FootNote | 30,000 | 2017 | Q1/2017 | Q2/2017
4.2 Surveillance and Individual Monitoring at Repository Site | [6 empty] | Q1/2017 | Q3/2017
| 4.2.5 Training/Assistance through scientific visit for surveillance and individual monitoring of the Repository site | Agency | Scientific Visit | HardCore | 3,000 | 2017 | Q1/2017 | Q3/2017
4.3 Record Keeping | [6 empty] | Q1/2016 | Q2/2016
| 4.3.2 To Purchase barcode equipment and required materials for waste repository workplace, portable barcode reader with support from the provider and software services. | Local Cost (MS) | Procurement |  | 6,000 | 2017 | Q1/2016 | Q2/2016
Sub-Total for 2017 |  |  |  |  | 553,200
1.3 Updating project work plan | [6 empty] | Q1/2018 | Q1/2018
| 1.3.3 Counterpart travel to agency in order to review/update workplan | Agency | Scientific Visit | HardCore | 2,400 | 2018 | Q1/2018 | Q1/2018
1.4 Preparing and submitting PPARs (every six months) | [6 empty] | Q2/2018 | Q2/2018
| 1.4.5 PPAR from 1/1/2018 to 30/6/2018 | Local Cost (MS) | Subcontract |  | 500 | 2018 | Q2/2018 | Q2/2018
| 1.4.6 PPAR from 30/6/2018 to 30/12/2018 | Local Cost (MS) | Subcontract |  | 500 | 2018 | Q4/2018 | Q4/2018
3.5 Borehole construction phase | [6 empty] | Q4/2017 | Q3/2018
| 3.5.1 Construction of temporary storage of spent radioactive sources | Local Cost (MS) | Subcontract |  | 50,000 | 2018 | Q4/2017 | Q3/2018
| 3.5.2 Manufacture of capsules and containers for spent radioactive sources | Local Cost (MS) | Subcontract |  | 30,000 | 2018 | Q4/2017 | Q3/2018
| 3.5.3 Preparation of the process of welding and fabrication conditioning area for spent radioactive sources | Local Cost (MS) | Subcontract |  | 15,000 | 2018 | Q4/2017 | Q3/2018
| 3.5.4 Borehole construction | Local Cost (MS) | Subcontract |  | 50,000 | 2018 | Q4/2017 | Q3/2018
| 3.5.5 Equipment and instrument purchasing for the Borehole construction phase | Local Cost (MS) | Procurement |  | 30,000 | 2018 | Q1/2018 | Q3/2018
| 3.5.6 2 experts for inspecting and reviewing the whole construction phase | Agency | Expert | HardCore | 14,000 | 2018 | Q3/2018 | Q4/2018
| 3.5.7 Equipment and instrument purchasing | Local Cost (MS) | Subcontract |  | 40,000 | 2018 | Q1/2018 | Q3/2018
4.1 Surveillance and Environmental Monitoring of Repository Site | [6 empty] | Q1/2018 | Q4/2018
| 4.1.2 Environmental Sample Analysis: Purchasing of the low-level Background Liquid scintillation Counter in addition to tracers and standard solution, Scintillation cocktail suitable for alpha/beta separation. | Donor extrabudgetary contribution (footnote-a/) | Procurement | FootNote | 50,000 | 2018 | Q1/2018 | Q4/2018
| 4.1.7 Training/Assistance through scientific visit for surveillance and environmental monitoring of the Repository site | Agency | Scientific Visit | HardCore | 3,000 | 2018 | Q1/2018 | Q2/2018
| 4.1.9 Expert support for Quality Management | Agency | Expert | HardCore | 5,000 | 2018 | Q2/2018 | Q2/2018
| 4.1.15 To Purchase online external radiation monitor Instruments and Equipment in addition to their related Software for including of a network of online dosimeters, Portable survey meters (GM or Scintillation dose monitor, In-situ gamma spectrometer) | Local Cost (MS) | Procurement |  | 30,000 | 2018 | Q1/2018 | Q2/2018
4.2 Surveillance and Individual Monitoring at Repository Site | [6 empty] | Q2/2018 | Q2/2018
| 4.2.4 Training course of Radiation Protection in repository site, External and Internal Dosimetry including practical workshop. | Agency | Training Course | HardCore | 7,000 | 2018 | Q2/2018 | Q2/2018
4.3 Record Keeping | [6 empty] | Q2/2018 | Q3/2018
| 4.3.1 To send an Expert to check our Record Keeping software. | Agency | Expert | HardCore | 5,000 | 2018 | Q2/2018 | Q3/2018
| 4.3.3 training course of administration of software which is used in record keeping | Agency | Training Course | HardCore | 7,000 | 2018 | Q1/2018 | Q2/2018
Sub-Total for 2018 |  |  |  |  | 339,400
1.3 Updating project work plan | [6 empty] | Q1/2019 | Q1/2019
| 1.3.4 TO's mission to Iran in order to review/update the workplan | Agency | Expert | HardCore | 4,000 | 2019 | Q1/2019 | Q1/2019
1.4 Preparing and submitting PPARs (every six months) | [6 empty] | Q2/2019 | Q2/2019
| 1.4.7 PPAR from 1/1/2019 to 30/6/2019 | Local Cost (MS) | Subcontract |  | 500 | 2019 | Q2/2019 | Q2/2019
| 1.4.8 PPAR from 30/6/2019 to 30/12/2019 | Local Cost (MS) | Subcontract |  | 500 | 2019 | Q4/2019 | Q4/2019
4.1 Surveillance and Environmental Monitoring of Repository Site | [6 empty] | Q1/2019 | Q4/2019
| 4.1.1 Environmental Sample Analysis: Purchasing of the high resolution gamma spectrometer system including of HPGe detector, Shielding, Software and Mixed Reference Gamma sources (Liquid, soil, sediment, Vegetation, Animal). | Agency | Procurement | HardCore | 90,000 | 2019 | Q1/2019 | Q4/2019
| 4.1.3 Environmental Sample Analysis: Purchasing of the low-level gross Alpha-Beta counter including of a gas flow proportional counter and standard calibration sources. | Agency | Procurement | HardCore | 50,000 | 2019 | Q1/2019 | Q4/2019
4.2 Surveillance and Individual Monitoring at Repository Site | [6 empty] | Q1/2019 | Q4/2019
| 4.2.3 To Purchase Individual Monitoring of Internal and External Exposure Equipment including of a network of online dosimeters, Air sampler piping+Pomp+Filter, Personal dosimeter, TLD, Film Badge, Portal Radon Monitor, Whole Body and Hand & Foot Monitor. | Donor extrabudgetary contribution (footnote-a/) | Procurement | FootNote | 45,000 | 2019 | Q1/2019 | Q4/2019
Sub-Total for 2019 |  |  |  |  | 190,000
This report was generated on 2016-01-07 10:43:34 by MISHAR, Marina Binti Binti

## IRA9024
Activity | Input | Input Type | Sub Type | Funding | Budget | Budget Year | Start | End
1.1 Confirming/Setting-up project team (CP, CP team in MS, PMO/TO) | [6 empty] | / | /
0
1.2 Conducting project review meetings | [6 empty] | / | /
0
1.3 Updating project work plan | [6 empty] | / | /
0
1.4 Preparing and submitting PPARs (every six months) | [6 empty] | / | /
0
1.5 IAEA Field Monitoring | [6 empty] | / | /
0
3.2 Reviewing INRA’s review and assessment of submitted documents for Research Reactor (RR) | [6 empty] | / | /
0
5.2 Strengthening regulatory control for protecting workers, public and environment during radiation practices/applications | [6 empty] | / | /
0
2.1 Reviewing INRA’s updated / new regulations and regulatory guides for NPP | [6 empty] | Q1/2016 | Q1/2016
| 2.1.1 Expert Mission to review INRA’s regulations on design and construction for NPPs. Duration of this EM will be around 5days within the period of first quarter of 2016 by one experts | Agency | Expert | HardCore | 5,000 | 2016 | Q1/2016 | Q1/2016
| 2.1.2 Expert Mission to review INRA’s regulations on design and construction for NPPs. Duration of this EM will be around 5days within the period of first quarter of 2016 by one experts | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2016 | Q1/2016 | Q1/2016
2.2 Reviewing INRA’s updated / new regulations and regulatory guides for Research Reactor (RR) | [6 empty] | Q4/2016 | Q4/2016
| 2.2.1 Expert Mission to review INRA’s regulations on Licensing process for RRs. Duration of this EM will be around 5days within the period of fourth quarter of 2016 by 1 experts | Agency | Expert | HardCore | 5,000 | 2016 | Q4/2016 | Q4/2016
| 2.2.2 Expert Mission to review INRA’s regulations on Licensing process for RRs. Duration of this EM will be around 5days within the period of fourth quarter of 2016 by 1 expert | Agency | Expert | HardCore | 5,000 | 2016 | Q4/2016 | Q4/2016
| 2.2.3 Expert Mission to review INRA’s regulations on design and construction for RRs. Duration of this EM will be around 5days within the period of first quarter of 2016 by one expert | Agency | Expert | HardCore | 5,000 | 2016 | Q1/2016 | Q1/2016
| 2.2.4 Expert Mission to review INRA’s regulations on design and construction for RRs. Duration of this EM will be around 5days within the period of first quarter of 2016 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2016 | Q1/2016 | Q1/2016
2.3 Reviewing INRA’s updated / new regulations and regulatory guides for Radioactive Waste and / or spent fuel Management | [6 empty] | Q1/2016 | Q1/2016
| 2.3.1 Expert Mission to review INRA’s regulations on Licensing process for Near Surface Radioactive Waste Disposal Facility. Duration of this EM will be around 5days within the period of first quarter of 2016 by one expert | Agency | Expert | HardCore | 5,000 | 2016 | Q1/2016 | Q1/2016
| 2.3.2 Expert Mission to review INRA’s regulations on Licensing process for Near Surface Radioactive Waste Disposal Facility. Duration of this EM will be around 5days within the period of first quarter of 2016 by two expert | Agency | Expert | HardCore | 5,000 | 2016 | Q1/2016 | Q1/2016
2.4 Reviewing INRA’s updated / new regulations and regulatory guides and procedures for NPPs, RR and Radioactive Waste Management | [6 empty] | Q2/2016 | Q2/2016
| 2.4.1 Expert Mission to review INRA’s regulations on site evaluation for nuclear facilities. Duration of this EM will be around 5days within the period of second quarter of 2016 by one expert | Agency | Expert | HardCore | 5,000 | 2016 | Q2/2016 | Q2/2016
| 2.4.2 Expert Mission to review INRA’s regulations on site evaluation for nuclear facilities. Duration of this EM will be around 5days within the period of second quarter of 2016 by one expert | Agency | Expert | HardCore | 5,000 | 2016 | Q2/2016 | Q2/2016
5.1 Strengthening regulatory control for protecting workers, public and environment during normal operation and emergency situations of NPPs, RR and Radioactive Waste Management | [6 empty] | Q1/2016 | Q1/2016
| 5.1.4 Expert Mission to review INRA’s regulations on radiological environmental impact assessment for Nuclear Facilities. Duration of this EM will be around 5days within the period of first quarter of 2016 by one expert | Agency | Expert | HardCore | 5,000 | 2016 | Q1/2016 | Q1/2016
| 5.1.5 Expert Mission to review INRA’s regulations on radiological environmental impact assessment for Nuclear Facilities.Duration of this EM will be around 5days within the period of first quarter of 2016 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2016 | Q1/2016 | Q1/2016
| 5.1.6 Expert Mission to review INRA’s regulations on radiological environmental impact assessment for Nuclear Facilities.Duration of this EM will be around 5days within the period of first quarter of 2016 by expert | Agency | Expert | HardCore | 5,000 | 2016 | Q1/2016 | Q1/2016
| 5.1.7 Workshop on use of safety assessment computer codes for modeling and dispersion of radioactive material in the atmosphere environment. Duration of this WS will be around 5days within the period of first quarter of 2016 by 3 experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 10,500 | 2016 | Q1/2016 | Q1/2016
| 5.1.8 Workshop on Radon Survey and Radon Measurement Methods and Risk Assessment. Duration of this WS will be around 5days within the period od first quarter of 2016 by 2 experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2016 | Q1/2016 | Q1/2016
| 5.1.11 Workshop on Patient Dose Evaluation. Duration of this WS will be around 5days within the period of fourth quarter of 2016 by 2 experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2016 | Q4/2016 | Q4/2016
| 5.1.12 Workshop on Licensing of Cyclotron and Irradiation Facilities. Duration of this WS will be around 5days within the period of first quarter of 2016 by two experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2016 | Q1/2016 | Q1/2016
6.1 Improving regulatory competence for adequate safety control of the national programme for NPP, RRs and Radioactive Waste Management and Disposal Facilities | [6 empty] | Q2/2016 | Q2/2016
| 6.1.7 Workshop on SSAC. Duration of this WS will be around 2 weeks within the period of first quarter of 2016 by 4 experts. | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 39,200 | 2016 | Q2/2016 | Q2/2016
Sub-Total for 2016 |  |  |  |  | 135,700
2.1 Reviewing INRA’s updated / new regulations and regulatory guides for NPP | [6 empty] | Q2/2017 | Q2/2017
| 2.1.3 Expert Mission to review INRA’s regulations on commissioning and operation for NPPs. Duration of this EM will be around 5days within the period of second quarter of 2017 by 1 expert | Agency | Expert | HardCore | 5,000 | 2017 | Q2/2017 | Q2/2017
| 2.1.4 Expert Mission to review INRA’s regulations on commissioning and operation for NPPs. Duration of this EM will be around 5days within the period of second quarter of 2017 by 1 expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q2/2017 | Q2/2017
2.2 Reviewing INRA’s updated / new regulations and regulatory guides for Research Reactor (RR) | [6 empty] | Q2/2017 | Q2/2017
| 2.2.5 Expert Mission to review INRA’s regulations on commissioning, operation and extension of operation for RRs. Duration of this EM will be around 5days within the period of second quarter of 2017 by one expert | Agency | Expert | HardCore | 5,000 | 2017 | Q2/2017 | Q2/2017
| 2.2.6 Expert Mission to review INRA’s regulations on commissioning, operation and extension of operation for RRs. Duration of this EM will be around 5days within the period of second quarter of 2017 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q2/2017 | Q2/2017
2.3 Reviewing INRA’s updated / new regulations and regulatory guides for Radioactive Waste and / or spent fuel Management | [6 empty] | Q2/2017 | Q2/2017
| 2.3.3 Expert Mission to review INRA’s regulations on licensing process for spent fuel Management. Duration of this EM will be around 5days within the period of second quarter of 2017 by one expert | Agency | Expert | HardCore | 5,000 | 2017 | Q2/2017 | Q2/2017
| 2.3.4 Expert Mission to review INRA’s regulations on licensing process for spent fuel Management. Duration of this EM will be around 5days within the period of second quarter of 2017 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q2/2017 | Q2/2017
2.4 Reviewing INRA’s updated / new regulations and regulatory guides and procedures for NPPs, RR and Radioactive Waste Management | [6 empty] | Q3/2017 | Q3/2017
| 2.4.3 Expert Mission to review INRA’s regulations on Licensing process | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q3/2017 | Q3/2017
| 2.4.4 Expert Mission to review INRA’s regulations on Licensing process for fuel cycle facilities. Duration of this EM will be around 5days within the period of third quarter of 2017 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q3/2017 | Q3/2017
3.1 Reviewing INRA’s review and assessment of submitted documents for WWER | [6 empty] | Q4/2017 | Q4/2017
| 3.1.1 Expert Mission to review INRA’s standard review plan on how to review and assess submitted documents of WWER. Duration of this EM will be around 5days within the period of fourth quarter of 2017 by one expert | Agency | Expert | HardCore | 5,000 | 2017 | Q4/2017 | Q4/2017
| 3.1.2 Expert Mission to review INRA’s standard review plan on how to review and assess submitted documents of WWER. Duration of this EM will be around 5days within the period of fourth quarter of 2017 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q4/2017 | Q4/2017
| 3.1.3 Expert Mission to assist INRA to review and assessment of selected SAR chapters of new BNPP. Duration of this EM will be around 5 days in 2017 by one expert | Agency | Expert | HardCore | 5,000 | 2017 | Q2/2017 | Q2/2017
| 3.1.4 Expert Mission to assist INRA to review and assessment of selected SAR chapters of new BNPP. Duration of this EM will be around 5 days within the period of fourth quarter of 2017 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q4/2017 | Q4/2017
| 3.1.5 Expert Mission to assist INRA to review and assessment of selected SAR chapters of new BNPP. Duration of this EM will be around 5 days within the period of fourth quarter of 2017 by one expert | Agency | Expert | HardCore | 5,000 | 2017 | Q4/2017 | Q4/2017
| 3.1.6 Expert Mission to assist INRA to review and assessment of selected ER chapters of new BNPP. Duration of this EM will be around 5 days within the period of third quarter of 2017 by one expert | Government Cost Sharing (footnote-a/) | Expert | FootNote | 5,000 | 2017 | Q3/2017 | Q3/2017
| 3.1.7 Expert Mission to assist INRA to review and assessment of selected ER chapters of new BNPP. Duration of this EM will be around 5 days within the period of third quarter of 2017 by three expert | Agency | Expert | HardCore | 5,000 | 2017 | Q3/2017 | Q3/2017
| 3.1.8 Expert Mission to assist INRA to review and assessment of selected ER chapters of new BNPP. Duration of this EM will be around 5 days within the third quarter of 2017 by one expert | Agency | Expert | HardCore | 5,000 | 2017 | Q3/2017 | Q3/2017
5.1 Strengthening regulatory control for protecting workers, public and environment during normal operation and emergency situations of NPPs, RR and Radioactive Waste Management | [6 empty] | Q3/2017 | Q3/2017
| 5.1.10 Workshop on Modeling Dispersion and Dose Assessment of the Public using Simulation Methods. Duration of this WS will be around 5days within the period of third quarter of 2017 by 2 experts | Agency | Training Course | HardCore | 7,000 | 2017 | Q3/2017 | Q3/2017
| 5.1.16 Workshop on Assessment of public exposure in existing situations. Duration of this WS will be around 5days within the period of second quarter of 2017 by two experts. | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2017 | Q2/2017 | Q2/2017
6.1 Improving regulatory competence for adequate safety control of the national programme for NPP, RRs and Radioactive Waste Management and Disposal Facilities | [6 empty] | Q1/2016 | Q1/2016
| 6.1.29 Scientific Visit on authorization processes from a WWER operating state. Duration of the SV will be one week within 2017 by one expert. | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 4,200 | 2017 | Q1/2016 | Q1/2016
| 6.1.30 Scientific Visit on authorization processes from a WWER operating state. Duration of the SV will be one week within 2017 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2017 | Q2/2017 | Q2/2017
| 6.1.31 Scientific Visit on a systematic approach to develop of regulations and guides for WWER. Duration of the SV will be one week within 2017 by one expert. | Government Cost Sharing (footnote-a/) | Scientific Visit | FootNote | 4,200 | 2017 | Q1/2017 | Q1/2017
| 6.1.32 Scientific Visit on a systematic approach to develop of regulations and guides for WWER. Duration of the SV will be one week within 2017 by expert. | Agency | Scientific Visit | HardCore | 4,200 | 2017 | Q1/2017 | Q1/2017
Sub-Total for 2017 |  |  |  |  | 110,800
2.4 Reviewing INRA’s updated / new regulations and regulatory guides and procedures for NPPs, RR and Radioactive Waste Management | [6 empty] | Q3/2018 | Q3/2018
| 2.4.5 Expert Mission to review INRA’s safety regulations for fuel cycle facilities. Duration of this EM will be around 5days within the period of third quarter of 2018 by one expert | Agency | Expert | HardCore | 5,000 | 2018 | Q3/2018 | Q3/2018
| 2.4.6 Expert Mission to review INRA’s safety regulations for fuel cycle facilities. Duration of this EM will be around 5days within the period of third quarter of 2018 by one expert | Agency | Expert | HardCore | 5,000 | 2018 | Q3/2018 | Q3/2018
3.3 Reviewing INRA’s review and assessment of submitted documents for Radioactive Waste and management system | [6 empty] | Q1/2018 | Q1/2018
| 3.3.1 EM to review INRA’s standard review plan on how to assess Radioactive Waste Safety Case/Reports for disposal facility. Duration of this EM will be around 5days within the period of first quarter of 2018 by one expert | Agency | Expert | HardCore | 5,000 | 2018 | Q1/2018 | Q1/2018
| 3.3.2 Expert Mission to review INRA’s standard review plan on how to assess Radioactive Waste Safety Case /Reports for disposal facility. Duration of this EM will be around 5days within the period of first quarter of 2018 by one expert | Agency | Expert | HardCore | 5,000 | 2018 | Q1/2018 | Q1/2018
3.4 Reviewing INRA's review and assessment of submitted documents for Management System | [6 empty] | Q1/2018 | Q1/2018
| 3.4.1 Expert Mission to review INRA’s standard review plan on how to review and assess Management System documents/Reports of Nuclear Facilities. Duration of this EM will be around 5days within the period of first quarter of 2018 by one expert | Agency | Expert | HardCore | 5,000 | 2018 | Q1/2018 | Q1/2018
| 3.4.2 Expert Mission to review INRA’s standard review plan on how to review and assess Management System documents/Reports of Nuclear Facilities. Duration of this EM will be around 5days within the period of first quarter of 2018 by one expert | Agency | Expert | HardCore | 5,000 | 2018 | Q1/2018 | Q1/2018
5.1 Strengthening regulatory control for protecting workers, public and environment during normal operation and emergency situations of NPPs, RR and Radioactive Waste Management | [6 empty] | Q2/2018 | Q2/2018
| 5.1.9 Workshop on Neutron Personnel Dosimetry. Duration of this WS will be around 5days within the second quarter of 2018 by 2 experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2018 | Q2/2018 | Q2/2018
| 5.1.17 Workshop on use of safety assessment computer codes for modeling and dispersion of radioactive material in aquatic media. Duration of this WS will be around 5days within the period of third quarter of 2018 by 3 experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 10,500 | 2018 | Q3/2016 | Q3/2016
| 5.1.18 Workshop on Internal Dosimetry (Advanced and basic). Duration of this WS will be around 5 days within the period of second Quarter of 2018 by 2 experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2018 | Q2/2016 | Q2/2016
6.1 Improving regulatory competence for adequate safety control of the national programme for NPP, RRs and Radioactive Waste Management and Disposal Facilities | [6 empty] | Q1/2018 | Q1/2018
| 6.1.12 Scientific Visit on regulatory assessment activities for WWER. Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q1/2018 | Q1/2018
| 6.1.13 Scientific Visit on regulatory assessment activities for WWER. Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q1/2018 | Q1/2018
| 6.1.15 Scientific Visit on radiological monitoring assessment and Oversight activities during operation of WWER. Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q2/2018 | Q2/2018
| 6.1.16 Scientific Visit on radiological monitoring assessment and Oversight activities during operation of WWER. Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q2/2018 | Q2/2018
| 6.1.17 Scientific Visit on radiological monitoring assessment and Oversight activities during operation of WWER. Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q2/2018 | Q2/2018
| 6.1.21 Scientific Visit on regulatory supervision of Near Surface Disposal Facility (South Africa). Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q2/2018 | Q2/2018
| 6.1.22 Scientific Visit on regulatory supervision of Near Surface Disposal Facility (South Africa). Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q1/2018 | Q1/2018
| 6.1.23 Scientific Visit on regulatory supervision of Near Surface Disposal Facility (South Africa). Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q1/2018 | Q1/2018
| 6.1.24 Scientific Visit from an Emergency Center of a WWER operation state. Duration of the SV will be around 1 week within 2018 by one experts. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q1/2018 | Q1/2018
| 6.1.25 Scientific Visit from an Emergency Center of a WWER operation state. Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q1/2018 | Q1/2018
| 6.1.26 Scientific Visit from an Emergency Center of a WWER operation state. Duration of the SV will be around 1 week within 2018 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2018 | Q2/2018 | Q2/2018
Sub-Total for 2018 |  |  |  |  | 100,700
3.3 Reviewing INRA’s review and assessment of submitted documents for Radioactive Waste and management system | [6 empty] | Q1/2019 | Q1/2019
| 3.3.3 Workshop on regulatory supervision and assessment of Safety (including internal and external hazards) for Fuel Cycle Facilities. Duration of this EM will be around 5days within the period of first quarter of 2019 by two experts | Agency | Training Course | HardCore | 7,000 | 2019 | Q1/2019 | Q1/2019
4.1 IRRS Mission related activities | [6 empty] | Q4/2019 | Q4/2019
| 4.1.1 IRRS Preparatory Mission Duration of this EM will be around 3 days within the period of fourth quarter of 2019 by one expert | Agency | Expert | HardCore | 3,000 | 2019 | Q4/2019 | Q4/2019
| 4.1.2 IRRS Preparatory Mission Duration of this EM will be around 3 days within the period of fourth quarter of 2019 by one expert | Agency | Expert | HardCore | 3,000 | 2019 | Q4/2019 | Q4/2019
| 4.1.3 IRRS Preparatory Mission Duration of this EM will be around 3 days within the period of fourth quarter of 2019 by one expert | Agency | Expert | HardCore | 3,000 | 2019 | Q4/2019 | Q4/2019
| 4.1.4 IRRS Preparatory Mission Duration of this EM will be around 3 days within the period of fourth quarter of 2019 by one expert | Agency | Expert | HardCore | 3,000 | 2019 | Q4/2019 | Q4/2019
| 4.1.5 IRRS Preparatory Mission Duration of this EM will be around 3 days within the period of fourth quarter of 2019 by one expert | Agency | Expert | HardCore | 3,000 | 2019 | Q4/2019 | Q4/2019
| 4.1.6 IRRS Preparatory Mission Duration of this EM will be around 3 days within the period of fourth quarter of 2019 by one expert | Agency | Expert | HardCore | 3,000 | 2019 | Q4/2019 | Q4/2019
5.1 Strengthening regulatory control for protecting workers, public and environment during normal operation and emergency situations of NPPs, RR and Radioactive Waste Management | [6 empty] | Q2/2019 | Q2/2019
| 5.1.1 EM to review National Infrastructure and INRA’s integrated regulations for preparedness and response to off-side nuclear emergency. Duration of this EM will be 5days within the period of second quarter of 2019 by one expert. | Agency | Expert | HardCore | 5,000 | 2019 | Q2/2019 | Q2/2019
| 5.1.2 EM to review National Infrastructure and INRA’s integrated regulations for preparedness and response to off-side nuclear emergency. Duration of this EM will be 5days within the period of second quarter of 2019 by one expert. | Agency | Expert | HardCore | 5,000 | 2019 | Q2/2019 | Q2/2019
| 5.1.3 EM to review National Infrastructure and INRA’s integrated regulations for preparedness and response to off-side nuclear emergency. Duration his EM will be 5days within the period of second quarter of 2019 by one expert. | Agency | Expert | HardCore | 5,000 | 2019 | Q2/2019 | Q2/2019
| 5.1.13 Workshop on principles, standards and methods of Calibration (Gamma,X, Neutron). Duration of this WS will be around 5days within the period of third quarter of 2019 by two experts | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2019 | Q3/2019 | Q3/2019
| 5.1.14 Workshop on Personnel Monitoring Methods other than TLD and filmbadge (such as OSL). Duration of this WS will be around 5days within the period of the fourth quarter of 2019 by two experts. | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2019 | Q4/2019 | Q4/2019
| 5.1.15 Workshop on Accidental Personnel Dosimetry. Duration of this WS will be around 5days within the period of first quarter of 2019 by two experts. | Government Cost Sharing (footnote-a/) | Training Course | FootNote | 7,000 | 2019 | Q1/2019 | Q1/2019
6.1 Improving regulatory competence for adequate safety control of the national programme for NPP, RRs and Radioactive Waste Management and Disposal Facilities | [6 empty] | Q3/2016 | Q3/2016
| 6.1.1 Scientific Visit from an implementation of Management System at a WWER operating State. Duration of the SV will be around 1 week within 2019 by one expert | Agency | Expert | HardCore | 7,000 | 2019 | Q3/2016 | Q3/2016
| 6.1.2 Scientific Visit from an Emergency Center of a WWER operation state to share experiences regarding consequences analyses and risk assessment for accidents at nuclear facilities Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q3/2016 | Q3/2016
| 6.1.3 Scientific Visit from an Emergency Center of a WWER operation state to share experiences regarding consequences analyses and risk assessment for accidents at nuclear facilities Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q1/2016 | Q1/2016
| 6.1.4 Scientific Visit from an Emergency Center of a WWER operation state to share experiences regarding consequences analyses and risk assessment for accidents at nuclear facilities Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q1/2016 | Q1/2016
| 6.1.5 Scientific Visit on authorization processes from a WWER operating state. Duration of the SV will be one week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q3/2016 | Q3/2016
| 6.1.6 Scientific Visit on authorization processes from a WWER operating state. Duration of the SV will be one week within 2019 by expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q3/2016 | Q3/2016
| 6.1.8 Scientific Visit on inspection activities during operation of WWER. Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q2/2019 | Q2/2019
| 6.1.9 Scientific Visit on inspection activities during operation of WWER. Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q1/2019 | Q1/2019
| 6.1.10 Scientific Visit on inspection activities during operation of WWER. Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q2/2019 | Q2/2019
| 6.1.11 Scientific Visit on regulatory assessment activities for WWER. Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q1/2018 | Q1/2018
| 6.1.14 Scientific Visit on regulatory assessment activities for WWER. Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q1/2019 | Q1/2019
| 6.1.18 Scientific Visit on radiological monitoring assessment and Oversight activities during operation of WWER. Duration of the SV will be around one week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q2/2019 | Q2/2019
| 6.1.19 Scientific Visit on radiological monitoring assessment and Oversight activities during operation of WWER. Duration of the SV will be around one week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q2/2018 | Q2/2018
| 6.1.20 Scientific Visit on radiological monitoring assessment and Oversight activities during operation of WWER. Duration of the SV will be around 1 week within 2019 by one expert. | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q2/2019 | Q2/2019
| 6.1.27 Scientific Visit from an implementation of Management System at a WWER operating State. Duration of the SV will be around 1 week within 2019 by one expert | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q1/2019 | Q1/2019
| 6.1.28 Scientific Visit from an implementation of Management System at a WWER operating State. Duration of the SV will be around 1 week within 2019 by one expert | Agency | Scientific Visit | HardCore | 4,200 | 2019 | Q3/2016 | Q3/2016
Sub-Total for 2019 |  |  |  |  | 131,000
This report was generated on 2016-01-07 10:44:47 by MISHAR, Marina Binti Binti