MINUTES OF MEETING

on NPPD TC Projects: IRA4035, IRA2011, IRA2012 and IRA2013

10-12 May 2016 Vienna

- Participants

- NPPD:

- Mr. Rahnama

- Mr. Shahrokh Bagh Panah

- IAEA:

- Mr. Pal Vincze

- Mr. Peter Tarren

- Mr. Diego Telleria

- Mr. Anthony Patrick Ulses

- Mr. Yoshimitsu Fukushima

- Ms. Marina Mishar

- Mr. Ki-Sig Kang

- Mr.David Drury

- Mr. Boris Gueorguiev (External Expert)

- 2. Objectives:

- Clarification of scope and objectives and confirmation of dates for activities scheduled for 2016 (Annex 1)

- Clarification of funding of priority activities

- Preparation of first draft of new project for TC Cycle 2018/2019

- 3. Relevant TC Projects:

- IRA2012 Increasing NPPD’s Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety (ends 2017)

- IRA2013 Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1 (ends 2019)

- IRA 2011 Strengthening and upgrading capabilities for safe and reliable operation and maintenance of BNPP-1;

- Work Done

- Agenda of the meeting was discussed and approved (Attachment 1)

- The counterpart presented the priority activities in IRA2012 and IRA2013

- Work plans of IRA2012 and IRA2013 were updated accordingly to the current progress and prioritization with focus on tasks planned for implementation during Q2/2016 – Q1/2017 (Attachments 2 and 3)

- Discussions were held on the proposed new project for 2018/2019 and issues/topics provided for further consideration

- Draft of IRA2011 Project Achievement Report was discussed and finalized (Attachment 4)

- Conclusions

- In order to proceed with implementation of updated work plan activities in 2016, the NPPD to provide to the IAEA the first part of GCS by the end of June, and the remaining part as soon as possible.

- To continue the good practice of regular coordination meetings. For 2016: in addition to the Annual meeting held in March and current coordination meeting (May), next coordination meeting to be held in 3-5 October in Vienna, and another one if needed in Q4 in Vienna

- To convert the planned SVs under activity 3.2 of IRA2013 on environmental qualification of equipment to technical visit to NPP in Germany or Brazil (Angra-2) on specific issues (maintenance, spare parts) of integrated KWU equipment into the BNPP-1 design.

- To make arrangements in the IRA2013 work plan under activity 7.4 of an EM of one IAEA staff (D. Talleria) in the Q4 to Bushehr for acceptance of the installed ESTE software and training.

- To continue exchange of views/proposals for the new project design for 2018/2019 and beyond between the project team members in order to support the counterpart in timely submission of its proposal by the end of August 2016 for further consideration/evaluation.

- Timely submission NFs for group fellowship in S.Korea in Q4/2016 by end of July.

- The IAEA will inform the NPPD on the expected time of submission of Risk Spectrum software for necessary preparations for its utilization

- The PMO will share additional funding needed to implement planned activities for 2016 before end of May.

| Attachments: - Agenda of the meeting - Updated Work Plan of IRA2012 - Updated Work Plan of IRA2013 - Final draft of IRA2011 Achievement Report |  |
| --- | --- |

Attachment 1

Attachment 1

Agenda

Meeting on NPPD TC Projects: IRA2012 & IRA2013

10 – 12 May 2016

- Vienna, VIC, Room:  A2486 & MOE18

- NPPD:

- Mr. Rahnama

- Mr. Shahrokh Bagh Panah

- IAEA:

- Mr. Pal Vincze

- Mr. Peter Tarren

- Mr. Diego Telleria

- Mr. Anthony Patrick Ulses

- Mr. Yoshimitsu Fukushima

- Ms. Marina Mishar

- Mr. Boris Gueorguiev (External Expert)

- Objectives:

- Clarification of priority, scope and objectives and confirmation of dates for activities planned for IRA2012 and IRA2013

- Clarification of funding of priority activities

- Preparation of first draft of new project for TC Cycle 2018/2019

- Relevant TC Projects:

- IRA2011 Strengthening and Upgrading Capabilities for Safe and Reliable Operation and Maintenance of a Pressurized Light Water Reactor (under closure)

- IRA2012 Increasing NPPD’s Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety (ends 2017)

- IRA2013 Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1 (ends 2019)

- Prior Information Needed from Counterparts:

- Priority of activities planned for 2016 under IRA2012 and IRA2013

- Procurement of Softwares (status of funds)

- Copy of existing Integrated Management System Procedure of the NPP

- Status follow-up actions on recommendations made in previous expert missions including status of action plans

| Tuesday 10 May 2016 |  |  |  |
| --- | --- | --- | --- |
| Time |  | Main Topic | Responsible |
| 09:00-09:15 |  | Introductions | All |
| 09:15-09:30 |  | Agenda Review & Meeting Deliverables | All |
| 09:30-10:00 |  | Presentation on Priority Activities in IRA2012 & IRA 2013 | CPs |
| 10:00- 10:30 |  | Funding status for all activities in both TC Projects | CPs, Marina |
| 10:30-10:45 |  | Coffee Break |  |
| 10:45-11:45 |  | Session I : Review of Achievement & Progress - Closure of IRA2011: identify outputs, outcomes and other key elements of the closure report - Mid-term review of IRA2012 (taking into consideration the achievements made under IRA4023) and IRA2013: discussion on the status of all tasks; definition of priorities and assessment of feasibility of implementation of tasks | CPs, Pal & Boris |
| 11:45-12:45 |  | Finalization of project achievement report & drafting of success story | CPs, Pal & Boris |
| 12:45-14:00 |  | Lunch |  |
| 14:00-15:00 |  | Session 2: Clarification of scope and objectives for the activities scheduled for 2016: - Needs of NPPD on Seismic - Exchange on current status of progress of the report - Discussion on future actions | CPs, Yoshi & Boris |
| 15:00 – 15:30 |  | Continue with Session I | CPs, Pal & Boris |
| 15:30-15:50 |  | Coffee Break |  |
| 15:50-16:30 |  | Session 2: Clarification of scope and objectives for the activities scheduled for 2016: - Discussion on implementation of a system for environmental impact assessment and management (software ESTE). Confirmation by Counterpart and NLO of licenses modules, scope and period of maintenance and funding resources, to start immediately the procurement process. Planning of the mission for installation of the software and basic training. Planning for advanced training. - PM, IMS, KM and DBI (Design Basis Information) systems | CPs, Diego, Tony, Pal & Boris |
| 15:00 – 15:30 |  | Continue with Session I | CPs, Pal & Boris |
| Wednesday 11 May 2016 |  |  |  |
| Time | Main Topic |  | Responsible |
| 09:00-10:00 | Session 2: Clarification of scope and objectives for the activities scheduled for 2016: - Safety assessment related task |  | CPs, Tony, Pal & Boris |
| 10:00-10:30 | - Fresh and spent fuel management related activities |  | CPs, Tony & Pal |
| 10:30-10:45 | Coffee Break |  |  |
| 10:45-12:45 | Session 2: Clarification of scope and objectives for the activities scheduled for 2016: - Safety and quality requirements - HRD/Training activities |  | CPs, Pal & Boris |
| 12:45-14:00 | Lunch |  |  |
| 14:00-15:30 | Session 3: Project Design for TC Cycle 2018/2019 - Discussions on the key objectives of the project for 2018-2019. - Identification of key deliverables and potential mechanism of the new project. - Local industry utilization and public information and awareness related activities |  | CPs, Pal & Boris |
| 15:30-15:50 | Coffee Break |  |  |
| 15:50-17:00 | Session 3 continues with the drafting of the project design for Concept # IRA2016003 ‘Further Increasing NPPD's Capability in Planning and Implementing Activities Related to Design, Construction and Commissioning of Two New NPP Units in Bushehr with Emphasis on Safety |  | CPs, Pal & Boris |
| Thursday 12 May 2016 |  |  |  |
| Time | Main Topic |  | Responsible |
| 09:00-10:30 | Session 2: Clarification of scope and objectives for the activities scheduled for 2016: - Softwares - Training on construction and commissioning management (group training in Korea and technical visits) - Updating training system and materials including maintenance training system - Environmental Monitoring and Emergency Preparedness and Response |  | CPs, Pal, Peter, Tony & Boris |
| 10:30-10:45 | Coffee Break |  |  |
| 10:45-12:45 | Continue with session 3 : Project Design |  | CPs, Pal, Boris & Marina |
| 12:45-14:00 | Lunch |  |  |
| 14:00-15:30 | Continue with session 3 : Finalization of project design |  | CPs, Pal, Boris & Marina |
| 15:30-15:50 | Coffee Break |  |  |
| 15:50-17:00 | Closure of Meeting: - Agreement of 2016 planned activities, project achievement & success report & first draft of project design - Preparations of meeting’s minutes - Closure |  | All |

Attachment 2

Updated Work Plan of IRA2012

| as of 12.05.2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Increasing NPPD's Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority |  |  | Comments |
| 1.2 Conducting project review meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 1.2.1 | Annual project review and planning meeting 2014 | IAEA: Gueorguiev, NPPD: Fatourechian | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | Q1/2014 | Completed |  |  |  |  |
| 2 | 1.2.2 | Annual project review and planning meeting 2015 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | Q1 2015 | Completed, 15-17 February 2015 in Tehran |  |  |  |  |
| 3 | 1.2.3 | Annual project review and planning meeting 2016 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | Q1 2016 | Completed 29 February - 2 March |  |  |  |  |
| 4 | 1.2.4 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Vienna | EM | Q1 2017 |  |  |  |  |  |
| 1.5 IAEA field monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | 1.5.1 | Reqular field monitoring and review missions | IAEA: Gueorguiev, NPPD: Fatourechian | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | 2014 | Completed |  |  |  |  |
| 6 | 1.5.2 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | 2015 | Completed |  |  |  |  |
| 7 | 1.5.3 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | 2016 |  |  |  |  | 1-2 missions per quarter jointly with IRA2013 |
| 8 | 1.5.4 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting | 2017 |  |  |  |  | 1-2 missions per quarter jointly with IRA2013 |
| 2.2 Spent fuel storage and waste management programs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | 2.2.1 | EM to assist in radioactive waste management programme, including scaling factor application | IAEA:Ormai/Dyck, NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX |  | Tehran | EM | 27 Sept - 1 Oct 2014 | Jointly with IRA2011/1.17.3 Completed |  |  |  |  |
| 10 | 2.2.2 | EM to assist in spent fuel storage | IAEA: C. Hill NPPD: Derakhahandeh | 1 IAEA staff and 3 IEX |  | TBD | EM | Q1/2017 |  |  | H |  | Follow-up mission under 2011 |
| 3.1 Development of training materials for two new NPP projects |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | 3.1.1 | EM to assist in review of selected/developed training materials for future operatorsfor two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q4/2017 | To be implemented on the developed materials provided by the supplier of two new units |  | H |  |  |
| 12 | 3.1.2 | EM to assist in review of selected/developed training materials for future operators for two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q4/2017 | To be implemented on the developed materials provided by the supplier of two new units |  | H |  | merged with 3.1.1 |
| 3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | 3.2.1. | WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety | IAEA: Kang, NPPD: Tajbakhsh | 1 IAEA staff and 2 IEX for 4 days |  | Tehran Bushehr | WS | 27-30 April 2014 | Completed |  |  |  |  |
| 5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | 5.1.1 | EM To assist in development of the Local Industry Utilization Plan | IAEA: Kang NPPD: Derakhshandeh | 1 IAEA staff and 2 IEX for 3 days |  | Tehran | EM | Q4/2016 |  |  | M |  | NPPD: Specific issues related to local industry will be sent to the IAEA two months before the WS |
| 6.1 Public information and awareness programmes development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 | 6.1.1 | WS on public information and awareness programmes | IAEA:B. Pagannone/ NPPD:Rahnama | 4-6 NEX and 2 IEX |  | Tehran | WS | 28 Sept-1 Oct 2014 | Completed |  |  |  |  |
| 16 | 6.1.2 | EM to assist on the establishment of public information and awareness centre | IAEA: T, Tigerstedt NPPD: Rahnama | 1 IAEA staff and 2 IEX |  | Tehran/Bushehr | EM | Q4/2016 |  |  | M |  | NPPD is requested to send the IAEA two months before the draft plan/status description for the Centre. |
| 17 | 6.1.3 | EM to review results of Stakeholder Involvement Plan | IAEA: T, Tigerstedt NPPD: Rahnama | TBD |  | Tehran | EM | Q3/2017 |  |  | M |  | Additional request as follow-up of 6.1.1. New request |
| 17 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: T, Tigerstedt NPPD:Rahnama | TBD |  | TBD | SV | 2017 |  |  | M |  | Additional request as follow-up of 6.1.1. New request |
| 2.1 Seismic safety assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 | 2.1.1 | EM to assist in seismic safety assessment | IAEA:Y.Fukushima, NPPD: Shirzadi/Derakhshandeh | 1 IAEA staff and 3 IEX |  | Tehran / Bushehr | EM | September 2016 ( 4 working days) |  |  | H |  | Specific issues of interest for site data provided. NPPD to provide report on Seismic Hazard Evaluation in advance by end of june. |
| 3.3 Corporate knowledge management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 | 3.3.1 | EM on corporate knowledge management for BNPP - 2&3 with focus on safety | IAEA:Z. Pasztory NPPD:Rahnama/Sheikholeslami | 1 IAEA staff and 3 IEX, 4 days |  | Tehran | EM | 15-18 Nov. 2015 | Completed |  |  |  |  |
| 20 | 3.3.2 | EM on Management and maintaining design basis information through life cycle of BNPP-2&3 | IAEA:J. de Grosbois, Kolomiets 1 IAEA staff and 3IEX | I IAEA + 2 IEX |  | Tehran | EM | 21-25 April 2016 (3 days) | Completed |  |  |  |  |
| 3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21 | 3.4.1 | WS on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (cancelled) |  |  |  |  |  |  | NPPD does not need further assistance |  |  |  |  |
| 22 | 3.4.2 | SV on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (SG) | IAEA: M. Mishar, SG NPPD: NPPD:Amini | 3NEX |  | TBD | SV | 2016 |  | H |  | NFs to be provided timely in advance |  |
| 4.4 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23 | 4.1.1 | EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units | IAEA: Drury/Tarren, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q2/2017 |  | H |  | Specific needs to be provided by NPPD on the basis of the contract for two new units. Jointly with 4.2.1 New task (Possible home based assignment) |  |
| 24 | 4.1.2 | EM to assist in evaluation of developed programmes to update owner's training system for the two new PWR units | IAEA: Drury/Tarren, NPPD: Rahnama/ Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | Q2/2017 |  | H |  | Specific needs to be provided by NPPD on the basis of the contract for two new units. New task |  |
| 25 | 4.1.3 | Group Trainig programme on pre-construction management with focus on safety requirements | IAEA: Kang; NPPD: Fatourechian | 1 IAEA Staff, 20 NEX |  | ICTC, Beijing, China | WS | 24 Aug.-4 Sept. 2015 | Completed |  |  |  |  |
| 26 | 4.1.4 | EM to assist in development of comprehensive model for effective project management of the two new NPP units (1 + 3 IEX) | IAEA: Pekka Pyy. NPPD: Rahnama | 1 IAEA Staff and 3 IEX |  | Tehran | EM | 8-11 Nov. 2015 | Completed |  |  |  |  |
| 27 | 4.1.5 | Group Fellowship Trainig on construction and commissioning management with focus on safety requirements | IAEA: K. S. Kang NPPD: Fatourechian/Rahnama | 2 IAEA staff and 20 NEX. The cost for the WS is expected cca. 100 000 EURs. |  | S. Korea | Group fellowship training | Q3-Q4/2016 |  | H |  | NPPD: To send GCS until 30 June. New request |  |
| 28 | 4.1.6 | EM to assist in the review of the developed Project Management System for units 2 and 3 of the new project. | IAEA: Pekka Pyy. NPPD: Fatourechian/Rahnama | 1 IAEA/3 IEX 4 days. |  | Tehran | EM | Q4 2016 |  | H |  | NPPD: To send the scope and focus and the related documents two months before the mission. New request |  |
| 4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 29 | 4.2.1 | EM to assist in review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and # IEX |  | TBD | EM and HBA | Q2/2017 |  | H |  | Jointly with 4.1.1 and 4.1.2 |  |
|  | Cancelled / shift to new project |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Further clarifications needed |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Completed |  |  |  |  |  |  | 11 active tasks ( 1 deleted and 3 merged) including 3 new request |  |  |  |  |  |

Attachment 3

Updated Work Plan of IRA2013

| as of 12.05.2016 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority |  | Comments |
| 1.2 Conducting project review meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed |  |  |  |
| 2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Vienna | PRM | Q1/2017 |  |  |  |  |
| 1.5 IAEA Field Monitoring (once per quarther) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Preparatory visit for OSART mission |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | Q4/2016 |  | H |  | Planned for 14-16 November 2016 |
| 2.4 Implementation the nuclear safety oversight function |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | 2.4.1 | One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: Derakhshandeh | 1 IAEA+2IEX |  | Tehran | EM | Q1/2017 |  | M |  | The need to be confirmed at March 2016 follow-up visit |
| 3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | 3.1.1 | WS on "modern methods for measuring hydrogen concentration in containment " | IAEA: S. Monti, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q4/2016 |  | H |  | NPPD to provide the final expectations by end of May. |
| 3.2 Training on environmental qualification of safety equipment of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | 3.2.1 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD | SV | Q3/2016 |  | H |  | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. |
| 7 | 3.2.2 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q3/2016 |  | H |  | To be deleted |
| 8 | 3.2.3 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q3/2016 |  | H |  | To be deleted |
| 3.3 Training on equipment reliability assessment techniqes of equipment during operation |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" | IAEA: K. Kang, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016 |  |  |  | Deleted |
| 3.8 Development of ageing management program for BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q3/2016 |  | H |  |  |
| 11 | 3.8.2 | WS developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: J. Moore, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q2/2017 |  | M |  | New request |
| 3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | 3.10.1 | EM on "Assistance on review of safety analysis model for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Ghods-Derakhshandeh | 1 IAEA+3IEX/5 days( HBA 5 days) |  | Tehran | EM | Oct.2016 |  | H |  | NPPD to provide one month before, information on modeles and any result of calculation. |
| 13 | 3.10.2 | E M on independent analysis of root-cause results for BNPP-1 | IAEA: P. Tarren, NPPD: Abbaspour/Ghods | 1 IAEA+3IEX/5 days |  | Tehran | EM | Q2/2017 |  | H |  | NPPD to provide two month before information in English on the root cause analysis in the last two years. |
| 3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q4/2016 |  | H |  | IAEA request further clarification of what NPPD are seeking. |
| 3.14 Assistance on safety aspacts of fresh and spent fuel engineering |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: T. Ulses, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2018 |  |  |  | Move to the next cycle. (2018-2019) |
| 16 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; C .Hill, NPPD: Ghods-Abbaspour | 1 IAEA+2 IEX |  | Tehran | EM | Q2/2017 |  | M |  |  |
| 5.5 Assistance in development of selected training scenarios for severe accidents in FSS |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | Q2 /2018 |  |  |  | To be discussed afterimplementation of 6.3.1, |
| 5.6 Assistance in development & improvement of training system of maintenance & repair personnel |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: D. Drury, J. Song NPPD: Rahnama-Talebianzadeh | 1IAEA+2IEX |  | Bushehr/Tehran | EM | Q4/2016 |  | H |  |  |
| 6.1 Asistance in review of BNPP-1 off-site emergency preparedness and response |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA: P. Salinas, NPPD: Abbaspour | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | M |  | NPPD: To send clarification on the focus: Training on off-site response to radiological emergency situation BNPP-1? |
| 6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 20 | 6.3.1 | EM to review progress in development of the severe accident analysis model (using computer code) for BNPP-1 | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | EM | Q2/2017 |  | H | Depending on availability computer code |  |
| 21 | 6.3.2 | RM to review the progress in development of the severe accident managementguidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | TSR-AM | Q3/2017 |  | H | TSR-AM: Technical Safety Review- Accident Management |  |
| 7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening, NPPD: Abbaspour | 1IAEA+3IEX |  | Bushehr | EM | Oct.2016 |  | H | IAEA to confirm the date. BNPP-1 will provide tools for measurements. |  |
| 7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011) |  |  |  |  |  |  |  |  |  |  |  |  |
| 23 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: D. Talleria, NPPD: Abbaspour | Procurement |  | Bushehr | Procurement | Oct.2016 |  | H | NPPD: to clarify the scope and duration of maintenance period. The IAEA will inform anout the expected price. NPPD will proceed with the officils request. Timely payment of GCS is important. |  |
| 2.3 Implementation of OSART mission |  |  |  |  |  |  |  |  |  |  |  |  |
| 24 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  | Bushehr | EM | Q4/2017 |  | H | IAEA: November 2017 is recommended. An official request is needed untl the end of Q2 2016 |  |
| 2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers |  |  |  |  |  |  |  |  |  |  |  |  |
| 25 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | Tehran | EM | Q3/2016 |  | H | The scope and focus submitted by NPPD,will be considered for implementation by the end of Q3/beginning of Q4. |  |
| 2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission |  |  |  |  |  |  |  |  |  |  |  |  |
| 26 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q1 2017( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1-2 NEX |  | TBD | FS | 2017 |  | H |  |  |
| 3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment |  |  |  |  |  |  |  |  |  |  |  |  |
| 27 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: B.Song, K.Makela, NPPD: Deylami | 1 IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | H |  |  |
| 3.4 Training on containment leakage tests and calculations after outage |  |  |  |  |  |  |  |  |  |  |  |  |
| 28 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H |  |  |
| 29 | 3.4.2 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H |  |  |
| 30 | 3.4.3 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H |  |  |
| 31 | 3.4.4 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2017 |  | H |  |  |
| 3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system |  |  |  |  |  |  |  |  |  |  |  |  |
| 32 | 3.5.1 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q1/2017 |  | M |  | NFs should be sent to IAEA at least 8 months before. |
| 33 | 3.5.2 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q1/2017 |  | M |  | NFs should be sent to IAEA at least 8 months before. |
| 34 | 3.5.3 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | TBD | SV | Q1/2017 |  | M |  | NFs should be sent to IAEA at least 8 months before. |
| 35 | 3.5.4 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | TBD | SV | Q1/2017 |  | M |  | NFs should be sent to IAEA at least 8 months before. |
| 3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR |  |  |  |  |  |  |  |  |  |  |  |  |
| 36 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1IAEA+3IEX |  |  | WS | Q1/2018 |  |  |  | Shifted to next cycle(2018-2019_ |
| 3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles |  |  |  |  |  |  |  |  |  |  |  |  |
| 37 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  | Tehran | EM | Q1/2017 |  | H |  |  |
| 3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system |  |  |  |  |  |  |  |  |  |  |  |  |
| 38 | 3.9.1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests, High and low cycle fatigue analysis for strength assessment of Reactor Coolant System | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  | Tehran | WS | Q3/2017 |  | M |  | the IAEA will contact to NPPD by end of june 2016. |
| 3.12 Assistance in performing the living PSA of the BNPP-1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 39 | 3.12.1 | EM to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: I Kuzmina, NPPD: Ghods | 1IAEA+2IEX |  |  | EM | Q1/2018 |  |  |  | NPPD: To send information on the scope and focus including utilization of risk spectrum softwarein two months before the mission. |
| 3.14 Assistance on safety aspacts of fresh and spent fuel engineering |  |  |  |  |  |  |  |  |  |  |  |  |
| 40 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: C. Hill / T.Ulses, NPPD: Derakhshandeh | 1 IAEA+2 IEX |  | Tehran / Bushehr | EM | Q2/2017 |  | M |  |  |
| 4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes |  |  |  |  |  |  |  |  |  |  |  |  |
| 41 | 4.1.1 | EM on "modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes " in Q1 2017, (1 IAEA +3 IEX ) | IAEA: H. Varjonen, NPPD: Roshankar | 1IAEA+3IEX |  | Bushehr | EM | Q3/2017 |  | H |  |  |
| 4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance |  |  |  |  |  |  |  |  |  |  |  |  |
| 42 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:J. Moore, NPPD: Tajbakhsh | 1IAEA+3IEX |  | Tehran | EM/HBA | Q4/2016 |  | H |  | NPPD to provide expectations,focus and approach by the end of june. |
| 5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel |  |  |  |  |  |  |  |  |  |  |  |  |
| 43 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 |  | M |  |  |
| 5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel |  |  |  |  |  |  |  |  |  |  |  |  |
| 44 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  |  |  |  |
| 45 | 5.2.2 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  |  |  |  |
| 46 | 5.2.3 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  |  |  |  |
| 7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011) |  |  |  |  |  |  |  |  |  |  |  |  |
| 47 | 7.4.2 | EM on "Review and assesment of results of environmental monitoring programme using the software ESTE" | IAEA: D. Talleria, NPPD: Abbaspour | 1 IAEA+2IEX |  | Bushehr | EM | Q4/2017 |  | M |  |  |
| 4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators |  |  |  |  |  |  |  |  |  |  |  |  |
| 48 | 4.4.1 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD |  | SV | 2017 | H |  | New request for 2016 NPPD: to send the scope and focus of this task two months before the mission. (Potential for UKR, Zhaporozhe) |
| 4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs |  |  |  |  |  |  |  |  |  |  |  |  |
| 49 | 4.3.1 | WS on outage optimization through advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs | IAEA: H. Varjonen NPPD:Roshankar | 1IAEA+3IEX(4 days) |  | Bushehr |  | WS | Q3/2017 | H |  | New for 2017. NPPD: to send the scope and focus of this task two months before the mission. |
|  | Deleted / shifted to 2018-2019 |  |  |  |  |  |  |  |  |  |  |  |
|  | Further clarifications needed |  |  |  |  |  |  | 31 active tasks including 2 new request |  |  |  |  |
|  | Completed |  |  |  |  |  |  |  |  |  |  |  |

Attachment 4

Final draft of IRA2011 Achievement Report

PROJECTPROGRESS ASSESSMENT REPORT (PPAR)

National Projects

|  |  | Explanations |
| --- | --- | --- |
| SECTION-1: BASIC INFORMATION |  |  |
| Project Number and Title | IRA/2/011 Strenghtening and updating capabilities for safe and reliable operation and maintenance of a pressurized light water reactor | (prefilled) |
| Country | Islamic Republic of Iran, |  |
| Counterpart Name & Institution | Nuclear Power Production and Development Company of Iran, Atomic Energy Organization of Iran |  |
| 1st Year of Approval | 2012 |  |
| Estimated Duration | 4 Years |  |
| Expected End Date | 31/03/2016 |  |
| Total Project Budget(as per IAEA White Book) |  |  |
| Reporting Period | 2012-2015 | Tick one reporting period |
| Report Contributors | Amir Afshin Rahnama | Other contributors to the report besides counterpart |
| Has there been any major change that affected the project? |  Yes No If yes, tick to specify nature of change(s): ☐ CP1☐ NLO2 PMO3☐ TO4 ☐Budget/funding; ☐ Other(specify) [Provide explanation]……Due to the additional measures taken by the whole project team the difficulties are being offset. | Select “Yes” or “No” and, if “Yes”, please tick relevant box(es) and describe nature of impact |
| SECTION-2: OUTPUTS ACHIEVEMENT |  |  |
| Select status of Output and briefly describe elements of progress towards target indicators: (1st column prefilled) |  |  |
| Output 1: Safety program is assessed and improved (95%) Indicator(s): Safety performance indicators are collected and analyzed |  Completed ☐ On schedule ☐ Delayed ☐ Other (specify). Achievements - Updated Organization and structures of emergency repairs teams and list of requirements for portable and mobile equipment determined. Scientific visit in this regards were requested for 2016-2017 - Improved BNPP knowledge on nuclear fuel management and performance. - Defined parameters to strengthening routine and post-accident radiation environmental monitoring for BNPP, Technical Assignment for suitable software for environmental monitoring has been developed and official request submitted to IAEA for procurement. - Improved Knowledge and experience on methodology and application of IAEA requirements for preparation of OSART mission. - Enhanced knowledge on: important aspects of thermal hydraulic analysis of the nuclear power plant; two-phase flow and fluid dynamic modeling in computer codes for thermal hydraulic analysis; the role of uncertainty in best estimate analysis of the plant; phenomena identification in TH analysis; validation of input deck for best estimate analysis; sensitivity analyses in the TH for further improvement safety performance of the plant - Detailed evaluation of effectiveness of physical protection system and developed Physical Protection procedures improved security of the plant. - Advanced nuclear material accounting software (STAR) customized, five responsible staff trained for enhancing nuclear safety and security BNPP-1; - Strengthened owner's capabilities on safety culture at all level of BNPP-1 through developed procedure on annual assessment of safety culture and first assessment was done for 50 managers; - Methodology for stress test provided, staff trained and action plan developed - in progress of implementation; - Reviewed and modified On-site Emergency plan (evaluation of off-site emergency plan planned under IRA2 013 for 2017), organization of emergency repairs and use of mobile equipment established to further improve emergency preparedness and responses; - Updated radioactive waste management programme and procedures including application of scaled factors for intermediate storage at the BNPP site and transportation to the disposal facility; - First draft of severe accident management guidance document developed; - Strengthen capabilities on BNPP personnel on using the practical application of Living Probabilistic Safety Assessment(PSA), technical specification of suitable software(Risk Spectrum) developed and official for procurement submitted to IAEA; | Select status and provide explanation/ supporting background information (e.g., Why is the output delayed? What mitigation measures have been taken to solve the issue?) |
| Output 2: … Maintenance program is optimized and updated (95%) - Indicator(s): - 20 staff of M&R department capable of using the new methods in M&R process planning and implementation of procedures |  Completed ☐ On schedule ☐ Delayed ☐ Other (specify)[Provide explanation]…… Achievements: - Specialized NPPD maintenance and repairs company organization (TAPNA) established, large number of staff trained and performed significant part of scope of maintenance and repair works during the outage and maintenance periods of BNPP-1 during 2014-2015. - Developed M&R documents based on manufacturing documents and assembly drawings, incorporating changes during construction; - Established permanent warehouse system in BNPP; - Prepared checklist, control/ monitoring documents of main equipment M&R activities increased quality performance and analysis of results; - Improved corrective preventive maintenance programme, recording the history of repairs; - Improved outage on outage optimization strategy and risk monitoring in BNPP-1 operation utilizing modern methods, techniques and tools for M&R activities with focus on organization and implementation. Scientific visit on advanced equipment and techniques for In-Service Inspection (ISI) of BNPP-1 primary circuit equipment is shifted to project IRA2013 for 2016-2017. - Strengthened owner's knowledge on reactor pressure vessel degradation, surveillance specimens laboratory establishment and a map way regarding surveillance program; |  |
| Output 3: Technical Support program is modified (90%) Indicator(s): 20 staff of Technical support department capable of using the new methods in planning and implementation of new methods for modernization of equipment and inspection activities |  Completed ☐ On schedule ☐ Delayed ☐ Other (specify)[Provide explanation]…… - Achievements: - Established a new NPPD company for NPPs Technical Support in safert development and promotion (Tavana), staff trained and contributes in respective activities for enhancement of safety and reliability of BNPP-1. - Improved safety performance indicators in according with IAEA guidlines; - Enhanced owner's Knowledge on Plant life management programme; - Enhanced knowledge BNPP personnel and capabilities of BNPP staff to analyze the collected data related to steam generators, pipes and systems of BNPP-1 primary circuit. - 8 BNPP experts trained and certified for NDT in Eddy current test Level-2 and Ultrasoninc test Level- - Five BNPP staff trained on modern methods of maintenance and repair of rotating equipment (reactor coolant pomps and turbogenerator). Training (SV) on proved methods for safety analysis of BNPP-1 equipment reliability (3.3.3) – some issues to be covered under (2.3.1) and SV shifted to the new project in 2016-2017. - Modified water chemistry procedures for primary and secondary circuits on the base of the best practice. |  |
| Output 4: BNPP training program is updated (70%). - Indicator(s): - All procedures and training plans are revised | ☐ Completed  On schedule ☐ Delayed ☐ Other (specify)[Provide explanation]…… Achievements: - Revised training programme and most of BNPP-1 operational training procedures, remaining part to be completed by the end of 2017 with some additional assistance under IRA 2013. | Insert additional rows if more than 4 outputs |
| Output 5. Improved capability in legal and contractual issues relating preparation of required contracts for operation and maintenance of BNPP1 (100%) - Indicator(s): Number of staff trained by field and qualification |  Completed ☐ On schedule ☐ Delayed ☐ Other (specify)[Provide explanation]…… Achievement: Strengthened capabilities of NPPD experts provided for development of contracts on BNPP operation, maintenance and repair and radioactive waste management. |  |
| Output 6. Overall HRM system for BNPP-1 is in progress of improvement (60%) - Indicator(s): Status report on the implementation of the WFP | ☐ Completed  On schedule ☐ Delayed ☐ Other (specify) Provide explanation]…… - Achievement: - Improved HRM programme. Implementation in progress to be completed by the end of 2018 with some additional assisstance to be provided in IRA 2013. - Established the NPPD knowledge management program and developed respective documents. - Improved technical specification of human performance laboratory and its implementation is in progress; |  |
| Output 7. Improvement of BNPP-1 full scope simulator (FSS) performance in progress (30%) - Indicator(s): Quarterly review of the workload and services delivered | ☐ Completed  On schedule ☐ Delayed ☐ Other (specify)[Provide explanation]…… Achievement: - Improvement of BNPP-1 FSS performance is expected through its planned modification and modernization in order to reflect results of commissioning and initial operation of BNPP-1. Due to delay in submittion of FSS relavant documents by the supplier, the programme of modernization is expected to be completed by end of 2016. |  |
| Output 8. Increased owner organization capability in application of nuclear oversight function (90%) |  Completed  On schedule ☐ Delayed ☐ Other (specify)[Provide explanation]…… Achievement: - Established NPPD procedures and methods for nuclear oversight function; - Established NPPD nuclear oversight team and trained two conduct safety oversight activity at BNPP-1; - Implementation of NPPD nuclear oversight function assessed; - Progress has been made with implementation of NPPD action plan to improve nuclear oversight activities taking into consideration of lesson learned. |  |
| Output 9. BNPP Training Centre in process of upgrading (30%) Indicator(s): Number of trainers, their qualifications and the number of training activities implemented | ☐ Completed  On schedule ☐ Delayed ☐ Other (specify)[Provide explanation]…… Achievement: - Improved strategy and plan for upgrading of BNPP training center including the maintenance and repair training system. Further assistance is under IRA 2 013 in 2016-2017. - Qualifications of 12 trainers strengthened through special training at Balakovo training center. |  |
| SECTION-3: EQUIPMENT & HUMAN RESOURCES |  |  |
| Based on TC Input categories, rate overall contribution towards achievement of project Outputs of Procurement and Human Resources capacity building Activities implementedthus far |  |  |
| Equipment (EQ)/ Sub-Contract (SC) | ☐Not Applicable  Very Good ☐ Good ☐ Fair ☐ Poor - The delivered START software for advanced NMAC very important for strengthening effectiveness of BNPP-1 safeguard reporting system - The purchase of RISK SPECTRUM software for LPSA for BNPP-1 to be finalized in Q1 2016 - Assistance in the detail technical specifications for the software on environmental monitoring system and relevant software completed – the purchase is considered under the new IRA2013 project in 2016 | Select overall rating and provide explanation/ supporting background information deemed relevant to support rating (e.g., Is the procured EQ on schedule as regards delivery/ custom clearance/ installation-commissioning/ utilization? If not, what is being done to overcome difficulties? How did/ will the training received through FEs/ SVs support the establishment of new services? Are the trainees still employed? How did/ will the technical guidance received during/after EMs help improve capabilities of the Counterpart Institute? Was/will the knowledge and experience gained by TC/ WS participants shared/ be shared among colleagues to enhance institutional performance? How was/ will this done/ be done?) |
| Expert Missions (EM) | ☐ Not Applicable ☐Very Good  Good ☐ Fair ☐ Poor |  |
| Fellowships (FE) | ☐Not Applicable  Very Good ☐ Good ☐ Fair ☐ Poor Getting training certificate in Eddy current test Level-2 and ultrasonic Test Level-2 in methods: Phased Array, Time of Flight Diffraction (TOFD) and Advanced sizing techniques .)(3.3.2) |  |
| Scientific Visits (SV) |  Not Applicable ☐ Very Good ☐Good ☐ Fair  Poor Difficulties with accepting requested SVs in several organizations in some member states. |  |
| National Training Courses (TC) |  Not Applicable ☐ Very Good ☐ Good ☐ Fair ☐ Poor [Provide explanation]…… |  |
| Meetings (MT)/ Workshops (WS) | ☐Not Applicable  Very Good ☐ Good ☐ Fair ☐ Poor |  |
| SECTION-4: COMMENT AND RECOMMENDATIONS BY CP |  |  |
| Rating by CP | The project performance: ☐ Very Good  Good ☐ Fair ☐ Poor☐ Very Poor [Provide explanation]…… | Select rating based on experience thus far and provide explanation/ supporting background information deemed relevant to support rating |
|  | The support received from the Agency:  Very Good  Good ☐ Fair ☐ Poor☐ Very Poor [Provide explanation]…… There is a need for more IAEA support in preparatory and technical issues, some difficulties are such as; - Long duration of organizing the activities; for example conducting a scientific visit - Difficulties with timely issuance of entry visa for NEX and IEX - Extended involvement of high professional experts from western countries such as Spain, Germany |  |
| Lessons learned | Taking into account the complexity of areas and scope of assistance; considering that some factors are beyond of the project management team control as delays in completion of scheduled national activities in BNPP-1 commissioning and operation, submission of required documents by the main contractor, as well as some new emerging high priority needs for assistance, the regular monitoring, reviews and flexibility to adjust properly planned work plan activities were extremely important for the successful implementation and completion of stated objectives. In this regard, several of the originally planned work plan activities were refocused and some additional requests for assistance incorporated and implemented, which led to the successful achievement of project’s objectives. Project management approach including active participation, contribution and coordination between stakeholders and project team members, the close follow-up and the high level of financial GCS allocations are among main factors of success. Utilizing the available expertise and experience in knowledge management system for further enhancement of the safe and reliable operation of the plant. | Highlight key factors of success / failure that can promote/ hinder the achievement of project outputs and may impact TC Programme delivery |
| Recommendation(s) by CP to: | PMO TO ☐NLO/Government ☐CP Management ☐Other (specify) As follow-up the successful implementation of the assistance it is recommended to : - Continue the current practice of capturing and tracking recommendations from expert mission reports with emphasis on the need for more effective implementation - Continue with efforts to overcome difficulties with participation of qualified external experts in field missions in Iran and acceptance of Iranian experts for SVs and FSs. | Select addressee and provide recommendation(s) to be addressed |
| SECTION-5: OUTCOME PROGRESS: (1st column prefilled) |  |  |
| Outcome Statement Assessment of BNPP performance and safety indicators and Improvement in some area |  Achieved☐To be achieved as planned (on schedule) ☐ Delayed☐Other (specify) Increased capacity and capabilities in independent review and acceptance of safety reports for BNPP-1. Established technical requirements and specification of safety and operational performance indicators (PI) and training on software application that supports PI system management and its application. Achievements from the IAEA assistance support under previous and current TC projects, contributed significantly to :the successful commissioning of the first NPP unit at Bushehr; reached full (100%) power on 3 September 2012; turned-over to the owner in summer 2013; and proceeds with its initial operation, producing electricity to alleviate high electricity demand in the country and with large spin-off effects to the future development of National nuclear power programme and whole national infrastructure. | Select status and provide explanation/ supporting background information (e.g.,based on the outcome indicator and its target value, to what extent the outcome is being achieved? Is there any deviation from expectations? Why?) |
| Outcome Indicator (s) Performance and safety indicators are assessed and in some area improved by the end of 2015 in comparison with the baselin |  |  |

| SECTION-6: CLEARANCE BY NLO |  |  |
| --- | --- | --- |
| Clearance by NLO | Date: | Day, Month and Year |
|  | Remarks: | Provide any additional remark deemed relevant |
| SECTION-7: FEEDBACK BY IAEAON THE REPORT |
| Comments by TO(s) | ☐ Very Good ☐ Good ☐ Fair ☐ Poor ☐ Very Poor[Provide explanation]…… | Rating and feedback from TO(s)on the report |
| Comments by PMO | ☐ Very Good ☐ Good ☐ Fair ☐ Poor ☐ Very Poor[Provide explanation]…… | Rating and feedback from PMO(s) on the report |

1CP: Counterpart					2 NLO: National Liaison Officer

3PMO: Programme Management Officer			4TO: Technical Officer