## IRA2013_May 2017
IRA2013: Action Plan for implementation of Workplan activties in 2016-2017
as of 15.05.2017
Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed
2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | PRM | 14-15 Feb. 2017 | Completed
1.5 IAEA Field Monitoring (once per quarther)
2.2 Preparatory visit for OSART mission
3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | 14-16 Nov 2016 | Completed | H
2.4 Implementation the nuclear safety oversight function
4 | 2.4.1 | One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: | 1 IAEA+2IEX |  | Tehran | EM | Q4/2017 |  | M | NPPD will send the expectations and scope by the end of July.
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
5 | 3.1.1 | WS on "modern methods for measuring hydrogen in primary loop and analysis | IAEA: Song, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | 18-21 Feb 2017 | Completed | H
3.2 Training on environmental qualification of safety equipment of BNPP-1
6 | 3.2.1 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD | SV | Q4/2017 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or France
7 | 3.2.2 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q4/2017 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or France
8 | 3.2.3 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang, NPPD: Banazadeh | 1 NEX |  | TBD | SV | Q4/2017 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | To be refocused on specific issues of integrated KWU equipment into BNPP-1 Project. The venue can be Germany or France
3.3 Training on equipment reliability assessment techniqes of equipment during operation
9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" | IAEA: K. Kang, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016 | TO is awaiting confirmation/response from the CP for this mission. We urgently need the confirmation of dated for this mission (possible to take place end of November and December if we receive the proposed dates by next week.) |  | Deleted
10 | 3.3.10 1 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017.
11 | 3.3.10 2 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017.
12 | 3.3.10 3 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017.
13 | 3.3.10 4 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | Q4/2017 | Shifted from previous project IRA /2/011 | H | NFs will send to IAEA by the end of May, 2017.
14 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | 11-13 Feb 2017 | Completed | H |  | Completed
15 | 3.8.1-1 | EM on review of BNPP-1 AMP | IAEA: K.Kang,Robert Krivanek, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | EM | Q2 / 2018 |  | H | New Request | EM-Q2-2018-Talebi
16 | 3.8.1-2 | SV on AMP | IAEA: K.Kang,Robert Krivanek, NPPD: Ghods | 4NEX |  | TBD | SV | Q4/2017 |  | H | NFs will send to IAEA 6 months before.It is prefer to France-Areva. | SV-Q4-2017-Talebi
17 | 3.8.1-3 | Procurement of FAC software , COMSY | IAEA: K.Kang, NPPD: Ghods |  |  |  | Procurement | TBD |  | M | New Request. IAEA will inform NPPD on its price by the end of Feb, 2017. | Supply of Comsy-Talebi
18 | 3.8.2 | WS developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: K.Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q3/2018 |  | H |  | WS-Q3-2018-Talebi
3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1
19 | 3.10.1 | EM on "Assistance on review of safety analysis model for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Ghods-Derakhshandeh | 1 IAEA+3IEX/5 days( HBA 5 days) |  | Tehran | EM | Q3 / 2017 | Pending information on models and any result of calculation-information needed one month prior to the mission date. Need confirmation on mission dates. | M | NPPD to provide one month before, information on modeles and any result of calculation. In progress. | EM-CFD-Q3-2017-Raji
20 | 3.10.2 | EM on independent analysis of root-cause results for BNPP-1 | IAEA: Dian Zahratka, P.Tarren, NPPD: Ghods/Derakhshandeh | 1 IAEA+3IEX/5 days |  | Tehran | EM | Q2/2017 19-23 August |  | H | NPPD to provide two month before information in English on the root cause analysis in the last two years.Dian Zahradka is the Implementing Officer from IAEA side. | EM-RCA-Q2-2017-Raji
3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1
21 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q4 /2017 | In progress | M | IAEA request further clarification of what NPPD are seeking at least two months before.(availability of software and scope of the mission) | EM-Q4-2017-Ertejaee
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
22 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: T. Ulses, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2018 |  |  | NPPD Provide more information two months before. | Q2-2018
23 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; C .Hill, NPPD: Ghods-Abbaspour | 1 IAEA+2 IEX |  | Tehran | EM | Q4/2017 |  | M | NPPD Provide more information two months before. | Q4-2017-Ertejaee
5.5 Assistance in development of selected training scenarios for severe accidents in FSS
24 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | Q2 /2018 |  |  | To be discussed after implementation of 6.3.1,
5.6 Assistance in development & improvement of training system of maintenance & repair personnel
25 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: J. Song NPPD: Rahnama-Talebianzadeh | 1IAEA+2IEX |  | Bushehr/Tehran | EM | Oct. 2017 |  | H | NPPD will provide more information on area(s) two months before.
F
26 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA:V.Welter, NPPD: Abbaspour | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 - 06-10 May 2017 | NPPD will send its expectations and scope 2 months in advance. In progress | M | NPPD: To send clarification on the focus: Training on off-site response to radiological emergency situation BNPP-1. Ramon De la Vega is the IEC Contact Point.BNPP will send off-site emergency prepardeness and response plan by the end of March, 2017.
6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1
27 | 6.3.1 | EM to review progress in development of the severe accident analysis model for BNPP-1 | IAEA: T. Ulses, NPPD: Ghods/Derakhshandeh | 1IAEA+2IEX |  | Tehran | EM | Q4/2017 |  | H | IAEA will request more clarification of the mission and NPPD will reply by the end of June. | SAM-Q4-2017-Raji
28 | 6.3.2 | RM to review the progress in development of the severe accident managementguidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | TSR-AM | Q3/2017 |  | H | NPPD will provide additional information on statues of SAMG by the end of June.
7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1
29 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening, NPPD: Abbaspour | 1IAEA+3IEX |  | Bushehr | EM | 3-7 Dec 2016 | Completed | H
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
30 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: D. Talleria, NPPD: Abbaspour | Procurement |  | Bushehr | Procurement | May, 2017 | IAEA had initiated the procurement process, GCS has been transferred into the project. The procurement process is in proceed . It is expected to install and operate in Nov. 2017 at Bushehr. | H | IAEA is requested to provide the report on the last status of submitting ESTE to CP.
2.3 Implementation of OSART mission
31 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  | Bushehr | EM | 29 Sep- 17 Oct. 2018 |  | H
2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers
32 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | Tehran | EM | 16-20 July 2016 | Completed | H
2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission
33 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q4 2018( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1-3NEX |  | TBD | FS | 2017 |  | H | NPPD requests to involve 3 NEXs.One place agreed for 13-30 November 2017 in Leningrad.
34 | 2.7.2 | Asist visits on operation,Maintenance and technical support areas as preparation for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 1IAEA+4IEX |  | Q4 / 2017 , 5 working days/ Bushehr | EM |  |  | H
35 | 2.7.3 | Asist visits on HTO and GSR-Part2 areas as preparation for OSART mission | IAEA: P. Tarren, NPPD: Khezri | 1IAEA+2IEX |  | 3 working days , Bushehr | EM | Nov. 2017 |  | H | Ms.Helen Rycraft is implementing officer from IAEA side.
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
36 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: B.Song, K.Makela, NPPD: Deylami | 1 IAEA+2IEX |  | Bushehr | WS | Q2/2017 | Deleted. | H
3.4 Training on containment leakage tests and calculations after outage
37 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
38 | 3.4.2 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
39 | 3.4.3 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
40 | 3.4.4 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 |  | H | Move to the next cycle. (2018-2019)
3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system
41 | 3.5.1 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M
42 | 3.5.2 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M
43 | 3.5.3 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M
44 | 3.5.4 | SV on "Decreasing the time response of modern I&C system" | IAEA: J. Eiler, NPPD: | 1 NEX |  | China | SV | 22-30 Nov. 2017 | 4 NFs sentin Jan. 2017, In progress | M
3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR
45 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1IAEA+3IEX |  | Bushehr | WS | Q1/2018 |  |  | NPPD requsted to provide more information to the content of the WS by the end of Sep. 2017.
3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles
46 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  | Tehran | EM | Q1/2017 | Deleted | H |  | Deleted
3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system
47 | 3.9.1 -1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests. | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  | Tehran | WS | Dec,2017 |  | M |  | Q4-2017-Talebi
48 | 3.9.1 -2 | WS on High and low cycle fatigue analysis for strength assessment of Reactor Coolant System | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  | Tehran | WS | TBD |  | M |  | TBD-Talebi
3.12 Assistance in performing the living PSA of the BNPP-1
49 | 3.12.1 | EM to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: I Kuzmina, NPPD: Ghods | 1IAEA+2IEX |  |  | EM | Q1/2018 |  |  | NPPD: To send information on the scope and focus including utilization of risk spectrum softwarein two months before the mission. | EM-PSA--Q1-2018-Raji
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
50 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: A. Gonzalez Espartero / T.Ulses, NPPD: Ghods | 1 IAEA+2 IEX |  | Tehran / Bushehr | EM | Q2/2017 | Dublicated with 3.14.2 | M | NPPD requested to provide information two months before. | Deleted
4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
51 | 4.1.1 | EM on modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes | IAEA: H. Varjonen, NPPD: Roshankar | 1IAEA+3IEX |  | Bushehr | EM | Q3/2017 |  | H | NPPD will provide more information on area(s) by the end of May.
4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
52 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:Kang, NPPD: Mohebi/ | 1IAEA+3IEX |  | Tehran | EM/HBA | Q4/ 2017, |  | H | NPPD will update the expectations by the end of May,2017.
5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
53 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  | Bushehr | WS | Q3/2017 |  | M | NPPD has been sent the expectation in 29.04.2017
5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
54 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before.
55 | 5.2.2 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before.
56 | 5.2.3 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 |  | M | NFs will send 6 months before.
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
57 | 7.4.2 | EM on "Review and assesment of results of environmental monitoring programme using the software ESTE" | IAEA: D. Talleria, NPPD: Abbaspour | 1 IAEA+2IEX |  | Bushehr | EM | Q2/2018 |  | M | One year after installation of ESTE at BNPP-1.
4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators
58 | 4.4.1 1 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016. | H | New request for 2016 NPPD, China
59 | 4.4.1 2 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016. | H | New request for 2016 NPPD, China
60 | 4.4.1 3 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. S. Kang NPPD:Roshankar | 3NEX | 5 days | TBD | SV | 2017 | 3 NFs sent through official channel 23.11.2016. | H | New request for 2016 NPPD, China
4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs
61 | 4.3.1 | WS on outage optimization through advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs | IAEA: H. Varjonen NPPD:Roshankar | 1IAEA+3IEX | 4 days | Bushehr |  | WS | Q3/2017 | H | NPPD will provide more information on area(s) by the end of May. (It is not possible to combine 4.1.1 and 4.3.1)
Cancelled
| Further clarifications needed | [6 empty] | 27 active tasks
| Completed | [6 empty] | H= 18,M=9
Move to the next cycle