## PCMFExport 1
Overall Objective (or Developmental Objective)
To enhance ownerâ€™s capabilities towards safe and reliable operation and maintenance of Bushehr NPP-1
Logical Framework Matrix (LFM) for IRA2014001
Export to Excel¦Export to Excel 2007¦Print¦Close Window
| Design Element | Indicator | Means of Verification | Assumptions
Outcome | Enhanced owner's capabilies towards safe and reliable operation and maintenance of BNPP-1. | Performance and safety indicators are assessed by the end of 2018 and in all areas implemented in 2019 in comparison with the baseline | Annual report of performance section in 2018 IAEA and NPPD assessment and project review meetings | Qualified external experts can be readily recruited for the implementation of planned activities and adequate progress is made in finding suitable institutes for hosting Scientific Visits and Fellowships. Adequate resources are available for providing laboratory equipment and improving access to proper computer codes necessary for nuclear safety.
Output | 1 Project Management Team Operational
| 2 A reviewed and improved safety management programme | Safety performance indicators are collected and analyzed by the end of 2018 and implemented in 2019,Capabilities for independent safety analysis | Annual report of performance section in 2018
| 3 Revised and improved Technical Support program . | 25 staff of Technical support department capable of using the new methods in planning and implementation of new methods for modernization of equipment and inspection activities. | assessment report
| 4 An optimized and updated Maintenance and Outage Management programme | 25 staff of M&R department capable of using the new methods in M&R process planning and implementation of procedures | assessment report
| 5 Improved Human resources management system. | All procedures and training plans are revised by the end of 2Q 2018 and implemented in 2019 | Revised procedures , docs. and training plans
| 6 A reviewed and updated programme on accident/severe accident management and nuclear emergency response | procedures and accident management plans are revised by the end of Q2, 2018 and implemented in 2019. 25 staff of BNPP personel capable of using the new methods inaccident management | Annual report of safety manger
| 7 An improved programme for occupational safety and environmental management | procedures and their plans are revised by the end of Q2 , 2018 and implemented in 2019 | Annual report of safety manger
Activity (Summary) | 1 .1 Confirming/Setting-up project team (CP, CP team in MS, PMO/TO)
1 .2 Conducting project review meetings
1 .3 Updating project work plan
1 .4 Preparing and submitting PPARs (every six months)
1 .5 IAEA Field Monitoring
2 .1 Safety training on radioactive waste management, radiation monitoring, core calculation and emergency preparedness
2 .2 Training on safety management in the field of operation, radiation protection, technical support and emergency preprdness.
2 .3 Preparatory mission for OSART mission
2 .4 Implementation of OSART Mission
2 .5 Implementation the nuclear safety oversight function
2 .6 Assistance in review of implementation of the developed NPPD Co. Integrated Management System, plans for improvements including safety requirements for compliance by servises providers
2 .7 Implementation of effective safeguards system for BNPP-1 operators
2 .8 Implementation the Nuclear safety oversight function
3 .1 Training on modern method for measuring hydrogen of aerosol, and corrosives chemical-physical cleaning of radioactive Power plant equipment
3 .2 Training to strengthen Technical Control Section capabilities for technical and quality control of BNPP-1 maintenance and modifications
3 .3 Training on environmental qualification of safety equipment of BNPP-1
3 .4 Training on failure analysis and necessary tests on equipment during operation
3 .5 Training on after outage containment tests and calculations
3 .6 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system;
3 .7 .Assistance to strengthen the capability of BNPP personnel on application of new IAEA standards in modification MCR (new TLSU system)
3 .8 Training on computer networks security
3 .9 Assistance in development of measures for extention of BNPP-1 refueling period through modification of nuclear fuel
3 .10 Assistance in reactor core operation in normal and transient conditions
4 .1 Training on modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
4 .2 Training on implementation of strategies and advanced method/tools for Condition Based Maintenance at NPPs.
4 .3 Training on advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor , refuling machine ,equipment and pipelines at Nuclear Power Plants
4 .4 Trainig on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strengthen the capablity refuling machine operators
4 .5 Training on reverse engineering of some of the integrated equipment in BNPP-1
4 .6 Training for optimizing the reverse engineering of some of the integrated equipment in BNPP-1 and designing of special tools
4 .7 Training on enhancement of preparedness of BNPP emergency repair teams.
4 .8 Assistance on development of a procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
5 .1 Training on competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel
5 .2 Training on competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel
5 .3 Assistance in improvement of the performance assessment system of BNPP-1 personnel
5 .4 Assistance in improvement of job classifications to support career development for Bushehr NPP staff
5 .5 Assistance in improvement of job career-paths guidance for Bushehr NPP
5 .6 Assistance in development of selected training scenarios for severe accidents in FSS
5 .7 Assistance in development & improvement of training system of maintenance & repair personnel .
6 .1 Training on off-site response to radiological emergency situation BNPP-1.
6 .2 Assistance in reviewing BNPP on-site emergency preparedness program
7 .1 Training on improving BNPP occupational health and safety management system including specifications and methods for reducing the human errors and supervision on personnel performance.
7 .2 Training on assessing doses in normal operation and radiological emergency.
7 .3 Assistance on methods in alpha and beta-emitting radionuclides in high activity samples.
7 .4 Assistnace on methods for gamma spectrometry for high activity samples and counting devices in spectrometry Laboratories