## IRA2013
IRA/2/013 activities in Q4-2016 and Q1-2017
Task 3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days | Bushehr | WS | Q4/2016 | H | Planned for 14-16 November 2016
Task 5 | 3.1.1 | WS on "modern methods for measuring hydrogen concentration in containment " | IAEA: J. Song, NPPD: Deilami | 1 IAEA+3IEX | Bushehr | WS | Q4/2016 | H | NPPD to provide the final expectations by end of May.
Task 10 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX | Tehran | WS | Q3/2016 | H
Task 14 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX | Tehran | EM | Q4/2016 | H | IAEA request further clarification of what NPPD are seeking.
Task 18 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: D. Drury, J. Song NPPD: Rahnama-Talebianzadeh | 1IAEA+2IEX | Bushehr/Tehran | EM | Q4/2016 | H
Task 22 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening, NPPD: Abbaspour | 1IAEA+3IEX | Bushehr | EM | Oct.2016 | H | IAEA to confirm the date. BNPP-1 will provide tools for measurements.
Task 37 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX | Tehran | EM | Q1/2017 | H
Task 42 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:J. Moore, NPPD: Tajbakhsh | 1IAEA+3IEX | Tehran | EM/HBA | Q4/2016 | H | NPPD to provide expectations,focus and approach by the end of june.