PROCEDURE
of Bushehr-2Construction

Schedule Development and Support

TABLE OF CONTENTS

LIST OF AGREEMENT	3

1.	APPLICABILITY	4

2.	TERMS, DEFINITIONS AND ABBREVIATIONS	4

3.	STRUCTURE OF SCHEDULES	4

3.1.	Hierarchy of Schedules	4

3.2.	Relations between the Schedules	5

3.3.	System of Schedule Coding	5

3.4.	Names used in the Schedules	5

3.5.	Work Breakdown Structure (WBS)	5

3.6.	Identification of Activities	7

3.7.	Schedule Archiving and Statistics Accumulation	7

4.	SCHEDULE UPDATING	7

4.1.	COMPILATION OF THE UPDATING OF THE FORM AND ITS DISPATCH TO THE PERSONS IN CHARGE OF DISCIPLINES ON SITE	7

4.2.	FORM FILLING WITH ACTUAL DATA BY PERSONS IN CHARGE OF DISCIPLINES AT BUSHEHR-2 NPP CONSTRUCTION SITE	8

4.2.1.	General Provisions	8

4.2.2.	Rules of Entering Actual Information	8

4.2.2.1.	Filling of the Field “Actual as of Updating Date”	8

4.2.2.2.	Filling of the Field “Actual Finish as of Updating Date”	9

4.2.2.3.	Filling of the Field “% as of Updating Date”	10

4.2.2.4.	Filling in of the Field “Remarks”	11

4.2.2.5.	Assignment of Personal Supervisor to Each Activity	11

4.3.	PROCESSING OF ACTUAL DATA	11

4.4.	ENTERING OF ACTUAL DATA INTO THE SCHEDULE	11

4.5.	SCHEDULE CALCULATION, ANALYSIS OF DEVIATIONS AND DEVELOPMENT OF SUGGESTIONS ON THE METHOD OF DELAY COMPENSATION	11

4.6.	COMPILATION OF ANALYTICAL REPORT	12

4.6.1.	Progress Report	12

4.6.2.	The List of changes, corrections and compensating activities for Level-2 Schedule or the reporting period	12

4.6.3.	List of Project Critical Path Activities	13

4.7	CONSUMERS OF THE SCHEDULE (ROLES AND FORMAT OF THE USE OF INFORMATION FROM THE SCHEDULE)	13

5.	ALLOCATION OF CONTRACTOR’S STRUCTURAL UNITS RESPORNSIBILITY	13

5.1	PARTICIPANTS OF THE PROCESS	13

5.2	MAIN FUNCTIONS OF LEVEL 1, 2, 3 SCHEDULES DEVELOPMENT AND SUPPORT PROCESS PARTICIPANTS.	13

5.2.1	Comprehensive design development bureau No.4 of NIAEP JSC	13

5.2.2	JSC ASE-NIAEP Division for NPP Construction in Iran	13

5.2.3	JSC ASE-NIAEP Branch Office at Bushehr NPP Site	14

5.2.4	JSC ASE-NIAEP Division for Prjects Methodology	14

6.	MAIN TARGET DATES OF SCHEDULING.	14

ANNEX A	15

ANNEX B	17

- LIST OF AGREEMENT

| Activity | Position | Name | Signature | Date |
| --- | --- | --- | --- | --- |
| FINALLY AGREED BY | Vice-President for the Projects in Middle East and Central Asia | V. N. Pavlov |  |  |
| AGREED BY | Head of Division for NPP construction in Iran | А.А. Shevyriev |  |  |
| AGREED BY | Deputy Head of Division for NPP construction in Iran | S.А. Amburtsumian |  |  |
| AGREED BY | Deputy Director for Designing – Head of Complex Design Bureau (BKP-4) | А.P. Zonov |  |  |
| AGREED BY | Head of network scheduling department of BKP-4 | А.U. Pankratijev |  |  |
| AGREED BY | Head of Division for methodology of Projects | А.А. Zyablov |  |  |

- APPLICABILITY

The document establishes the basic rules and approaches towards the development and support of Bushehr-2 NPP construction.

The document change may be initiated by the Principle and Contractor and effected upon mutual consent.

- TERMS, DEFINITIONS AND ABBREVIATIONS

Тerms, definitions and abbreviations used only in the text of this procedure are indicated below:

| Terms | Definitions |  |
| --- | --- | --- |
| Level 0 schedule | Level 1 General Time Schedule (Level 0) is the schedule containing all main activities and milestones of the Project envisaged in Contract activities implementation The dates set forth in the General Time Schedule are directive ones and may be changed only after agreed with the Principal. |  |
| Level 1 schedule | Overall Time Schedule (OTS) is a program which is fully compatible with the General Time Schedule which is based on the critical path method. This Time Schedule includes all activities starting from Project start through to completion that shall be submitted to the Principal. |  |
| Level 2 schedule | Integrated overall time schedule (IOTS) is a program which is fully compatible with the Overall Time Schedule which is based on the critical path method (CPM) |  |
| Level 3 schedule | Detail Time Schedules (DTS) are the separate schedules that include design, licensing, LMCE manufacture, supply, construction, installation and commissioning and are completely compatible with IOTS |  |
| Abbreviation/ | Description |  |
| WBS | Work Breakdown Structure that is a hierarchical sequential decomposition of the project work packages into different levels, detailed work packages to ensure the achievement of specific objectives |  |
| KKS | Electric Power Plants Coding System developed by the Technical Committee of Association of Industrialists VGB (Germany) |  |

- STRUCTURE OF SCHEDULES

  - Hierarchy of Schedules

Schedules of four levels are used in the system:

Level 0 schedule - General Time Schedule

Level 1 schedule – OTS (Overall Time Schedule),

Level 2 schedule – IOTS (Integrated Overall Time Schedule)

Level 3 schedule – DTS (Detail Time Schedules)

General Time Schedule (Level 0) is the schedule containing all main activities and milestones of the Project envisaged in Contract activities implementation The dates set forth in the General Time Schedule are directive ones and may be changed only after agreed with the Principal.

Overall Time Schedule (Level 1) is a program which is fully compatible with the General Time Schedule which is based on the critical path method. This Time Schedule includes all activities starting from Project start through to completion that shall be submitted to the Principal.

Level 1 Schedule includes breakdown of activities for design, manufacturing, supply, construction, erection, testing and commissioning into buildings.

Integrated overall time schedule (Level 2) is a program which is fully compatible with the Overall Time Schedule which is based on the critical path method (CPM).Level 2 Schedule shall be divided into two different stages:

Stage 1: Initial stage (Date of activities start of the Contract till the first pour of concrete);

Stage 2: Stage of activities implementation.

Detailing of Level 2 Schedule shall be performed as below:

- for civil and design activities – floor/elevation of the activities performed;

- for equipment installation activities - floor/elevation, where equipment is being installed, for activities of pipeline installation – system in the building;

- for electric wiring, ventilation installation, I&C, communication and alarm, lighting, radiation control systems  – building;

- for LMCE manufacture and supply – dates delivery to the site of each Unit;

- for manufacture and supply of the rest of equipment – system/building;

- for commissioning activities – commissioning stages.

Detail Time Schedules (Level 3) are the separate schedules that include design, licensing, LMCE manufacture, supply, construction, installation and commissioning and are completely compatible with the Integrated Overall Time Schedule, but sufficiently detailed to enable monitoring. All detail time schedules are subject to agreement with the Principal.

  - Relations between the Schedules

Level 1 and 2 schedules are combined into one schedule where difference between the levels is indicated by activity codes. Level 3 schedules are synchronized with Level 2 schedule by means of reporting formats.

  - System of Schedule Coding

Below the structure of schedule identification number is provided:

Bushehr-II-year.mm.dd, where year.mm.dd  is the schedule updating time.

  - Names used in the Schedules

All scheduled activities, work breakdown structure and activity codes have bilingual names, in English and in Russian.

  - Work Breakdown Structure (WBS)

| Section | 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- | --- |
|  | N | A | N | A | A | AA |

N: Digital,

А: Digital and/or letter symbol,

Section 1: Object: number of the unit of object of BNPP-2 (0, 2, 3).

| 0 | General |
| --- | --- |
| 2 | Unit 2 |
| 3 | Unit 3 |

Section 2: Referred to Parts of the Project

| G | General |
| --- | --- |
| B | Buildings & Structures |
| P | Process |
| E | Electrical |
| A | I&C |

Section 3: Numbering for similar systems or plants, being part of single sector of power installation codes (0 - 9)

Section 4: Referred to code of building / system as belongs according the Project/

Letter for building or system according to KKS.

Section 5: Referred to code of system object that are based on coding of project.

Letter for building or system according to KKS.

Section 6: Type of Activities

| D# | Design |
| --- | --- |
| BD | Basic Design |
| DD | Detailed Design |
| ES | Engineering Survey |
| M# | Manufacture & Supply |
| R# | Site preparation |
| V# | Civil Works |
| E# | Erection Works |
| C# | Commissioning Works |
| L# | Licensing |
| P# | Permits |
| G# | General |

  - Identification of Activities

List of codes of activities

| № | Name of Code |
| --- | --- |
| 1 | Number of the Unit |
| 2 | Project Part |
| 3 | KKS code of building |
| 4 | KKS code of system |
| 5 | Types of Activities |
| 6 | Responsibility (The Principal / The Contractor ) |
| 7 | Executor (Subcontractor) |
| 8 | Stage (Preliminary /Implementation ) |
| 9 | Level of Schedule (1,2,3) |
| 10 | ID code of an activity of higher level |

  - Schedule Archiving and Statistics Accumulation

A new copy of the working Schedule is generated during each Schedule updating, with a new ID in conformance with updating date.  Actual information is also entered into the newly generated schedule. After all compensating measures are taken, changes are registered and analytical report is issued, the schedule is assigned the ”Valid” status.

The “Schedule Archive” section is arranged in the shared information environment accessible for the Principle and the Principal. The schedule valid in the previous month is handed over to the “Schedule Archive”.

- SCHEDULE UPDATING

Updating consists of the following stages:

- compilation of the updating of the form and its dispatch to the persons in charge of disciplines on site;

- form filling with actual data by persons in charge of disciplines at Bushehr-2 NPP construction site;

- processing of actual data;

- entering of actual data into the schedule;

- schedule calculation, analysis of deviations and development of suggestions on the method of delay compensation;

- compilation of analytical report.

  - COMPILATION OF THE UPDATING OF THE FORM AND ITS DISPATCH TO THE PERSONS IN CHARGE OF DISCIPLINES ON SITE

The form is compiled automatically with the help of a macro in MS Excel software.

The sample of updating form is provided in Appendix A to this document.

After the form is compiled, it is sent to the responsible persons on Site.

  - FORM FILLING WITH ACTUAL DATA BY PERSONS IN CHARGE OF DISCIPLINES AT BUSHEHR-2 NPP CONSTRUCTION SITE

The responsible specialists of the Contractor on site enter the actual information into the reporting form table.

The requirements for form filling in are provided hereinafter.

    - General Provisions

The following columns to be filled in:

- ”actual start as of updating date”;

- „actual finish as of updating date”;

- „% as of updating date”;

- „Remarks”.

    - Rules of Entering Actual Information

Updating form contains the built-in diagnostics tool to check the actual information entering correctness. So one shall pay attention to the relevant fields of the form and shall analyze for absence of mistakes with subsequent correction.

      - Filling of the Field “Actual as of Updating Date”

Is entered into relevant column „Actual Start as of the date of updating”.

The date of actual start shall be within the reporting period (for example, schedule is updated as of 01.04.2015, then the starting date may be from 01.03.2015 to 30.03.2015).

Adjustment of actual start may be an exception, if during the previous updating it was missing or incorrect.

The starting date of the activities being performed and earlier completed is not necessary (in „Activity status” in this case is „being performed” or „Completed” is indicated), except for the case of adjustment.

At the same time it is necessary to pay attention to the column “Wrong start”.

In case the actual start is entered correctly, the column “Wrong start” shall have the value “OK”. In case information entered is incorrect the below error messages are issued automatically:

| No. | Error | Error description | Importance | Actions required / Remarks |
| --- | --- | --- | --- | --- |
| 1. | ”Start is missing” | Actual finish and/or % of fulfilment is entered of an activity which has not yet started, and actual starting date is missing | Critical | Actual start shall be entered |
| 2. | ”Repeated” | Actual start equal to the schedule start is indicated | Not critical | Delete value in “actual Start as of the date of updating” |
| 3. | ”Start is changed” | Actual start for an activity being performed or completed is indicated which differ from actual start specified during the earlier periods | Not critical | Allowed if refined |
| 4. | ”Start elapsed” | Actual start of an activity not yet started is indicated before the reporting period | Not critical | Allowed if refined |
| 5. | ”Start has not occurred” | Actual start is indicated exceeding the date of updating | Critical | Correct date shall be indicated. If the indicated starting date is expected, relevant comment shall be provided in “comments” column. |
| 6. | ”Is not a date” | Format of the information entered into the „actual start as of the date of updating” is not a date | Not critical | Information in the form of a date shall be entered. |

      - Filling of the Field “Actual Finish as of Updating Date”

Is entered into relevant column “Actual Fish as of Updating Date”.

The actual finish date shall be within the reporting period (similar to actual start).

Adjustment of actual finish of the prior finished activities may be an exception, if during the previous updating it was missing or incorrect.

Entering the actual finish date of the activities being performed and earlier completed is not necessary (in „Activity status” in this case is „being performed” or „Completed” is indicated), except for the case of adjustment.

At the same time it is necessary to pay attention to the column “Wrong finish”.

In case the actual finish is entered correctly, the column “Wrong Finish” shall have the value “OK”. In case information entered is incorrect the below error messages are issued automatically:

| No. | Error | Error description | Importance | Actions required / Remarks |
| --- | --- | --- | --- | --- |
| 1. | ”Finish is missing” | Actual % equal to 100 is specified and data of actual finish is not specified | Critical | Actual finish shall be entered |
| 2. | ”Repeated” | Actual finish equal to the schedule finish is indicated | Not critical | Delete value in “actual finish as of the date of updating” |
| 3. | ”Finish is changed” | Actual finish for an activity being performed or completed is indicated which differ from actual finish specified during the earlier periods | Not critical | Allowed in case of adjustment |
| 4. | “Finish has passed” | Specified actual finish for an activity not yet started before beginning of reporting period | Not critical | Allowed in case of adjustment |
| 5. | “Finish has not been reached yet” | Actual finish is after the date of updating | Critical | Correct date shall be indicated. If the indicated finish date is expected, relevant comment shall be provided in “comments” column. |
| 6. | “Precedes the start” | The specified finish date precedes the actual start date | Critical | Correct date shall be indicated |
| 7. | ”Is not a date” | Format of the information entered into the „actual finish as of the date of updating” is not a date | Not critical | Information in the form of a date shall be entered. |

      - Filling of the Field “% as of Updating Date”

The percentage of work performance is defined by the Contractor’s specialist by an expert assessment on the basis of the presented data confirmed by the Principal. The data are entered into the respective column “% as of updating date”. Percent may be within the range form 1 up to 100.

It is not necessary to specify 0% except for the case of adjustment (for example, if the per cent previously has been incorrectly).

The percent of implementation is not also required, in case the previously started activity was not performed during the reporting period (percent of implementation did not change within the reporting period).

At the same time one shall pay attention to the column “Errors in %”.

In case % as of updating date is entered correctly, the column “Errors in %” will be “OK”.

In case information entered is incorrect the below error messages are issued automatically:

| No. | Error | Error description | Importance | Actions required / Remarks |
| --- | --- | --- | --- | --- |
| 1. | “ % is missing” | Actual start is indicated and at the same % is not specified | Critical | % shall be indicated |
| 2. | “ 100 % is not specified” | Actual finish is entered and at the same time 100% is not specified | Critical | 100 % shall be specified, or actual finish date shall be deleted if activity has not been completed yet |
| 3. | “Repeated” | % is specified equal to the % according to the schedule | Not critical | Delete value in the field “% as of updating date” |
| 4. | “% not correct” | Percent value is not numerical | Not critical | Correct % value shall be entered |
| 5. | “Increment missing” | The earlier started work was not performed during the reporting period (percent of implementation did has not changed within the reporting period) | Critical | The reason of work suspension shall be indicated in column “Remarks” |
| 6. | “Reverse increment” | The percent specified is less than the one indicated during the previous updating | Critical | The reason for reverse increment shall be indicated (adjustment, equipment dismantling due to detection of defects etc.) |

      - Filling in of the Field “Remarks”

Introduced into the column „Remarks”. The following shall be mentioned as remarks:

- reason for reverse increment,

- reason for activity suspension,

- reason for actual start and finish dates,

- reason for not starting the activity planned for start during the reporting period,

-  remarks of the activity supervisor (revelation of repetitions, incorrect/unclear statements, incorrect start or finish dates etc.);

- revision/detailing provided by the activity supervisor,

- other comments of the activity supervisor.

      - Assignment of Personal Supervisor to Each Activity

The Contractor’s personal supervisor to each schedule activity is assigned to:

- facilitation of the supervisor’s search for his own activities;

- simplification of working interaction between the supervisors of the Contractor’s Branch Office and specialists of the Contractor’s headquarters’ scheduling department.

In case supervisor of an activity is replaced, or if supervisor is assigned incorrectly in the schedule, respective comments shall be introduced into the column “Remarks”.

  - PROCESSING OF ACTUAL DATA

The actual data are processed automatically with a macro in MS Excel software.

  - ENTERING OF ACTUAL DATA INTO THE SCHEDULE

Actual data are introduced into the scheduling software with standard function of data export/import into MS Excel.

The following fields are filled in:

Activity ID;

WBS code;

Actual start is the field for the user to indicate the actual start date;

Actual finish  is the field for the user to indicate the actual finish date;

Actual % is the field for the user to enter the updated value of the performed work.

  - SCHEDULE CALCULATION, ANALYSIS OF DEVIATIONS AND DEVELOPMENT OF SUGGESTIONS ON THE METHOD OF DELAY COMPENSATION

After the transfer of all the actual data into the Schedule, Project timetable is calculated. Here the stages of the unit Commissioning shall be controlled. As all the activities in the Schedule are linked into a unique network model, any change of activity finish date which is on the critical path, will lead to revising the finish date of the whole Project.

When a Unit Commissioning stage delay is predicted, the feasibility of delay compensation is studied. To achieve the goal the current period activities are identified which, being not fulfilled or insufficiently intensive, may lead to some delay.

If a predicted delay is revealed with regard to the Unit Commissioning stages, the possibility to compensate the delay is analyzed. With this in mind, activities of the current stage are revealed which have not been performed or have been performed in the whole scope and therefore caused the delay. Afterwards, a planner of JSC ASE-NIAEP Division for NPP Construction in Iran together with technicians shall work out one or several options of solving the existing situation:

- raising the intensity rate of the activity performance – a recommendation is issued to increase the manpower involved in the activity performance,

- change of date of one or several subsequent activities,

- change of sequence of activities performance (analysis of a possibility to perform the activities in parallel).

  - COMPILATION OF ANALYTICAL REPORT

The analytical report on updating is developed automatically by means of a macro in MS Excel software. An example of a format of the Analytical report is presented in annex B.

The analytical report consists of four three items.

    - Progress Report

- It provides details of total amount of activities of the Schedule, amount of completed activities, activities being performed and not-started activities.

- Also, it specifies the total amount of the activities being performed during the reporting period and status thereof.

    - The List of changes, corrections and compensating activities for Level-2 Schedule or the reporting period

The list of recommended compensating activities is provided in order to prevent any delay from directive dates of commissioning of the NPP Unit. For each activity with predicted delays it shall be mentioned as follows: directive finish under the Contract, finish as per the results of updating during the previous period and difference in these dates (in days). Also the proposed compensating activities are described along with the finish upon the results of compensating activities.

The following belong to the significant adjustments of the Schedule within the reporting period:

- Adjustment of scopes (should be approved by the Principal);

- Change in activity durations;

- Change in the sequence of activities;

- Incorporation of the approved Detail Time Schedule into the Integrated Overall Time Schedule;

- etc.;

The reasons for adjustment are as follows:

- comments and adjustments offered by the Principal;

- modification of working documentation,

- comments and detailing of supervisors from the Contractor’s Branch Office,

- comments and detailing of departments of the Contractor’s Headquarter;

    - List of Project Critical Path Activities

Section of the analytical report that specifies the activities critical for the Project. This part of the report is a part of Levels 1 and2 schedules with Gantt diagram of the activities with zero time float, i.e. elongation of such activities results in extension of the whole Project duration.

  - CONSUMERS OF THE SCHEDULE (ROLES AND FORMAT OF THE USE OF INFORMATION FROM THE SCHEDULE)

Level 2 and 3 schedules working tool of the Contractor for arrangement and monitoring of the activities performance progress. The Contractor monthly updates and submits to the Principal Level 2 Schedule.

In case of any deviation during the updating of the Unit commissioning directive dates the Contractor shall elaborate the compensating activities for removal thereof.

If it is impossible to elaborate such compensating activities that deviations are removed, appropriate revision of Level 0 Schedule shall be agreed with the Principal in writing.

The updated Level 2 Schedule is used by the Principal’s units to monitor the progress of construction, analysis and elaboration of recommendations for optimizing the construction activities and its modification is documented in accordance with item G.4.3 of Appendix G to the Contract (“General Time Schedule can be changed only through the Contract change procedure”).

- ALLOCATION OF CONTRACTOR’S STRUCTURAL UNITS RESPORNSIBILITY

  - PARTICIPANTS OF THE PROCESS

- Comprehensive design development bureau No.4 of JSC ASE-NIAEP

- JSC ASE-NIAEP Division for NPP Construction in Iran

- JSC ASE-NIAEP Branch Office at Bushehr NPP Site

- JSC ASE-NIAEP Division for  Project Management Methodology

- Units that develop Level 3 schedules for licensing, designing, equipment supply, commissioning etc.

  - MAIN FUNCTIONS OF LEVEL 1, 2, 3 SCHEDULES DEVELOPMENT AND SUPPORT PROCESS PARTICIPANTS.

    - Comprehensive design development bureau No.4 of NIAEP JSC

- Level 1 Schedule development and participation in agreement with the Principal.

- Level 2 Schedule development and participation in agreement with the Principal.

- Agreement of adjustments of Level 1, 2, 3 Schedules.

    - JSC ASE-NIAEP Division for NPP Construction in Iran

- Agreement by the Principle of the developed Level 1 and Level 2 schedules.

- Monthly updating of Level 2 schedule

- Modification of updated level 1 time schedule  upon the result of monthly updating of level 2 schedule

- Development of the Analytical report on Level 2 schedule updating.

- Monthly submittal of the updated Level 2 schedule and updating results-based analytical report to the Principal

- arrangement of development and approval of Level 3 schedule

- Synchronization of Level 2 schedule with the approved Level 3 schedules.

- Keeping of official correspondence with the Principal on the issues of Level 1, 2, 3 schedules.

    - JSC ASE-NIAEP Branch Office at Bushehr NPP Site

- Acquisition of actual data on Level 2 schedule activities performance and filling out the updating form.

- Development of proposals on Level 2 and 3 schedules adjustment.

    - JSC ASE-NIAEP Division for Prjects Methodology

- Development and updating of regulating scheduling documents;

- Interfaces with the Principle on the issues of scheduling methodology and tools;

- Delivery of training in network scheduling.

- MAIN TARGET DATES OF SCHEDULING.

Level 1 Schedule is annually submitted to the Principal by October, 30 for approval.

Valid Level 2 Time Schedule and the updating result-based Analytical Report is submitted to the Principal monthly before the 10th of the month following the reporting one. All data actual as of the last day of the reporting month are incorporated into the schedule.

Level 3 schedules are integrated into Level 2 schedule within 10 calendar days are they are approved by the Principal.

- ANNEX A

(for reference)
Example of updating format of data collection
of Level 3 Schedule

| 01.04.2015 | - Updating date |  |  |  |  | Activity code |  |  |  |  | Responsible person |  | Data from Level 3 schedule |  |  |  | Actual data as of 01.04.2012 |  |  |  | Checking of mistakes |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID of activity | Activity status |  | Name of activity |  | Initial duration | Island | Building | Section of Project | System | Type of activity | Head of department | Supervisor | Start as per schedule | Finish as per schedule | % as per Schedule | Deviation (finish) from the Contract, days | Actual Start | Actual Finish | Actual % of performance | Remarks | for the Start | for the Finish | for % | Growth |
| Section 2. Main construction objects (№ А-86850 rev.2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Special Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Architectural and civil section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General, system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction and Erection Works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| #N100010 | Completed | Civil activities for special unit |  |  | 82 | 2 | 02.06 | ARST | && | C&I | Ivanov Р.М. | Petrov А.B. | 01.05.14 | 19.11.14 | 100 | 0 |  |  |  |  |  |  |  |  |
| Process part |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (TB30-90) Pipelines of reagents for SG chemical flushing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mechanical installation activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| #A42680 | being performed | А-159629 Erection of ammonia pipeline |  |  | 10 | 2 | 02.06 | TECH | TB30-90 | ТМР | Sidorov А.G. | Shnihelson M. | 31.10.14 |  | 56 | -7 |  |  |  |  |  |  |  |  |
| #A42690 | being performed | А-159629 Erection of hydrazine-hydrate pipeline |  |  | 10 | 2 | 02.06 | TECH | TB30-90 | ТМР | Minin А.G. | Pozharsky D.V. | 31.10.14 |  | 22 | -10 |  |  |  |  |  |  |  |  |
| #A42700 | Not started | А-159629 Erection of drainage pipelines |  |  | 10 | 2 | 02.06 | TECH | TB30-90 | ТМР | Sorokin А.G. | Smirnov D.V. | 02.04.14 |  | 0 | -10 |  |  |  |  |  |  |  |  |

- ANNEX B

(for reference)
Example of Analytical Report Format

| Analytical report upon the results of updating of Level 3 schedule ________ for the reporting period from __.__.201_ to __.__.201_ |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Summary Progress Report |  |  |  |  |  |  |  |  |  |
| Total activities in the schedule |  |  |  |  | 6412 |  |  |  |  |
| thereof | - activities completed |  |  |  | 4742 |  |  |  |  |
|  | - performed |  |  |  | 718 |  |  |  |  |
|  | - not started |  |  |  | 952 |  |  |  |  |
| Total amount of activities performed during the reporting period |  |  |  |  | 765 |  |  |  |  |
| thereof | - activities started |  |  |  | 58 |  |  |  |  |
|  | - performance duration |  |  |  | 209 |  |  |  |  |
|  | - activities completed |  |  |  | 498 |  |  |  |  |
| 3. List of Level 3 Schedule Changes and Adjustments |  |  |  |  |  |  |  |  |  |
| Activity ID | Name of activity |  | Cause of Change |  |  | Change of activities scope of |  |  |  |
| 4. Critical Path |  |  |  |  |  |  |  |  |  |