Technical and commercial proposal (TCP)

for the activities related to BNPP-1 FSS update (IRI)

Moscow

2016.

# Summary

This TCP was elaborated in compliance with the provisions stipulated in the technical part of “The protocol of the meeting related to the FSS software and hardware modification and the BNPP-1 FSS update” among the representatives of the Contractor (ASE JSC) and the Principal  (NPPD/BNPP/OCE), which took place in Tehran on  23-24.05.2016.

The issues related to the NPP FSS update are examined in BNPP-1 TCP within the scope approved at the above mentioned meeting:

- development/revision of the power unit model  – prototype, which functions in a new FSS software-hardware environment.

- implementation of all the changes performed at the power unit  – prototype form the dated of the latest “freezing”  (31.12.2014) till the date of signing the contract for FSS updated

- development and implementation of a serve accidents model with the fuel melt

- replacement of the low level models for the advanced ones, which will allow the Principal to correct the models as far as the changes are incorporated into the power unit systems

- handover of a technology for development of VVER-1000 reactor core neutronic model and the models for the monitoring systems of neutronic, heat-hydraulic and other reactor core parameters (NFME and ICIS/MCDS, ULCS, GICS) to the Principal by additional personnel training (5 persons as per the program approved by the Principal) out of FSS technical support group, assigning qualification and issuance of a respective certificate, ensure their participation in the activities related to FSS upgrade.

- modification of FSS models connected with  introduction of a new nuclear fuel  TVS-2M at Unit No. 1 by the Principal’s specialists with technical support of the Developer’s specialists

- preparation of a List and supply of the spare parts with account of the new FSS configuration after upgrade  (not less than 20% of the total scope)

- FSS acceptance tests after upgrade

Suppose that computer technology for FSS hardware upgrade: Servers  (IRANSIM, IRANVU, IRANASU), IRANIS1, IRANIS2, IRANGATE computers, ULCS workstations: IRANWS1:14, will be purchased by the Principal at the IRI internal market as per the technical specifications provided by FSS Developer (VNIIAES).

# List of adopted abbreviations and notations

| No. | Abbreviation | Interpretation |
| --- | --- | --- |
|  | R.C. | Reactor core |
|  | NPP | Nuclear Power Plant |
|  | MCR | Main Control Room |
|  | FSS at BNPP | Full Scale Simulator at BNPP |
|  | The Principal | BNPP |
|  | The Contractor | ASE JSC |
|  | FSS developer | VNIIAES JSC |
|  | Spares | Spare parts and accesories |
|  | VAT | Value added tax |
|  | Neutronic | Neutronic (model, characteristics) |
|  | EMA | A set of equipment, materials and accessories for MCR simulator upgrade |
|  | SCP NC | A software complex for preparing neutronic constants |
|  | FSS user | The organization, which performs acceptance and operation of the FSS: TC for the Bushehr NPP. |
|  | DD | Design documentation |
|  | FSS | Full-Scale Simulator |
|  | CW | Commissioning Works |
|  | SW | Software |
|  | AT | acceptance tests |
|  | CAS/CAK/CAT | Computerized (automation) system/subsystem/suite/kernel |
|  | IWS | Instructors’ work place |
|  | TCP | Technical and commercial proposal |
|  | TM | Training materials |
|  | TC | Training Center |
|  | NF | Nuclear fuel |

# Calendar Plan

# for the activities related to BNPP-1 FSS update

| No. Stage | - Name of the Works | Deadline | - Reporting Document |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |
| 1 | The stage of pre-design works Technical Assignment (on RF territory) | ~3.0 months | Technical Assignment for FSS upgrade (in Russian and in English, as soft a copy and as a hard copy) |
| 1.1 | Collection and analysis of the input data related to the resource and the current status of the FSS components on the changes performed at the power unit - prototype form the date of the last “freezing” (31.12.2014) till the date of signing the contract for the FSS upgrade pursuant to the needs, wishes and requirements of the Principal to the scope and the character of FSS upgrade | ~0.5 months D1+0.5 months |  |
| 1.2 | Development and approval of the FSS upgrade concept, which meets the requirements of the Customer and Supplier’s possibilities | 1.0 moths+ D1+1,5 months |  |
| 1.3 | Development, finalization and approval of the SW complex concept for calculation of neutronic constants (SCP NC) of the new generation nuclear fuel TVS-2M and the scope for the personnel training, which meets the requirements of the Principal and the Developer’s possibilities | ~0.5 months D1+1.0 months |  |
| 1.4 | Development, finalization and approval of the Technical Assignment for the FSS upgrade | 1.5 moths+ D1+3,0 months |  |
| 2 | Basic Design (on the RF territory) | ~6.0 months |  |
| 2.1. | Analysis of the process and design documentation related to the modifications at the prototype station; development of decision on modification of the main FSS configuration (SW and HW) | ~0.5 months D2+0,5 months |  |
| 2.2 | Modification of the project DB according to the input data related to the changes. Legalization, finalization and “freezing” of the input data. | ~0.5 months D2+1.0 months | A soft version of the Project DB modified as per the agreed scope of upgrade. |
| 2.3 | Development/correction of the design (functional and technical) specifications (FDS) for the FSS upgrade, including SW, the computer complex (servers, ULCS computers, IS and others ) upgrade, MCR simulator equipment, spares | ~2.0 months D2+3.0 months | Developed/modified design specifications of the FSS upgraded systems |
| 2.4 | Preparation, finalization and approval of the FSS upgrade design / program. Submission of design specifications for the software upgrade for purchasing the servers, computers and others at the IRI internal market. | ~3.0 months D2+6.0 months | FDS of the modified systems. FSS Design/Upgrade program |
| 3 | The stage of purchasing equipment and components: | ~1.0 months |  |
| 3.1 | Purchase procedures for supply of a computer complex (servers, ULCS computers, IS and others) (at IRI internal market) | done by BNPP | BNPP notice to VNIIAES |
| 3.2 | Purchase and tax-export procedures for supply of MCR simulators, spare parts, system SW and instrumental development means of the SW (at the RF internal market) | ~1.0 months D3+3,0 months | Consignment note (s) in the TORG-12 format |
| 4. | Detailed Design (on the RF territory) | ~7.0 months | Handover certificate(s) for the performed works. Design, electrical, working and operation documentation (in Russian and in English, as soft a copy and as a hard copy). |
| 4.1 | Development/correction of the FSS design, detailed design and operational documentation with respect to the modified systems. Preparation and finalization with the Principal the FSS AT program and procedures after upgrade | 2.0 moths+ D1+2,0 months |  |
| 4.2 | Development and adjustment of SCP NC for the new generation nuclear fuel TVS-2M | 2.0 moths+ D1+2,0 months |  |
| 4.3 | Development of the operational documentation for the SW complex concept for calculation of neutronic constants (SCP NC) TVS-2M | 2.0 moths+ D1+2,0 months |  |
| 4.4 | Preparation of a training program for Prinsipal’s personnel and a set of TM at the exchange rate: “Development of a neutronic model for VVER -1000 reactor core and the models for neutronic, heat-hydraulic and other core parameters monitoring system. (NFME and ICIS/MCDS, ULCS, GICS) | ~2.0 moths+ D3+2,0 months |  |
| 4.5 | Development/upgrade of the application programs for the FSS systems: |  | Software on an electronic carrier |
| 4.5.1 | - processing of mathematical models in the modern programming environments | ~2.0 moths+ D3+2,0 months |  |
| 4.5.2 | - implementation of all the changes performed on the prototype power unit from the latest “freezing” date (31.12.2014) till the date of signing the contract for upgrade | ~2.0 moths+ D3+4,0 months |  |
| 4.5.3 | - development of a serve accidents model with the fuel melt | ~2.0 moths+ D3+4,0 months |  |
| 4.5.4 | - replacement of the low level models for the advanced ones, which will allow the Principal to correct the models as far as the changes are incorporated into the power unit systems | ~2.0 moths+ D3+4,0 months |  |
| 4.6 | FSS integrated tests and adjustment at the Developer’s test bench | ~2.0 moths+ D3+6,0 months |  |
| 4.7 | Delivery of developed SW and documentation to the BNPP Site | ~1.0 moths+ D3+7,0 months | Consignment note (s) in the TORG-12 format |
| 5 | Putting into operation at the BNPP construction site | ~4 months | Handover certificate(s) for the performed works. FSS handover and acceptance tests certificate after upgrade. Detailed design and operational documentation (in the electronic and hard carrier) CW and Acceptance Tests. Report on the carries Acceptance Tests. |
| 5.1 | Upgrade of the panels and remote controls of MCR simulator pursuant to design-erection documentation | ~1.0 months D4+1.0 months |  |
| 5.2 | Installation of the system SW, instrumental means for the new servers of the FSS computer complex | ~0.5 months D4+0.5 months |  |
| 5.3 | Completion of the interface part of the installed servers with the existing HW and SW environment up to FSS operable state in general | ~0.5 months D4+1.0 months |  |
| 5.4 | Assembly, mechanical inspection, electrical and functional tests of a computerized complex (servers, ULCS computers and so on) and FSS hardware | ~0.5 months D4+1.5 months |  |
| 5.5 | Installation of a SW complex for calculation of neutronic constants for the new generation nuclear fuel TVS-2M to one of the FSS SW working stations. Integrated tests and adjustment | ~0.5 months D4+0.5 months |  |
| 5.6 | Training of the Principal’s personnel in compliance with the Training program at BNPP Site at the rate: “Development of a neutronic model for VVER -1000 reactor core and the models for neutronic, heat-hydraulic and other core parameters monitoring system. (NFME and ICIS/MCDS, ULCS, GICS) | ~0.5 months D4+1.0 months |  |
| 5.7 | Development of a neutronic model for BNPP-1 reactor core on the basis of the new generation nuclear fuel TVS-2M as part of FSS by the specialists of the Principal with technical support of the Developer’s specialists. | ~1 month D4+2.0 months |  |
| 5.8 | Development/modification of NFME and ICIS/MCDS, GICS models as part of FSS by the specialists of the Principal with technical support of Developer’s specialists | ~1 month D4+2.0 months |  |
| 5.9 | Installation to the new servers and adjustment of the software models for the power unit systems | ~1 month D4+3.0 months |  |
| 5.10 | FSS integrated tests and adjustment | ~1 month D4+4.0 months |  |
| 6 | AT and FSS handover to the Principal | ~2.0 month |  |
| 6.1 | Testing | ~1 month D4+6.0 months |  |
| 6.2 | Elimination of revealed non-conformances | ~0.5 month D4+6.5 months |  |
| 6.3 | Correction of FSS detail design and operation documentation upon the results of adjustment and AT | ~0.5 month D4+6.5 months |  |
| 6.4 | Report preparation and finalization | ~0.5 month D4+7.0 months | Report on the performed AT |
| 6.5 | Signing handover and acceptance documentation | ~0.5 month D4+7.0 months | FSS handover and acceptance tests certificate upon upgrade. |
| TOTAL for the stages 1÷6 |  | ~23 months |  |

Note: D1 - contract signing date; D2 -  approval date of the TA for FSS and Software complex concept upgrade; D3 - approval date of the FSS upgrade project/program; D4 - delivery date of a set of EMA, software and documentation to the BNPP site

Activities specified in the timetable are planned to be performed within 23 months period. Cost of activities shall be Euro 2 819 000.