## PCMFExport
IRA/2/011: Action Plan for Implementation of | [7 empty] | 2015-04-21
Workplan activities in 2012-2013 |  | and 2014-2015
Activity | Implementing Officers/ Input | Venue | Type | Funding | Budget | Budget Year | Date | Comments
1.1 Safety Training through a Visit to an Incident Emergency Center | IAEA: Lipar, Tarren; NPPD: Abbaspour
| 1.1.1-1.1.5 SV1-5 for one week Converted to Obrervers to IAEA OSART missions | a)1 observer in at Kola NPP in 2014. b)1 observer at Novovoronesh NPP in 2015 | 1+1 SVs | FootNote | 3,095 | 2012 | a)Nov'2014 b) Nov.2015 | a) Completed. b) In progress
1.2 Training to strengthen the capability of BNPP personnel on routine Core analysis for safe operation. | IAEA: Poulat, NPPD: Abbaspour/Ghods
| 1.2.1 WS on routine core analysis forsafe operation of BNPP-1 | Bushehr | WS | HardCore | 15,678 | 2012 | 16-20 Aug/2014 | Joitly with 1.22.1 Completed
1.5 Training to assist BNPP-1 in operation of physical protection sytem | IAEA: Ubeev, NPPD: Amini
| 1.5.1 WS on BNPP-1 security procedures including operation of physical protection system | Bushehr | WS | FootNote | 21,800 | 2012 | 1-4 Dec 2013 | Completed
1.6 Training to assist NPPD for application of physical protection against insiders and sabotage at BNPP-1 | IAEA: Ubeev, NPPD: Amini
| 1.6.1 WS on Evaluation of BNPP-1 physical protection system effectiveness | Bushehr | WS | FootNote | 21,800 | 2012 | 18-21 Aug. 2013 | Completed
1.10 Workshop in security procedures at utility level | IAEA: Ubeev/Lipar, NPPD: Amini | [6 empty] | Security procedures incorporated in 1.5.
| 1.10.1 Sunergy between Nuclear Safety and Security at BNPP-1 (2 IAEA staff and 1 EX) | Tehran/Bushehr | WS | HardCore | 13,065 | 2012 | 30 Nov-3 Dec.2014 | Focus changed on the BNPP-1 request. Completed
| 1.10.2 Strengthening Nuclear Security Culture (1 IAEA + 2 EX) NSNS | Tehran | WS |  |  |  | Q4/2015 | Focus changed on the BNPP-1 request In progress
1.22 WWER in Core Fuel Management activities including preparation of optimized core pattern configuration by applying an overall optimized model | IAEA: Lipar/Poulat/Villalibre/Bevilacqua, NPPD: Abbaspour/Ghods
| 1.22.1 WS on routine core analysis for safe operation of BNPP-1 (2 Agency Expert and 2 External Experts) | Bushehr | WS | HardCore | 16,780 | 2012 | 16-20 Aug. 2014 | Jointly with 1.2.1 Completed
| 1.22.2 WS on WWER Fuel integrity monitoring for safe operation of BNPP-1 (P. Villalibre) | Bushehr | WS |  |  |  | 8-10 Dec.2014 | Completed
| 1.22.3 WS on spent fuel storage for safe operation of BNPP-1 (P. Bevilacqua) | Tehran | WS |  |  |  | 28 Feb.- 3 March 2015- | Completed
1.23 Steady state thermal-hydraulics paramenters of WWER reactor including coupling thermal-hydraulic codes with neutronic | IAEA: M. Lipar, Tarren/Poulat,Ulses NPPD: Sheikholeslami/Ghods
| 1.23.1 WS on models in computer codes and application to perform Thermal-hydraulics analysis for safe operation of BNPP-1 (Ulses/Ghods) (1 IAEA + 2 IEX) | Tehran | WS | FootNote | 13,065 | 2012 | June-July 2015 | Topics refocusssed on the request of NPPD. In progress
| 1.23.2 WS/EM on reviewing actual calculations and recommending improvements to the models for BNPP-(Ulses/Ghods) (1 IAEA+2 IEX) | Tehran | WS/EM |  |  |  | end Nov.-beg. Dec. 2015 | follow-up of 1.23.1
3.1 Training on outage management with focus on organization, implementation and supporting. | IAEA: Kang, Varjonen; NPPD/BNPP:Deylami/Roshankar
| 3.1.1 WS on Outage management with focus on organization | Paks NPP | WS | FootNote | 21,000 | 2012 | 27-30 Nov.2012 | Completed
| 3.1.2 To support development of statement of Work (SoW) to computerized BNPP-1 outage management activities with focus on safety aspects (Roshankar) | Bushehr | EM |  |  |  | 8-12 August 2015 | In progress - jointly with 2.2.1
3.5 To strengthen the capability of BNPP personnel in establishment of Safety Performance Indicators in compliance with the latest IAEA guidance and best world practices. | IAEA: Yllera, Mandula; BNPP-1: Deylami
| 3.5.1 one week WS with 1 Agency Expert and 3 External Experts practices. | Bushehr | WS | FootNote | 21,800 | 2012 | 1-5 Dec.2012 | Completed
3.7 Modern methods of maintenance and repair of rotating/turbomachinery equipment | IAEA: Kang; BNPP-1: Roshankar | [6 empty] | The title changed on the request of BNPP-1.
| 3.7.1 One week WS with 1 IAEA and 5 national experts (NEX) | Hungary, Paks | WS | HardCore | 13,065 | 2012 | 12-15 Nov. 2013 | Completed
5.1 To asist BNPP-1 legal, contractual and technical provisions in operation contract between owner and operator company | IAEA: Vincze, NPPD: Tajbakhsh
| 5.1.1 EM on Building in safety requirements/considerations in contractual arrangements between NPPD and BNPP-1 | Vienna | HBA +EM | FootNote | 16,350 | 2012 | 3-6 Sept.2012 | Completed
5.2 To assist BNPP-1 on general structure and special provisions in contracts for repair and/or maintemance and of NPPs | IAEA: Kang, NPPD: Tajbakhsh
| 5.2.1 WS on Building in safety requirements/considerations in contractual arrangements for repair and/or maintenance of BNPP-1 | Vienna | WS | HardCore | 16,350 | 2012 | 24-26 Feb.2014 | Completed
5.3 To assist on general structure and special provisions in contract on waste management of BNPP-1 | IAEA: Vincze, P.Ormai;NPPD: Tajbakhsh
| 5.3.1 WS on building in safety requirements/considerations in contractual arrangements for waste management of BNPP-1 between NPPD and WMco. (1 + 2 IEX) for 5 days | Tehran | WS/EM |  |  |  | Oct. 2015 | new request. Dates to be confirmed. In progress
8.2 Guidance on development of international safety oversight obligation | IAEA: Gest, BNPP-1: Abbaspour
| 8.2.1 WS on Proactive safety management during operation and outage, operational safety indicators (1 Agency staff and 2 IEX) | Bushehr | WS | HardCore | 21,000 | 2012 | 25-29 May'13 | Completed
8.3 Enhancement on NPPD safety performance control | IAEA: Lipar, NPPD: Sheikholeslami
| 8.3.1 One week Meeting with 1 Agency Expert and 2 External Experts | Tehran | WS | FootNote | 16,350 | 2012 | 3-6 Feb. 2013 | Completed
8.1. Assist in development and establishment of NPPD nuclear oversight organization | IAEA: Lipar,Tarren, NPPD: Sheikholeslami
| 8.1.1 EM to assist NPPD nuclear oversight team to conduct safety oversight activity at BNPP-1 (1 IAEA staff and 1 IEX) | Tehran and Bushehr | EM |  |  |  | 15-18 June,2014 | follow-up on 8.3.1 Completed
| 8.1.2 EM to assess implementation of the NPPD nuclear oversight function (1 +2 IEX) | Tehran and Bushehr | EM |  |  |  | 4 days in Sept.or Dec./2015 | new request, follow-up of 8.1.1 In progress
8.4 To assist and support NPPD on supervision and control of NPPs outage program | IAEA: K.S. Kang, BNPP-1: Banazadeh
| 8.4.1 WS on maintenance strategy: predictive, preventive maintenance programme development (2-3 IEX) | Vienna | WS | FootNote | 21,000 | 2012 | 3-6 July 2012 | Completed
1.3 Training to strengthen the capability of BNPP Personnel on using the practical application of Living Probabilistic Safety Assessment for safe operation | IAEA: M. Lipar/B. Poulat, NPPD: Abbaspour/Ghods
| 1.3.1 WS on practical application of LPSA for safe operation of BNPP-1 (3 IEX +5 NEX) | Vienna | WS | FootNote | 17,820 | 2013 | 28 Oct -1 Nov 2013 | Completed
| 1.3.2 Asistance in the purchase and application of RISK SPECTRUM software |  | TBD |  |  |  | TBD | In progress
1.4 Training (Scientific Visits) on methods for reduction of personnel dose during operation, routine maintenance and outage | IAEA: Lipar/F. Jiang, BNPP-1: Abbaspour
| 1.4.1-WS on root cause analysis of NPP safety events(1-2 IAEA staff+2 IEX) | Bushehr | WS | FootNote | 3,155 | 2013 | 8-10 Dec/2014 | Completed
1.9 Implementation of OSART Mission | IAEA: Lipar, BNPP-1: Derakhshandeh
| 1.9.1 Three weeks Expert Mission with 2 Agency staff and 10 international experts | Busher | EM | HardCore | 83,625 | 2013 |  | NPPD requested postponement under the new project for 2016-2017
1.11 Preparatory mission for OSART mission | IAEA: Lipar, BNPP-1: Derakhshandeh
| 1.11.1 Three days EM with one Agency staff and tow external experts | Bushehr | EM | HardCore | 8,019 | 2013 | 3-4 Feb.2013 | Completed
1.12 To assist BNPP-1 in analysis of recent events and operational experience and create action plan for implementation of lessons learned | IAEA: Yllera, NPPD: Sheikholeslami
| 1.12.1 EM on good practices in implemnentation of stress test in IAEA Member States and identification of potential areas for improvement in BNPP-1 (1 IAEA staff and 3 IEX) | Tehran or Vienna | EM | FootNote | 17,820 | 2013 | 9-13 Dec.2012 | Completed
3.2 To strengthen the capability of BNPP personnel in methods and procedures for Plant life management program. | IAEA: Kang, BNPP-1: Deylami
| 3.2.1 WS on methods and procedures for Plant life management program (1 IAEA staff + 2 IEX + 4 NEX) | Vienna | WS |  |  |  | 22-24 Oct. 2013 | Completed
1.13 To support in development of a proces for assessment and improvement of safety culture in BNPP-1 | IAEA: M. Haage, BNPP-1: Abbaspour
| 1.13.1 WS to support BNPP-1 Senior Management for assessment and improvement of safety culture in BNPP-1 (1 IAEA staff and 3 IEX) | Busher or Tehran | WS | HardCore | 14,256 | 2013 | 19-21 Aug. 2013 | Completed
1.16 To support NPPD/BNPP-1 in strengthening routine and post accident environmental monitoring | IAEA: Polyakov, NPPD: Sheikoleslami
| 1.16.1 WS on routine and post accident environmental monitoring (1 IAEA staff and 2 IEX) | Tehran | WS | FootNote | 13,365 | 2013 | 17-20 Feb.2013 | Completed
| 1.16.2 EM to define parametrs to strengthen radiation environmental monitoring for BNPP (D. Talleria) (1 IAEA +2 IEX) | Tehran/Bushehr | EM |  |  |  | 13-17 Juni or 11-15 July 2015 | Follow-up on assistance provided. IAEA submited proposal for software. BNPP-1 confirmed the need and requested new dates. In progress
2.1 Scientific visit on spare part management including warehouse | IAEA: Kang, BNPP-1: Roshankar
| 2.1.1-2.1.5 SV1-5 for one week | Paks NPP, Hungary | 5 SVs | FootNote | 3,155 | 2013 | 12-15 Nov.2013 | Completed jointly with 3.7
3.3 To strengthen the capability of BNPP personnel in using advanced Ultrasonic Test methods, standards, evaluation and techniques. | IAEA: Kang, BNPP-1: Deylami
| 3.3.1 EM on advanced UT methods, standards and techniques (2 External Experts) | Bushehr | EM | FootNote | 13,365 | 2013 | 6-8 July 2013 | Completed
| 3.3.2 Training (Fellowships) on advanced non-destructive methods and techniques for enhancement of safety of BNPP-1 reactor equipment (6 FSs for 3 weeks - total 20 m/w) | HRID, Croatia | 6 FSs |  |  |  | Q1/2015 | Request for follow-up activity. Completed
| 3.3.3 Scientific visits on proven methods for safety analysis of BNPP-1 equipment reliability (SV 1-4 for one week) | TBD | SV |  |  |  | Q4/2015 | Additional input requested. NFs submitted. In progress. Partialy to be included under 2.3.1. SVs to be incorporated in IRA2014001
3.4 To strengthen the capability of BNPP personnel in application of best practices in water chemistry for Primary and Secondary circuit with focus on erosion corrosion. | IAEA: Kim, BNPP-1: Deylami
| 3.4.1 EM on application of best practices in water chemistry for Primary and Secondary circuit with focus on erosion corrosion ( 1 IAEA staff and 3 IEX) | Bushehr | EM | FootNote | 22,300 | 2013 | 15-18 Nov./2014 | Completed
4.1 Assessment of BNPP-1 selected operational training program and procedures, assistance in the development of corrective action plan. | IAEA: Molloy, BNPP-1: Talebianzadeh | [6 empty] | Feedback provided by the IAEA in Feb.2014 on 2 JTAs submitted by NPPD, including general guidance on self-assessment. NPPD informed that improvements were made and no further assistance is needed under IRA2011
| 4.1.1 Asistance on assessment of BNPP-1 selected operational training program and procedures (EM or/and HBA) |  |  | FootNote | 13,365 | 2013 |  | Further assistance will be considered under the new project for 2016-2017
6.1 To evaluate BNPP HRM system and to provide recommendations for improvement | IAEA: Molloy / Lipar, NPPD: Rahnama, BNPP-1: Talebianzadeh
| 6.1.1 Assistance in evaluation of BNPP HRM system (1 +2 IEX) for 3 days | Bushehr | EM | FootNote | 13,365 | 2013 | Q4 2015 | NPPD submitted the BNPP-1 self-assessment and feedback provided by IAEA in Sept.2014. NPPD informed that improvements were made or in process of implemetation Results of asessment to be provided 2 mounths in advance
| 6.1.2 Assistance to Establish of BNPP-1 Human performance Laboratory | Vienna | EM |  |  |  | 18-21 May 2015 | IAEA provided information on good practices in MS. Draft SoW submitted by BNPP by 30 April 2014 and comments provided. Full SoW by 30 April and presentation 2 weeks beforethe EM. In progress
6.2 To assist NPPD/BNPP-1 on improvement of knowledge management system | IAEA: Pasztory, NPPD: Rahnama
| 6.2.1 EM on improvement of NPPD/BNPP-1 knowledge management system (1 IAEA staff and 2 IEX) | Tehran | EM | FootNote | 13,365 | 2013 | 8-10 December 2013 | Completed
7.1 To assist in evaluation of FSS performance | IAEA: Molloy NPPD: Rahnama, Talebianzadeh
| 7.1.1 EM to assist in review of procedure for evaluation and in development of an action plan for modification of BNPP-1 FSS (1 IAEA staff and 3 IEX) | TBD | EM/HBA | FootNote | 17,820 | 2013 | 2016 | BNPP to provide draft report on planned modifications of the training programs, scenarios, procedures, and lessons learned from commissioning - in progress with main contractor. To be implemented under IRA2014001
8.7 To familiarize NPP experts with structure, function and qualification requirement for technical support of utility/operation organization | IAEA: Kang, NPPD: M. Sheikholeslami
| 8.7.1 WS on practical application of technical support of utility/operating organization | Tehran | WS |  |  |  | 4-6 May 2013 | Completed
9.1 To support BNPP-1 in the development of the strategy for continuous improvement of the BNPP Training Centre | IAEA: Molloy BNPP-1: Talebianzadeh | In partnership with WANO,
| 9.1.2 EM with I external expert | Balakovo | EM |  |  |  | 2013-05-01 | Completed
| 9.1.1 SV1-5 for one week | Balakovo | 5 SVs | FootNote | 3,155 | 2013 | 20-25 May 2013 | Completed
| 9.1.3 Assistance in T&Q of maintenance personnel using BTC | [6 empty] | to be considered under the new project
3.6 Expert Mission on Performance and Safety Indicators | IAEA: Mandula NPPD: Deylami
| 3.6.1 Expert Mission on procedures and methods for oerating and maintenance of PI system | Bushehr | EM |  |  |  | 23-26 May. 2015 | Postponed to 2015. In progress
2.2 To strengthen the capability of BNPP in advanced maintenance methods, techniques, materials and tools | IAEA: Kang/Eiler/Moore, BNPP-1: Roshankar/Deylami
| 2.2.1 WS on Advanced maintenance methods, materials and tools to enhance BNPP-1 safety (1 IAEA staff Varjonen and 3 IEX) | Bushehr | WS |  |  |  | 8-12 August 2015 | Jointly wit 3.1.2. In progress
| 2.2.2 Training of BNPP-1 personnel on surveillance speciments management of main safety equipment (RPV) (4 days WS with 1 IAEA staff and 2-3 IEX + 5 NEX) | Vienna | WS |  |  |  | 14-16 Oct.2015 | BNPP-1 requested change of the venue to Bushehr but IEX not available. In progress
| 2.2.3 Training on methods of vibration monitoring of rotating machines including reactor cooling pomp (RCP) and turbogenerator | Vienna | WS |  |  |  | 8-11 Sept. 2014 | Completed
| 2.2.4 Assistance on computer based management of safety related operational and inspection procedures/documents | TBD | WS/EM |  |  |  | 2015 | No need
2.3 Scientific visits on outage management with focus on organization, implementation and supporting | IAEA: Kang, BNPP-1: Roshankar/Deylami
| 2.3.1 Scientific visits on outage management - converted in WS "Outage Optimization Strategy and Risk monitoring in NPP operation" Roshenkar | Vienna | WS |  |  |  | 7-10 Sept.2015 | BNPP-1 to submit requested information. In progress jointly with 2.4.1
| 2.3.2 Scientific visits on advanced equipment and techniques for In-Service Inspection (ISI) of BNPP-1 primary circuit equipment (SV 1-4 for one week) Deylami | TBD | SV |  |  |  | 2015 | NFs submitted and evaluated. To be included in IRA2014001
2.4 Introduction of modern methods of outage management | IAEA: Kang/; BNPP-1: Roshankar
| 2.4.1 EM on modern methods of outage management (1 IAEA staff , 4 IEX, 5 NEX) | Vienna | WS |  |  |  | 7-10 Sept. 2015 | Jointly with 2.3.1. In progress
1.21 To visit NPPs for safety management systems with focus on radioactive waste management, radiation monitoring, core calculation and emergency preparedness | IAEA: Lipar, BNPP-1: Abbaspour
| 1.21.1-5 SV1-5 for one week | TBD | SV |  |  |  | 2015 | NFs submitted and evaluated. In progress
1.18 To support NPPD/BNPP-1 in enhancement of on-site and of-site emergency preparedness and response | IAEA: Lipar/Vincze,Tarren NPPD/BNPP-1: Abbaspour/Roshankar
| 1.18.1 EM to support the national self-assessment on of-site emergency preparedness and response (1 IAEA staff and 1 IEX) (Abbaspour) | Bushehr | EM |  |  |  | 5 days in Nov. 2015 | In progress On -site emergency preparedness and response under new project for 2016-2017
| 1.18.2 Assistance in organization of emergency repairs and use of mobile equipment (3 IEX + 4 NEX) Roshenkar- Lipar | Vienna | WS |  |  |  | 18-20 August 2015 | In progress
| 1.18.3 EM to assist in the review of the first draft Severe Accident Management (SAM) document of BNPP-1 (2 IEX) (Sheikholeslami) | Tehran | EM |  |  |  | 11-13 Jan.2015 | Additional request. Completed
1.17 To advice BNPP-1 on proven approaches in radioactive waste management | IAEA: Ormai and Lipar, BNPP-1: Abbaspour/Roshankar
| 1.17.1 EM on radioactive waste management programme improvements (1 IAEA staff and 2 IEX) | Bushehr | EM |  |  |  | 14-18 September 2013 | Completed
| 1.17.2 To strengthen BNPP-1 capability on practical experience in decontamination related activties ( 2 IAEA staff and 2 IEX) Roshenkar | Bushehr | EM |  |  |  | 27-30 Sept 2014 | Completed
| 1.17.3 EM to asist in radioactive waste management programme, including scaling factor application (1 IAEA staff and 3 IEX) Sheikholeslami | Tehran | EM |  |  |  | 27 Sept - 1 Oct 2014 | Jointly with IRA2012/2.2.1 Completed
1.8 To assist BNPP-1 for implementation of effective accountancy and control measures | IAEA: Lipar, NPPD: Amini
| 1.8.1 Advanced training on effective nuclear accountancy and control using STAR software (one week training by software developer) | Tehran | EM |  |  |  | Q1/2015 | Completed
| 1.8.2 Training on nuclear material accountancy for enhansing nuclear safety and security at BNPP-1 (IAEA SG Department) | Tehran | WS |  |  |  | 23-27 Aug.2014 | Additional request. Completed
Legend:
New request
Needs further clarification/confirmatuion
Completed