## IRA2012 May 2018
Attachment 1
IRA2012: Action Plan for implementation of Workplan activities in 2018
as of 31.05.2018
Increasing NPPD's Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Funding | Budget | Budget Year | Date | Changed Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting 2014 | IAEA: Gueorguiev, NPPD: Fatourechian | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | FootNote | 39,195 | 2012 | Q1/2014 |  | Completed
2 | 1.2.2 | Annual project review and planning meeting 2015 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2015 |  | Completed, 15-17 February 2015 in Tehran
3 | 1.2.3 | Annual project review and planning meeting 2016 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2016 |  | Completed 29 February - 2 March
4 | 1.2.4 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | EM |  |  |  | Q1 2017 |  | Completed |  | 14-15 Feb 2017 as agreed date
1.5 IAEA field monitoring
5 | 1.5.1 | Reqular field monitoring and review missions | IAEA: Gueorguiev, NPPD: Fatourechian | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2014 |  | Completed
6 | 1.5.2 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2015 |  | Completed
7 | 1.5.3 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2016 |  | Completed |  | 1-2 missions per quarter jointly with IRA2013
8 | 1.5.4 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Vienna | Meeting | FootNote | 21,000 | 2012 | 2017 |  | Completed |  | 1-2 missions per quarter jointly with IRA2013
2.2 Spent fuel storage and waste management programs
9 | 2.2.1 | EM to assist in radioactive waste management programme, including scaling factor application | IAEA:Ormai/Dyck, NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX |  | Tehran | EM | FootNote | 3,095 | 2012 | 27 Sept - 1 Oct 2014 |  | Jointly with IRA2011/1.17.3 Completed
10 | 2.2.2 | EM to assist in spent fuel storage | IAEA: C. Hill NPPD: Derakhahandeh | 1 IAEA staff and 3 IEX |  | TBD | EM |  |  |  | Q2/2018- Shifted to New Project |  | Deleted | H | Should take place during Q2/2018.
3.1 Development of training materials for two new NPP projects
11 | 3.1.1 | EM to assist in review of selected/developed training materials for future operatorsfor two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | 2018 |  | Shifted to another project | H | To be implemented on the developed materials provided by the supplier of 2 new units. 27.01.18: IAEA asks NPPD who is going to be trained. See activity 4.5.1 IRA2014
12 | 3.1.2 | EM to assist in review of selected/developed training materials for future operators for two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | FootNote | 16,725 | 2012 | 2018 |  | To be implemented on the developed materials provided by the supplier of two new units | H | merged with 3.1.1, Move to the new Project 2018-2019
3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant
13 | 3.2.1. | WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety | IAEA: Kang, NPPD: Tajbakhsh | 1 IAEA staff and 2 IEX for 4 days |  | Tehran Bushehr | WS | HardCore | 21,000 | 2012 | 27-30 April 2014 |  | Completed
5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations
14 | 5.1.1 | WS To assist in development of the Local Industry Utilization Plan | IAEA: H. Delabre NPPD: Derakhshandeh | 1 IAEA staff and 3 IEX for 5 days |  | Tehran | WS | FootNote | 21,000 | 2012 | 25-27 November 2017 |  | Completed | M | NPPD: Specific issues related to local industry will be sent to the IAEA two months before the WS
6.1 Public information and awareness programmes development
15 | 6.1.1 | WS on public information and awareness programmes | IAEA:B. Pagannone/ NPPD:Rahnama | 4-6 NEX and 2 IEX |  | Tehran | WS | FootNote | 16,350 | 2012 | 28 Sept-1 Oct 2014 |  | Completed
16 | 6.1.2 | EM to assist on the establishment of public information and awareness centre | IAEA: Ms. L. Berthelot / NPPD: Fatorechian/Pirali | 1 IAEA staff and 2 IEX |  | Tehran/Bushehr | EM |  |  |  | Q3/2017 Q1/2018 |  | Shifted to another project | M | 15.05.18: new dates for the EM are 24-28.11.18.
17 | 6.1.3 | EM to review results of Stakeholder Involvement Plan | IAEA: Ms. L. Berthelot / NPPD: Faroutechian/Pirali | TBD |  | Tehran | EM |  |  |  | 2018 |  | Shifted to another project | M | 23.10.17: NPPD feedback expected on the outcome of the EM. Merged with 6.1.2. NPPD contacted on content/expectations again on 07.12.17
18 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: Ms. L. Berthelot, NPPD: Fatourechian/Pirali | 3NEX |  | TBD | SV |  |  |  | 2018 |  | Shifted to another project | M | 15.05.18: SV planned in Japan beg. Of July 2018. Probably 7-11.07.18. NPPD will sent the nomination forms to IAEA by the end of May 2018.
19 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: Ms. L. Berthelot, NPPD: Fatourechian/Pirali | 3NEX |  | TBD | SV |  |  |  | 2018 |  | Shifted to another project | M | 15.05.18: SV planned in Japan beg. Of July 2018. Probably 7-11.07.18. NPPD will sent the nomination forms to IAEA by the end of May 2018.
20 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: Ms. L. Berthelot, NPPD: Fatourechian/Pirali | 3NEX |  | TBD | SV |  |  |  | 2018 |  | Shifted to another project | M | 15.05.18: SV planned in Japan beg. Of July 2018. Probably 7-11.07.18. NPPD will sent the nomination forms to IAEA by the end of May 2018.
2.1 Seismic safety assessment
21 | 2.1.1 | EM to assist in seismic safety assessment | IAEA:Y.Fukushima, NPPD: Shirzadi/Derakhshandeh | 1 IAEA staff and 3 IEX |  | Tehran / Bushehr | EM | FootNote | 40,095 | 2013 | 1-4 october 2016 | 1-4 October, Planned Implementation | Completed | H
22 | 2.1.2 | EM on seismic safety | IAEA:Y.Fukushima, NPPD: Tourafshan/Derakhshandeh | TBD ( 4 days) |  | Tehran | EM |  |  |  | Q3/2017 Q1/2018 Q1/2019 |  |  | M | 10.10.17: CPs will be contacted by the IAEA. 08.12.17: scope and content TBC during next coord. Meeting (Yoshis feedback expected before). 29.01.18: postponed to Q1 2019. - shifted to new cycle (IRA/2/014)
3.3 Corporate knowledge management
23 | 3.3.1 | EM on corporate knowledge management for BNPP - 2&3 with focus on safety | IAEA:Z. Pasztory NPPD:Rahnama/Sheikholeslami | 1 IAEA staff and 3 IEX, 4 days |  | Tehran | EM | FootNote | 7,805 | 2013 | 15-18 Nov. 2015 |  | Completed
24 | 3.3.2 | EM on Management and maintaining design basis information through life cycle of BNPP-2&3 | IAEA:J. de Grosbois, Kolomiets 1 IAEA staff and 3IEX | I IAEA + 2 IEX |  | Tehran | EM |  |  |  | 21-25 April 2016 (3 days) |  | Completed
3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr
25 | 3.4.1 | WS on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (cancelled) | [5 empty] | FootNote | 22,275 | 2013 |  |  | NPPD does not need further assistance
26 | 3.4.2 | SV on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (SG) | IAEA: M. Mishar, SG NPPD: NPPD:Amini | 3NEX |  | TBD | SV |  |  |  | 2016 |  | Cancelled | H | NFs to be provided timely in advance
4.4 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr
27 | 4.1.1 | EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units | IAEA: M. Van Sickle, NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | HardCore | 27,875 | 2013 | Q2/2017 2018/2019 |  |  | H | 27.01.18: Should be integrated to new cycle project IRA2014. Update IRA2014 Planning. 15.05.18: IAEA will provide NPPD with training effectiveness document. Topic will be discussed during next coord Meeting
28 | 4.1.2 | EM to assist in evaluation of developed programmes to update owner's training system for the two new PWR units | IAEA: M. Van Sickle, NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | Q2/2017 2018/2019 |  | Shifted to another project | H | 27.01.18: see previous activity
29 | 4.1.3 | Group Trainig programme on pre-construction management with focus on safety requirements | IAEA: Kang; NPPD: Fatourechian | 1 IAEA Staff, 20 NEX |  | ICTC, Beijing, China | WS |  |  |  | 24 Aug.-4 Sept. 2015 |  | Completed
30 | 4.1.4 | EM to assist in development of comprehensive model for effective project management of the two new NPP units (1 + 3 IEX) | IAEA: Pekka Pyy. NPPD: Rahnama | 1 IAEA Staff and 3 IEX |  | Tehran | EM |  |  |  | 8-11 Nov. 2015 |  | Completed
31 | 4.1.5 | Group Fellowship Trainig on construction and commissioning management with focus on safety requirements | IAEA: K. S. Kang NPPD: Fatourechian | 2 IAEA staff and 20 NEX. The cost for the WS is expected cca. 100 000 EURs. |  | China | Group fellowship training |  |  |  | Q4/2018 |  |  | H | 27.01.18: China accepted. The venue dates are still to be defined. The main topic will be commissioning. IAEA asks for non-experienced people to join the fellowship. Ask TC to shift to new cycle project.31/05/2018: CNPE is host.IAEA will arrange all technical and administrative issues. date fixed 15-26.10.2018
32 | 4.1.6 | EM to assist in the review of the developed Project Management System for units 2 and 3 of the new project. | IAEA: Pekka Pyy. NPPD: Fatourechian/Rahnama | 1 IAEA/3 IEX 4 days. |  | Tehran | EM |  |  |  | Q3 /2017 |  |  | H | NPPD combine it with 3.1.1
4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units
33 | 4.2.1 | EM to assist in review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | EM and HBA | FootNote | 13,365 | 2013 | Q2/2017 |  |  | H | Jointly with 4.1.1
Cancelled
Further clarifications needed
| Completed | [9 empty] | 10 active tasks
| Move to new project (2018-2019) |  |  |  | H=5,M=5

## IRA2013_May 2018
Attachment 2
IRA2013: Action Plan for implementation of Workplan activities in 2018-2019
as of 31.05.2018
Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed
2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | PRM | 14-15 Feb. 2017 | Completed
1.5 IAEA Field Monitoring (once per quarther)
2.2 Preparatory visit for OSART mission
3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | 14-16 Nov 2016 | Completed | H
2.4 Implementation the nuclear safety oversight function
4 | 2.4.1 | One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: JALILI (responsible person) | 1 IAEA+2IEX |  | Tehran | EM | Q4/2017 Q2/2018 |  | M | 27.01.18: NPPD will summarize the actions from the 2 previous missions and send a summary to the IAEA 6 months before the expert mission.
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
5 | 3.1.1 | WS on "modern methods for measuring hydrogen in primary loop and analysis | IAEA: Song, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | 18-21 Feb 2017 | Completed | H
3.2 Training on environmental qualification of safety equipment of BNPP-1
6 | 3.2.1 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang / NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD (France) | SV | 2018 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | 27.01.18: SV will be replaced by an Expert Mission at BNPP with 2 IEX from KWU Design NPPs. 14.05.18: K-S. Kang will ask China again to hold a SV on this topic.
7 | 3.2.2 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang / NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD (France) | SV | 2018 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | 27.01.18: SV will be replaced by an Expert Mission at BNPP with 2 IEX from KWU Design NPPs. 14.05.18: K-S. Kang will ask China again to hold a SV on this topic.
8 | 3.2.3 3 | SV on " specific issues of integrated KWU equipment into BNPP-1 Project" | IAEA: K. Kang / NPPD: Banazadeh | 1 NEX+HBA IEX |  | TBD (France) | SV | 2018 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | 27.01.18: SV will be replaced by an Expert Mission at BNPP with 2 IEX from KWU Design NPPs. 14.05.18: K-S. Kang will ask China again to hold a SV on this topic.
3.3 Training on equipment reliability assessment techniqes of equipment during operation
9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" |  | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016 | TO is awaiting confirmation/response from the CP for this mission. We urgently need the confirmation of dated for this mission (possible to take place end of November and December if we receive the proposed dates by next week.) |  | Deleted
10 | 3.3.10 1 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | 2018 | Deleted | H | Shifted from previous project IRA/2/011, NFs will send to IAEA expectations by the end of May 17. IAEA sent Email on 03.11.17 to NPPD. No feedback still.27.01.18: NPPD will respond by end of Feb 18.
11 | 3.3.10 2 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | 2018 | Deleted | H | Shifted from previous project IRA/2/011, NFs will send to IAEA expectations by the end of May 17. IAEA sent Email on 03.11.17 to NPPD. No feedback still.27.01.18: NPPD will respond by end of Feb 18.
12 | 3.3.10 3 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | 2018 | Deleted | H | Shifted from previous project IRA/2/011, NFs will send to IAEA expectations by the end of May 17. IAEA sent Email on 03.11.17 to NPPD. No feedback still.27.01.18: NPPD will respond by end of Feb 18.
13 | 3.3.10 4 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | 2018 | Deleted | H | Shifted from previous project IRA/2/011, NFs will send to IAEA expectations by the end of May 17. IAEA sent Email on 03.11.17 to NPPD. No feedback still.27.01.18: NPPD will respond by end of Feb 18.
14 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | 11-13 Feb 2017 | Completed | H
15 | 3.8.1-1 | EM on review of BNPP-1 AMP | IAEA: G. Petofi / NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | EM | - | Shifted to another project | H | 14.05.18: Postponed to upcoming years (Talebi) - WS possible. Feedback from NPPD expected.
16 | 3.8.1-2 | SV on AMP | IAEA: Robert Krivanek, NPPD: Ghods-Deylami | 4NEX |  | TBD | SV | Q1-2/2018 |  | H | 14.05.18: see MoM (SALTO observers). IAEA suggests that it takes place after 3.8.1-1.
17 | 3.8.1-3 | Procurement of FAC software , COMSY | IAEA: K.Kang NPPD: Ghods | TBD |  | TBD | Procurement | TBD |  | M | 14.05.18: NPPD will clarify the topic internally and inform IAEA
18 | 3.8.2 | WS developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: K.Kang,Robert Krivanek, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | Q3/2018 |  | H | 27.01.18: Postponed to Q4 2018. 14.05.18: still up-to-date, NPPD will send ToR by end of June 18.
3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1
19 | 3.10.1 | EM on "Assistance on review of safety analysis model for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Ghods (Raji)-Derakhshandeh | 1 IAEA+3IEX/5 days( HBA 5 days) |  | Tehran | EM | Q1/2018 Q4/2018 | Pending information on models and any result of calculation-information needed one month prior to the mission date. Need confirmation on mission dates. | M | 27.01.18:. Review activity is postponed to Q4/18. Inputs (results of calculation) are needed 2 months prior to EM. 14.05.18: IAEA requests ToR by the end of June 18.
20 | 3.10.2 | EM on independent analysis of root-cause results for BNPP-1 | IAEA: Dian Zahratka, P.Tarren, NPPD: Ghods/Derakhshandeh | 1 IAEA+3IEX/5 days |  | Bushehr | EM | Q4/2017 (07-11 October) | Completed | H | NPPD to provide two month before information in English on the root cause analysis in the last two years.Dian Zahradka is the Implementing Officer from IAEA side.
3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1
21 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q4 /2017 | Deleted | M | 10.10.17: IAEA request further clarification of what NPPD are seeking at least two months before.(availability of software and scope of the mission). 13.11.17: low priority, postponed to Q2/2018. 27.01.18: deleted
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
22 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: T. Ulses, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2018 Q4/2018 |  |  | 28.01.18: postponed to Q4 2018. 14.05.18: NPPD is requested to send ToR by the end of June 18.
23 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; A. Gonzalez Espartero, NPPD: Ghods (Ertejaie) | 1 IAEA+2 IEX |  | Tehran | EM | Q4/2017 Q4/2018 | In progress | M | 14.05.18: Q4/18. Mail sent to Ghods on 14.05.18. NPPD will reply by the end of May 2018. This EM might be merged with EM 2.7.1 IRA2014.
5.5 Assistance in development of selected training scenarios for severe accidents in FSS
24 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | Q2 /2018 |  |  | To be discussed after implementation of 6.3.1,
5.6 Assistance in development & improvement of training system of maintenance & repair personnel
25 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: D. Drury / NPPD: Rahnama;Talebianzadeh | 1IAEA+2IEX |  | Bushehr | EM | Q1/2018 Q2/2018 | Completed | H | 10.01.18: New IAEA Responsible for this task: D. Drury. Postponed to April/May 2018. 27.01.18: situation is clarified. Mission will take place 28.04 - 1.5.18
F
26 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA:V.Welter, NPPD: Abbaspour | 1IAEA+2IEX |  | Bushehr | WS | Q2/2017 - 06-10 May 2017 | Completed | M | NPPD: To send clarification on the focus: Training on off-site response to radiological emergency situation BNPP-1. Ramon De la Vega is the IEC Contact Point.BNPP will send off-site emergency prepardeness and response plan by the end of March, 2017.
6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1
27 | 6.3.1 | WS on severe accident analysis model for BNPP-1 | IAEA: T. Ulses, NPPD: Ghods (Raji)/ Derakhshandeh | 1IAEA+2IEX |  | Tehran | EM | Q4/2017 Q3/2018 | In progress | H | 14.05.18: takes place during Aug 18.
28 | 6.3.2 | EM to review the progress in development of the severe accident management guidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh- | 1IAEA+2IEX |  | Tehran | TSR-AM | Q3/2017 Q1/2018 |  | H | 17.10.17: To be implemented during Q1/2018, preparatory work not completed. 29.01.18: merged with 6.3.1
7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1
29 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening, NPPD: Abbaspour | 1IAEA+3IEX |  | Bushehr | EM | 3-7 Dec 2016 | Completed | H
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
30 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: S. Foister, NPPD: Abbaspour | Procurement |  | Bushehr | Procurement | May, 2017 | IAEA had initiated the procurement process, GCS has been transferred into the project. The procurement process is in proceed . It is expected to install and operate in Nov. 2017 at Bushehr. Completed | H | 11.10.17: all clearance processes have been completed, waiting for procurement. The target date for issuance of the purchase order is end of November 2017. Installation of the software in Iran will be schedule thereafter by BNPP and supplier with support
2.3 Implementation of OSART mission
31 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  | Bushehr | EM | 29 Sep- 17 Oct. 2018 | Shifted to another project | H | 27.01.18: NPPD asked for team size and composition. Venue date is 29.09.18 - 17.10.18
2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers
32 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | Tehran | EM | 16-20 July 2016 | Completed | H
2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission
33 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q4 2018( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1NEX |  | Leningrad NPP (St Petersburg Russia) | FS | 30.11.2017 | Completed | H | NPPD requests to involve 3 NEXs.One place agreed for 13-30 November 2017 in Leningrad.
34 | 2.7.2 | EM- Assist visits on operation,Maintenance and technical support areas as preparation for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2IAEA+1IEX |  |  | EM | 5 working days/ Bushehr Q2/2018 |  | H | 08.03.18: Takes place 28-30 May 18
35 | 2.7.3 | Asist visits on HTO and GSR-Part2 areas as preparation for OSART mission | IAEA: R. Cavellec, H. Rycraft NPPD: Khezri | 2IAEA+1IEX |  | 4 working days , Bushehr | EM | Q4/2017 20-23 November | Completed | H | 10.10.17: EM
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
36 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: B.Song, K.Makela, NPPD: Deylami | 1 IAEA+2IEX |  | Bushehr | WS | Q2/2017 | Deleted | H
3.4 Training on containment leakage tests and calculations after outage
37 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 | Cancelled | H | Move to the next cycle. (2018-2019)
38 | 3.4.2 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 | Cancelled | H | Move to the next cycle. (2018-2019)
39 | 3.4.3 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 | Cancelled | H | Move to the next cycle. (2018-2019)
40 | 3.4.4 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 | Cancelled | H | Move to the next cycle. (2018-2019)
3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system
41 | 3.5.1 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD:Dehghani | 1 NEX |  | China | SV |  | Completed | M | 29.01.18: takes place in April 18
42 | 3.5.2 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD:Dehghani | 1 NEX |  | China | SV |  | Completed | M | 29.01.18: takes place in April 18
43 | 3.5.3 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD:Dehghani | 1 NEX |  | China | SV |  | Completed | M | 29.01.18: takes place in April 18
44 | 3.5.4 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD:Dehghani | 1 NEX |  | China | SV |  | Completed | M | 29.01.18: takes place in April 18
3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR
45 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: Dehghani | 1IAEA+3IEX |  | Bushehr | WS | Q3/2018 |  |  | 14.05.18: NPPD action: ToR to be sent by the of May 2018. The mission will take place Beginning of December 2018. IAEA will send the final dates by the end of May.
3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles
46 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  | Tehran | EM | Q1/2017 | Deleted | H
3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system
47 | 3.9.1 -1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests. | IAEA: K. Kang;R. Krivanek / NPPD:Deylami | 1IAEA+2IEX |  | Tehran | WS | Dec,2017 Q1/2018 Q3/2018 |  | M | Proposition for WS on Fatigue. 14.05.18: postponed to Q4/2018. NPPD will send the ToR to IAEA by end of July.
48 | 3.9.1 -2 | WS on high and low cycle fatigue analysis for strength assessment of reactor coolant system | IAEA: K. Kang;R. Krivanek / NPPD:Ghods/Deylami | 1IAEA+2IEX |  | Tehran | WS | Q3/2018 |  | M | 14.05.18: IAEA continues to find experts and recommends to hold the EM in Vienna or Slowakia. NPPD will consider it and will reply by the end of July 18..
3.12 Assistance in performing the living PSA of the BNPP-1
49 | 3.12.1 | EM to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: T. Ulses / NPPD: Ghods | 1IAEA+2IEX |  | TBD | EM | Q1/2018 Q2/2018 |  |  | 14.05.18: NPPD will confirm by mid of July that this activity is still an EM and not a SV. IAEA requests ToR by middle of July.
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
50 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: A. Gonzalez Espartero / T.Ulses, NPPD: Ghods | 1 IAEA+2 IEX |  | Tehran / Bushehr | EM | Q2/2017 | to be removed | M | NPPD requested to provide information two months before.
4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
51 | 4.1.1 | EM on modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes | IAEA: H. Varjonen, NPPD: Roshankar | 1IAEA+3IEX |  | Bushehr | EM | Q4/2017 25-30 November | Completed | H | NPPD will provide more information on area(s) by the end of May.
4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
52 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:Kang, NPPD: Mohebi/ | 1IAEA+3IEX |  | Tehran/Vienna | EM/HBA | Q4/ 2017 Q1/2018 |  | H | 08.12.17: new proposal: Participation of a CS Meeting in June 18 in Vienna + WS in Q3/18 (Ki-Sig makes the follow-up. 14.05.18: nomination forms needed for the technical Meeting in Vienna (25-27.06.18). NPPD will respond by end of May 2018.
5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
53 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: V. Roué, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  | Bushehr | WS | Q4/2017 12-15 November Q4/2018 | Follow up the IAEA | M | 14.05.18: The WS should include HR and Training Performance Indicators. Expectations to be sent by NPPD (Talebianzadeh) by the end of June 2018. Focus on Competency Model and Performance Management.
5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
54 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: M. Van Sickle, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 Q3/2018 | NFs will send 6 months before | M | Postponed to Q3/2018. If request is sent now, possible to take place Q4/2018. 27.01.18: Japan? 15.05.18: NPPD will provide feedback by the end of October 2018. Cancelled at the moment.
55 | 5.2.2 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: M. Van Sickle, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 Q3/2018 | NFs will send 6 months before | M | Postponed to Q3/2018. If request is sent now, possible to take place Q4/2018. 27.01.18: possibly Japan. Feedback expected soon from them
56 | 5.2.3 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: M. Van Sickle, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 Q3/2018 | NFs will send 6 months before | M | Postponed to Q3/2018. If request is sent now, possible to take place Q4/2018. 27.01.18: possibly Japan. Feedback expected soon from them
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
57 | 7.4.2 | EM on "Review and assessment of results of environmental monitoring programme using the software ESTE" | IAEA: S. Foister, NPPD: Abbaspour | 1 IAEA+2IEX |  | Bushehr | EM | Q2/2018 |  | M | Will take place 1 year after ESTE installation at BNPP-1. 27.01.18: expected Q1/2019
4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators
58 | 4.4.1 1 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. Kang NPPD:Roshankar | 3NEX | 5 days | Russian (balakova) | SV | 2018 29-2 Feb | 3 NFs sent through official channel 23.11.2016. | H | 29.01.18: currently ongoing in Russia
59 | 4.4.1 2 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. Kang NPPD:Roshankar | 3NEX | 5 days | Russian (balakova) | SV | 2018 29-2 Feb | 3 NFs sent through official channel 23.11.2016. | H | 29.01.18: currently ongoing in Russia
60 | 4.4.1 3 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: K. Kang NPPD:Roshankar | 3NEX | 5 days | Russian (balakova) | SV | 2018 29-2 Feb | 3 NFs sent through official channel 23.11.2016. | H | 29.01.18: currently ongoing in Russia
4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs
61 | 4.3.1 | WS on outage optimization through advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs | IAEA: H. Varjonen NPPD:Roshankar | 1IAEA+3IEX | 4 days | Bushehr | WS | Q4/2017 22-25 October | Completed | H | NPPD will provide more information on area(s) by the end of May. (It is not possible to combine 4.1.1 and 4.3.1)
62 | - | WS on IGALL workshop on Structure system and component scoping and development of AMP's for BNPP, INRA and TAVANA in Q1 2018 | IAEA: NPPD:Deylami, Ghods | - | - | TBD | WS | Q1/2018 27-29 Jan | Completed | H | BNPP will inform IAEA if this workshop is needed by email before 30 June 2017
Cancelled
| Further clarifications needed | [6 empty] | 27 active tasks
| Completed | [6 empty] | H= 18,M=9
Move to the next cycle

## IRA2014_May 2018
Attachment 3
IRA2 0/14: Action Plan for implementation of Workplan activities in 2018-2020
as of 31.05.2018
IRA/2/014: Increasing the Nuclear Power Production and Development Company's Capability in Planning and Implementing Activities Related to Design, Construction and Commissioning of Two New Nuclear Power Plant Units with the Emphasis on Safety
No. | Activity | Input | Implementing Officers | Resource | Venue | Type | Date | Status | Priority | Comments | Status | Priority | Comments
1. Project Management Team Operational
2. Demonstrated reliance on local staff to perform necessary safety-related engineering/technical tasks and licensing processes
1 | 2.1.1 | Expert Mission on Design Change Management | IAEA: N. Kilic / NPPD: Tourafshan/Derakhshandeh | 1 IAEA + 2 IEX | Tehran | Expert Mission | 27.01.18: Q3 2019 | Planned
2 | 2.2.1 | Expert Mission on Review Mission (IERICS) on I&C Systems of NPP | IAEA: J. Eiler / NPPD: Tourafshan/Derakhshandeh | 1 IAEA + 4 IEX | Tehran | Expert Mission | 27.01.18: Q2/3 2018. | Planned |  |  | 14.05.18: NPPD will provide ToR by the end of may 2018.The proposed date is Q3/4 2018.
3 | 2.3.1 | Expert Mission on Design the intake, discharge and cooling systems of NPP (civil structures) | IAEA: P. Vincze / NPPD: Tourafshan/Derakhshandeh | 1 IAEA + 2 IEX | Tehran | Expert Mission |  | Planned |  |  | 14.05.18: IAEA suggests Q4/2018. NPPD is asked to provide details on the topic by the end of July 2018.
4 | 2.4.1 | Workshop on transient Neutronic Analysis of Bushehr-2 Reactor Core | IAEA: T. Ulses / NPPD: E. Emamjomeh/Derakhshandeh | 1 IAEA + 2 IEX | Tehran | Workshop | 27.01.18: Q2 2019 | Planned |  |  | 27.01.18: Q2 2019
5 | 2.6.1 | Expert Mission on Managing Project Risks during Construction Phase of new BNPPs | IAEA: K. Kang / NPPD: Salimpour/Fatourechian | 1 IAEA + 2IEX | Tehran | Expert Mission | 27.01.18: Q4 2019 | Planned |  |  | 27.01.18: Q4 2019 (1 year after SV). NPPD is requested to provide information 3 months before EM
6 | 2.7.1 | Expert Mission on Spent Fuel Storage | IAEA: A. Gonzalez Espartero / NPPD: Derakhshandeh | 1 IAEA + 3IEX |  | Expert Mission | Q4 2018 |  |  |  | 27.01.18: Task 2.2.2 (IRA2012). 14.05.18: NPPD will answer to IAEA on content and expectations + consider to merge it with the EM on Fuel Behaviour (3.14.2 IRA2013). Mail re-sent to Ghods on 14.05.18
7 | 2.8.1-3 | Scientific Visit on environmental monitoring system for operation (during construction stage) | IAEA: T. Ulses / NPPD: Tourafshan/Derakhshandeh | 3NEX | TBD | Scientific Visit | 27.01.18: Q1 2019. | Planned |  |  | 27.01.18: Q1 2019. An EM will follow after the SV
3. Increase number of trained staff to promote and support strong ownership on design and construction two new NPPs
8 | 3.1.1-3 | Scientific Visit on Severe Accident Management Establishment in NPPs | IAEA: T. Ulses / NPPD: | 3NEX | TBD | Scientific Visit | 29.01.18: | Planned |  |  | 29.01.18: To observe an emergency exercise (use of portable equipment). Q2/2019
9 | 3.4.1-3 | Scientific Visit on Intermediate Storage of Nuclear Spent Fuel at Bushehr site | IAEA: C. Hill / NPPD: E. Emamjomeh | 3NEX | TBD | Scientific Visit | 27.01.18: | Planned |  |  | not before 2019
10 | 3.7.1-3 | Scientific Visit on Managing Risks of Corporate Level in Construction NPPs | IAEA: K. Kang / NPPD: Salimpour/Fatourechian | 3NEX | TBD | Scientific Visit | 27.01.18: Q4/2018 | Planned |  |  | 27.01.18: Q4/2018. 14.05.18: postponed to Q2/2019.
11 | 3.10.1-3 | Scientific Visit on Safety Culture Improvements in NPPs | IAEA: R. Rycraft / NPPD: E. Emamjomeh/Derakhshandeh | 3NEX | TBD | Scientific Visit | 27.01.18: Q4/2019 | Planned |  |  | 27.01.18: Q4/2019
12 | 3.13.1-3 | Scientific Visit on Safety Improvements in NPPs in order to prevent incidents and accidents in WWER-1000 reactors | IAEA: D. Zahradka/K. Kang / NPPD: E. Emamjomeh/Derakhshandeh | 3NEX | TBD | Scientific Visit | 27.01.18: 2020 | Planned |  |  | 27.01.18: 2020
13 | 3.16.1-3 | Scientific Visit on lessons learned of construction and design of BNPP-2 reference plant | IAEA: D. Zahradka/K. Kang / NPPD:Tourafshan/Derakhshandeh | 3NEX | India KK NPP | Scientific Visit | 27.01.18: 2019 | Planned |  |  | 27.01.18: 2019
14 | 3.19.1-3 | Scientific Visit on Interface management between owner, operator, general contractor and local companies during manufacturing stage | IAEA: P. Pyy / NPPD: Ordikhani | 3NEX | TBD | Scientific Visit | 27.01.18: Q1/2019 | Planned |  |  | 27.01.18: Q1/2019
4. Improved comprehensive human resource management (HRM) programme for two new NPPs
15 | 4.1.1 | EM on HRD improvement | IAEA: M. Van Sickle / NPPD: Rahnama/Talebianzadeh | 1 IAEA + 2 IEX |  | Expert Mission | 29.01.18: Q1 2020 | Planned
16 | 4.2.1 | Expert Mission on HRM strategy for new NPPs (transition to operation) | IAEA:M. Van Sickle / NPPD: A. Rahnama | 1 IAEA + 2 IEX | Tehran | Expert Mission | 27.01.18: Q4/2019 | Planned
17 | 4.3.1 | Expert Mission on Bushehr Training Center improvement | IAEA: M. Van Sickle / NPPD: Rahnama/Talebianzadeh | 1 IAEA + 2 IEX | Bushehr | Expert Mission | 29.01.18: 2020 | Planned
18 | 4.4.1 | Expert Mission on Improvement KM System | IAEA: O. Gloeckler / NPPD: A. Rahnama | 1 IAEA + 2 IEX | Tehran | Expert Mission | 27.01.18: Q2/2020 | Planned
19 | 4.5.1 | Expert Mission on how to review of training materials for FSS | IAEA: M. Van Sickle / NPPD: Rahnama/Talebianzadeh | 1 IAEA + 2 IEX | Bushehr | Expert Mission | 27.01.18: | Planned |  |  | Task 3.1.1 (IRA2012), Q2/2021
20 | 4.6.1 | Expert Mission on Improvement of Personnel Performance Appraisal | IAEA: M. Van Sickle / NPPD: Rahnama/Talebianzadeh | 1 IAEA + 2 IEX | Tehran/Bushehr | Expert Mission | 27.01.18: Q1/2019 | Planned
5. Increased capabilities in adherence to safety and quality requirement by local organization participating in manufacturing and construction two new NPPs
21 | 5.1.1 | Workshop on Effective localization plan, its key elements and criteria | IAEA: K. Kang / NPPD: Ordikhani | 1 IAEA + 2 IEX | Tehran | Workshop | 27.01.18: Q3/2020 (after SV) | Planned
22 | 5.2.1 | Workshop on how to dedicate commercial grade items for NPP applications | IAEA: K. Kang / NPPD: Ordikhani | 1 IAEA + 2 IEX | Tehran | Workshop | 27.01.18: Q4/2019 | Planned
23 | 5.3.1-2 | Scientific Visit on Quality supervision of localization processes | IAEA: P. Pyy / NPPD: Ordikhani | 2NEX | TBD | Scientific Visit | 27.01.18: Q1/2020 | Planned