Protocol of the meeting

02.06.2015										Moscow

Participants of negotiations:

| The Principal’s representatives Mr. M. Ahmadian Mr. M. Jafari |  | The Contractor’s representatives Mr. V.I. Limarenko Mr. A.B. Khazin Mr. A.V. Deriy Mr. A. I.. Kozhinov Mr. A.V. Yatsenko |
| --- | --- | --- |

The Parties have discussed a number of issues on preparation for Final Acceptance of Bushehr NPP Unit No.1, on commencement of activities on Units Nos. 2 &3 construction, on implementation of engineering survey at Bushehr NPP Site as well as on perspectives of further cooperation. The Parties have reached the following conclusions and will do their best to implement these conclusions although the conclusions shall not affect performance of contractual obligations by the Parties:

- In accordance with the Agreement dated 19.02.2015 on the issue relating to delay in payment under the Addenda Nos. 65 and 66, the Principal shall repay in full the indebtedness under the said Addenda thereto not later than 01.08.2015 and shall do its best to pay in full the existing indebtedness under the main contract for construction of BNPP-1 not later than 01.08.2015.

- The Principal shall open a Letter of Credit under the Contract for engineering survey not later than within 4 weeks from the date of this Protocol.

- The Parties have agreed on availability and necessity of Final Acceptance of Unit No.1 in the possible shortest terms. The Principal shall submit a list of required activities, performance of which shall enable Final Acceptance of Unit No.1. The list shall be submitted within a week before June 10.

- The Principal and the Contractor shall establish a working group with participation of representatives of Bank Markazi in order to arrange payments under the Contracts via third countries. The Principal shall arrange joint meetings of representatives of the Principal and the Contractor with the Principal’s banks in the Bank Markazi Jomhouri Islami Iran during June 2015.

- The Principal shall jointly with the Contractor conduct analysis of terms of the Contract for construction of Unit 1 of Bushehr NPP, relevant Addenda thereto and guidelines to issuing of repair documentation and shall make a decision on elimination of delay in issuing of repair documentation.

- The Contractor has confirmed its obligations relating to refilling of Spare Parts for 3 years after guaranty period of operation.  Replacement Parts as described in the Appendix H to the Contractwhich was utilized to ensure the Contractor’s guaranty obligations shall not be reimbursed. Spare Parts refilling schedule shall be agreed by the Parties within 1 weekstarting from the date of the present Protocol, so that refilling shall be accomplished by the time of Final Acceptance.

- The Contractor shall submit a TCP for stator within the framework of Spare Parts extension for after-guaranty period. The proposal shall be technically justified and cost-effective.

- The Principal will send the draft of the Guarantee of State Corporation Rosatom and the draft Comfort letter of Ministry of Economic Development of Russian Federation submitted by the Contractor to the Principal with the letter on 19.05.2015 to the relevant IRI Authorities and use its best effort in order to obtain their comments to the wording of the documents mentioned above and upon receiving the comments from the relevant IRI Authorities, shall officially dispatch their comments to the Contractor.

- The Parties accepted the completion of work on detailed schedules of payments for Basic Design and LMCE with detailed elaboration on the basis of the referencePlant, with possibility of updating of the schedules of paymentsfor Basic Design  after completion of Technical Assignment, and for LMCE after completion of Basic design subject to consent of the Principal.

| The Principal |  | The Contractor |
| --- | --- | --- |