## Sheet1
| workshop/Practical class/simulator | Price of services ($) | Time priority/Stages for Equipping | First year | [47 empty] | Second year | [47 empty] | Third year | [47 empty] | fourth year | [47 empty] | Fifth year | [47 empty] | sixth year | [47 empty] | Seventh year | [47 empty] | Eighth year
|  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12
No. |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Refueling machine simulator | 150000000 | 1 | bar: 1 1 to 12 4
2 | Practical training in discipline “Transducers” | not required | Equipped
3 | Practical training in discipline “Repair of heat-exchange equipment”, Assembly and sealing of flange connections of reactor UU, steam generators, ECCS tanks, CPS, TC, ER” |  | 2 | bar: 1 1 to 12 4
4 | Practical training in discipline “Repair of Heat Exchange Equipment - Ventilation Systems” |  | 2 | bar: 1 1 to 12 4
5 | Practical training in discipline “Rotating mechanisms” |  | 2 | bar: 1 1 to 12 4
6 | Workshop (metalwork skills, electric hand tools) |  | 2 | bar: 1 1 to 12 4
7 | Practical training in discipline “Repair of valves and pipelines” |  | 2 | bar: 1 1 to 12 4
8 | “Main electrical circuitry” simulator |  | 3 | bar: 1 1 to 12 4
9 | Practical training in discipline “RPA and Cable System” |  | 3 | bar: 1 1 to 12 4
10 | Practical training in discipline “Electrical Machinery and Switching Devices” |  | 3 | bar: 1 1 to 12 4
11 | Practical training of the M&R personnel in discipline “Terminals and switchgear” |  | 3 | bar: 1 1 to 12 4
12 | Mock-ups of the main NPP equipment |  | 1 | bar: 1 1 to 12 4
13 | “Virtual Reality” simulator |  | 4 | bar: 1 1 to 12 4
14 | Simulator “RP modes analyzer” |  | 4 | bar: 1 1 to 12 4
15 | Simulator “NO APCS, ESFAS and TLS-U, being parts of I&C” |  | 2 | bar: 1 1 to 12 4
16 | Practical training in discipline “Radiation safety and dosimetry” | 50000 | Equipping Stage | bar: 1 1 to 6 4
17 | Software and hardware complex “Actions of personnel during implementation of the personnel protection plan in the event of an accident on the NPP” on the topic “Radiation safety and dosimetry” |  | 4 | bar: 1 1 to 12 4
18 | Simulators “Fire protection instrumentation and control equipment and systems (FP I&C)” and “Process system equipment (LRS)” |  | Equipping Stage | bar: 1 1 to 6 4
19 | Room for practical training in disciplines “PPE” and First aid resuscitation measures. | 330000 | Equipped
20 | CH equipment mock-ups |  | 4 | bar: 1 1 to 12 4
21 | “Reactor plant I&C simulator. NFME” and “Reactor plant I&C simulator. MCDS” |  | 2 | bar: 1 1 to 12 4
22 | Fire safety class /Класс по пожарной безопасности |  | 4 | bar: 1 1 to 12 4
23 | Class of pre-and after-simulator lesson analysis |  | 4 | bar: 1 1 to 12 4
24 | BTC Language Lab |  | Contract Stage | bar: 1 1 to 12 4
25 | Emergency control room-simulator | 134000 | 3 | bar: 1 1 to 12 4
26 | Modernization of BNPP-1 FSS (Scope of FSS modernization: Data freeze 2020, FSS SW/HW, УТВС to ТВС-2М, NFME, MCDS, CPS, sever accidents, modeling of the reactor core melting) |  | 1 | bar: 1 1 to 12 4
27 | ساخت و تجهیز "مجتمع بازتوانی درمانی، رفاهی و تفریحی" جهت انجام برنامه اقدامات اصلاحی که به درخواست پزشک و روانشناسان آزمایشگاه روانشناسی و فیزیولوژی هر سال به صورت انفرادی و گروهی برای کارکنان و شیفت های نیروگاه توصیه می شوند. |  | 1 | bar: 1 1 to 12 4