"Severe Accident Management Guidelines for Angra 2 NPP (BR1.01/09T1) - Brazil"

TASK 2: REVIEW OF THE BEST INTERNATIONAL PRACTICES AND SITUATION IN BRAZIL

Within this task the Consultant shall perform the following activities:

- The Consultant shall analyse the best international practices and available documentation concerning SAMG development and application, and assess its applicability to Angra 2 NPP.

This assessment shall be made based on comparative analysis of the applicable design, operation, scientific research, and regulatory documentation available for the Angra 2 NPP (to be provided by the End User/Beneficiary) with available western sources of information, related to the development and implementation of SAMG programmes for PWR in different countries over the world.

During this analysis, the Consultant shall make maximum usage of already existing Angra 2 NPP documentation (Level 1+ PSA, EOPs procedures and background documents, etc…). SAMGs guidelines and background documents already developed for Angra 1 NPP shall also be taken into account where applicable.

For this task the End User/Beneficiary will provide the Consultant with all information relevant to the subject and already available at Eletronuclear, including among others:

  - Available materials of the BDBA analysis, PSA Level 1+ for Angra 2

  - EOPs procedures and background documents for Angra 2

  - Effective emergency documentation of the Angra 2 NPP;

  - SAMGs guidelines and background documents already developed for Angra 1 NPP (by making it available for consultation at the Angra site)

  - Relevant Brazilian regulatory and normative framework in the field of use of symptom-oriented approaches to the development of emergency documentation

- Based on the results of the above work, the Consultant shall:

  - identify the need for and scope of additional analyses to support this project, and

  - ascertain the structure, contents and schedule of the next project activities.

The Consultant shall organise and conduct one or more technical meetings in order to present and discuss the results of the above activities and finally to agree on them with the Beneficiary/End User. The Minutes of these technical meetings as well as the Beneficiary/End User’s remarks shall be included in the Task 2 Technical Report.

The Consultant shall prepare the Task 2 Technical Report.

This Technical Report shall include as a minimum:

  - A list and description of the background information that has been used by the Consultant to review the Best International Practices and to assess the situation for Angra 2 regarding Severe Accident Management, and

  - A list and description of the additional analyses needed to support the development of Severe Accident Management Guidelines for Angra 2 for at power conditions.

This Task 2 Technical Report shall be sent to the EC Project Manager for approval after it has been endorsed by the Beneficiary/End User.

Expected output of Task 2:

  - The Task 2 Technical Report

TASK 3: DEVELOPMENT OF SEVERE ACCIDENT MANAGEMENT GUIDELINES

Task 3.1: Development of Plant Specific Computerized Model necessary to support SAMG development.

The objective of this task is to develop all the necessary tools (methods, Plant Specific Computerized Model …) necessary for the identification of the main phases of the severe accident progression for Angra 2 NPP, the definition of the SAM strategies and the final validation of the SAMGs guidelines.

Within this task, the Consultant shall:

- Identify the severe accident analysis methods and codes to support SAMG development.

This task shall be based on the results of Task 2. Within this task, the Consultant shall select the methods, codes (such as for instance MELCOR/MAAP) and plant models that will allow severe accidents to be analysed realistically for the purpose of SAMG development, taking into account uncertainties related to the severe accident phenomena.

- Use the selected codes that are already available at the Beneficiary’s offices, or ensure otherwise the availability of the selected codes for the purpose and duration of this project.

- Develop the Plant Specific Computerized Model of Angra 2 NPP, needed to perform the Severe Accident analyses

- Verify the Angra 2 Plant Specific Computerized Model on a series of predefined Severe Accident scenarios

- Provide training to the End User/Beneficiary in the development and use of the Plant Specific Computerized Model for Angra 2 NPP

Within this task, the Beneficiary/End User will:

- Support the Consultant in his selection process for severe accident analysis methods and codes to support SAMG development

- Ensure the availability to the project of the selected codes that are already available at the Beneficiary/End User offices, and/or support the Consultant in his efforts to ensure the availability of the selected codes for the purpose and duration of this project

- Provide all necessary plant specific data to allow the Consultant to develop the Plant Specific Computerized Model(s) of Angra 2

- Attend the training related to the development and use of the Plant Specific Computerized Model(s) for Angra 2

- Review the Plant Specific Computerized Model(s) of Angra 2 developed by the Consultant within this task

The Consultant shall prepare the Task 3.1 Technical Report.

This Technical Report shall include as a minimum:

  - A list of the severe accident analysis methods and codes that should be used to support SAMG development;

  - The results of the verification of Angra 2 Plant Specific Computerized Model on a series of predefined Severe Accident scenarios, and

  - A copy of the training material provided to the End User/Beneficiary

The Beneficiary/End User shall also review and agree on the Task 3.1 Technical Report.

The Consultant shall send the Task 3.1 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

Expected output of Task 3.1:

  - The Task 3.1 Technical Report

Task 3.2: Identification of the main phases of the severe accident progression for Angra 2

The objective of this task is identify the main phases of the severe accident progression for Angra 2 NPP.

Within this task, the Consultant therefore shall:

- Perform a series of “base case” severe accident analyses to identify the main phases of the severe accident progression for Angra 2 NPP;

- Define the list of additional calculations needed for sensitivity studies;

- Identify (ascertain) the severe accident phenomena and the mechanisms (threats) by which these phenomena may affect the safety barriers of the plant, and

- Identify the possible routes of radioactive substance release to the environment.

The Beneficiary/End User will support the Consultant in his evaluation by performing additional calculations (according to the list defined by the Consultant) necessary for the identification of the main phases of the severe accident progression for Angra 2 NPP for accident occurring during at power conditions.

These additional calculations shall mainly be composed of sensitivity studies for uncertainties evaluation. In this way, the Beneficiary/End User also will gain experience in applying the tools developed in task 3.1.

For selecting and for making available the required calculation codes, the same responsibilities of respectively the Consultant and the Beneficiary apply as those described in Task 3.1.

The Consultant shall prepare the Task 3.2 Technical Report.

This Technical Report for task 3.2 shall include as a minimum:

  - The list and description of the severe accident analysis calculations performed during this task

  - A description of the main phases of the severe accident progression and the possible routes of radioactive substance release to the environment for Angra 2 NPP for accidents occurring during at power conditions

The Beneficiary/End User shall also review and agree on the Task 3.2 Technical Report.

The Consultant shall send the Task 3.2 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

Expected output of Task 3.2:

  - The Task 3.2 Technical Report

Task 3.3: Identification of Angra 2 Plant Capabilities

The objectives of this task are twofold:

  - to assess the availability, applicability and adequacy of Structures, Systems and Components (SSC) existing at Angra 2 NPP for severe accident management, and

  - to evaluate the necessity of plant modifications to implement the Severe Accident Management program.

Within this task, the Consultant shall:

- Support the End User/Beneficiary to establish a list of available and additionally required technical means (Structure, Systems and Components (i.e. SSC)), which could be used during practical implementation of the chosen accident management actions. Technical capabilities of these means shall be specified and their ability to perform the required functions under the chosen strategy shall be justified.

- Support the End User/Beneficiary to establish a list of all possible means of monitoring and measurement (MMM) for a required parameter (identification and prioritisation). For monitoring and measurement (MMM) prioritisation, specific consideration shall be given to:

  - expected probability of failure of the monitoring and measurement concerned under the expected environmental conditions;

  - monitoring and measurement ability to perform the required function;

  - monitoring and measurement (MMM) qualification, and

  - monitoring and measurement (MMM) physical location on the Unit.

- Guide and support the End User/Beneficiary performing operability assessments of SSCs for Severe Accident purposes by using to a maximum extent the experience gained in that field by the Consultant during other SAMG development programs

- Evaluate the necessity of plant modifications to implement the Severe Accident Management program. This evaluation shall be based as a minimum on best international practices, previous conducted evaluations for Plants of similar design and specific data related to the subject available for Angra 2

- Identify possible severe accident calculations necessary to support the evaluation of plant modifications to implement the Severe Accident Management program

- Support the End User performing the required analyses and calculations necessary to support the evaluation of plant modifications

Within this task the Beneficiary/End User will provide the following support to the Consultant:

- establish the list of available and additionally required technical means (Structure, Systems and Components (i.e. SSC) including MMM), which could be used during practical implementation of the chosen accident management actions (with their availability, accuracy and limitation during severe accidents);

- with the guidance and the support of the Consultant, perform for these Structure, Systems and Components (SSCs) the following analyses:

  - Operability assessment of instruments and indicators under the expected emergency conditions, and possibility of measurements to be made in the ranges exceeding the range of their normal operation equipment.

  - Operability assessment of the plant safety system and normal operation system components to perform the required severe accident management and mitigation actions. It is also important to identify alternative systems and equipment which could be used for the performance of the required function (for example equipment of the neighbouring unaffected Unit(s) provided that this will not jeopardise the safety of these power units).

  - Analysis of all intersystem dependencies, including assessment of operability and effectiveness of the respective support systems under various conditions of the severe accident progression.

- provide to the Consultant all available information to support the evaluation of the plant modifications needed to implement the Severe Accident Management;

- perform the severe accident analyses and calculations necessary to support the evaluation of plant modifications needed to implement the Severe Accident Management program

For selecting and for making available the required calculation codes, the same responsibilities of respectively the Consultant and the Beneficiary apply as those described in Task 3.1.

The Consultant shall prepare the Task 3.3 Technical Report.

This Technical Report for task 3.3 shall include as a minimum:

  - Present for each Structure, Systems and Component (SCC), necessary to manage a severe accident, their technical capabilities and limitations for the accident management purpose.

  - Include for each parameter necessary to manage a severe accident, the different available means to measure this parameter with their availability, accuracy and limitation during severe accidents

  - Include the results of the evaluation regarding the necessity of plant modifications to implement the Severe Accident Management program

The Beneficiary/End User shall also review and agree on the Task 3.3 Technical Report.

The Consultant shall send the Task 3.3 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

This Task 3.3 Technical Report needs to be endorsed before the activities on Task 3.7 can be started.

Expected output of Task 3.3:

The Task 3.3 Technical Report

Task 3.4: Identification of Severe Accident Management Strategies for Angra 2 NPP

The objective of this task is identification of the accident management strategies applicable to Angra 2 NPP for severe accidents occurring when the reactor is at power.

Within this task the Consultant shall perform the following activities:

- Perform, in collaboration with the End User, analytical or computer code calculations which will be needed to determine the accident management strategies and possible actions.

- Identify possible actions (i.e. not detailed, “high level” actions) of the staff to respond to each challenge/phenomenon, aimed to meet one or more main objectives of the severe accident management, including:

  - termination of the reactor core melting, protection of the primary circuit pressure boundaries and return of the power unit to the controlled and stable state;

  - ensuring the containment integrity as long as practically achievable, and

  - minimisation of radioactive releases.

- Select acceptable severe accident management strategies.

- Identify the criteria and the respective parameter values, which would help identify the physical state of the affected Unit and take necessary accident management measures at every phase of the severe accident progression.

- Assess systematically the strategies which may be used at each phase of severe accident. Failure to fulfil a certain strategy at one phase should leave the possibility to achieve the same set objectives at following phases.

When choosing and analysing a strategy, it is necessary to:

  - take into account both positive and negative consequences of this strategy, including long term effects;

  - know the features (criteria and parameters) by which the strategy implementation procedure shall be initiated;

  - know the features (criteria and parameters) indicating the start of the strategy implementation;

  - know the features (criteria and parameters) which let make sure the applied strategy is effective;

  - Know the actions of the staff aimed at “exiting” the ineffective strategy and choosing an alternative strategy.

  - Identify and document the weak points of the plant design which may become a source of controversy in decision making for the selection of the optimum strategy. This point is directly linked to the task 3.3 ‘Identification of Angra 2 Plant Capabilities”.

- The Consultant shall also identify the conditions of transition to the severe accident management and choose the key parameters which will be used to determine this transition.

These choices (conditions end key parameters) for the transition conditions to SAMG shall be presented to and discussed with the Beneficiary/End User and approved by him.

- The Consultant shall also propose within this task the recommended strategy regarding usage of EOP when the severe accident management domain is entered.

This choice shall be presented to and discussed with the Beneficiary/End User and approved by him.

- The Consultant shall define the parameters to be monitored to ensure that safe and stable conditions have been successfully achieved for termination and exit from SAMG.

The Beneficiary/End User will support the Consultant during this task with the following activities:

- Support the Consultant by performing some analytical or computer code calculations which will be needed to determine the accident management strategies and possible actions.

- Review the choice made by the Consultant regarding the SAMG strategies and actions and endorse this choice.

- Review the choice made by the Consultant regarding parameters defining the transition to SAMG and endorse this choice.

- Review the choice made by the Consultant regarding transition between EOP and SAMG and endorse this choice.

- Review the choice made by the Consultant showing that safe and stable conditions have been successfully achieved at the end of the accident and endorse this choice.

The development of the Severe Accident Management strategies for Angra 2 and the review of the choices presented in this task by the Consultant shall be mainly carried out by the SAMG JWG.

For selecting and for making available the required calculation codes, the same responsibilities of respectively the Consultant and the Beneficiary apply as those described in Task 3.1.

The Consultant shall prepare the Task 3.4 Technical Report.

This Technical Report for task 3.4 shall present the different strategies and actions identified within this task to manage severe accident and shall include as a minimum:

  - A list of accident phenomena/challenges to the safety barriers with a reference to the main safety objectives;

  - The strategy and actions (i.e. not detailed, “high level” actions) of the staff in response to each of the challenges;

  - Limitations and possible negative consequences of the considered accident management actions;

  - Prioritisation of various alternative actions of the staff (if any);

  - The choice for conditions and key parameters regarding the transition conditions to SAMG;

  - The choice regarding parallel usage of SAMG and EOP, and

  - The choice of parameters showing that safe and stable conditions have been successfully achieved at the end of the accident.

The Beneficiary/End User shall review and agree on the Task 3.4 Technical Report.

The Consultant shall send the Task 3.4 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

This Task 3.4 Technical Report needs to be endorsed before the activities on Task 3.7 can be started.

Expected output of Task 3.4:

  - The Task 3.4 Technical Report

Task 3.5:  Establishment of SAMG Set-points and Computational Aids

The objectives of this task are:

  - to prepare the Computational Aids and diagnostic tools needed to support the usage of the SAMG guidelines for a severe accident occurring when the reactor is at power, and

  - to develop the SAMGs setpoints.

Within this task the Consultant shall perform the following activities:

- Select the threshold values of the monitored parameters for correct assessment of the Unit state or potential risks.

- Identify the Computational Aids and diagnostic tools needed to support the usage of the SAMG guidelines.

- Supervise the End User/Beneficiary during the development of the Computational Aids and diagnostic tools. The Consultant shall provide the necessary instructions at the beginning of the development of each computational aid and diagnostic tool, and shall develop a few examples together with the Beneficiary personnel.

- Supervise the End User/Beneficiary during the development of the SAMGs setpoints. The Consultant shall provide support during the establishment of the SAMG set-points and computational aids, and shall review the work after its completion.

The Beneficiary/End User will perform the following activities during this task:

- Prepare the Computational Aids and diagnostic tools needed to support the usage of the SAMG guidelines.

- Develop the SAMGs setpoints needed to support the usage of the SAMG guidelines.

For selecting and for making available the required calculation codes, the same responsibilities of respectively the Consultant and the Beneficiary apply as those described in Task 3.1.

The Consultant shall prepare a detailed Task 3.5 Technical Report.

This Technical Report shall include as a minimum the list, copies and way of usage of the Computational Aids and diagnostic tools developed within this task to support the usage of the SAMG guidelines. The Technical Report shall also include the SAMGs setpoints list and values.

The Beneficiary/End User shall review and agree on the Task 3.5 Technical Report.

The Consultant shall send the Task 3.5 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

This Task 3.5 Technical Report needs to be endorsed before the activities on Task 3.7 can be started.

Expected output of Task 3.5:

  - The Task 3.5 Technical Report

Task 3.6: Development of a Writer’s Guide and a User’s Guide for SAMG

The objective of this task is:

  - to ensure consistency between all guidelines within the full set of SAMGs.

Within this task the Consultant shall:

- Decide jointly with the SAMG JWG the structure (format) and technical contents of standard SAMG guidelines. The peculiarities of Angra 2 NPP shall be taken into account, and smooth transition interface ensured between the current EOP and SAMG.

- Produce a Writer’s Guide and a User’s Guide to describe the format and content of the guidelines, transitions between the SAMG Guidelines and finally transition between EOPs and SAMG. These two documents shall describe the scope of the SAMGs and establish the overall guidelines for the preparation and further maintenance of the SAMGs.

The Consultant shall prepare a detailed Task 3.6 Technical Report.

This Technical Report shall include as a minimum the major choices made regarding structure and technical contents of a standard SAMG Guideline and including a copy of the Writer’s Guide and of the User’s Guide.

The Beneficiary/End User shall review and agree on the Task 3.6 Technical Report.

The Consultant shall send the Task 3.6 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

This Task 3.6 Technical Report needs to be endorsed before the activities on Task 3.7 can be started.

Expected output of Task 3.6:

  - The Task 3.6 Technical Report

Task 3.7: Development of SAM Guidelines

The objective of this task is:

  - to write the SAM guidelines, and

  - to ensure the best transfer of actual working knowledge between the Consultant and End User/Beneficiary.

Therefore, the Consultant shall use the following approach for the actual writing of the SAM Guidelines for Angra 2 NPP.

  - The Consultant shall write approximately 60 percent of the total number of SAM Guidelines.

  - About 20 percent of the total number of SAM Guidelines will be written completely by the Beneficiary/End User. The Consultant shall be responsible for the close supervision of the Beneficiary/End User during these activities.

  - The remaining approximately 20 percent of the SAM Guidelines will be written by the Beneficiary/End User with just a review of the results by the Consultant.

The choice of Guidelines to be written by the Consultant and the Beneficiary/End User, and the sequence in which these Guidelines should be written, shall be agreed between the Consultant and the Beneficiary/End User at the beginning of this task.

The SAM Guidelines to be developed by Consultant and End User/Beneficiary shall include but not be limited to:

  - a diagnostic part, including the key parameters and their threshold values, which enable identification of risks (threats, challenges) and/or the physical state of the Unit, and

  - an executive part, consisting of a set of specific instructions which are triggered from the diagnostic part of SAMG and detail the high-level actions identified at the stage of analysis and selection of the acceptable severe accident management strategies.

Within this task, the Consultant shall perform the following activities:

- Organise training (workshop(s)) for all future SAMG developers (at Consultant and at End User/Beneficiary side) of SAMG strategies, Computational Aids and Setpoints previously defined for Angra 2 NPP, and of Writer’s Guide and User’s Guide

Writing of SAMGs includes a number of interrelated activities, each of which influences the quality of SAMGs as a final product in a certain manner. Therefore the Consultant shall ensure that adequate requirements for the Quality Assurance of the project deliverables are established, including various reviews of the written accident management strategies and procedures or the ones still under development by independent members of the SAMG JWG and by the CR operators and TSC members of the Unit concerned.

Special attention shall be paid by the Consultant to:

  - include relevant references to background material providing the basis of the SAMG,

  - absence of any controversies or non-compliances between the already written strategies and procedures/guidelines and the newly developed (or updated) ones, and

  - clarity of the document and consistency of terminology.

- Writing of the SAM Guidelines.

This task shall be performed in a way ensuring the best transfer of knowledge between the Consultant and End User/Beneficiary.

Within this task the Consultant shall:

  - Write about 60 percent of the total number of SAM Guidelines.

  - Closely supervise the End User/Beneficiary during his writing of another 20 percent of the total number of SAM Guidelines.

  - Review the remaining 20 percent of the total number of SAM Guidelines, written by the End User/Beneficiary without close supervision by the Consultant.

- Support the End User/Beneficiary to perform the analyses needed to access the physical accessibility of equipments which require local action during a severe accident.

- Support the End User/Beneficiary to perform the other analyses needed (roles and responsibilities for the End User/Beneficiary teams involved in the accident management, modifications to the EOPs…).

Within this task, the End User/Beneficiary will also take care of the following activities:

- Under the supervision of the Consultant: Identification and distribution of the roles and responsibilities for:

- CR operators;

- Field operators;

- NPP shift supervisors;

- Technical Support Centres (TSC);

- NPP head offices;

- Technical support groups;

- Eletronuclear Headquarters Crisis centre

- Review SAM Guidelines developed by the Consultant.

- Perform the analyses needed to access the physical accessibility of equipments which require local action during a severe accident (such as restoration of power supply, sampling of water or gas within the primary circuit or in the containment, etc.). The physical accessibility of the equipment concerned in terms of hazardous effects of radiation, temperature, combustion products and other adverse factors need to be studied thoroughly when writing the SAMG procedures/guidelines. Minimum protection measures (e.g. protective screens, isolating gas masks, etc.) must be envisaged as necessary.

- Modify existing EOP as appropriate to take into account the new developed SAMG.

The development of the Severe Accident Management Guidelines for Angra 2 and all other supporting analyses shall be mainly carried out by the SAMG JWG.

The Consultant shall prepare a detailed Task 3.7 Technical Report.

The Task 3.7 Technical Report shall as a minimum present:

  - An overview of the different SAMG guidelines developed within this task and their technical justifications for Angra 2 NPP.

  - Copies of the materials and documentation, used for the training course on writing SAMGs.

The Beneficiary/End User shall review and agree on the Task 3.7 Technical Report.

The Consultant shall send the Task 3.7 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

Expected output of Task 3.7:

  - The Task 3.7 Technical Report

  - A complete set of written SAM Guidelines for Angra 2 NPP

Task 3.8: SAMG verification, validation and workshop

Within this task, the Consultant shall perform the following activities:

- Verification of the SAM Guidelines

Verification is an integral part of the project QA procedure and must be conducted to confirm the correctness of a written guideline and to ensure that all necessary technical aspects and human factors have been properly incorporated. The verification activities (including independent reviews by MCR/FSS operators and specialised organisations) shall be planned, arranged and conducted by the Consultant in accordance with the best international quality assurance practice.

- Validation of the SAM Guidelines:

Validation shall be planned, arranged and conducted by the Consultant in order to determine that the actions specified in the guidelines can actually be performed by the trained staff. This also implies to confirm that the strategy and its implementation have been chosen correctly.

Currently one of the most widely used methods of the SAMG validation is through

  - table-top exercises, in combination with

  - simulation exercises on the Full-Scale Simulators/FSS (or engineering simulators if FSS is not available) for transitions between EOPs and SAMGs

Integrated exercises involving all on-site emergency response teams are recommended. 		The possibility of such exercise shall be discussed with the End User at the project Kick-off

meeting.

- Based on the validation results, the Consultant together with the End User shall identify the necessary corrective actions and plan their implementation.

- At the end of this task the Consultant shall organise a training (workshop) for the members of the SAMG JWG to present a complete overview of the SAMG package (Strategies, Guidelines, Computational Aids, etc…) which was developed.

Within the scope of support of the Consultant concerning this task, the End User/Beneficiary will take care of the following:

  - Reservation of free access periods to the Full Scope Simulator for the Consultant and End User/Beneficiary team during the validation process of the SAM Guidelines to test as a minimum the transition between EOPs and SAMGs.

  - Participation in the verification/validation program conducted by the Consultant for the SAMG whole package.

The Beneficiary/End User shall review and agree on the Task 3.8 Technical Report.

The Consultant shall prepare a detailed Task 3.8 Technical Report.The Consultant shall send the Task 3.8 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

Expected output of Task 3.8:

  - The Task 3.8 Technical Report

Task 3.9: SAMG training material development, TSC and MRC Pilot Training

The objective of this task is:

  - to prepare the training material presenting SAM Guidelines for TSC and MCR personnel and to perform one Pilot training session.

Within this task, the Consultant shall perform the following activities:

- Preparation of training material presenting SAMG guidelines for TSC and MCR personnel

- Preparing and conducting one Pilot training session for TSC and MCR personnel

This pilot training session shall include as a minimum, classroom presentation (based on presentation slides) of Angra 2 NPP Severe Accident Management Strategies and Guidelines and practical exercises of SAMG usage.

Within this task, the End User/Beneficiary will take care of the following:

  - Reservation of free access periods to the Full Scope Simulator for the Consultant and End User/Beneficiary team during the pilot training session of the SAMG guidelines to test as a minimum the transition between EOPs and SAMGs.

  - Allow one team from the MCR and one team from the TSC to participate in the pilot training session.

  - Review and agree on the training material developed by the Consultant.

The Beneficiary/End User shall review and agree on the Task 3.9 Technical Report.

The Consultant shall prepare a detailed Task 3.9 Technical Report, including the training material.

The Consultant shall send the Task 3.9 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

Expected output of Task 3.9:

  - The Task 3.9 Technical Report

A copy of all training materials and documentation developed for the pilot training session

Task 3.10: Permanent consolidation of project results throughout the project

The accident management strategies, SAMG format and SAMG guidelines are subject for agreement with the State Nuclear Regulatory Committee (CNEN). Such task shall be planned and implemented by Eletronuclear.

This activity shall be taken care of by the Beneficiary/End User throughout the duration of the project (all project tasks).

Within this activity the Beneficiary/End User will be responsible to:

- Present to CNEN the severe accident management strategies as developed for Angra 2 NPP within task 3.4

- Present to CNEN the Structures, Systems and Components (SCC) and the Means of Monitoring and Measurement (MMM) available during severe accidents as identified and assessed in task 3.3

- Present to CNEN the Severe Accident Management Guidelines, Computational Aids, etc… as developed in tasks 3.5, 3.6 and 3.7

- Provide regular feedback to the Consultant during the discussion with CNEN

In order to help consolidate the project results, the Consultant shall support and assist the Beneficiary (on his request) during the project in presentations or discussions on Severe Accident Management he might have with the regulator CNEN. In case the Beneficiary receives preliminary regulatory comments that he would like to have addressed during the project, the Consultant shall give due consideration to these comments and shall take them into account in the final project deliverables to the extent possible. Under no circumstances, however, the consideration of such regulatory comments shall result in project delays.

It shall be noticed that all decision making on the acceptability of the SAMG package (Strategies, Guidelines, Computational Aids, etc..) and its subsequent agreement with CNEN is completely the responsibility of the End User – Eletronuclear.

The Beneficiary/End User shall review and agree on the Task 3.10 Technical Report.

The Consultant shall prepare the Technical Report for task 3.10.

The Task 3.10 Technical Report shall as a minimum present an overview of the different questions submitted to the Consultant in the frame of this task an the replies provided by the Consultant.

The Consultant shall send the Task 3.10 Technical Report for approval to the EC Project Manager after this Report has been endorsed by the Beneficiary/End User.

Expected output of Task 3.10:

  - The Task 3.10 Technical Report