## IRA2013_March_2016
IRA2013: Action Plan for implementation of Workplan activties in 2016-2017
2016 march 01
Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed
2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Vienna | PRM | Q1/2017
1.5 IAEA Field Monitoring (once per quarther)
2.2 Preparatory visit for OSART mission
3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | Q4/2016 |  |  | Planned for November 2016
2.4 Implementation the nuclear safety oversight function
4 | 2.4.1 | One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: Derakhshandeh | 1 IAEA+2IEX |  | Tehran | EM | Q1/2017 |  |  | The need to be confirmed at March 2016 follow-up visit
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
5 | 3.1.1 | WS on "modern methods for measuring hydrogen concentration in containment " | IAEA: S. Monti, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q2/2016 |  |  | NPPD: expecations and focus until 30 March
3.2 Training on environmental qualification of safety equipment of BNPP-1
6 | 3.2.1 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Deilami | 1 NEX |  | TBD | SV | Q3/2016 |  |  | NPPD: Nomination forms until 15 April
7 | 3.2.2 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Deilami | 1 NEX |  | TBD | SV | Q3/2016 |  |  | NPPD: Nomination forms until 15 April
8 | 3.2.3 3 | SV on " environmental qualification of safety equipment BNPP" | IAEA: K. Kang, NPPD: Deilami | 1 NEX |  | TBD | SV | Q3/2016 |  |  | NPPD: Nomination forms until 15 April
3.3 Training on equipment reliability assessment techniqes of equipment during operation
9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" | IAEA: K. Kang, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016
3.8 Development of ageing management program for BNPP-1
10 | 3.8.1 | EM on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | EM | Q3/2016
11 | 3.8.2 | Training on developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | Trainig course | Q2/2017 |  |  | New request
3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1
12 | 3.10.1 | WS on "Assistance on review of safety analysis model for safe operation for BNPP-1" | IAEA: T. Ulses, NPPD: Ghods-Derakhshandeh | 1 IAEA+3IEX/5 days |  | Tehran | EM | Q3/2016
13 | 3.10.2 | E M on independent analysis of root-cause results for BNPP-1 | IAEA: P. Tarren, NPPD: Abbaspour/Ghods | 1 IAEA+3IEX/5 days |  | Tehran | EM | Q2/2017
3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1
14 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q4/2016 |  |  | IAEA request further clarification of what NPPD are seeking.
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
15 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: T. Ulses, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2017
16 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; C .Hill, NPPD: Ghods-Abbaspour | 1 IAEA+2 IEX |  | Tehran | EM | Q2/2017
5.5 Assistance in development of selected training scenarios for severe accidents in FSS
17 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: D. Drury/T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | Q4/2017 |  |  | NPPD: to be implemented after 6.3.1, and additional training assiatnce - to be discussed in February
5.6 Assistance in development & improvement of training system of maintenance & repair personnel
18 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: D. Drury, NPPD: Rahnama-Talebianzadeh | 1IAEA+2IEX |  |  | EM | Q4/2016
6.1 Asistance in review of BNPP-1 off-site emergency preparedness and response
19 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" | IAEA: P. Salinas, NPPD: Abbaspour | 1IAEA+2IEX |  |  | WS | Q4/2016 |  |  | NPPD: To send clarification on the focus: Training on off-site response to radiological emergency situation BNPP-1?
6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1
20 | 6.3.1 | EM to review progress in lopment of the severe accident analysis model (using computer code) for BNPP-1 | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | WS | Q1/2017
21 | 6.3.2 | EM to review the rpogress in development of the severe accident managementguidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh | 1IAEA+2IEX |  | Tehran | EM | Q2/2017 |  |  | New request
7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1
22 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" | IAEA: M. Groening?, NPPD: Abbaspour | 1IAEA+3IEX |  |  | EM | Q2/2016 |  |  | IAEA to confirm the date. BNPP-1 will provide tools for measurements.
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
23 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: D. Talleria, NPPD: Abbaspour | Procurement |  |  |  | 2016 |  |  | NPPD: to clarify the scope and duration of maintenance period. The IAEA will inform anout the expected price. NPPD will proceed with the officils request. Timely payment of GCS is important.
2.3 Implementation of OSART mission
24 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  |  |  | Q4/2017 |  |  | IAEA: November 2017 is recommended. An official request is needed untl the end of Q2 2016
2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers
25 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  |  | EM | Q3/2016 |  |  | The scope and focus if the review mission need agreed by the 30 March.
2.7 Enhancing the capabilities in nuclear oversight functions by participation in OSART mission
26 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q1 2017( partially/ local cost to be paid by the host) | IAEA: P. Tarren, NPPD: Abbaspour | 1-2 NEX |  |  | FS | 2017
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
27 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: P. Vincze, P. Tarren, NPPD: Deylami | 1 IAEA+2IEX |  |  | WS | Q2/2017
3.4 Training on containment leakage tests and calculations after outage
28 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: Deylami | 1NEX |  |  | SV | Q2/2017
29 | 3.4.2 | SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: Deylami-Dehghani | 1NEX |  |  | SV | Q2/2017
30 | 3.4.3 | SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: Deylami-Dehghani | 1NEX |  |  | SV | Q2/2017
31 | 3.4.4 | SV on " Containment leakage tests and calculations after outage" | IAEA: P. Vincze, NPPD: Deylami-Dehghani | 1NEX |  |  | SV | Q2/2017
3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system
32 | 3.5.1 | SV on "Decreasing the time response of APCS system" | IAEA; J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  |  | SV | Q1/2017
33 | 3.5.2 | SV on "Decreasing the time response of APCS system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  |  | SV | Q1/2017
34 | 3.5.3 | SV on "Decreasing the time response of APCS system" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1 NEX |  |  | SV | Q1/2017
35 | 3.5.4 | SV on "Decreasing the time response of APCS system" | IAEA: J. Eiler, NPPD: | 1 NEX |  |  | SV | Q1/2017
3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR
36 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: J. Eiler, NPPD: Deylami-Dehghani | 1IAEA+3IEX |  |  | WS | Q1/2017
3.7 Assistance on safety aspects of extended BNPP-1 refueling cycles
37 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: C. Hill, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  |  | EM | Q1/2017
3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system
38 | 3.9.1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests, High and low cycle fatigue analysis for strength assessment of Reactor Coolant System | IAEA: K. Kang, NPPD: Ghods-Deylami | 1IAEA+2IEX |  |  | WS | Q3/2017
3.12 Assistance in performing the living PSA of the BNPP-1
39 | 3.12.1 | EM to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: I Kuzmina, NPPD: Ghods | 1IAEA+2IEX |  |  | EM | Q1/2017 |  |  | NPPD: To send information on the scope and focus two months before the mission.
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
40 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: C. Hill, NPPD: Derakhshandeh | 1 IAEA+2 IEX |  |  | EM | Q2/2017
4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
41 | 4.1.1 | EM on "modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes " in Q1 2017, (1 IAEA +3 IEX ) | IAEA: H. Varjonen, NPPD: Roshankar | 1IAEA+3IEX |  |  | EM | Q4/2017
4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
42 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA:J. Moore, NPPD: Tajbakhsh | 1IAEA+3IEX |  |  | EM | Q4/2016
5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
43 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  |  | WS | Q1/2017
5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
44 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  |  | SV | Q2/2017
45 | 5.2.2 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  |  | SV | Q2/2017
46 | 5.2.3 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: D. Drury, NPPD: Talebianzadeh - Rahnama | 1 NEX |  |  | SV | Q2/2017
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
47 | 7.4.2 | EM on "Review and assesment of results of environmental monitoring programme using the software ESTE" | IAEA: D. Talleria, NPPD: Abbaspour | 1 IAEA+2IEX |  |  | EM | Q4/2017
4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators
48 | 4.4.1 | Training on optimizing safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators | IAEA: P. Vincze NPPD:Roshankar |  |  |  |  | SV | Q3/2016 |  | New request for 2016 NPPD: to send the scope and focus of this task two months before the mission.
4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs
49 | 4.3.1 | Training on advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs | IAEA: P. VinczeNPPD:Roshankar |  |  |  |  | WS | Q3/2017 |  | New for 2017. NPPD: to send the scope and focus of this task two months before the mission.
[8 empty] | 37 active tasks |  |  | 3 new requests