## PCMFExport
IRA2012: Action Plan for implementation of Workplan activities in 2014-2017 | [8 empty] | 2015-02-11
Activity | Implementing Officers/Input | Resource required | Venue | Type | Funding | Budget | Budget Year | Date | Status/Comments
1.2 Conducting project review meetings
1.2.1 Annual project review and planning meeting 2014 | IAEA: Gueorguiev, NPPD: Fatourechian | 3 IAEA staff for 3 days | Tehran and Bushehr | EM | FootNote | 39,195 | 2012 | Q1/2014 | Completed
1.2.2 Annual project review and planning meeting 2015 |  | 3 IAEA staff for 3 days | Tehran and Bushehr | EM |  |  |  | Q1 2015 | Meeting 1.2.2 scheduled for 15-17 Feb 2015
1.2.3 Annual project review and planning meeting 2016 |  | 3 IAEA staff for 3 days | Tehran and Bushehr | EM |  |  |  | Q1 2016
1.2.4 Annual project review and planning meeting 2017 |  | 3 IAEA staff for 3 days | Tehran and Bushehr | EM |  |  |  | Q1 2017
1.5 IAEA field monitoring
1.5.1 Reqular field monitoring and review missions | IAEA: Gueorguiev, NPPD: Fatourechian | 1 IAEA staff for 4 days | Tehran and Bushehr | Meeting |  |  |  | 2014 | Completed
1.5.2 Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days | Tehran and Bushehr | Meeting |  |  |  | 2015 | 2015 planned dates:
1.5.3 Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days | Tehran and Bushehr | Meeting |  |  |  | 2016 | 1-2 missions per quarter
1.5.4 Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days | Tehran and Bushehr | Meeting | FootNote | 21,000 | 2012 | 2017 | 1-2 missions per quarter
2.2 Spent fuel storage and waste management programs
2.2.1 EM to assist in radioactive waste management programme, including scaling factor application | IAEA:Ormai/Dyck, NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX | Tehran | EM | FootNote | 3,095 | 2012 | 27 Sept - 1 Oct 2014 | Jointly with IRA2011/1.17.3 Completed
2.2.2 EM to assist in spent fuel storage (1 IAEA staff and 3 IEX) |  |  | TBD | EM |  |  |  | Q1/2017
3.1 Development of training materials for two new NPP projects
3.1.1 EM to assist in review of selected/developed training materials for two new NPP units | IAEA:Pal Vincze, B. Molloy NPPD: Fatourechian | 1 IAEA staff and 3 IEX | TBD | HBA/EM TBD |  |  |  | Q4/2015 | To be implemented on the developed materials provided by the supplier of two new units
3.1.2 EM to assist in review of selected/developed training materials for two new NPP units |  | 1 IAEA staff and 3 IEX | TBD | HBA/EM TBD | FootNote | 16,725 | 2012 | Q1/2017 | To be implemented on the developed materials provided by the supplier of two new units
3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant
3.2.1. WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety | IAEA: Kang, NPPD: Tajbakhsh | 1 IAEA staff and 2 IEX for 4 days | Tehran Bushehr | WS | HardCore | 21,000 | 2012 | 27-30 April 2014 | Completed
5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations
5.1.1 WS to assist NPPD in addressing safety requirements in construction of new PWR units at Bushehr for compliance by supliers local organizations | IAEA: Yagi/Tarren; NPPD: Sheikholeslami | 6 NEX and 3 IEX | Tehran/Vienna | WS | FootNote | 21,000 | 2012 | Q2-3/2015 | IAEA submited the new publication. Specific issues of interest to be provided by NPPD
6.1 Public information and awareness programmes development
6.1.1 WS on public information and awareness programmes | IAEA:B. Pagannone/ NPPD:Rahnama | 4-6 NEX and 2 IEX | Tehran | WS | FootNote | 16,350 | 2012 | 28 Sept-1 Oct 2014 | Completed
6.1.2 EM to assist on the establishment of public information and awareness centre |  | 1 IAEA staff and 2 IEX | Tehran/Bushehr | EM |  |  |  | Q4/2016
6.1.3 EM to review draft Stakeholder Involvement Plan |  | TBC | Tehran | EM |  |  |  | Q3/4 2015 | Additional request as follow-up of 6.1.1
2.1 Seismic safety assessment
2.1.1 EM to assist in seismic safety assessment | IAEA:O.Coman, Tarren NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX | Bushehr | EM | FootNote | 40,095 | 2013 | Q2/2015 | Specific issues of interest for site data to be provided by NPPD (Sheikholeslami)
3.3 Corporate knowledge management
3.3.1 EM on corporate knowledge management for BNPP - 2&3 with focus on safety | IAEA:Z. Pastory NPPD:Rahnama/Sheikholeslami | 1 IAEA staff and 3 IEX | Tehran | EM | FootNote | 7,805 | 2013 | 12-15 Apr.2015 | NPPD to cofirm days and to submit requested information (Rahnama)
3.3.2 EM on Management and maintaining design basis information through life cycle of BNPP-2&3 | IAEA:J.deGrosbois, Kolomiets 1 IAEA staff and 3IEX |  | Tehran | EM |  |  |  | 16-19 May/2015 | IAEA submitted propsal. NPPD to submit requested information (Sheikholeslami)
3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr
3.4.1 WS on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr |  |  |  |  | FootNote | 22,275 | 2013 |  | NPPD does not need further assistance
3.4.2 SV on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (SG) | IAEA: Khangi, SG NPPD: NPPD:Amini |  | TBD | SV |  |  |  | Q4/2015 | NFs to be provided timely in advance
Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr
4.1.1 EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units | IAEA:Molloy/Kang/Tarren, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX | TBD | HBA/EM TBD | HardCore | 27,875 | 2013 | Q3-4/2015 | Specific needs to be provided by NPPD on the basis of the contract for two new units
4.1.2 EM to assist in evaluation of developed programmes to update owner's training system for the two new PWR units |  | 1 IAEA staff and 3 IEX | TBD | HBA/EM TBD |  |  |  | Q3-4/2016 | Specific needs to be provided by NPPD on the basis of the contract for two new units
4.1.3 Trainig WS on BNPP-2&3 project management with focus on safety requirements | IAEA: Kang; NPPD: Fatourechian | 1 IAEA Staff, 3 IEX, 15 NEX | ICTC, Beijing, China | WS |  |  |  | 24 Aug.-4 Sept. 2015 | IAEA to prepare Prospectus. NPPD to confirm and to provide timely NFs for NEX
4.1.4 EM to assist in development of comprehensive model for effective project management of the two new NPP units | IAEA: P. Vincze, Kahg | 1 IAEA Staff and 3 IEX | Tehran | EM |  |  |  | Q3/2015 | New request. NPPD to provided information on current status and plans and specific issues of interes
4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units
4.2.1 EM to assist in review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units | IAEA: Vincze NPPD: Fatourechian | 1 IAEA staff and # IEX | TBD | EM and HBA | FootNote | 13,365 | 2013 | Q3-4/2015 | Jointly with 4.1.1