NUCLEAR POWER PRODUCTION AND DEVELOPMENT COMPANY OF IRAN

BUSHEHR-2 NPP

POWER UNITS 2, 3

Project Management Procedure

Design Documentation Change Management

BU2.0130.0.0.PM.DC0001

Revision B01

| APPOVED |  | APPROVED |
| --- | --- | --- |
| M. Jafari |  | V.N. Pavlov |
| BNPP Project Manager |  | Vice-President for Projects in the Middle East and Central Asia NIAEP JSC |
| _____ ._______.20__ |  | _____ ._______.20__ |

2016

ROSATOM STATE ATOMIC ENERGY CORPORATION

ATOMSTROYEXPORT

JOINT STOCK COMPANY

(ASE JSC)

BUSHEHR-2 NPP

POWER UNITS 2, 3

Project Management Procedure

Design Documentation Change Management

| Documentation package № |  |  |  |
| --- | --- | --- | --- |
| Document number | Total number of sheets | Date | Revision |
| BU2.0130.0.0.PM.DC0001 | 17 |  | B01 |
| Place of storage | File | ПП ГК.БУШЕР-2.002-2016 |  |

| Contract number | № NPP/4100/5500 – 2,3 |
| --- | --- |

2016

GROUP OF COMPANIES

ASE JSC, NIAEP JSC MOSCOW BRANCH, NIAEP JSC MOSCOW REPRESENTATIVE OFFICE

INTEGRATED MANAGEMENT SYSTEM

| Level 3 | Project Management Procedure |  |  |
| --- | --- | --- | --- |
| DESIGN DOCUMENTATION CHANGE MANAGEMENT |  |  |  |
| ПП ГК.БУШЕР-2.002-2016 BU2.0130.0.0.PM.DC0001 |  |  |  |
| Effected: |  | Version: 1 | Total number of pages: 17 |

Information regarding changes:

moscow

2016

APPROVAL AND AGREEMENT LIST

| Action | Position | Full Name | Signature | Date |
| --- | --- | --- | --- | --- |
| APPROVED | Vice-President for Projects in the Middle East and Central Asia NIAEP JSC | V.N. Pavlov |  |  |
| AGREED | Director for construction of Bushehr NPP NIAEP JSC | A.V. Deriy |  |  |
| AGREED | Director for designing of Bushehr-2 NPP Atomenergoproekt JSC | S.M. Takh |  |  |
| AGREED | Head o ASE JSC Representative Office in Iran (Tehran) | V.A. Skripichnikov |  |  |
| AGREED | Deputy Director for Quality Management – Head of Overseas NPP Quality and Normalization Assurance Division | A.G. Mukhlynin |  |  |
| AGREED | Head of Division for Construction of the NPP in Iran ASE JSC | A.A. Shevyrev |  |  |
| AGREED | Head of Information Model Configuration Division | I.M. Vlasova |  |  |
| AGREED | Head of Division for Quality Assurance during Designing NIAEP JSC | T.F. Konyakhina |  |  |

| Action | Position | Full name | Signature | Date |
| --- | --- | --- | --- | --- |
| Translation is checked by |  |  |  |  |
| Translated by |  |  |  |  |
| Checked by | Head of Engineering Procedure Section of Project Methodology Division NIAEP JSC | I.P. Belyaeva |  |  |
| Developed by | Chief Specialist of the Engineering Procedure Section of Project Methodology Division Главный NIAEP JSC | E.V. Churkina |  |  |

annotation

This document is developed within the framework of implementation of the Contract for construction of Bushehr nuclear power plant (Bushehr-2 NPP) № NPP/4100/5500 – 2, 3 dated 11.11.2014.

table of contents

1	Purpose	7

2	Scope of application	7

3	Terms, definitions and abbreviations	7

4	Responsibility	7

4.1	Responsibility of the Contractor	7

4.2	Responsibility of the Principal	8

5	Process of decision making on entering changes	8

5.1	General provisions	8

5.2	Decision making on entering changes as per the Principal’s initiative	9

5.3	Decision making on entering changes as per the Contractor’s initiative	10

5.4	Grounds for entering changes	11

6	Entering changes into Design Documentation	11

7	 Control of entering changes into Design Documentation	11

APPENDIX A (mandatory)   Scheme of the process of entering changes into Design Documentation	13

appendix B (mandatory) Form of the application for entering changes	14

appendix С    Structure of change management database	15

Change registration list	17

- purpose

- This management procedure specifies the order and documenting for entering changes into Design Documentation necessary for construction of Units No. 2, 3 of Bushehr NPP (hereinafter referred to as Bushehr-2 NPP and accepted by the Principal.

- This management procedure is the document of the Project management guide and is being developed in accordance with Appendix R to the Contract for construction of Bushehr nuclear power plant (Bushehr-2 NPP).

- This procedure specifies the responsibility of the Parties for ensuring effective management of changes in Design Documentation of Bushehr-2 NPP.

- This management procedure shall ensure complete and precise entering of changes agreed by the Parties, into Design Documentation, as well as the possibility for tracing thereof.

- SCOPE OF APPLICATION

- This management procedure specifies the requirements to the processes of initiating, review, agreement upon and entering changes into Design Documentation of Bushehr-2 NPP.

- This management procedure is valid for the Principal, Contractor and its subcontractors at all stages of Bushehr-2 NPP construction up to provisional acceptance of the units.

- Correction of Design Documentation in the process of development and agreement with other organizations, till sending thereof to the Principal, is not the change considered within the framework of validity of this procedure, and is not subject to documenting in accordance with this procedure.

- TERMS, DEFININTIONS AND ABBREVIATIONS

- The list of terms and definitions, abbreviations of the words and names which have a meaning for this document, is given in the text of the Contract.

- Terms, definitions and abbreviations which are used only in the text of this document, are given below:

| Design Documentation | Documentation containing materials in the text form and in the form of maps (schemes), and specifying architectural, functional-technological, design and engineering-technical solutions for ensuring construction, reconstruction of capital construction objects, their parts, capital repair, including Basic Design, PSAR, PSA, FSAR |
| --- | --- |

- responsibility

## responsibility of the contractor

  - ASE JSC Division for construction of the NPP in Iran is responsible for the following:

- arrangement of the work for entering changes into Design Documentation,

- registration of the Application in the database for changes and control of the Application review process (Technical Section)

- submission of changed Design Documentation to the Principal,

- ensuring of use of updated documentation by all subcontractors,

- preparation of draft addenda to the Contract,

- control of entering changes into Design Documentation as per decisions made (minutes of the meeting, technical solutions) (Technical Section).

  - Design Unit and subcontractors of the Contractor for designing are responsible for the following:

- Consideration of proposals for entering changes into Design Documentation received from the Principal (the Principal’s application may be conditioned by requirements of INRA and other competent bodies);

- Preparation of justification for entering changes into Design Documentation or the refusal;

- Participation in decision making for entering changes into DD on the basis of proposals/justifications provided by a person appointed by the Head of design unit responsible for handling the applications for changes in Design Documentation;

- entering changes and annulment of non-relevant documentation stored at the developer of the documentation,

  - ASE JSC Directorate at Bushehr NPP site is responsible for the following:

- receiving and issuance of the up-to-date revision of Design Documentation to users at the Site, if necessary;

- organization of annulment of the documentation received earlier and issuance of the valid revision for application.

## responsibility of the principal

    - The Principal (NPPD Co.) is responsible for the following:

- agreement upon this procedure and fulfillment of its requirements by its personnel,

- receiving and submission of the application for entering changes into Design Documentation of INRA and other competent bodies,

- preliminary agreement, with NRA, of changes to be requested by the Principal,

- organization of discussion of requested changes with participation of the Contractor’s specialists and IRI competent bodies concerned.

- process of decision making on entering changes

- general provisions

- Changes in the Design Documentation approved by the Principal, may be caused by the following reasons:

- change in the regulatory base adopted in the Project;

- lack of necessary technologies for implementation of design solutions;

- as per requirement of the Principal/ regulator INRA, if the changes do not negatively influence the temporary schedules of the plant, safety level and quality guarantees (in accordance with conditions and procedure for actions of the Contract Article 9);

- in connection with the information on innovations related to supplies and services of the Contractor, about which it informed the Principal;

- proposals of the Contractor in connection with innovations and achievements related to Supplies and Services of the Contractor.

- Entering changes in the documents approved by the Principal, may be initiated by any of the Parties or the Contractor’s subcontractor performing the work under such documents.

- The scheme of the process of entering changes into Design Documentation is given in Appendix А.

- decision makin on entering changes as per the principal’s initiative

- The Principal shall be entitled at any moment in the course of the Contract performance up to the preliminary acceptance of the corresponding unit, to send the Contractor with the accompanying letter an application for entering changes (hereinafter referred to as the Application). The form of the Application is given in Appendix B hereto.

- The letter and the scanned Application with all signatures shall be sent to the Contractor’s Project Manager. The subject of the accompanying letter shall mention “Application for entering changes LLN.NNNN.0.0.LL.NNNN». The accompanying letter shall be sent to the head of the Design Unit of the Project Office on the day when it was received from the Principal.

- The Principal shall also place the Application in the EDW information system, including that in the editable format (for ensuring the possibility of operative translation). The system shall send the Application for translation automatically, and shall automatically return the document to PM and the head of PO Design Unit. Translation of the Application without attachments shall be performed within one working day.

- The person appointed by the Head of PO Design Unit as responsible for handling the applications for changes in the Design Documentation within one working day shall ensure sending of this Application to all concerned subdivisions (by the memo) and subcontractors (by the outgoing letter).

- Responsibility for registration of the Application in database for changes (Appendix C hereto), sending for review and control of the Application review process lies with the Head of the Technical Section of the NPP Construction Division. A person authorized by the Head of the Technical Section of the NPP Construction Division shall be entitled to control and edit the records in the database.

- Within 5 working days the participants of the review shall review the received Application and send their opinion regarding acceptability of the Application and regarding the influence of the entered changes on the Project as a whole to the responsible person appointed in accordance with item 5.2.4 for compilation and submission to the Head of the PO Design Unit and PM.

- The final decision on acceptability of the proposed changes shall be made by PM.

- Within 15 working days after receipt of the Application the Contractor shall inform the Customer on its acceptability for review and expected timeframes for submission of fulfillment or rejection conditions to the Principal, if the changes requested by the Principal negatively influence the temporary schedules of the Plant or Guarantees and/or Quality Guarantees, safety level and conformance of the works or achievement of Performance Guarantees.

- Should no corresponding refusal be provided to the Principal within 15 working days, the Application shall be deemed accepted, and the Contractor shall undertake all necessary actions for entering such change.

- If the Application is acceptable, the Contractor within the deadlines mentioned in the reply to the Application shall send the Principal the detailed information regarding the deadlines and conditions of execution thereof, having attached, if necessary, the draft addendum to the Contract according to the established form.

- In the event the Application is not acceptable, the Contractor shall provide the justification of its refusal within 30 working days after sending the notification on refusal to consider the Application. The justification shall include the assessment of the impact of the requested change, where applicable, on the following:

- price;

- schedule;

- Guarantees and Quality Guarantees;

- conformity of the proposed changes to the Plant design,

- equipment safety;

- Plant safety on the whole.

- The Principal shall send the Contractor its decision regarding results of the consideration in the written form not later than 15 working days upon receipt of the justified refusal from the Contractor.

- Upon receipt of the Principal’s decision, if necessary, the Contractor within 15 working days shall arrange the topical meeting for settlement of disagreements, including the deadlines, scope and methods for compensation of the costs.

- If a decision is made at the meeting to fully implement the change, the decision, deadlines of performance and responsible persons shall be fixed in the Minutes of the Meeting, entered into the database for changes and implemented in accordance with the internal procedures of the Contractor upon execution of the addendum to the Contract.

- If a decision is made to implement the change partially, the decision, deadlines of performance and responsible persons shall be fixed in the Minutes of the Meeting. The considered Application shall get the status “rejected, subject to correction”, and the Principal shall execute a new Application for that scope of changes which is agreed in the course of the meeting.

- The decision from the minutes of the meeting shall be entered into EDW.

- The Project Manager shall control that the deadlines for entering changes have been met.

- Should the Parties fail to reach the agreement, the issue shall be transferred to the nearest coordination meeting where the decision is made to

- reject;

- correct;

- accept the Application for work with the mention of conditions and the deadline for concluding the Addendum to the Contract.

- decision making on entering changes as per the Contractor’s initiative

- The Contractor shall be entitled, at any moment in the course of the Contract performance till the provisional acceptance of the corresponding unit, to send the Principal, with the accompanying letter, the Application for entering changes according to the form of Appendix B hereto. The Contractor shall also place the Application in EDW information system, including that in the editable format (for ensuring the possibility of operative translation).

- The Principal shall consider the proposal and not later than in 15 working days shall provide the official reply for the Application. Should no reply be received within 15 working days, the Application shall be deemed accepted. The Principal shall not be able to reject the changes without convincing justifications.

- In the event the change is not followed by additional costs for the Principal or prolongation of the supply deadline, the Contractor shall be entitled to enter the change prior to receiving the Principal’s consent.

- In the event of the justified refusal, the Contractor shall arrange the topical meeting for settlement of disagreements. The implementation of the change shall be stopped for this period.

- Should the Parties fail to reach the agreement, the issue shall be transferred to the nearest coordination meeting.

- grounds for entering changes

- The agreed Application or the decision, fixed in the Minutes of the Meeting, or the signed Addendum to the Contract may be the grounds for entering changes into Design Documentation.

- entering changes into design documentation

- Changes into Design Documentation shall be entered as per instruction of the Project Manager by organizations-developers of the documentation to be changed, in accordance with BU2.0120.0.0.QM.DC0004 «Terms of Reference for Bushehr-2 NPP». Appendix 6. Design Documentation Execution System. Basic Design Documentation Execution Manual. General Provisions»).

- The changed documentation shall be entered into EDW system, undergo the established agreements, as the initial documentation. After issuance of the documentation the Contractor shall load the documents into EDW and provide the access to the Principal.

- The process of agreement upon and approval of changes entered into Design Documentation corresponds to the process set forth in document BU2.0120.0.0.PM.DС0001 «Terms of Reference for Bushehr-2 NPP». Appendix 8. «Bushehr-2 NPP Project documentation submission, review and approval system». Procedure for documentation submission, review and approval with use of EDW system. BU2.0120.0.0.PM.DC0001.

- The changed documentation shall be submitted to the Principal in accordance with requirements set forth in the Procedure for supply of the documentation under NPP project BU2.0120.0.0.PM.DС0003.

- The information and references to justifying documents shall be loaded into the data base automatically from EDW in the course of their status change in the system.

- control of entering changes into Design documentation

- The Head of PO Design Unit shall ensure and control the deadlines and correctness of entering changes. The Technical Section of the NPP Construction Division shall ensure proper information of the concerned organizations regarding entered changes. The Contract Section of the NPP Construction Division shall issue the invoice if it is stipulated by the Addendum to the Contract.

- Distribution and annulment of invalid documents shall be controlled in accordance with QAP(G) and QAP of the documentation developers.

# appendix A
(mandatory)
Scheme of the process of entering changes into Design Documentation

# Приложение B / appendix B
(обязательное / mandatory)
Форма заявки о внесении изменения / Form of application on entering changes

| Проект АЭС «Бушер-2» / Bushehr-2 NPP Project |  | Код документ / Document code | Блок No. / Unit No. | Дата / Date |
| --- | --- | --- | --- | --- |
| Заявка о внесении изменения (Change Request) |  |  |  |  |
| Инициатор: |  |  |  |  |
| Initiating entity: |  |  |  |  |
| - Содержание изменения (описание, указание кодов и наименований соответствующих документов, в которые предполагается внести изменения): |  |  |  |  |
| Change (description, indication of codes and titles of the documents whereto the changes are suggested to be introduced): |  |  |  |  |
| - Причина изменения и обоснование необходимости: |  |  |  |  |
| Cause of change and justification: |  |  |  |  |
| - Перечень приложений, обосновывающих необходимость внесения изменений; копии листов документов (чертежей) с указанием предлагаемого изменения |  |  |  |  |
| List of attachments justifying the need in changes, copies of documents (drawings) indicating the suggested change |  |  |  |  |
| - Перечень документов (аспектов), на которые такое изменение повлияет: |  |  |  |  |
| List of documents (aspects) prone to effects caused by the change in question: |  |  |  |  |
| - Предлагаемые сроки выполнения изменения: |  |  |  |  |
| Suggested dates of implementation: |  |  |  |  |
| □ Требуется выпуск Дополнения к Контракту Contract variation is required | □ Не требуется выпуск Дополнения к Контракту Contract variation is not required |  |  |  |
| Должность уполномоченного лица, дата, подпись, ФИО латинскими буквами |  |  |  |  |
| Position of the authorized person, date, signature, full name in Latin letters, |  |  |  |  |

- appendix С
Structure of change management database

| Order number | Code of application for changes | Building/ structure KKS | System KKS | Document code | Developer of the document | Date of sending the proposal | Date of receipt | Date of distribution for review | Decision made under this proposal (number of the letter or minutes of the meeting) | List (Title, code) and the date of submission of changed documents, who entered the data | Main design changes | Mark regarding acceptance by the Principal (number of the letter, minutes of the meeting, e-mail |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |

list of adopted abbreviations

| NPPD Co | Nuclear Power Production and Development Company of Iran |
| --- | --- |
| ASE JSC | Atomstroyexport JSC |
| NPP | Nuclear Power Plant |
| Bushehr-2 NPP | Units № 2, 3 of Bushehr nuclear power plant |
| PSA | Probabilistic Safety Analysis |
| Directorate | ASE JSC Directorate at Bushehr NPP site |
| Contract | Contract for construction of Bushehr NPP (Bushehr-2) dated 11.11.2014 № NPP/4100/5500-2,3 |
| PO | Project Office |
| QAP | Quality Assurance Program |
| PSAR | Preliminary Safety Analysis Report |
| PM | Project Manager |
| NPP CD | Division for construction of NPP in Iran, ASE JSC |
| EDW | Electronic Document Workflow |
| FSAR | Final Safety Analysis Report |

- change registration lisT

| Change | Numbers of sheets (pages) |  |  |  | Description and the reason of changes | Total number of sheets (pages) in the document | Document № | Signature | Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | changed | replaced | new | annulled |  |  |  |  |  |

The document code assigned in accordance with document BU2.0120.0.0.QM.DC0003 «Bushehr-2 NPP». Terms of Reference for Bushehr-2 NPP. Appendix 5. Coding System. Project Documentation Coding Manual»