## IRA2013_July 2019
Attachment 2
IRA2013: Action Plan for implementation of Workplan activities in 2019-2020
as of 07.07.2019
Enhancing the Level of Operational Safety and Reliability of the Bushehr Nuclear Power Plant-1
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  | 3 IAEA staff for 4 days |  | Tehran | PRM | Q1/2016 | Completed
2 | 1.2.2 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | PRM | 14-15 Feb. 2017 | Completed
1.5 IAEA Field Monitoring (once per quarther)
2.2 Preparatory visit for OSART mission
3 | 2.2.1 | Preparatory mission for OSART mission | IAEA: P. Tarren, NPPD: Abbaspour | 2 IAEA/3 days |  | Bushehr | WS | 14-16 Nov 2016 | Completed | H
2.4 Implementation the nuclear safety oversight function
4 | 2.4.1 | EM, One week follow-up Expert Mission to assist NPPD for Implementation the Nuclear oversight function | IAEA: P. Tarren, NPPD: JALILI (responsible person) | 2 IAEA+2IEX |  | Tehran | EM | Q3/2019 |  | M | 27.01.18: NPPD will summarize the actions from the 2 previous missions and send a summary to the IAEA 6 months before the expert mission. 08.01.19: See according SV "additional task 1" below (Chapter 8). CEZ accepted to host an iranian for this SV, detailed to be clarified
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
5 | 3.1.1 | WS on "modern methods for measuring hydrogen in primary loop and analysis | IAEA: Song, NPPD: Deilami | 1 IAEA+3IEX |  | Bushehr | WS | 18-21 Feb 2017 | Completed | H
3.2 Training on environmental qualification of safety equipment of BNPP-1
6 | 3.2.1 3 | Training on environmental qualification of safety equipment of BNPP-1 (SV on environmental qualification of safety equipment BNPP by the end of Q2 2018 (topic: "specific issues of integrated KWU equipment into BNPP-1 Project")) | IAEA: E. Bradley / NPPD: Banazadeh | 1 NEX+HBA IEX |  | Bushehr | EM | Q2/2019 | 3 NFS sent through official channel in Jan. 2017.it is expected to hold the task on Q2/Q3 2017 | H | 27.01.18: SV will be replaced by an Expert Mission at BNPP with 2 IEX from KWU Design NPPs. 14.05.18: K-S. Kang will ask China again to hold a SV on this topic. 17.10.18: China is not responding, EM will have to be planned (see MoM May 2018 Annex 1, 7.)., 06.05.19: ToR has been sent to Mr. Bradley on 09.12.18. Difficult to find experts. NPPD will discuss with BNPP to come to Vienna (4NEXs) and come back to IAEA by end of June 2019.
7 | 3.2.2 3 | " | IAEA: E. Bradley / NPPD: Banazadeh | 1 NEX+HBA IEX |  | Bushehr | EM | Q2/2019 | " | H | "
8 | 3.2.3 3 | " | IAEA: E. Bradley / NPPD: Banazadeh | 1 NEX+HBA IEX |  | Bushehr | EM | Q2/2019 | " | H | "
3.3 Training on equipment reliability assessment techniqes of equipment during operation
9 | 3.3.9 | WS on "Equipment reliablity assessment techniqes of equipment during operation" |  | 1 IAEA+3IEX |  | Bushehr | WS | Q3/2016 | Deleted
10 | 3.3.10 1 | SV on SPI and reliability application and evaluation | IAEA: Mandula, NPPD:Deylami | 4 NEX |  | TBD | SV | 2018 | Deleted | H
11 | 3.3.10 2 | " | " | " | " | " | " | " | " | "
12 | 3.3.10 3 | " | " | " | " | " | " | " | " | "
13 | 3.3.10 4 | " | " | " | " | " | " | " | " | "
14 | 3.8.1 | WS on development of ageing management program for BNPP | IAEA: K. Kang, NPPD: Ghods-Deylami | 1 IAEA+3IEX |  | Tehran | WS | 11-13 Feb 2017 | Completed | H
15 | 3.8.1-1 | WS on SALTO | IAEA: G. Petofi / NPPD: Ghods-Talebi | 1 IAEA+3IEX |  | Tehran | EM | Q2/2019 | Shifted to another project | H | 14.05.18: Postponed to upcoming years (Talebi) - WS possible. Feedback from NPPD expected. 17.10.18: EVT1705047, AMP EM to be discussed after implementation of the SALTO WS. planned 10-12.06.19
16 | 3.8.1-2 | SV on AMP | IAEA: Robert Krivanek, NPPD: Ghods-Deylami | 4NEX |  | TBD | SV | Q1-2/2018 |  | H | 14.05.18: see MoM (SALTO observers). IAEA suggests that it takes place after 3.8.1-1.
17 | 3.8.1-3 | Procurement of FAC software , COMSY | IAEA: E.Bradley, NPPD: Ghods | TBD |  | TBD | Procurement | 1905-07-11 | 14.05.18: NPPD will clarify the topic internally and inform IAEA. 18.11.18: TAVANA will send to Mr. Vincent Roue by 25.11.18 on the 4 specific modules they want to buy. IAEA will investigate the procurement and financial aspect., 4 modules have been selected by NPPD (Modules 2,3,4 and 7) to reduce costs. the technical officer will investigate new price and contractual details by the end of July 2019
18 | 3.8.2 | WS developing a corrosion management programme for BNPP-1 with focus on FAC management | IAEA: Varjonen, NPPD: Ghods-Talebi | 1 IAEA+3IEX |  | Tehran | WS | Q1/2020 |  | H | 17.10.18: difficult to find experts. Could we open the scope to Ageing Management? Could take place Q1/2019 if experts are found. 18.11.18: Q1/19 accepted, Mr. Varjonen will make a proposal to Mr. Talebi on the scope before 25.11.18. Postponed to July.2019.,06.05.19: EVT1805160 Scope extended to AM. NPPD requested to extend the scope to piping vibration which might be difficult. Moreover, TO is still looking for experts. Postponed to Q1 2020
3.10 Assistance on Computational Fluid Dynamic (CFD) analysis for safe operation of BNPP-1
19 | 3.10.1 | EM on Assistance on Review of Safety Analysis Model | IAEA: Petkov, NPPD: Ghods (Raji)-Derakhshandeh | 1 IAEA+3IEX/5 days( HBA 5 days) |  | Tehran | EM | Q1/2018 Q4/2018 | Completed | M | 27.01.18:. Review activity is postponed to Q4/18. Inputs (results of calculation) are needed 2 months prior to EM. 14.05.18: IAEA requests ToR by the end of June 18.18. 17.10.18: is happening 3-5.12.18
20 | 3.10.2 | EM on independent analysis of root-cause results for BNPP-1 | IAEA: Dian Zahratka, P.Tarren, NPPD: Ghods/Derakhshandeh | 1 IAEA+3IEX/5 days |  | Bushehr | EM | Q4/2017 (07-11 October) | Completed | H | NPPD to provide two month before information in English on the root cause analysis in the last two years.Dian Zahradka is the Implementing Officer from IAEA side.
3.13 Assistance in improvement of Core Management Activities for Safe Operation of BNPP-1
21 | 3.13.1 | EM on "Core Management calculation for Safe Operation of BNPP-1" | IAEA:T. Ulses, NPPD: Ghods-Abbaspour | 1 IAEA+2IEX |  | Tehran | EM | Q4 /2017 | Deleted | M | 10.10.17: IAEA request further clarification of what NPPD are seeking at least two months before.(availability of software and scope of the mission). 13.11.17: low priority, postponed to Q2/2018. 27.01.18: deleted
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
22 | 3.14.1 | EM on "Fuel Integrity Monitoring for Safe Operation of BNPP-1 "(Follow up - of the related activity conducted under project IRA 2 011) | IAEA: N. Kilic, NPPD: Ghods-Abbasopur | 1 IAEA+2IEX |  | Tehran | EM | Q2/2018 Q4/2019 |  |  | Task is urgent. (Mr. Kilic has been re-informed on 04.01.19). 13-17,June,2019., Varjonen Deputy TO. 06.05.19: no experts found yet. Postponed to Q4/2019. TO will try to organize the meeting in Vienna or second in Tehran by the end of 2019 (first choice).
23 | 3.14.2 | EM on physical behaviour (thermal, neutronic and radiation) of spent fuel | IAEA; Christoph Gasti, NPPD: Ghods (Ertejaie) | 1 IAEA+3 IEX |  | Tehran | EM | Q3/2019 | In progress | M | Postponed to May/2019 18.11.18: Ms. Gonzalez is asked to provide TAVANA with dates and experts. 08.01.19: Ms 90 4 Maintenance and outage management Gonzalez has been. EVT1806858 Mission is postponed - one expert cannot join at the moment (planned for Q3/2019)
5.5 Assistance in development of selected training scenarios for severe accidents in FSS
24 | 5.5.1 | EM on " Development of selected training scenarios for severe accidents in FSS " | IAEA: T. Ulses NPPD: Talebianzadeh, A. Rahnama | 1 IAEA+2IEX |  | Bushehr | EM | TBD |  |  | To be discussed after implementation of 6.3.1,
5.6 Assistance in development & improvement of training system of maintenance & repair personnel
25 | 5.6.1 | EM on " Development & improvement of training system of maintenance & repair personnel" | IAEA: D. Drury / NPPD: Rahnama;Talebianzadeh | 1IAEA+2IEX |  | Bushehr | EM | Q1/2018 Q2/2018 | Completed | H
6.1 Asistance in review of BNPP-1 off-site emergency preparedness and response
26 | 6.1.1 | WS on " Assistance in review of off-site emergency prepardness and response of BNPP and off-site organizations in Emergency situation" |  | 1IAEA+2IEX IAEA:V.Welter, NPPD: Abbaspour |  | Bushehr | WS | Q2/2017 - 06-10 May 2017 | Completed | M
6.3 Assistance on Severe Accident (SA) Analysis of BNPP-1
27 | 6.3.1 | WS on severe accident analysis model for BNPP-1 | IAEA: T. Ulses, NPPD: Ghods (Raji)/ Derakhshandeh | 1IAEA+2IEX |  | Bushehr | EM | Q4/2017 Q2/2019 | In progress |  | 17.10.18: has been postponed to 26-30.01.19 (Q1/2019). 08.01.19: re-postponed later on in 2019. 06.05.19: New target date is Sept/oct 2019. The IAEA will come back to NPPD asap.
28 | 6.3.2 | EM to review the progress in development of the severe accident management guidelines (SAMG) for the BNPP-1 (2017) | IAEA: T. Ulses, NPPD: Derakhshandeh- | 1IAEA+2IEX |  | Tehran | TSR-AM | Q3/2017 Q1/2018 |  | H | 17.10.17: To be implemented during Q1/2018, preparatory work not completed. 29.01.18: merged with 6.3.1
7.3 Assistance on methods for gamma spectrometry analysis of primary circuit samples and on off-site environmental samples for normal and emergency conditions of BNPP-1
29 | 7.3.1 | EM on " Assistance on methods for gamma spectrometry analysis of primary circuit samples and on and off-site environmental samples for normal and emergency conditions of BNPP-1" |  | 1IAEA+3IEX IAEA: M. Groening, NPPD: Abbaspour |  | Bushehr | EM | 3-7 Dec 2016 | Completed | H
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
30 | 7.4.1 | Support for the procurement ESTE environmental monitoring software specific for BNPP-1 | IAEA: S. Foister, NPPD: Abbaspour | Procurement |  | Bushehr | Procurement | May, 2017 |  | H | 11.10.17: all clearance processes have been completed, waiting for procurement. The target date for issuance of the purchase order is end of November 2017. Installation of the software in Iran will be schedule thereafter by BNPP and supplier with support
2.3 Implementation of OSART mission
31 | 2.3.1 | 18 days , OSART Mission ( Partial/local cost supporting by host) | IAEA: P. Tarren, NPPD: Abbaspour (90 000 EUR) | 3IAEA+12IEX for 18 days |  | Bushehr | EM | 29 Sep- 17 Oct. 2018 | Completed | H | 27.01.18: NPPD asked for team size and composition. Venue date is 29.09.18 - 17.10.18
2.5 Assistance in review of implementation of the NPPD Integrated Management System (IMS), plans for improvements including safety requirements for compliance by services providers
32 | 2.5.1 | EM on " Assistance in review of implementation of the developed NPPD IMS" | IAEA: P. Pyy, NPPD: Choupanzideh | 1 IAEA+3IEX |  | Tehran | EM | 16-20 July 2016 | Completed | H
a
33 | 2.7.1 | Participation in external OSART mission in NPP, preferable the same as BNPP is,for more readiness to implement own OSART mission in Q4 2018( partially/ local cost to be paid by the host) |  | 1NEX IAEA: P. Tarren, NPPD: Abbaspour |  | Leningrad NPP (St Petersburg Russia) | FS | 30.11.2017 | Completed | H | NPPD requests to involve 3 NEXs.One place agreed for 13-30 November 2017 in Leningrad.
34 | 2.7.2 | EM- Assist visits on operation,Maintenance and technical support areas as preparation for OSART mission |  | 2IAEA+1IEX IAEA: P. Tarren, NPPD: Abbaspour |  |  | EM | Q2/2018 | Completed | H | 08.03.18: Takes place 28-30 May 18
35 | 2.7.3 | Asist visits on HTO and GSR-Part2 areas as preparation for OSART mission | IAEA: R. Cavellec, H. Rycraft NPPD: Khezri | 2IAEA+1IEX |  | 4 working days , Bushehr | EM | Q4/2017 20-23 November | Completed | H | 10.10.17: EM
3.1 Training on modern method for measuring hydrogen concentration in containment and chemical-physical internal cleaning of NPP equipment
36 | 3.1.2 | WS on "Chemical-Physical internal cleaning of reactor equipment" | IAEA: B.Song, K.Makela, NPPD: Deylami | 1 IAEA+2IEX |  | Bushehr | WS | Q2/2017 | Deleted | H
3.4 Training on containment leakage tests and calculations after outage
37 | 3.4.1 | SV on " Containment leakage tests and calculations after outage" | IAEA: B.Song, NPPD: Deylami | 1NEX |  | TBD | SV | Q2/2018 | Cancelled | H | Move to the next cycle. (2018-2019)
38 | 3.4.2 | " | " | " | " | " | " | " | " | " | "
39 | 3.4.3 | " | " | " | " | " | " | " | " | " | "
40 | 3.4.4 | " | " | " | " | " | " | " | " | " | "
3.5 Training on planning, organizing and implementing the modernization in top level control unit systems under LICS operating system
41 | 3.5.1 | SV on "Decreasing the time response of modern I&C system" | IAEA; J. Eiler, NPPD:Dehghani | 1 NEX |  | China | SV |  | Completed | M | 29.01.18: takes place in April 18
42 | 3.5.2 | " | " | " | " | " | " | " | " | " | "
43 | 3.5.3 | " | " | " | " | " | " | " | " | " | "
44 | 3.5.4 | " | " | " | " | " | " | " | " | " | "
3.6 Assistance to strenghten the capability of BNPP personnel on application of new IAEA standards in modification MCR
45 | 3.6.1 | WS on " Application on new IAEA standadrds in modification I&C on MCR" | IAEA: V. Roue, NPPD: Dehghani | 1IAEA+3IEX |  | Bushehr | WS | Q3/2018 1-4.12.2018 | Completed |  | 14.05.18: NPPD action: ToR to be sent by the of May 2018. The mission will take place Beginning of December 2018. IAEA will send the final dates by the end of May.Take place 1-4.12.2018
t
46 | 3.7.1 | EM on "safety aspects of extended BNPP-1 refueling cycles" | IAEA: T.Ulses / H.Varjonen, NPPD: Ghods, Abbaspour | 1IAEA+2IEX |  | Tehran | EM | Q1/2017 | Deleted | H
3.9 Integrity safety analysis of thereactor pressure vessel and reactor coolant system
47 | 3.9.1 | WS on Assessment of the RPV neutron irradiation embrittlement as well as Analysis of RPV surveillance specimens mechanical tests | IAEA: A. Dutta Ray / NPPD:Ghods | 1IAEA+2IEX |  | Tehran | WS | Dec,2017 Q1/2018 Q2/2019 |  | M | 08.01.19: See Email sent by Mr. Ed Bradley (NPES internal Email) for list of 4 Experts found originally by Mr. Kang. Task should take place during Q2/19. For ToR see email sent by tavanaengdep on 28.11.18., 06.05.19: Planned for Q3 2019 (2nd week of September) – Experts have been identified. 07-11.09.2019.
48 | 3.9.1 -2 | WS on high and low cycle fatigue analysis for strength assessment of reactor coolant system | IAEA: E. Bardley, NPPD:Ghods/Deylami | 1IAEA+2IEX |  | Tehran | WS | 2019 |  | M | 14.05.18: IAEA continues to find experts and recommends to hold the EM in Vienna or Slowakia. NPPD will consider it and will reply by the end of July 18.No answer from NPPD. Q1/2019 possible? Vienna? Tehran?
3.12 Assistance in performing the living PSA of the BNPP-1
49 | 3.12.1 | SV to review the progress and to improve NPPD capability in living PSA of the BNPP-1 | IAEA: Shahaen Poghosyan / NPPD: Ghods | 1IAEA+2IEX |  | TBD | EM | Q4/2019 |  |  | 18.11.18: Changed into a SV (Q4/19). Preferred hosts: Bulgaria, CZ rep, Hungary. Communication with TAVANA through tavananuc@nppd.co.ir (4NFs will be sent). Tavana will send ToR by 05.12.18. 08.01.19: Shahen Poghosyan has been asked to support.
3.14 Assistance on safety aspacts of fresh and spent fuel engineering
50 | 3.14.2 | EM on Physical Behaviour (thermal, nuetronic and radiation) of spent fuel | IAEA: A. Gonzalez Espartero / T.Ulses, NPPD: Ghods | 1 IAEA+2 IEX |  | Tehran / Bushehr | EM | Q2/2017 | to be removed | M | NPPD requested to provide information two months before.
4.1 Training on modern methods of Codition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes
51 | 4.1.1 | EM on modern methods of Condition Based Maintenance at BNPP-1 for optimizing maintenance and repair programmes |  | 1IAEA+3IEX IAEA: H. Varjonen, NPPD: Roshankar |  | Bushehr | EM | Q4/2017 25-30 November | Completed | H | NPPD will provide more information on area(s) by the end of May.
4.6 Asistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance
52 | 4.6.1 | EM on " Assistance on improvement of the procurement system for goods and services necessary for BNPP safe and reliable operation and maintenance" | IAEA: A. Dutta Ray / NPPD: Mohebi | 1 IAEA + 3 IEX |  | Tehran/Vienna | EM/HBA | Q2/2019 Q4/2019 |  | H | 18.11.18: ToR will be sent by 15.12.18,EM in Bushehr middle of May 2019, Expert preference: Hungary, CZ Rep, Germany, Russia. 08.01.19: Mr. Dutta Ray might be the TO. Should take place during May 19., 06.05.19: 1IEX (Russia) has been identified at the moment. EM needs to be postponed to Q4 2019 (Nov Dec). EVT1803631. Expert Preference: GER, CZ Rep, Hun, Russia
5.1 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
53 | 5.1.1 | WS on " Competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: V. Roué, NPPD: Talebianzadeh - Rahnama | 1IAEA+2IEX |  | Bushehr | WS | Q4/2018 3-6.11.2018 | Completed | M | 14.05.18: The WS should include HR and Training Performance Indicators. Expectations to be sent by NPPD (Talebianzadeh) by the end of June 2018. Focus on Competency Model and Performance Management.
5.2 Training on competency models, method/assessment tools for effective competence and performance management of BNPP-1 personnel
54 | 5.2.1 | Scientific visit on " competency models, method /assessment tools for effective competence and performance management of BNPP-1 personnel" | IAEA: M. Van Sickle, NPPD: Talebianzadeh - Rahnama | 1 NEX |  | TBD | SV | Q3/2017 Q3/2018 | NFs will send 6 months before | M | Postponed to Q3/2018. If request is sent now, possible to take place Q4/2018. 27.01.18: Japan? 15.05.18: NPPD will provide feedback by the end of October 2018. Cancelled at the moment.
55 | 5.2.2 | " | " | " | " | " | " | " | " | " | "
56 | 5.2.3 | " | " | " | " | " | " | " | " | " | "
7.4 Assistance in environmental monitoring programme for BNPP-1 (follow-up of assistance provided in IRA2011)
57 | 7.4.2 | EM on "Review and assessment of results of environmental monitoring programme using the software ESTE" | IAEA: Diego Telleria / NPPD: Rostami | 1 IAEA+2IEX |  | Bushehr | EM | Q1/2019 |  | M | 06.05.19: 1 IEX working in an NPP with a similar SW (Hungary, Slovakia or Cz Rep), 1 IEX from the developer (Abmerit Company). D. Telleria to check with Mr. Rostami if all required inputs are available for implementation. Date also TBD.
4.4 Training on optimizing overall WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators
58 | 4.4.1 1 | Scientific Visit on safe WWER-1000 reactor and refuling process with focus on new techniques and materials, modern tools and advance method to strenghten the capability refuiling machine operators |  | 3NEX IAEA: K. Kang NPPD:Roshankar | 5 days | Russian (balakova) | SV | TBD | 3 NFs sent through official channel 23.11.2016. | H | 29.01.18: currently ongoing in Russia
59 | 4.4.1 2 | " |  | 3NEX | 5 days | Russian (balakova) | SV | TBD | " | H | 29.01.18: currently ongoing in Russia
60 | 4.4.1 3 | " |  | 3NEX | 5 days | Russian (balakova) | SV | TBD | " | H | 29.01.18: currently ongoing in Russia
4.3 Training on advance methods, new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs
61 | 4.3.1 | WS on outage optimization through advance methods,new techniques and materials,modern tools for maintenance and repair of WWER-1000 reactor refuling machine equipment and pipelines at NPPs |  | 1IAEA+3IEX IAEA: H. Varjonen NPPD:Roshankar | 4 days | Bushehr | WS | Q4/2017 22-25 October | Completed | H | NPPD will provide more information on area(s) by the end of May. (It is not possible to combine 4.1.1 and 4.3.1)
62 | - | WS on IGALL workshop on Structure system and component scoping and development of AMP's for BNPP, INRA and TAVANA in Q1 2018 |  | IAEA: NPPD:Deylami, Ghods | - | TBD | WS | Q1/2018 27-29 Jan | Completed | H | BNPP will inform IAEA if this workshop is needed by email before 30 June 2017
63 | - | WS on establishment of Corporate Emergency Control Centre of BNPP-1 in operating organization capability refueiling machine operators | IAEA: Elena Bulgova / NPPD: Ghods | - | - | - | WS | Q2/2019 14-18 May | - | - | 08.01.19: Ms Bulgova is looking for experts to implement during Q2/2019. CP request to move to Q3 2019 (Jul or Aug) but TO asks 4-8 May TO proposed IEXs (Mrs Mariana & Mr Bonov) accepted. 06.05.19: currently ongoing (04-08.05.19).
64 | - | Implementation of Design Bases Management for BNPP-1capability refuiling machine operators | IAEA: N. Kilic / NPPD: A. Rahnama | - | - | - | EM | Q2/2019 | - | - | 08.01.19: Mr. Kilic has been asked on 04.01.19 to proceed with the implementation as soon as possible. 14.01.19: proposed dates to IRAN are 6-8.7.19. Harri Varjonen is Deputy TO.ToR sent to IAEA. 06.05.19: Harri Varjonen is Deputy TO. Event has to be postponed (earliest Q4/2019), TO still looking for IEXs. TO is asked to come back to A. Rahnama by the end of June 2019.
65 | - | Organization of Training on Risk Spectrum Computer Code for LPSA | IAEA: T. Ulses / NPPD: Ghods | - | - | - | WS | Q2/2019 Q3/2019 | - | - | 08.01.19: Trainers still have to be found (P. Tarren). IAEA looking for potensial and experts. 08.01.19: Trainers still have to be found (P. Tarren). 06.05.19: EVT1807123. T. Ulses supporting this task (location in Russian NPP or Trieste run by IAEA staff) will come back to NPPD by the end of May 2019.
66 | - | EM on Review the progress of methods and Software for independent root-cause analyses of BNPP-1 (follow-up of a previous EM) |  | IAEA:T.Bilic Zatric NPPD: Ghods | - | Bushehr | EM | Q2/2019 7-11 May | Completed | - | 08.01.19: Mr. Zahradka is looking for experts to implement the mission.
67 | - | EM on Assessment of Risk Management Program for BNPP-1 operation | IAEA: A. Kawano / NPPD: K. Kehzri | - | - | - | EM | Q4/2019 | - | - | 08.01.19: To be started. ToR needs to be prepared by NPPD., 06.05.19: To be started. ToR still expected by the end of June 2019.
68 | Training | Advanced Training Support on ESTE SW | IAEA: Diego Telleria / NPPD: Rostami | - | TBD | Bushehr/Tehran | - | - | - | - | 06.05.19: Advanced Training (2 weeks) to be organized preferably in Iran (at NPPD request). Cost to be found in the procurement offer - Location in Iran could increase the costs.
69 | Procurement | Support on ESTE SW | IAEA: Diego Telleria | - | - | - | - | - | - | - | 06.05.19: Diego Telleria will send an email to Amir Rahnama on contractual details (next steps, support content…) incl. costs by the end of May 2019.
70 | - | Lesson learned and obtain experiences about implementing the management system including independent nuclear oversight function | IAEA: P. Tarren / NPPD: A. Rahnama | 4 NEX preferred |  | CEZ |  |  | Not Started (Planned) |  | 08.01.19: NPPD has been asked to provide Mr. Nayeri's availability in the next months to plan the SV. CEZ should be the host. 06.05.19: NF still pending for a 3 day SV in Nov 2019. TO will ask host if 4 NEXs can join.
| Further clarifications needed | [6 empty] | 20 active tasks
| Completed | [6 empty] | H= 18,M=9
Move to the next cycle