Engineering & technical support department

PROVISION

PROCEDURE OF DEVELOPMENT, AGREEMENT,

APPROVAL AND REGISTRATION OF TECHNICAL DECISIONS IN BNPP-1 OPERATION STAGE

90.BU.1 0.0.AB.PL.BNPP1151

1395

Revision 0

Review, coordination, distribution and approval sheet

|  | Full name | Position | Signature | Date |
| --- | --- | --- | --- | --- |
| Developed by | S. Rasti | Engineer of TD&PM |  |  |
| Checked up | M. Hojati | Manager of Technical Documents and Planning Management |  |  |
| Agreed with | E. Deilami | Deputy Chief Engineer for Technical & Engineering support |  |  |
| Agreed with | R. Banazadeh | Deputy Chief Engineer for Maintenance & Repairs |  |  |
| Agreed with | B. Farzi | Deputy Chief Engineer for Production |  |  |
| Agreed with | H. Abbaspour | Deputy Director for safety |  |  |
| Agreed with | K. Khezri | Manager of Management System & Inspection Management |  |  |
| Agreed with | S.A. Ambartsumian | Manager of the BNPP-1 Site JSC ASE Directorate |  |  |
| Agreed with | M.Shirazi | Plant Chief Engineer |  |  |
| Agreed with | H. Derakhshandeh | NPPD Co. deputy managing director for technical and engineering |  |  |
| Agreed with | K.Sepanloo | NNSD Director General |  |  |

Distribution:

| To be sent to | Number of copies | Notes |
| --- | --- | --- |
| Planning and technical documentation management | 2 | Original, Accounted copy, Soft copy |
| All structural units | 1 | Accounted copy |
| NPPD Co. | 1 | Accounted copy |
| NNSD | 1 | Accounted copy |
| DASE | 1 | Accounted copy |

Approved by

Managing Director

________________ H. Ghaffari

«____»  ____________ 1395

Contents

Terms and definitions	……………………………………………………………………………..4

Designations and abbreviations	…………………………………………………………………6

1	Introduction	…………………………………………………………………………..7

2	Purpose	………………………………………………………………………………7

3	Scope	…………………………………………………………………………………7

4	Responsibility	………………………………………………………………………..8

5	General	……………………………………………………………………………..10

6	Form, structure and contents of technical decisions	…………………………..12

7	Procedure of development of technical decision	……………………………….17

8	Agreement of technical decisions by NNSD……………………………………20

9	Procedure of realization, implementation and control of performance	……....22

10	Procedure of registration and archiving of technical decisions	……………….24

List of references

Appendix 1 Technical decision form formalized by BNPP Co. and IRI contracting organizations	……………………………………………………………………….26

Appendix 2 Sample of technical decision formalized by BNPP Co. and IRI contracting organizations	……………………………………………………………………….32

Appendix 3 Technical decision form formalized by organizations concerned	…………….35

Appendix 4 Sample of technical decision formalized by organizations concerned	………42

Appendix 5 Example of drawing up response to comments made by NNSD on technical decision…………………	………………………………………………………..…47

Appendix 6 Form of notification on implementation of technical decision	…………………48

Familiarization sheet	…………………………………………………………………………….49

Changes registration sheet	……………………………………………………………………..50

Change familiarization sheet	……………………………………………………………………51

Terms and definitions

|  | Components |  | Equipment, devices, pipelines, cables, construction components, etc., which ensure performance of established functions independently or as a part of a system |
| --- | --- | --- | --- |
|  | Contractor |  | JSC «Аtomstroyexport» |
|  | Copy |  | Documents formalized in a manner, which ensures their identity with the original and intended for direct use |
|  | Date of implementation of a document |  | Date when a document acquires legal power and its observance (application) becomes mandatory |
|  | Documentation |  | Written or visual information, which describes, determines, stipulates, informs or certifies types of works, requirements, techniques or results |
|  | Formalization of document |  | Putting down of all required elements and attributes set forth by the rules of documentation |
|  | License |  | A written permit of INRA issued to the Applicant (NPPD Co.) and granting the rights to perform activities related to Construction, Commissioning, Operation and Decommissioning of BNPP-1 |
|  | NNSD Consultant |  | Independent technical support organization, which may be engaged, on the contractual basis, by INRA/NNSD for analysis, review and assessment of safety issues in technical decisions related to operation of BNPP-1 |
| NNSD Representative Office at BNPP-1 Site |  | A structural subdivision of INRA/NNSD, which supervises BNPP-1 |  |
|  | Permit |  | A document issued by INRA/NNSD and certifying the right of NPPD Co. to perform works, which can affect safety, in the framework of the relative License |
|  | Principal |  | Nuclear Power Production and Development Company of Iran (NPPD Co.) within AEOI is an Operating Organization, which is entirely responsible for the safety of BNPP-1 |
|  | Safety systems (components) |  | Systems and components intended for implementation of safety functions |
|  | System |  | Set of components intended for implementation of specific functions |
|  | Systems (components) important for safety |  | Safety systems (components), as well as systems (components) of normal operation failures of which disturb normal NPP operation or prevent elimination of deviations from normal operating conditions and can lead to design basis or beyond design accident |
|  | Systems (components) of normal operation |  | Systems (components) intended for normal operation |
|  | Technical decision |  | Organizational-management document which establishes general technical requirements and sequence of works on resolution of the revealed problem of operation. Technical decision, if necessary, is the basis for performance of works on introduction of changes into design, engineering, process and operating documentation. |
|  | Warranty |  | Commitment of the Contractor to ensure that all its Supplies and Services comply with the Contract and have no defects, malfunctions and imperfections |

Designations and abbreviations

| AEOI | Atomic Energy Organization of Iran |
| --- | --- |
| BDBACM | Beyond design basis accident control manual |
| BNPP Co. | Bushehr Nuclear Power Plant Company - the organization directly operating Bushehr NPP-1 |
| DCETE | BNPP Co. Deputy Chief Engineer for Technical & Engineering- engineering support department manager |
| DCEP | BNPP Co. Deputy Chief Engineer for Production |
| DCEMR | BNPP Co. Deputy Chief Engineer for Maintenance & Repairs |
| EMI | Emergency mitigation instruction |
| FSAR | Final safety analysis report |
| INRA | Iran Nuclear Regulatory Authority within AEOI |
| IRI | Islamic Republic of Iran |
| LC | License conditions |
| LPD | BNPP Co. Labor Protection Department |
| ML | BNPP Co. Metal Laboratory |
| MS | BNPP Co. Metrological Service |
| MSD | BNPP Co. Manager of Safety Division |
| M&SSD | Management and supervision system department |
| NNSD | National Nuclear Safety Department within INRA |
| NP | Nuclear Plant |
| NPP | Nuclear Power Plant |
| NPPD Co. | Nuclear Power Production and Development Company of Iran |
| NSD | BNPP Co. Nuclear Safety Department |
| PPM | Planned preventive maintenance |
| PP&I | Process protections and interlocks |
| PTCC | Personnel training and control center |
| RF | Russian Federation |
| RP | Reactor plant |
| RSD | BNPP Co. Radiation Safety Department |
| TD&PM | Technical documents and planning management |
| TSSO | Technical specification of safe operation |

- Introduction

  - This Provision has been developed with due account of the requirements of document INRA-NS-RG-051-10/01-0-Dec.2016 “Regulatory Guide for INRA/NNSD Agreement of Operating Organization Decisions Important to Nuclear and Radiation Safety”, Rev. 0, and Validity Conditions of BNPP-1 Operation License No. NNSD-BNPP-3-OPL dated April 20, 2016.

  - This Provision has been developed to cancel the provision “Order of development, agreement, approval and registration of technical decisions" 90.BU.1 0.00.AB.RL.ATEX1151, revision 0.

  - This Provision shall be subject to revision every 5 years.

- Purpose

- This Provision shall govern the procedure of development, formalization, registration, accounting and implementation of technical decisions for Unit 1 of Bushehr NPP.

- Scope

  - The requirements hereof shall apply to all BNPP Co. subdivisions, as well as RF and IRI organizations and specify responsibilities of managers of BNPP Co. subdivisions and RF and IRI organizations when making technical decisions.

  - The requirements of this Provision shall cover the technical decisions for BNPP-1 made in its operation stage.

- Responsibility

  - BNPP Co. subdivision manager (manager of RF, IRI organization), who prepared a technical decision, shall be responsible for correctness of description of the revealed problem and ways of its solution, completeness and correctness of drawing up of the technical decision, sufficiency of attached materials.

  - BNPP Co. officials, as well as representatives of RF and IRI organizations who review technical decisions, within their functional obligations bear responsibility for the following:

- necessity, appropriateness and validity term of a technical decision;

- possibility of implementation of a technical decision with due consideration of rules and regulations effective at BNPP;

- observance of deadlines for works specified in a technical decision;

- compliance of performed works with the content of a technical decision, completeness and correctness of implementation of a technical decision;

- timely review (consideration) and signing of a technical decision;

- Refusal of signing of a technical decision without issue of well-reasoned comments.

  - Manager of the subdivision, developer of a technical decision (owner of equipment), and as a person responsible for adoption and implementation of the technical decision in general shall bear responsibility for:

- making of the decision about development of the technical decision;

- appointment and qualification of the person responsible for development of the technical decision;

- completeness and correctness of the use of rules and regulations effective at BNPP when developing a technical decision;

- sufficiency of taken organizational and technical measures aimed at observance of the procedure of consideration and acceptance of technical decision for modification of design, engineering, process and operational documentation affecting assurance of nuclear and radiation safety;

- organization of verification of developed technical decision;

- review and approval of technical decision with BNPP Co., and its review and signing with outside RF and IRI organizations;

- control over performance of works under technical decision, adoption and implementation of technical decision;

- timely filling-in and correctness of drawing-up of notification about the technical decision implementation, delivery of filled-in notification to TD&PM for storage;

  - The developer of a technical decision shall be responsible for:

- familiarization with all required materials for development of technical decision;

- development of technical decision before established deadline;

- compliance of drawing-up of technical decision with the requirements hereof, completeness of description and technical correctness of the text, compliance of the content with the requirements of regulatory documents;

- consistency of the technical decision with the design and previously adopted decisions;

- completeness and correctness of determination of agreeing officials;

- Collection of required signatures and elimination of comments.

  - BNPP Co. officials who are responsible for technical decisions review bear responsibility for verification of technical decision within the framework of their functional obligations in accordance with section 7.8.

  - TD&PM Manager shall bear responsibility for:

- verification of technical decision for compliance with the requirements hereof in part of its formalization;

- submitting of technical decision to RF and IRI organizations for review and signing;

- registration of approved technical decision, distribution of registered copies among organizations concerned and storage of control copies;

- Registration and storage of notification about implementation of a technical decision.

- General

  - Below are reasons for making technical decisions:

- results of analysis of deviations from the requirements of rules and regulations applied to the use of nuclear energy effective at BNPP-1;

- programs of improvement of safety and efficiency;

- results of analysis and assessments of safety;

- experience of operation of systems, equipment, buildings and structures;

- necessity of elimination of defects;

- necessity of replacement of materials (equipment);

- necessity of improvement of reliability of operation of equipment, reparability, efficiency of utilization of resources and areas;

- technical suggestions of organizations – developers of design of NP and RP;

- instructions of supervisory authorities;

- Analysis of malfunctions in operation of NP.

  - Technical decisions shall be drawn up for:

- deviations from requirements of norms and regulations in the area of nuclear power use effective at BNPP-1 at operation of equipment, pipelines, buildings and facilities, referred to 1,2,3 safety classes under NP-001-97 (PNAE G-01-011-97);

- changes of designs of systems and equipment, buildings and facilities of NPP referred to 1,2,3 safety classes under NP-001-97 (PNAE G-01-011-97);

- changes in limits and conditions of safe operation, established in the design of reactor plant and Technical specification of safe operation of the power unit;

- changes of limiting parameters of operation of equipment, pipelines referred to groups “A”, “B”  and “C” under PNAE G-7-008-89;

- modernization of systems referred to safety classes 1, 2, 3 under NP-001-97 (PNAE G-01-011-97), which require correction of report on assessment of safety, technical specification of safe operation of the Unit;

- modernization of equipment under programs of international cooperation;

- changes of algorithms and set-points of protections and interlocks;

- dismantling and taking equipment out of operation;

- Replacement of process equipment for a similar one.

  - In case the implementation of the technical decision provides for changing of system and equipment operation modes, changing of algorithms, protection and interlock system set points, then developer of the technical decision shall specify PTCC in the technical decision distribution list.

  - Copies of all technical decisions for changing of operational modes of systems and equipment, changing of algorithms and set-points of protections and interlocks shall be sent to PTCC for information and use.

  - Technical decision is an organizational and administrative document, which specifies a solution of the revealed problem in operation, repair, design, manufacturing, the procedure of its implementation and deadlines. If necessary, it can serve as an initial document for development of technical requirements to a new equipment and/or technical assignment for modification of design and engineering documentation of systems, equipment, buildings and structures.

  - When implementation of a technical decision does not require development of technical requirements and design and engineering documentation, technical decision shall be a basis for performance of works, and organizational issues can be included into it.

  - Technical decision shall serve as a ground for drawing-up of a notification of modification of operational documentation (after its implementation).

  - An approved technical decision can be cancelled only by the person, who approved it.

  - Modification of an approved technical decision is not allowed.

  - When it is necessary to modify a technical decision, extend its validity, or cancel it, a new technical decision shall be drawn up, which shall give instructions on the measures applied to the previously issued technical decision. At that new technical decision shall be approved by the same authority.

- Form, structure and contents of technical decisions

  - A technical decision shall include the following mandatory structural elements and details:

- detail – BNPP logo;

- detail – approval box;

- detail – designation of document type;

- detail – designation of technical decision;

- detail – designation of document code;

- section – information on the object of technical decision;

- section – substantiations;

- section – decisions;

- section – correction of documentation;

- section – appendix (if any);

- element – period of validity;

- element – person responsible for implementation;

- element – distribution list;

- element – note on implementation of the technical decision;

- detail – developer’s box;

- detail – agreement box;

- footer.

  - Technical decision developed by BNPP Co. subdivision or IRI third-party organization shall be formalized in two languages, in Farsi and Russian.

  - Technical decision developed by RF third-party organization shall be formalized in two languages, in Russian and English.

  - Forms and samples of technical decisions are given in Appendices 1, 2, 3, 4:

- form and sample of technical decision, which is formalized in BNPP or by a third-party IRI organization, are given in Appendices 1,2;

- form and sample of technical decision, which is formalized by RF organization, are given in Appendices 3,4;

  - Requirements to formatting the textual part of a technical decision are given in Appendices 1, 3 (forms of technical decisions).

  - Latin or Russian letters (digits) in the text of technical decision, which is drawn up in Farsi, shall be typed in Arial font, size 12.

  - Company name. BNPP Co. logo is used.

  - Designation of document type.

6.8.1	A code of technical decision shall be assigned by the developer as per the requirements of Appendix 3N of the Contract.

6.8.2	Registration number of technical decision shall be assigned by TD&PM. Code and registration number of technical decision shall be typed at preparation of technical decision.

  - Detail «DESIGNATION» shall contain brief information about the contents of a technical decision and shall begin with the preposition «On». For example - «On introduction of...», «On conditions of...», «On modification of...» etc. Designation shall contain standard terms and definitions of engineering processes.

  - Information on the object of technical decision

- In the “OBJECT” line the following is specified - name of the object, building, facility where technical decision is implemented. For example – Power Unit No.1, Building 1ZF.

- In the line “STRUCTURAL COMPONENT” the following is specified - full name and designation of the system and component, number of design drawing, passport, etc.

- With accounting of equipment planned to be involved in works:

- in the line classification of equipment – safety class in accordance with OPB-88/97 is indicated;

- in the line equipment group - group in accordance with PNAE G-7-008-89 is indicated;

- In the line seismic stability category - category in accordance with PNAE G-5-006-87 is indicated.

- In the line «TYPE OF WORK» works to be performed are specified - installation, demounting, repair and maintenance, change of types and scope of technical examination of equipment and pipelines, operation of reactor core, follow-up of operation, implementation of new equipment, modernization, new construction, economic needs, etc.

  - Section «SUBSTANTIATION».

6.11.1 General requirements. The section «SUBSTANTIATION» shall specify:

- The first paragraph specifies the nature of deviation from regulatory documents or other documentation: specific items of regulatory documents or other documentation used as the basis for the decision shall be specified.

- Reason of modifications and brief substantiation of necessity of works for introduction of modifications to arrangement of systems and equipment;

- List of measures and documentation, which justify the necessity of works under the technical decision (design or engineering documentation, reports, estimations, programs, instructions, conclusions of inspection, results of examinations etc.).

- Estimation of effect of proposed measures on safety.

- Impact of proposed measures on safety is assessed. If required, safety analysis is attached to technical decision. If there is no need in safety analysis, it shall be indicated – «Safety analysis is not required».

- Such information must be indicated – «activities related to this technical decision are nuclear hazardous activities» or «activities related to this technical decision are not nuclear hazardous activities».

6.11.1.6а. to be indicated – «complies with requirements of document 49.BU.1 0.0.OO.FSAR.RDR001 or «does not comply with requirements of document 49.BU.1 0.0.OO.FSAR.RDR001. In case of incompliance with the requirements – the cause of non-compliance is indicated in the evaluation of effect on safety, and actions to be taken in order to eliminate the cause of incompliance are indicated in the activities.

- Such information must be indicated – «modifications to LC are required» or «modifications to LC are not required».

6.11.2 If a technical decision causes modifications in design, process, engineering and operational documentation, which require correction of LC, the following information must be provided, additionally to the requirements of i. 6.11.1:

- in i. 6.11.1.7 – list of safety justification documents (FSAR, TSSO, EMI, BDBACM), which shall be modified;

- in section «UPDATING OF DOCUMENTS» - deadlines and persons responsible for development of modifications in safety justification documents (FSAR, TSSO, EMI, BDBACM);

- In section «UPDATING OF DOCUMENTS» - deadlines and persons responsible for development of the set of modification related documents, LC included, which is sent to INRA/NNSD for review. Requirements to this set of documentation are reflected in i. 5.5 Doc. INRA-NS-PR-051-10/01-0-Jun.2011.

6.11.3 Technical decisions on deviations from the requirements of regulatory documentation shall require obligatory justification of safety. Justification of safety shall be developed or agreed upon with a specialized or design (engineering) organization and shall contain an analysis of effect on safety of deviations from the requirements of regulatory documentation, and (if necessary) a list of compensatory measures, which ensure design or reached condition of safety.

    - Analysis of effect on safety shall at least include the following:

- essence of the modification;

- Results of own analysis of modifications (it shall indicate that the suggested technical decision will cause no deterioration of nuclear and radiation safety).

  - The section «DECISIONS» shall specify:

    - Organizational and technical measures required for adoption and implementation of the technical decision. The measures shall indicate:

- responsible subdivision (organization) – executor of works for each measure;

- Deadlines of each measure.

    - Approximate composition of measures shall contain:

- list of documentation subject to development and/or correction;

- formalization of contract for development of design estimates and engineering documentation (if necessary);

- preparation of technical assignment for development of documentation, if it is supposed to be developed by a design (engineering) organization;

- ordering and completion of equipment and materials required for performance of works;

- development of process, work production plan;

- performance of civil and erection works;

- performance of pre-operational tests;

- Requirements to quality assurance.

  - The section «CORRECTION OF DOCUMENTATION» shall indicate:

- Documentation, deviation with which is supposed to occur, and which is supposed to be modified:

- License conditions, design, and engineering documentation;

- Production and technical (specifications, instructions, charts, programs);

- As-built and working documentation.

- subdivision, deadline and employee, responsible for correction and modification (amendment) of documentation;

- If no correction and modification (amendment) of documentation is required, «Correction of documentation is not required» shall be indicated.

  - The section «APPENDIX» contains documents, which are referred to in the text of the technical decision. The list of documents to be included in the Appendix is specified by the developer of the technical decision.

Documents attached to a technical decision as appendices are an integral part of that technical decision.

  - The line «Period of validity» shall specify duration of the technical decision:

- Limited in time. For example – during PPM, during tests;

- over all the time of operation;

- Until fulfillment of certain conditions.

  - The line «Person responsible for implementation» shall specify the subdivision, position, full name and telephone number of the person, who is responsible for adoption and implementation of the technical decision.

  - The line «Distribution list» shall indicate BNPP Co. subdivisions and organizations, which participated in review and signing of the technical decision, and to whom the approved technical decision shall be sent to. Distribution list shall be determined by the developer of the technical decision.

  - The line «Note on implementation» shall indicate: «Implemented. Notification No.______ of ________». TD&PM engineer makes a record in the line of technical decision based on notification received from the subdivision.

  - The boxes of approval and agreement shall contain:

- words «APPROVED BY» and «AGREED WITH» respectively;

- Position of the person, who agrees upon the document, his signature, expansion of the signature and the date of signing.

  - Developer’s box shall contain:

- words «DEVELOPED BY»;

- Position of the manager of the BNPP Co. subdivision or subdivision of outside organization, which developed the technical decision, his signature, expansion of the signature and the date of signing.

  - Developer’s box shall be located right after the text of the technical decision.

  - The box of approval shall be the first on the first sheet, right above the text of technical decision.

  - Under approval box  the signatures of managers (representatives) of organizations who are not present at the BNPP-1 site are arranged in the following sequence:

- NNSD Director General/representative (Tehran);

- Technical Director of FSUE VO «Safety» /representative (Moscow).

- NPPD Co. representative (NPPD Co. deputy managing director for technical and engineering);

- JSC ASE representative (Moscow).

- Manager/representative of RF Design organization;

Agreement boxes for NNSD Representative Office at Bushehr NPP-1 Site are arranged under the approval box.

  - Under Developer’s box the following signatures of managers (representatives) of organizations who are present at the BNPP-1 site are arranged in the following sequence:

- Head of NNSD Representative Office at Bushehr NPP Site;

- Head of the organization-developer of technical decision;

- BNPP Co. officials responsible for specific areas of activities;

- Representative of Designer at BNPP-1 site;

- Representative of Manufacturer at BNPP-1 site;

- Representative of organization performing pre-operational tests at BNPP-1 site;

- Manager of JSC ASE Directorate at the BNPP-1 Site.

- OCE Manager (Consultant).

  - The box of agreement may contain a reference to the document, which demonstrates the agreement of the organization with the contents of the technical decision. In this case, at the official’s signature place there shall be a reference to the number and the date of the facsimile message. In this case a copy of the document shall be attached to that technical decision.

  - Each attachment (the first sheet of the attached document) shall have the following inscription in the upper top corner:

«Appendix No.___ to technical decision No. ___».

  - Each sheet of a technical decision, including appendices, shall have a footer indicating:

- technical decision immediate developer’s last name and initials;

- immediate developer’s signature;

- name of BNPP Co. subdivision (third party);

- developer’s telephone number;

- code and registration number of the technical decision;

- number of sheet of the technical decision, including appendices;

- Total number of sheets in the technical decision, including appendices.

Appendices to a technical decision may have no footers.

  - Statement of the contents of a technical decision shall be brief, clear, excluding any possibility of ambiguous interpretation.

  - All works provided for implementation shall be stated in an interconnected way and in chronological order. Labeling of systems and equipment, terminology and definitions shall be unified and shall comply with design, engineering and operational documentation.

  - The text of a technical decision shall be drawn-up in compliance with the existing requirements to formalization of the text part of documents in BNPP Co.

- Procedure of development of technical decision

  - Development of a technical decision shall include:

- development of draft technical decision;

- agreement of the technical decision with BNPP Co. subdivisions;

- agreement of the technical decision with IRI and RF organizations;

- approval of the technical decision by BNPP Co. Chief Engineer;

- agreement of the technical decision with NPPD Co.;

- agreement of the technical decision with NNSD;

- Registration, implementation.

  - The list of works, which require drawing-up of technical decisions, is indicated in item 5.2 hereof.

  - A developer of a technical decision, as a rule, shall be the subdivision, owner of equipment, or the subdivision responsible for the field of activity referred to the technical decision. A developer of a technical decision can be any other BNPP Co. subdivision at discretion of BNPP Co. Chief Engineer.

  - Development of a technical decision may be commissioned to a third party under a contract. However, control over preparation of the technical decision shall be charged to the subdivision-owner of the equipment.

  - If it is necessary to make modifications to composition of systems, equipment, buildings and structures, being in the area of responsibility of another BNPP Co. subdivision, that modification shall be formulated in the technical decision by the subdivision, which owns the facility being modified. However, the technical decision shall be reviewed and signed by the subdivisions, which are obliged to perform measures under the technical decision being adopted.

  - This is the duty of the developer of the technical decision to select the organizations that are authorized to review and sign technical decisions in accordance with the requirements of procedure hereof.

  - Review and signing of technical decision with the third party.

    - Developers of NP and/or RP design in compliance with the area of designing of components.

    - Engineering (design) organization and/or manufacturer of equipment and pipelines.

    - If necessary, representatives of design and engineering organizations at the site of BNPP-1, which perform field supervision of BNPP-1 according to their field of activity, manufacturers of equipment.

    - Subcontracting organizations at the site of BNPP-1, which take part in implementation of the technical decision.

  - Review and signing of a technical decision in BNPP Co.

    - A technical decision shall be reviewed and signed by:

- Deputy Chief Engineer as per subordination;

- Deputy Chief Engineer as per ownership of equipment;

- TD&PM Manager;

- Manager of the subdivision – executor of works under that technical decision;

- Manager of the subdivision – owner of the equipment, building, structure, room, where the technical decision will be implemented;

- The developer of the technical decision.

    - MSD shall review and sign technical decisions:

- if they are subject to agreement by NNSD

- if modifications in LC (when a correction of FSAR, EMI, BDBACM is required) and in TSSO, RPOM are necessary;

- if these technical decisions are related to performance of potentially radiation-hazardous works, modification of radiation monitoring systems, and changing of radiation situation in rooms being attended;

- If these technical decisions are related to performance of nuclear-hazardous activities or can affect nuclear and radiation safety.

    - DCEP shall review and sign technical decisions related to:

- modification of working modes of equipment and process systems;

- operational limits and conditions of operation of equipment and process systems;

- Amendments in operational documentation.

    - CPE shall review and sign technical decisions requiring introduction of changes in TSSO when changing PP&I algorithms or set points.

    - DCEMR shall review and sign technical decisions related to corrective repair and preventive maintenance of equipment.

    - DCETE shall review and sign technical decisions related to:

- modification of working modes of equipment and process systems;

- operational limits and conditions of operation of equipment and process systems;

- amendments in operational documentation;

- reliability of equipment;

- new technologies and engineering;

- Testing (trials) of equipment.

    - M&SSD Manager shall review and sign technical decisions:

- technical decisions that are subject to agreement by NNSD;

- due to a necessity to change LC (when a correction of FSAR, EMI, BDBACM is required);

- on modification of types and scopes of technical examination of equipment and pipelines;

- aimed at modification of engineering structures and facilities;

- related to increased fire hazard or modification of systems of fire alarm or fire-fighting systems, and aimed at enhancement of fire-prevention equipment;

- Aimed at enhancement of fire-prevention condition of equipment.

    - LPD Manager shall review and sign technical decisions:

- implementation of which is related to exposure of employees to hazardous and harmful industrial factors in case of a change in conditions of operation and maintenance of equipment;

- On organization of new jobs in case of a change in engineering design of a building or a structure.

    - RSD Manager shall review and sign technical decisions:

- implementation of which is related to performance of potentially radiation-hazardous works;

- modification of radiation monitoring systems;

- Changing of radiation situation in rooms being attended.

    - NSD Manager shall review and sign technical decisions related to performance of nuclear-hazardous works or with affecting assurance of nuclear and radiation safety.

    - Manager of subdivision- equipment owner shall review and sign technical decisions related to changes of PP&I algorithms or setpoints on the equipment that is assigned to this subdivision.

    - MS Manager shall review and sign technical decisions, if they are related to amendments in engineering and process documentation, which changes metrological characteristics, in case of transferring of measurement instrumentation to indicators.

    - ML Manager shall review and sign technical decisions on repair of equipment related to metal examination.

    - TD&PM Manager shall review and sign all technical decisions for compliance and correction of format in compliance herewith.

  - Technical decision shall be first reviewed and signed by BNPP Co. subdivisions and management, then with IRI and/or RF organizations at the site of BNPP-1, and with IRI (Tehran) and/or RF(Moscow) organizations, and finally with BNPP Co. Chief Engineer.

  - NPPD Co. deputy managing director for technical and engineering support shall sign technical decisions on behalf of NPPD Co.. Implementation of these technical decisions is only allowed after their signing in NPPD Co. and NNSD.

  - In case of comments in the stages of review of a technical decision, it shall be returned for improvement with indication of the reasons of refusal. After elimination of comments corrected technical decisions shall undergo repeated procedure of review and signing.

  - The developer of a technical decision shall ensure review of the technical decision by BNPP Co. subdivisions, IRI and/or RF organizations, and approval of the technical decision by BNPP Co. Chief Engineer.

  - If a technical decision has been developed by a third party, the manager of the subdivision, owner of the equipment, shall review and sign the technical decision and control all the stages of its review and approval.

  - TD&PM:

- Shall submit the technical decision to IRI contracting organizations.

- Shall organize elimination of comments of the above-mentioned organizations by BNPP Co. subdivisions.

  - Agreement of a technical decision by NNSD (Tehran) shall be organized by NPPD Co..

  - Technical decision is formalized in one copy, bilingual – Farsi/Russian or English/Russian, depending on organization-developer of the technical decision.

8	Agreements of technical decisions by NNSD

  - The below technical decisions are subject to review and agreement upon at the level of NNSD:

- technical decisions on deviations from the requirements of the regulatory documents related to safety systems (components) and systems (components) important to safety (NNSD Tehran);

- technical decisions on deviations from the requirements of the design, engineering, process and operation documentation related to safety systems (components) and systems (components) important to safety of safety class 1 (NNSD Tehran);

- Technical decisions on deviations from the requirements of the design, construction design, process and operation documentation related to safety systems (components) and systems (components) important to safety of safety classes 2 and 3 (NNSD Bushehr).

    - Technical decisions submitted to NNSD (Tehran) or NNSD Representative Office at BNPP-1 site for agreement shall have been previously signed by all authorities including NPPD Co., and approved by BNPP Co. Chief Engineer.

  - Technical decisions subject to review and agreement at the level of NNSD (Tehran):

    - NNSD (Tehran) reviews a technical decision with supporting documents received from NPPD Co. NNSD (Tehran) can request for the additional materials related to the technical decision under consideration from NPPD Co., as well as give the task to NNSD Representative Office at BNPP-1 Site to make these or those statements related to the technical decisions under consideration to be clearer.

    - Based on the results of review of the technical decision, NNSD (Tehran) either agrees or rejects it, and returns it to NPPD Co. along with the results of review.

    - Technical decisions rejected by NNSD (Tehran) are returned to NPPD Co. for modification with indication of the reasons of rejection. After rectification of the comments, the updated technical decisions undergo the recurrent procedure of review at NNSD (Tehran).

    - For recurrent (after the comments rectification) submission of the technical decision to NNSD (Tehran), the response to rectification of NNSD comments is attached to the technical decision. Sample of response format is given in Appendix 5.

  - Technical decision submitted to the NNSD Representative Office at BNPP-1 Site for agreement shall be signed by all subdivisions and organizations concerned and approved by the Chief Engineer of BNPP Co.

  - Technical decisions related to operation or repair of equipment:

    - Technical decision with supporting documents shall be sent by BNPP Co. to NNSD Representative Office at BNPP-1 Site;

    - NNSD Representative Office at BNPP-1 Site reviews the technical decision submitted by BNPP Co. NNSD Representative Office at BNPP-1 Site can request for the additional materials related to the technical decision under consideration from BNPP Co.

    - If necessary, NNSD Representative Office at BNPP-1 Site may involve NNSD Consultant for the expert review of the documents justifying the effect of the technical decision on Bushehr NPP-1 safety.

    - Based on the results of the technical decision review, NNSD Representative Office at BNPP-1 Site either agrees or rejects it, and returns it to BNPP Co. along with the review results.

    - If the technical decision needs to be agreed upon with NNSD (Tehran), NNSD Representative Office at BNPP-1 Site informs BNPP Co. thereof, see item 8.2.

- Procedure of realization, implementation and control of performance

  - Technical decision shall be implemented and accomplished after its approval and agreement by all organizations specified in the technical decision.

  - Technical decision shall be deemed implemented from the date of performance of all stages and works provided for therein.

  - Organizations specified in the approved technical decision shall ensure introduction of relevant changes in documentation (if necessary) or shall develop new documentation (if necessary).

  - The requirements to documents on changing of design, engineering, process, operational documentation affecting assurance of nuclear of radiation protection of BNPP-1 and procedure of review and decision-making in NNSD for those changes is specified in sections 5, 6 Doc. INRA-NS-PR-051-10/01-0-Jun.2011 and in sections 3, 4 Doc. INRA-NS-PR-051-15/01-0-May 2012.

  - The person responsible for realization and implementation of a technical decision shall be the manager of the subdivision, owner of the equipment, which the technical decision relates to.

  - Routine inspection of performance of technical decisions in subdivisions, referred to in the technical decision, shall be performed by the manager of the subdivision, the developer of the technical decision.

  - Performance of measures under technical decisions shall be included to monthly schedules of BNPP Co. subdivisions in compliance with the deadlines specified in the technical decision.

  - The results of performance of measures under technical decisions shall be included to monthly reports of works performed by BNPP Co. subdivisions or BNPP Co. subdivision not later than on the 5-th day of every month shall submit the information sheet on performance of measures related to technical decisions to TD&PM.

  - Regular control of performance of implementation of technical decisions shall be carried out by TD&PM by verification of deadlines of measures under technical decisions in reports of BNPP Co. subdivisions (in the information sheets of subdivisions) and deadlines indicated in measures related to technical decisions. TD&PM shall prepare an information sheet about the progress of development and implementation of technical decisions for BNPP Co. management every month before the 10th day.

  - The manager of the subdivision, owner of equipment, building, structure, room, which were modified, shall:

- timely organize modification of operational (manuals, drawings), process, design, repair documentation;

- inform operational personnel about all modifications of equipment and systems against signatures with relevant records in the log of instructions before commencement of operating switchovers on those systems and equipment (before confirmation of preparedness of modernized equipment and pipelines to tests or operation);

- Perform works under technical decision and put systems and equipment into operation only after introduction of modifications and additions to all sets (copies) of documentation.

  - Holding of unscheduled briefings and, if necessary, testing of personnel’s knowledge, personnel’s training and emergency drills shall be completed before the deadline of putting equipment in operation after modernization, reconstruction.

  - Notification on implementation of a technical decision shall be drawn up by the developing subdivision within two weeks after performance of all measures under the technical decision, registered in the subdivision and sent to TD&PM.

  - Note on implementation of a technical decision shall be put to the archival copy of a technical decision by an employee of the TD&PM archive.

  - The form of notification about implementation of a technical decision is specified in Appendix 5.

  - Information about the implemented technical decisions shall be distributed among the organizations concerned.

- Procedure of registration and archiving of technical decisions

  - The original of an approved and agreed technical decision shall be sent by developing subdivision to TD&PM for registration, putting into production and distribution.

  - TD&PM shall register a technical decision in the database of TD&PM archive documentation with assigning of an inventory number to it. On BNPP Co. Chief Engineer's approving signature there shall be a stamp “FOR PRODUCTION, BNPP Co. Chief Engineer, date”. On the originals of technical decisions there shall be the stamp «Controlled copy No.__» of established form, on all copies of technical decisions – stamp «Copy No.__».

  - TD&PM shall perform distribution of accounted copies of a technical decision in compliance with the distribution list of the technical decision.

  - It is compulsory that the implemented technical decisions are distributed to:

- NPPD Co. – all technical decisions;

- The Contractor (JSC ASE) – The Contractor (JSC ASE) – technical decisions that were agreed upon with JSC ASE.

- NNSD Representative Office at BNPP-1 site – technical decisions that were agreed upon with NNSD.

  - The date of implementation of a technical decision shall be the date of the issue to production specified on the relevant stamp.

  - The original of the technical decision shall be stored in TD&PM archive.

  - Technical decisions, which are not registered in the technical archive of TD&PM, shall be deemed invalid.

  - Notification of implementation and the technical decision shall be stored in the technical archive of TD&PM during the whole period of BNPP-1 operation.

List of references

- General rules of assurance of operation of operation of nuclear power stations, OPE AS. RD EO 0348–02.

- General provisions of preparation, consideration and adoption of decisions on modifications of design, engineering, process and operational documentation affecting assurance of nuclear and radiation safety. RD-03-19-94.

- INRA-NS-PR-051-10/01-0-Jun.2011 “Procedure for INRA/NNSD Approval of Operating Organization Decisions Important to BNPP-1 Nuclear and Radiation Safety”, Rev. 0.

- Validity Conditions of BNPP-1 Commissioning License No. NNSD-BNPP-2-CML dated October 23, 2010.

- General provisions of assurance of safety of nuclear power plants. OPB 88/97. (PNAE G-01-011-97).

- Regulations on designing of anti-seismic nuclear power plants. PNAE G-5-006-87.

- Rules of arrangement and safe operation of equipment and pipelines of nuclear power plants. PNAE G-7-008-89.

- Procedure of development and implementation of production and technical documents, 90.BU.1 0.0.QA.RPC.ATEX0204.

- Document No. 5 to Appendix 3N to the Contract, «Instruction on identification of technical documentation», 99.BU.1 0.0.QA.WI.ASE001.

- QAP (OP) «Description of quality assurance programme», 90.BU10.0.QA.QAPOP.BNPP001.

- QAP (OP) «Documents and QA records control», 90.BU1 0.0.QA.QAPOP.BNPP004.

- Accounting and storage of technical and contract documentation, 90.BU.1 0.0.QA.RPC.ATEX0132.

- Letter from NPPD Co. № 4900-936136 of 1393.06.03.

Appendix 1

Technical decision form formalized by BNPP Co. and IRI contracting organizations requiring NNSD (Bushehr) agreement

در همه متن-خطوط جدول پنهان، فاصله قبل و بعد0PT، فونت مورد استفاده براي لاتين Arial وبراي فارسي nazanin، فاصله مينيمم.

По всему тексту – скрытая таблица, интервал перед и после 0 пт,шрифт Arial, интервал межстр. минимум

пробел 12

فاصله 12

| تصويب اندازه 14 ضخيم | نام و نام‌خانوادگي اندازه 14 معمولي | سرمهندس نيروگاه اتمي بوشهر اندازه 14 معمولي | _________ امضاء подпись | _________ تاريخ дата |
| --- | --- | --- | --- | --- |
| УТВЕРЖДАЮ размер 10, прописные, начертание полужир, | Ф.И.О размер 10, начертание обычное | Главный инженер BNPP Co. размер 10, начертание обычное |  |  |
| موافقت | نام و نام‌خانوادگي | ‌دفتر‌نمايندگی ‌ايمنی هسته اي ‌در ‌نيروگاه ‌اتمی‌ بوشهر | _________ امضاء подпись | _________ تاريخ дата |
| СОГЛАСОВАНО | Ф.И.О. | Руководитель Представительства NNSD на площадке АЭС «Бушер-1» |  |  |
| تاييد | نام و نام‌خانوادگي | معاون فني و مهندسي شركت توليد و توسعه | _________ امضاء подпись | _________ تاريخ дата |
| СОГЛАСОВАНО | Ф.И.О. | Зам. директора NPPD Co. по инженерно-технической поддержки |  |  |
| تاييد | نام و نام‌خانوادگي | نماينده شركت JSC ASE | _________ امضاء подпись | _________ تاريخ дата |
| СОГЛАСОВАНО | Ф.И.О. | Представитель АО АСЭ |  |  |
| تاييد | نام و نام‌خانوادگي | نماينده شركت طراح | _________ امضاء подпись | _________ تاريخ дата |
| СОГЛАСОВАНО | Ф.И.О. | Руководитель/представитель проектной организации РФ |  |  |

пробел 12

فاصله 12

Appendix 1 continued

تصميم فنی شماره كد تصميم فني خطوط جدول مشخص باشد، سايه گذاری ملايم ، اندازه 14 ضخيم

ТЕХНИЧЕСКОЕ РЕШЕНИЕ код видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужир

عنوان: متن عنوان 14 ضخيم- متن عنوان 14 معمولي

НАЗВАНИЕ: текст названия НАЗВАНИЕ - размер 10, прописные, начертание полужир. Текст названия - размер 10, начертание обычное

пробел 12

فاصله 12

محل: متن محل 14 ضخيم – متن 14 معمولي

ОБЪЕКТ: текст ОБЪЕКТ - размер 10, прописные, начертание полужир. Текст объекта - размер 10, начертание обычное

المان ساختاري: متن

КОНСТРУКТИВНЫЙ ЭЛЕМЕНТ: текст

كلاس ايمني: متن

КЛАСС БЕЗОПАСНОСТИ: текст

گروه تجهيزات: متن

ГРУППА ОБОРУДОВАНИЯ: текст

طبقه بندي بر اساس شدت زلزله: متن

КАТЕГОРИЯ СЕЙСМОСТОЙКОСТИ: текст

نوع كار: متن

ВИД РАБОТЫ: текст

разрыв страницы

شكستن صفحه

| ОБОСНОВАНИЕ: видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужир. | دلايل: خطوط جدول مشخص باشد، سايه گذاری ملايم ، اندازه 14 ضخيم |
| --- | --- |

пробел 12

فاصله 12

1) متن دلايل اندازه 14 معمولي

1 Текст обоснования размер 10, начертание обычное

2) متن بندهاي بعدي دلايل اندازه 14 معمولي

2 Текст последующих пунктов обоснования размер 10, начертание обычное

пробел 12

فاصله 12

Appendix 1 continued

| РЕШИЛИ: видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужирное | تصميمات اتخاذ شده: خطوط جدول مشخص باشد، سايه گذاری ملايم ، اندازه 14 ضخيم |
| --- | --- |

пробел 12

فاصله 12

1) متن تصميمات اندازه 14 معمولي

1 Текст решения размер 10, начертание обычное

2) متن بندهاي بعدي دلايل: اندازه 14 معمولي

2 Текст последующих пунктов решения размер 10, начертание обычное

пробел 12

فاصله 12

| КОРРЕКТИРОВКА ДОКУМЕНТАЦИИ: видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужирное | تصحيح در مدارك: خطوط جدول مشخص باشد، سايه گذاری ملايم ، اندازه 14 ضخيم |
| --- | --- |

пробел 12

فاصله 12

1) متن اقدامات مربوط به اصلاح مدارك اندازه 14 معمولي

1 Текст мероприятий по корректировке документации размер 10, начертание обычное

2) متن بندهاي بعدي اقدامات اندازه 14 معمولي

2 Текст последующих пунктов мероприятий размер 10, начертание обычное

пробел 12

فاصله 12

| Приложения: видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужирное | ضمايم: خطوط جدول مشخص باشد، سايه گذاری ملايم ، اندازه 14 ضخيم |
| --- | --- |

пробел 12

فاصله 12

1) عنوان ضميمه اندازه 14 معمولي

1 Наименование приложения размер 10, начертание обычное

2) عنوان ضمايم بعدي اندازه 14 معمولي

Appendix 1 continued

2 Наименование последующих приложений размер 10, начертание обычное

пробел 12

فاصله

مدت زمان اعتبار تصميم فني: متن مدت زمان اعتبار 14 ضخيم – متن 14 معمولي

СРОК ДЕЙСТВИЯ: текст СРОК ДЕЙСТВИЯ - размер 10, прописные, начертание полужирное. Текст - размер 10, начертание обычное

مسئول اجرای تصميم فني: متن مسئول اجراي تصميم فتي 14 ضخيم – متن 14 معمولي

ОТВЕСТВЕННЫЙ ЗА ВНЕДРЕНИЕ: текст ОТВЕСТВЕННЫЙ ЗА ВНЕДРЕНИЕ - размер 10, прописные, начертание полужирное. Текст - размер 10, начертание обычное

گيرندگان تصميم فني: متن مسئول اجراي تصميم فتي 14 ضخيم – متن 14 معمولي

РАССЫЛКА: текст размер 10, прописные, начертание полужирное

توضيحات انجام مفاد تصميم فني: انجام كامل تصميم فني 14 ضخيم – متن 14 معمولي

ОТМЕТКА О ВНЕДРЕНИИ: размер 10, прописные, начертание полужирное

пробел 12

فاصله

| تاييد تصميم فني اندازه 14 ضخيم |  |  | Техническое решение подписали: размер 10, начертание полужирное |  |  |
| --- | --- | --- | --- | --- | --- |
| تدوين كننده اندازه 14 معمولي | نام و نام‌خانوادگي اندازه 14 معمولي | مدير واحد تدوين كننده از شركت بهره برداري و يا مدير ديگر واحد هاي تدوين كننده |  | _________ امضاء подпись | ________ تاريخ дата |
| Разработал размер 10, начертание обычное | Ф.И.О. размер 10, начертание обычное | Начальник подразделения BNPP Co. или руководитель подразделения организации разработчика |  |  |  |
| تاييد | نام و نام‌خانوادگي | مديرعامل سازمان خارجي تدوين كننده |  | _________ امضاء подпись | _________ تاريخ дата |
| Согласовано | Ф.И.О. | Руководитель сторонней организации разработчика |  |  |  |
| تاييد | نام و نام‌خانوادگي | عناوين شغلي از شركت بهره برداري در رابطه با حوزه فعاليت |  | _________ امضاء подпись | _________ تاريخ дата |

Appendix 1 continued

| Согласовано | Ф.И.О. | Должностные лица BNPP Co. по своим направлениям деятельности |  |  |
| --- | --- | --- | --- | --- |
| تاييد | نام و نام‌خانوادگي | نماينده شركت طراح در واحد اول نيروكاه اتمي بوشهر | _________ امضاء подпись | _________ تاريخ дата |
| Согласовано | Ф.И.О. | Представитель проектной организации на площадке АЭС «Бушер» |  |  |
| تاييد | نام و نام‌خانوادگي | نماينده كارخانه سازنده تجهيز در در واحد اول نيروگاه اتمي بوشهر | _________ امضاء подпись | _________ تاريخ дата |
| Согласовано | Ф.И.О. | Представитель завода изготовителя на площадке АЭС «Бушер» |  |  |
| تاييد | نام و نام‌خانوادگي | نماينده شركت راه انداز در واحد اول نيروگاه اتمي بوشهر | _________ امضاء подпись | _________ تاريخ дата |
| Согласовано | Ф.И.О. | Представитель пусконаладочной организации на площадке АЭС «Бушер» |  |  |
| تاييد | نام و نام‌خانوادگي | مدير عامل شركت JSC ASE در واحد اول نيروگاه اتمي بوشهر | _________ امضاء подпись | _________ تاريخ дата |
| Согласовано | Ф.И.О. | Руководитель Дирекции АО АСЭ на площадке АЭС «Бушер» |  |  |

- Footer on every sheet.

| تدوين كننده اندازه 10 معمولي Разработчик размер 8, начертание обычное | واحد/سازمان Подразделение/ организация | تلفن Телефон | امضاء Подпись | كد تصميم فني Код и регистрационный № | صفحه Лист | صفحات Листов |
| --- | --- | --- | --- | --- | --- | --- |
| اندازه 10 معمولي размер 8, начертание обычное на рус. |  |  |  |  |  |  |

Note: In the cases stipulated in item 7.6, under the box «Approved» after BNPP Co. agreement attribute, the agreement attributes of JSC ASE  (Moscow) shall be indicated, and under the attribute «Developed» in the end of the list the agreement attributes of JSC ASE  Directorate at the BNPP-1 Site shall be indicated(

Appendix 2

Sample of technical decision formalized by BNPP Co. and IRI contracting organizations

Requiring NNSD (Bushehr) agreement

| تصويب | نام و نام‌خانوادگي | سر مهندس نيروگاه اتمي بوشهر | __________ امضاء | _________ تاريخ |
| --- | --- | --- | --- | --- |
| УТВЕРЖДАЮ | Ф.И.О. | Главный инженер BNPP Co. |  |  |
| موافقت | نام و نام‌خانوادگي | ‌دفتر‌نمايندگی ‌ايمنی هسته اي ‌در ‌نيروگاه ‌اتمی‌ بوشهر | __________ امضاء | _________ تاريخ |
| СОГЛАСОВАНО | Ф.И.О. | Руководитель Представительства NNSD на площадке АЭС «Бушер-1» |  |  |
| تاييد | نام و نام‌خانوادگي | معاون فني و مهندسي شركت توليد و توسعه | __________ امضاء | _________ تاريخ |
| СОГЛАСОВАНО | Ф.И.О. | Зам. директора NPPD Co. по инженерно-технической поддержки |  |  |

تصميم فني شماره 67.BU.10.0.ABS.RT.BNPP1238

ТЕХНИЧЕСКОЕ РЕШЕНИЕ № 67.BU.10.0.ABS.RT.BNPP1238

عنوان : استفاده از تجهيزات محافظ با تيپ «гусак» بر روي لوله هاي ايمپالس سطح سنج هاي چهار متري مولد هاي بخار در واحد شماره يك نيروگاه اتمي بوشهر.

НАЗВАНИЕ: О применении защитных устройств, типа «гусак», на «минусовых» линиях уровнемеров ПГ с 4-х метровой базой энергоблока АЭС «Бушер»

محل : واحد شماره يك، ساختمان 1ZА

ОБЪЕКТ: Энергоблок № 1. Здание 1ZА

المان ساختاري: قطعه لوله هاي خطوط ايمپالس منفي سطح سنج هاي چهار متري مولد بخار درون پوسته مولد بخار بر اساس نقشه شماره 446.05.01 СБ

КОНСТРУКТИВНЫЙ ЭЛЕМЕНТ: Импульсные трубопроводы «минусовых» линий уровнемеров ПГ с 4-х метровой базой внутри корпуса ПГ. Чертеж № 446.05.01 СБ

كلاس ايمني: 2НУ مطابق مدرك ОПБ-88/97

КЛАСС БЕЗОПАСНОСТИ: 2НУ по ОПБ-88/97

گروه تجهيزات: گروه В مطابق مدرك ПНАЭ Г-7-008-89

ГРУППА ОБОРУДОВАНИЯ: группа В по ПНАЭ Г-7-008-89

طبقه بندي بر اساس شدت زلزله: گروه I مطابق مدرك ПНАЭ Г-5-006-87

КАТЕГОРИЯ СЕЙСМОСТОЙКОСТИ: I по ПНАЭ Г-5-006-87

Appendix 2 continued نوع كار: مدرنيزاسيون قسمت منفي خطوط ايمپالس سطح سنج هاي چهارمتري مولد بخار

ВИД РАБОТЫ: Модернизация узла «минусовой» линии уровнемеров ПГ с 4-х метровой базой

Разрыв страницы

| ОБОСНОВАНИЕ: | دلايل: |
| --- | --- |

1. هنگام بهره برداری به دفعات سيگنال هاي خطا از سطح سنج هاي چهارمتري دريافت شد كه منجر به كاهش توان توليدي نيروگاه گرديد:

1- В процессе эксплуатации неоднократно возникали ложные показания уровнемеров с 4-х метровыми базами, что приводило к разгрузке блока.

- 2. اختلالات مشابه دربعضي از نيروگاه هاي روسيه و اكراين نيز گزارش شده است ((№1КЛН-П07-01-07-10, №2КЛН-П06-03-08-10, № 2КЛН-П07-05-09-10, №4ЗАП-П05-24-10.01, - №1ЗАП-П05-25-10.01)

2- Аналогичные нарушения были зафиксированы на российских и украинских блоках (№1КЛН-П07-01-07-10, №2КЛН-П06-03-08-10, № 2КЛН-П07-05-09-10, №4ЗАП-П05-24-10.01, №1ЗАП-П05-25-10.01).

3. بر اساس تجارب بهره برداري در نيروگاه هاي مشابه روسيه و اكراين که تغييرساختاري بر روي قسمت منفي سطح سنج هاي مولد بخار انجام شده است ( تصميم فني شماره №1-6.РО.YB.Тр.6413 نيروگاه زاپاروژسكايا در خصوص تغييرات تجهيزات محافظ سطح سنج هاي مولد بخار) نشان می دهد که دفعات عملکرد حفاظت اضطراری راکتور و همچنين قطع پمپ مدار اول بدليل سيگنال خطای سطح سنجها کاهش يافته و يا به کلی برطرف شده است.

3- Опыт эксплуатации аналогичных блоков в России и на Украине, где произведена реконструкция узла «минусовой» линии внутри корпуса ПГ (Техническое решение №1-6.РО.YB.Тр.6413 Запорожской АЭС «О реконструкции защитных устройств ПГ»), показывает отсутствие или уменьшение срабатываний АЗ и отключений ГЦНА из-за ложных показаний уровнемеров с 4-х метровой базой.

| РЕШИЛИ: | تصميمات اتخاذ شده: |
| --- | --- |
| 1. مقرر گرديد تا تجهيزات محافظ روي خط منفي ايمپالس سطح سنج ها ي چهار متري کنوني به تيپ 320.01 СБ ( که توسط شركت گيدروپرس طراحي شذه است ) تعويض گردد بدين ترتيب که قسمت صافي مانند بالائي تجهيزات محافظ برداشته شده(بريده شود)و پس از آن لوله با مشخصات Ø18х2,5 و تبديل Ø38х4 نصب گردد(جوشکاری شود). اين كار در تعميرات نيمه اساسي 2014 ميلادي روي مولد هاي بخار شماره دو و شماره سه انجام شده و بر اساس نتايج بهره برداري براي انجام تغيير تجهيزات محافظ در تعميرات نيمه اساسي بعدي بر روي ساير مولد هاي بخار ، شماره يك و چهار، تصميم گيري شود. واحد مسئول اجرا: شركت پيمانكار اتم استروي اكسپورت، مهلت اجرا: تعميرات دوره اي سال 2014. |  |
| Appendix 2 continued 1- Провести замену защитных устройств «минусовых» импульсных линий уровнемеров с базой 4м на защитные устройства типа 320.01 СБ (разработки Гидропресс) в объеме срезки верхней перфорированной части защитного устройства с последующей приваркой элемента трубопровода Ø18х2,5 с переходником на Ø38х4. Работу выполнить в очередной ППР - 2014 на ПГ-2 и ПГ- 3. По результатам эксплуатации принять решение о реконструкции защитных устройств на остальных ПГ – 1,4 в следующий ППР. Срок – ППР 2014, Отв. – АО АСЭ |  |
| 2. مقرر گرديد تا تجهيزات محافظ بر اساس نقشه شماره 320.01 СБ. ساخته شود. مهلت اجرا : تا زمان شروع تعميرات نيمه اساسي 2014 ميلادي. واحد مسئول اجرا: شركت پيمانكار اتم استروي اكسپورت روسيه. |  |
| 2- Изготовить защитные устройства по чертежу 320.01 СБ. Срок – до ППР 2014. Отв. – АО АСЭ |  |

| КОРРЕКТИРОВКА ДОКУМЕНТАЦИИ: | تصحيح در مدارک : |
| --- | --- |

1. نتايج انجام كار در پاسپورت هاي مولد هاي بخار (446.05.01 ПС) دربازه زماني دو ماه بعد از انجام كار درج گردد. واحد مسئول اجرا: مديريت راكتور نيروگاه اتمي بوشهر.

1- Результаты выполненных работ внести в паспорта ПГ (446.05.01 ПС) в течение двух месяцев после выполнения работ. Отв. РО BNPP Co.

| Приложения: | ضمايم: |
| --- | --- |

1. نقشه شماره 320.01 СБ در 15 صفحه به زبان روسي.

1- Чертеж № 320.01 СБ - на 15 листах, на русском языке;

2. تصميم فني شماره 1-6.РО.YB.Тр.6413 مورخ 12.11.2001 در 3 صفحه به زبان روسي.

2-Техническое решение № 1-6.РО.YB.Тр.6413 от 12.11.2001г - на 3 листах, на русском языке;

مدت زمان اعتبار تصميم فني: دايمی

СРОК ДЕЙСТВИЯ: Постоянно

مسئول اجرای تصميم فني: مديريت راكتور نيروگاه اتمي بوشهر. تلفن 2569

ОТВЕСТВЕННЫЙ ЗА ВНЕДРЕНИЕ: РО, тел. 2569

گيرندگان تصميم فني: دفتر‌نمايندگی ‌ايمنی هسته اي ‌در ‌نيروگاه ‌اتمی‌ بوشهر -مجري طرح نيروگاه اتمي بوشهر-معاونت نگهداري و تعميرات-معاونت فني و مهندسي-مديريت راكتور-مديريت برنامه ريزي و مدارك فني-مديريت سيستم مديريت و نظارت

Рассылка: NNSD, NPPD Co., ЗГИР, ЗГИИП, РО, ОПиТД, ОСМиН

توضيحات انجام مفاد تصميم فني:

Отметка о внедрении:

| تاييد تصميم فني: |  |  | Техническое решение подписали: |  |  |
| --- | --- | --- | --- | --- | --- |
| تدوين كننده | نام و نام‌خانوادگي | مدير راكتور |  | __________ امضاء | _________ تاريخ |
| Разработал | Ф.И.О. | Начальник реакторного отделения |  |  |  |
| تاييد | نام و نام‌خانوادگي | معاون فني و مهندسي |  | __________ امضاء | _________ تاريخ |
| Согласовано | Ф.И.О. | Заместитель главного инженера по инженерной поддержке |  |  |  |
| تاييد | نام و نام‌خانوادگي | مدير سيستم مديريت و نظارت |  | __________ امضاء | _________ تاريخ |
| Согласовано | Ф.И.О. | Начальник ОCМиН |  |  |  |

Appendix 2 continued

| تاييد | نام و نام‌خانوادگي | مدير برنامه ريزي و مدارك فني | __________ امضاء | _________ تاريخ |
| --- | --- | --- | --- | --- |
| Согласовано | Ф.И.О. | Начальник ОПиТД BNPP Co. |  |  |
| تاييد | نام و نام‌خانوادگي | نماينده شركت JSC ASE | __________ امضاء | _________ تاريخ |
| Согласовано | Ф.И.О. | И.о. Заместителя начальника Управления по строительству АЭС в Иране |  |  |
| تاييد | نام و نام‌خانوادگي | مدير شركت AEP در نيروگاه اتمي بوشهر | __________ امضاء | _________ تاريخ |
| Согласовано | Ф.И.О. | Руководитель ОАО АЭП на площадке АЭС «Бушер-1» |  |  |

- Footer on every sheet

| تدوين كننده Разработчик | واحد/سازمان Подразделение/ организация | تلفن Телефон | امضاء Подпись | كد تصميم فني Код и регистрационный № | صفحه Лист | صفحات Листов |
| --- | --- | --- | --- | --- | --- | --- |
| نام و نام‌خانوادگي Ф.И.О. | مديريت راكتور РО | 2567 25-67 |  | 67.BU.10.0.ABS.RT. BNPP1238 |  |  |

Appendix 3

Technical decision form formalized by organizations concerned and

requiring NNSD(Tehran) agreement

Throughout the text – a hidden table, interval before and after – 3, font  used in the document - Arial, line interval – minimal

По всему тексту – скрытая таблица, интервал до и интервал после – 3пт, шрифт Arial, интервал межстр. минимум

White space 12

пробел 12

| APPROVED BY font size 12, all caps, bold | Full name font size 12, regular | BNPP Co. Chief Engineer font size 12, regular | ________ signature подпись | _________ date дата |
| --- | --- | --- | --- | --- |
| УТВЕРЖДАЮ размер 10, прописные, начертание полужир, | Ф.И.О размер 10, начертание обычное | Главный инженер BNPP Co. размер 10, начертание обычное |  |  |
| AGREED BY | Full name | NNSD Director General/representative (Tehran) | _________ signature подпись | _________ date дата |
| СОГЛАСОВАНО | Ф.И.О. | Генеральный директор NNSD/представитель (Тегеран) |  |  |
| AGREED BY | Full name | Manager of NNSD’s Consultant /representative | _________ signature подпись | _________ date дата |
| СОГЛАСОВАНО | Ф.И.О. | Руководитель Консультанта NNSD/ представитель |  |  |
| AGREED BY | Full name | NPPD Co. deputy managing director for technical and engineering | _________ signature подпись | _________ date дата |

Appendix 3 continued

| СОГЛАСОВАНО | Ф.И.О. | Зам. директора NPPD Co. по инженерно-технической поддержки |  |  |
| --- | --- | --- | --- | --- |
| AGREED BY | Full name | JSC ASE Representative | _________ signature подпись | _________ date дата |
| СОГЛАСОВАНО | Ф.И.О. | Представитель АО АСЭ |  |  |
| AGREED BY | Full name | Manager/representative of RF Designer | _________ signature подпись | _________ date дата |
| СОГЛАСОВАНО | Ф.И.О. | Руководитель/представитель проектной организации РФ |  |  |

White space 12

пробел 12

TECHNICAL DECISION code Visible table row, Filling with faint tint, font size 12, all caps, bold

ТЕХНИЧЕСКОЕ РЕШЕНИЕ код видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужир

TITLE: title text TITLE – font size 12, all caps, bold. Title text – font size 12, regular

НАЗВАНИЕ: текст названия НАЗВАНИЕ - размер 10, прописные, начертание полужир. Текст названия - размер 10, начертание обычное

White space 12

пробел 12

PROJECT: text Project – font size 12, all caps, bold. Text – font size 12, regular

ОБЪЕКТ: текст ОБЪЕКТ - размер 10, прописные, начертание полужир. Текст объекта - размер 10, начертание обычное

STRUCTURAL ELEMENT: text

КОНСТРУКТИВНЫЙ ЭЛЕМЕНТ: текст

SAFETY CLASS: text

КЛАСС БЕЗОПАСНОСТИ: текст

EQUIPMENT GROUP: text

ГРУППА ОБОРУДОВАНИЯ: текст

SEISMIC STABILITY CLASS: text

КАТЕГОРИЯ СЕЙСМОСТОЙКОСТИ: текст

TYPE OF ACTIVITY: text

ВИД РАБОТЫ: текст

Break page

разрыв страницы

Appendix 3 continued

| ОБОСНОВАНИЕ: видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужир. | REASON: Visible table row, Filling with faint tint, font size 12, all caps, bold |
| --- | --- |

White space 12

пробел 12

1 Reason text font size 12, regular

1 Текст обоснования размер 10, начертание обычное

2 Text of subsequent reason items font size 12, regular

2 Текст последующих пунктов обоснования размер 10, начертание обычное

White space 12

пробел 12

| РЕШИЛИ: видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужирное | DECISION: Visible table row, Filling with faint tint, font size 12, all caps, bold |
| --- | --- |

White space 12

пробел 12

1 Decision text font size 12, regular

1 Текст решения размер 10, начертание обычное

2 Text of subsequent reason items размер 12, regular

2 Текст последующих пунктов решения размер 10, начертание обычное

White space

пробел 12

| КОРРЕКТИРОВКА ДОКУМЕНТАЦИИ: видимая строка таблицы, заливка слабым тоном, размер 10, прописные, начертание полужирное | UPDATING OF DOCUMENTS: Visible table row, Filling with faint tint, font size 12, all caps, bold |
| --- | --- |

White space 12

пробел 12

1 Text of measures related to updating of documents font size 12, regular

1 Текст мероприятий по корректировке документации размер 10, начертание обычное

2 Text of subsequent measure items font size 12, regular

2 Текст последующих пунктов мероприятий размер 10, начертание обычное

White space 12

пробел 12

Appendix 3 continued

| Приложения: видимая строка таблицы, заливка слабым тоном, размер 10, обычный, начертание полужирное | Appendix: Visible table row, Filling with faint tint, font size 12, regular, bold |
| --- | --- |

White space 12

пробел 12

1 Title appendix font size 12, regular

1 Наименование приложения размер 10, начертание обычное

2 Titles of subsequent appendix font size 12, regular

2 Наименование последующих приложений размер 10, начертание обычное

White space 12

пробел 12

VALIDITY PERIOD: text VALIDITY PERIOD - font size 12, all caps, bold. Text - font size 12, regular

СРОК ДЕЙСТВИЯ: текст СРОК ДЕЙСТВИЯ - размер 10, прописные, начертание полужирное. Text - размер 10, начертание обычное

RESPONSIBLE FOR IMPLEMENTATION: text RESPONSIBLE FOR IMPLEMENTATION - font size 12, all caps, bold. Text - font size 12, regular

ОТВЕТСТВЕННЫЙ ЗА ВНЕДРЕНИЕ: текст ОТВЕСТВЕННЫЙ ЗА ВНЕДРЕНИЕ - размер 10, прописные, начертание полужирное. Текст - размер 10, начертание обычное

DISTRIBUTION: text MAIL DISTRIBUTION - font size 12, all caps, bold. Text - font size 12, regular

РАССЫЛКА: текст РАССЫЛКА - размер 10, прописные, начертание полужирное. Текст - размер 10, начертание обычное

IMPLEMENTATION MARK: IMPLEMENTATION MARK - font size 12, all caps, bold. Text - размер 12, regular

ОТМЕТКА О ВНЕДРЕНИИ: ОТМЕТКА О ВНЕДРЕНИИ - размер 10, прописные, начертание полужирное

White space 12

пробел 12

| Technical decision signed by: font size 12, bold |  |  | Техническое решение подписали: размер 10, начертание полужирное |  |  |
| --- | --- | --- | --- | --- | --- |
| Developed by font size 12, regular | Full name font size 12, regular | Manager of BNPP Co.subdivision or manager of development organization subdivision font size 12, regular |  | _________ signature подпись | _________ date дата |

Appendix 3 continued

| Разработал размер 10, начертание обычное | Ф.И.О. размер 10, начертание обычное | Начальник подразделения BNPP Co. или руководитель подразделения организации разработчика размер 10, начертание обычное |  |  |
| --- | --- | --- | --- | --- |
| Agreed by | Full name | Manager of development organization |  |  |
| Согласовано | Ф.И.О. | Руководитель сторонней организации разработчика |  |  |
| Agreed by | Full name | BNPP Co. officials of their activity areas | _________ signature подпись | _________ date дата |
| Согласовано | Ф.И.О. | Должностные лица BNPP Co. по своим направлениям деятельности |  |  |
| Agreed by | Full name | Representative of Designer at BNPP-1 site | _________ signature подпись | _________ date дата |
| Согласовано | Ф.И.О. | Представитель проектной организации на площадке АЭС «Бушер-1» |  |  |
| Agreed by | Full name | Representative of Manufacturer at BNPP-1 site | _________ signature подпись | _________ date дата |
| Согласовано | Ф.И.О. | Представитель завода изготовителя на площадке АЭС «Бушер» |  |  |
| Agreed by | Full name | Manager of JSC ASE Directorate at the BNPP-1 Site | _________ signature подпись | _________ date дата |
| Согласовано | Ф.И.О. | Руководитель Дирекции АО АСЭ на площадке АЭС «Бушер» |  |  |
| Agreed by | Full name | OCE Manager | _________ signature подпись | ____________ date дата |
| Согласовано | Ф.И.О. | Руководитель ОСЕ |  |  |

Appendix 3 continued

- Footer on every sheet

| Developer Разработчик font size 8, regular | Subdivision/ Organization Подразделение/ организация | Telephone number Телефон | Signature Подпись | Code and registration No Код и регистрационный № | Sheet Лист | Sheets Листов |
| --- | --- | --- | --- | --- | --- | --- |
| ENG - font size 8, regular рус. - размер 8, начертание обычное |  |  |  |  |  |  |

Appendix 4

Sample of technical decision formalized by organizations concerned and

requiring NNSD(Tehran) agreement

| APPROVED BY | Full name | BNPP Co. Chief Engineer | ________ signature | ________ date |
| --- | --- | --- | --- | --- |
| УТВЕРЖДАЮ | Ф.И.О. | Главный инженер BNPP Co. |  |  |
| AGREED BY | Full name | NNSD Director General/representative (Tehran) | ________ signature | ________ date |
| СОГЛАСОВАНО | Ф.И.О. | Генеральный директор NNSD/представитель (Тегеран) |  |  |
| AGREED BY | Full name | Manager of NNSD’s Consultant /representative | ________ signature | ________ date |
| СОГЛАСОВАНО | Ф.И.О. | Руководитель Консультанта NNSD/ представитель |  |  |
| AGREED BY | Full name | NPPD Co. deputy managing director for technical and engineering | ________ signature | ________ date |
| СОГЛАСОВАНО | Ф.И.О. | Зам. директора NPPD Co. по инженерно-технической поддержки |  |  |

TECHNICAL DECISION 65.BU.1 0.VE.TM.RT.FE1230

ТЕХНИЧЕСКОЕ РЕШЕНИЕ 65.BU.1 0.VE.TM.RT.FE1230

TITLE: Method of plugging the nozzles of the annulled process control points at the BNPP-1 sea water pipelines

НАЗВАНИЕ: О способе глушения штуцеров аннулированных точек технологического контроля на участках трубопроводов морской воды АЭС «Бушер» блок №1

PROJECT: Power Unit No.1

ОБЪЕКТ: Энергоблок № 1

STRUCTURAL COMPONENT: Control points of seawater pipelines

КОНСТРУКТИВНЫЙ ЭЛЕМЕНТ: Точки контроля трубопроводов морской воды

SAFETY CLASS: 2 as per GSP-88/97

Appendix 4 continued

КЛАСС БЕЗОПАСНОСТИ: 2 по ОПБ-88/97

EQUIPMENT GROUP: группа В as per PNAE G -7-008-89

ГРУППА ОБОРУДОВАНИЯ: группа В по ПНАЭ Г-7-008-89

SEISMIC STABILITY CLASS: I, II as per PNAE G-5-006-87

КАТЕГОРИЯ СЕЙСМОСТОЙКОСТИ: I, II по ПНАЭ Г-5-006-87

TYPE OF ACTIVITY: Repair activities

ВИД РАБОТЫ: Ремонтные работы

Разрыв страницы

| ОБОСНОВАНИЕ: | REASON: |
| --- | --- |

1 Deviation from item 3.1.2 PNAE G -7-008-89

1 Отступление от пункта 3.1.2 ПНАЭ Г-7-008-89

2 VE System pipelines are exposed to aggressive attack of “sea water” medium, which leads to destruction of protective coating and results in metal corrosion and pipeline fracture. Spots of control point nozzles welding are subject to highest risks.

2 Трубопроводы системы VE подвержены агрессивному воздействию среды «морская вода», что приводит к разрушению защитного покрытия, а в дальнейшем к коррозии металла и разрушению трубопровода. Самым большим рискам подвержены места приварки штуцеров точек контроля

3 In compliance with Technical Conditions of the plate-type heat exchanger of VJ system “structure, workmanship and applied materials ensure safe operation of the heat exchanger without contact servicing and inspection for at least one year”. In compliance with the Operation Manual the plate-type heat exchanger shall be subjected to flushing during PPM. Therefore the control points VE10(20,30,40)P004 in ZK1,2 buildings shall be plugged according to drawings 21.BU.1ZK1.VE.TM.OK.RDR021 and 21.BU.1ZK2.VE.TM.OK.RDR021

3 В соответствии с Техническими условиями на пластинчатый теплообменник системы VJ «конструкция, качество изготовления и применяемые материалы обеспечивают надежную работу теплообменника без непосредственного обслуживания и контроля в течение не менее года». Пластинчатый теплообменник в соответствии с инструкцией по эксплуатации должен подвергаться промывке в ППР. В связи с этим точки контроля VE10(20,30,40)P004 в зданиях ZK1,2 заглушить в соответствии с чертежами 21.BU.1ZK1.VE.TM.OK.RDR021 и 21.BU.1ZK2.VE.TM.OK.RDR021

4 Performance of TF10(20,30,40)В001 heat exchangers is monitored by the temperature difference at VE10(20,30,40)Т001point (inlet) and VE10(20,30,40)Т002 point (outlet). The contamination degree of tube sheet TF10(20,30,40)В001 is monitored by the pressure drop on the heat exchangers at control points VE10(20,30,40)P001 and VE10(20,30,40)P002. Thus, the control points VE10(20,30,40)P005 in ZB0 building shall be plugged according to drawing 21.BU.1ZB0.VE.TM.OK.RDR002

4 Работа теплообменников TF10(20,30,40)В001 контролируется по разнице температур в точках VE10(20,30,40)Т001 на входе и VE10(20,30,40)Т002 на выходе из теплообменника. Степень загрязненности трубчатки TF10(20,30,40)В001 контролируется по перепаду давления на теплообменниках, по точкам контроля VE10(20,30,40)P001 и VE10(20,30,40)P002. Таким образом, точки контроля VE10(20,30,40)P005 в здании ZB0 заглушить в соответствии с чертежом 21.BU.1ZB0.VE.TM.OK.RDR002

Appendix 4 continued

| РЕШИЛИ: | DECISION: |
| --- | --- |

| 1 The annulled control points on the sea water pipeline sections shall be plugged to reduce the risk of corrosion wear: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 На участках трубопроводов морской воды заглушить аннулированные точки контроля для уменьшения рисков возникновения коррозионного износа: |  |  |  |  |  |  |  |  |  |  |
|  | Building Здание | Point of Technological Control ТТК |  | Drawing No № проекта |  | Quantity Кол-во |  | Position No. of pipeline block № позиции блока |  |  |
|  | 1ZB0 |  | VE10,20,30,40P005 |  | 21.BU.1ZB0.VE.TM.OK.RDR002 |  | 4 |  | 18,30,49,68 |  |
|  | 1ZK1 |  | VE20,30P004 |  | 21.BU.1ZK1.VE.TM.OK.RDR021 |  | 2 |  | 2 |  |
|  | 1ZK1 |  | VE20,30P006 |  | 21.BU.1ZK1.VE.TM.OK.RDR021 |  | 2 |  | 34,29 |  |
|  | 1ZK2 |  | VE10,40P004 |  | 21.BU.1ZK2.VE.TM.OK.RDR021 |  | 2 |  | 2 |  |
|  | 1ZK2 |  | VE10,40P006 |  | 21.BU.1ZK2.VE.TM.OK.RDR021 |  | 2 |  | 2 |  |
|  | 1ZM-2-4-5 |  | VE21,31P003 VE21,31T001,502 |  | 21.BU.1ZM4-5.VE.TW.OK.RDR101 |  | 6 |  | 17 |  |

Responsible: DASE FE ID. Deadline: During PPM of the NPP Unit in 2014.

Ответственный: МП «ФЭ» ДАСЭ. Срок выполнения: В ППР энергоблока 2014г.

2 Nozzles shall be plugged at the cancelled control points in compliance with Appendix No.1 Responsible: DASE FE ID. Deadline: During PPM of the NPP Unit in 2014.

2 На местах аннулированных точек контроля штуцера заглушить согласно приложению 1 Ответственный: МП «ФЭ» ДАСЭ. Срок выполнения: В ППР энергоблока 2014г.

3 Plugs shall be fabricated from steel grade RSt37-2 according to DIN 17100 admitted to applying on the pipelines and equipment under BNPP-1 Completion Project (TD №CS.1.TAG.BAS.1ZM7.VE.0546 “on admissibility of flanges DIN 2632 (steel RSt37-2 DIN 17100) and sheet metal from steel RSt37-2 DIN 17100 for fabricating components of VE system pipelines) Responsible: DASE FE ID. Deadline: During PPM of the NPP Unit in 2014.

3 Заглушки изготавливать из стали марки RSt37-2 по DIN 17100, ранее допущенной к применению на трубопроводах и оборудованию в проекте достройки АЭС «Бушер-1» (ТР №CS.1.TAG.BAS.1ZM7.VE.0546 «о допустимости применения фланцев DIN 2632 (сталь RSt37-2 DIN 17100) и листового металла из стали RSt37-2 DIN 17100 для изготовления элементов трубопроводов системы VE) Ответственный: МП «ФЭ» ДАСЭ. Срок выполнения: В ППР энергоблока 2014г.

Appendix 4 continued

4 The present technical decision shall be considered an integral part of the set of reporting documentation for repair of pipeline blocks

4 Настоящее техническое решение считать неотъемлемой частью комплекта отчётной документации на ремонт блоков трубопровода

| КОРРЕКТИРОВКА ДОКУМЕНТАЦИИ: | UPDATING OF DOCUMENTS: |
| --- | --- |

1 Documents do not require updating

1 Корректировка документации не требуется

| Приложения: | Appendix: |
| --- | --- |

1 Scheme of nozzles plugging, on 1 sheet, RF variant

1 Схема глушения штуцеров, на 1 листе, рус.

VALIDITY PERIOD: For the period of BNPP-1 operation

СРОК ДЕЙСТВИЯ: На время эксплуатации АЭС «Бушер» блок №1

RESPONSIBLE FOR IMPLEMENTATION: RD BNPP Co. (t.25-69), TD BNPP Co. (t.25-58)

ОТВЕТСТВЕННЫЙ ЗА ВНЕДРЕНИЕ: РО BNPP Co. (т.25-69), TO BNPP Co. (т.25-58)

DISTRIBUTION: NNSD, Forpost-Energo ID of JSC ASE Directorate, FSUE TSNII KM “Prometey”, OAO AEP at BNPP-1 site. BNPP Co.: RC, TC

РАССЫЛКА: NNSD, МП «Форпост-Энерго» Дирекции АО АСЭ, ФГУП ЦНИИ КМ «Прометей», ОАО АЭП на площадке АЭС «Бушер-1» BNPP Co.: РО, ТО

IMPLEMENTATION MARK:

ОТМЕТКА О ВНЕДРЕНИИ:

| Technical decision signed by: | Техническое решение подписали: |
| --- | --- |

| Agreed by | Full name | BNPP Co. Manager of Planning and Technical Documentation Department | signature | date |
| --- | --- | --- | --- | --- |
| Согласовано | Ф.И.О. | Начальник отдела планирования и технической документации BNPP Co. |  |  |
| Agreed by | Full name | BNPP Co. Metal Laboratory Manager | signature | date |
| Согласовано | Ф.И.О. | Начальник лаборатории металлов BNPP Co. |  |  |
| Agreed by | Full name | BNPP Co. Deputy Chief Engineer for Engineering Support | signature | date |
| Согласовано | Ф.И.О. | Заместитель главного инженера по инженерно-технической поддержке BNPP Co. |  |  |
| Agreed by | Full name | Head of BNPP Co. Maintenance and Repair Department | signature | date |
| Согласовано | Ф.И.О. | Начальник департамента по техническому обслуживанию и ремонту BNPP Co. |  |  |
| Agreed by | Full name | BNPP Co. Manager of Management and Surveillance System Department | signature | date |
| Согласовано | Ф.И.О. | Начальник отдела системы менеджмента и надзора BNPP Co. |  |  |
| Agreed by | Full name | Representative of Designer at BNPP-1 site | signature | date |

Appendix 4 continued

| Согласовано | Ф.И.О. | Руководитель работ ОАО АЭП на площадке АЭС «Бушер» |  |  |
| --- | --- | --- | --- | --- |
| Agreed by | Full name | FSUE TSNII KM Prometey Co Deputy Director General | __№ 6-04-16/67МЭ | 28.06.13г. |
| Согласовано | Ф.И.О. | Заместитель Генерального директора ФГУП ЦНИИ КМ «Прометей» |  |  |

- Footer on every sheet

| Developer Разработчик | Subdivision/ Organization Подразделение/ организация | Telephone number Телефон | Signature Подпись | Code and registration No Код и регистрационный № | Sheet Лист | Sheets Листов |
| --- | --- | --- | --- | --- | --- | --- |
| Full name Ф.И.О. | Forpost-Energo ID МП «Форпост-Энерго» | 11-11 |  | 65.BU.1 0.VE.TM.RT.FE1230 |  |  |

In the document, appendices 1 and 3 are the format of technical decision. All of the requirements related to it (general requirements, size of the text, line spacing, location, etc.) have been mentioned. The appendices 2 and 4 are the completed samples for developing technical decision.

Appendix 5

Example of drawing up response to comments made by NNSD on technical decision

Response to comments issued by NNSD Representative Office at BNPP-1 site on technical decision (letter No хххх от хххххх) to technical decision No. ххххххххххх

| № | Comment | Response |
| --- | --- | --- |
| 1 | Section "JUSTIFICATION" contains the list of design documentation of AEP without indication of change (revision) divergence from which required the TD to be drawn up. | Accepted. Change (revision) divergence from which required the TD to be drawn up is specified in the list of design documentation of AEP in section "JUSTIFICATION" |
| 2 | Section "JUSTIFICATION" contains the record «Control points … shall be plugged in accordance with drawings 21.BU.1ZM4-5.VE.TW.OK.RDR101 and 21.BU.1ZM4-5.VE.TW.OK.RDR104», however, the drawings themselves do not contain either the requirement to control points plugging or the types of plugging. | Accepted. Technical decision was re-drawn up only under drawings, 21.BU.1ZK1.VE.TM.OK.RDR021, 21.BU.1ZK2.VE.TM.OK.RDR021, 21.BU.1ZB0.VE.TM.OK.RDR002 for the technique of plugging methods. |
| 3 | The type of semi-product (sheet, rolled section etc.) from which the plug was fabricated is not specified in TD (Appendix 1 to TD). Divergence from requirements of Appendix 9 of PNAE G-7-008-89. | Accepted. Appendix 1 was re-drawn up in accordance with the requirement of Appendix 9 of PNAE G-7-008-89, with indication – plug from steel RSt37-2 grade to be manufactured from disc ∅50mm. |
| 4 | Standard under which the flange was manufactured is not specified in TD (Appendix 2 to TD) Divergence from requirements of Section 2 of OST 108.030.124-85. | Not accepted. Justification of NNSD comment rejection is given. |

Manager of subdivision/head of subcontracting organization - (Name, initials, signature).

Developer of technical decision: - (Name, initials, signature).

Appendix 6

- Form of notification on implementation of technical decision

Notification No. _______ dated __________

On implementation of technical decision

Code and registration number of technical decision __________________________

Title of technical decision ______________________________________________

Inventory number of technical decision ___________________________________

| Item No. | Description of activities under the technical decision | Information on performed works | Deadline according to the technical decision | Actual date of implementation |
| --- | --- | --- | --- | --- |

Conclusions (for the notification on implementation) – all activities specified in the technical decision are performed and implemented.

Section Manager (Full name, signature)

Executor: (Full name, telephone number, signature)

Familiarization sheet

| Position | Full name | Signature | Date | Note |
| --- | --- | --- | --- | --- |

Changes registration sheet

| Change No | Number of pages |  |  |  | Total number of pages in the document after updating | Change note No | Signature and full name of the person that updated the document | Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Changed | Replaced | Added | Cancelled |  |  |  |  |

Change familiarization sheet

| Position | Full name | Change No | Signature | Date |
| --- | --- | --- | --- | --- |