## Лист1
| № | Finding code | Finding Description | Finding No. | Related Evidences | Reference Documents |  | Reason of non-conformance | Corrective actions | Responsible for fulfillment, deadline
код | [5 empty] | Name | Item |  | Correction: corrective actions | Responsible: | Deadline: | Actual: | Results of measures:
1 | 1 |  | 7.1 Planning and Time Management
2 | 1 | 1.1 | Except the DTS for Design, which is developed on the bases of MSP software, the other rest of DTS (such as DTS for DD, Licensing, Manufacturing for LMCE, Other Equipment & Delivery) have been developed and controlled based on Excel software. In addition, no evidences were observed to convince Audit Team that they have been agreed by the Principal. Therefore, controlling of the compatibility of the developed DTSs (in excel) level 3 to upper levels IOTS, OTS and GTS is not possible and can be lead to some of the Project risks such as the effect of each risk in each stage of the Project and its strength to other Project stages. In addition, delays on implementation of the DTS for Design & LMCE are happened and existed, but no documented records were observed to convince the Audit Team that necessary root cause analysis as well as specifying their negative impact on other activities and planning of the Project have been done by the Contractor. | NC7. 1.1 |  | App. G to the Contract | G.2.4 | It is not reasonable to develop and maintain DTS for DD and Other Equipment in MSP due to existing limitations of this software. Moreover, such schedules have a standard set of process steps, therefore, it is more preferable to use tabular form. It is reasonable to control collisions of deadlines between DD, equipment time schedules and IOTS in UTS software or in Excel as an option. Delays in fulfillment of ES and completion of handover of ID for design will definitely lead to postponement of NPP construction deadlines. After completion of ES (ESBD-5 stage) it is planned to prepare additional agreement to the Contract for postponement of deadlines of NPP delivery. | Preparation of the corrected version of GTS (Attachment G.A) and additional agreement to the Contract for postponement of deadlines of NPP delivery. | Expert of project management directorate Expert of corporate affairs directorate | 30.11.2019 |  | Letter No. 007/70/08/00225 dated 31.01.2020 was sent to the Principal about fulfillment of requirements of Appendix G. Preparation and submission to the Principal of a version of the schedule of level 0 adjusted for delays is possible after the completion of ES for BD of marine hydraulic structures according to stage ESBD-5 (letters to the Principal No. 007/BU2/02-01/00037 dated 20.02.2018, 007/BU2/02-01/00056 dated 15.03.2018, 007/46-12/02-877 dated 31.05.2018, 007/77/06/00091 dated 19.10.2018, 007/BU2/02-01/000619 dated 05.06.2019, 007/BU2/02-01/000997 dated 21.11.2019, 007/77/06/00328 dated 25.02.2020)
4 | [5 empty] | BU2.0903.0.0.PM.DC0015 | --- | Development and agreement upon schedule of issue and approval of DDD has not been finished | Compensating measures shall be developed and schedules of ES and design activities shall be finalized in WG-1 with the Principal | Design Director | 27.09.2019 |  | Letter has been sent to the Principal "On submission of schedule of DDD of implementation period" No. 007/BU2/02-01/01150 dd. 04.03.2020
7 |  |  |  |  | There were some records related to DTS-P in which delays had been colored by red, but finally cannot be achieved that if ASE has a systematic process to determine strength of these delays and what corrective actions have been done by them and how can be sure that these delays and other similar delays will not be repeated in future. | BU2.0903.0.0.PM.DC0015 | 5.1.8 | Development of schedule of obtaining of registrations, QAP, permits for manufacturing of equipment hasn't been finished | Schedule of obtaining of registrations, QAP, permits for manufacturing of equipment shall be agreed upon with the Principal | Expert of Quality Assurance Directorate Supply Director Head of material support and quality directorate | 30.11.2019 | Constantly. | It is carried out constantly in terms of QAP on a monthly basis. It is agreed with representatives of the Principal in Moscow
8 | [7 empty] | Development of schedule of obtaining of permits for CIW hasn't been finished | Schedule of obtaining of permits for CIW shall be agreed upon with the Principal | Chief expert of scientific-technical support directorate Head of Directorate for project management in Representative Office | 30.11.2019 |  | Fulfilled. Inter-office memo of Head of Directorate for project management in Representative Office No. 007 / 46-07 / 08-8 dated 15.03.2020 (schedule was prepared and submitted to K.V. Mityurev)
9 |  |  |  |  | Time Schedule is developed by the Contractor to control the "Time" in whole the Project Management Documents, but according to the accepted instruction, it has not been submitted to the Principal yet. Based on the accepted documents, it is so important that all DTSs shall be accepted by the Principal, but it has not been done yet. Submitting the Plan with Order № 40/324-P-DCP, 05.03.2019 | BU2.0903.0.0.PM.DC0015 | 5.1.10 | Agreement upon of Schedule of development and approval of PMM documents hasn't been finished | Schedule of development and approval of PMM documents shall be agreed upon with the Principal | Chief expert for standardization project methodology directorate | 30.12.2019 |  | Negotiations with the Principal were not finished about schedule of development and approval of PMM documents
10 | 2 | 1.2 | After updating of the IOTS, no evidence was observed that the Contractor, based on Appendix B of BU2.0903.0.0.PM.DC0015, has completely developed the Analytical Report. | OFI7. 1.1 | --- | BU2.0903.0.0.PM.DC0015 | App. B | Analytical report shall be submitted to the Principal | Analytical report is submitted to the Principal on a monthly basis within the Contractor's Report | Chief specialist of project management directorate Expert of project management directorate | 30.09.2019 | 2019-05-22 | Analytical report is sent monthly to the Principal as part of the Contractor's Report starting from the report as of February 2019 (letter to the Principal 007/70/0800136 dated 22.05.2019)
12 | 4 | 1.4 | The Contractor has not yet provided full facilities and access for the Principal to all detailed planning information, including file of Time Schedule, and to that of its subcontractors, for development and updating of schedules. The Contractor stated that some letters have been submitted to the Principal, but the issue has not been concluded yet. | NC7. 1.3 | --- | App. G to the Contract | G.5.1.1 | Detailed schedules of subcontractors shall be submitted to the Principal | Submission of detailed time schedules of subcontractors to the Principal | Head of representative office in Iran - Construction Director | 30.10.2019 | Fulfilled | Inter-office memo of Head of Directorate for project management in Representative Office No. 007 / 46-07 / 08-8 dated 15.03.2020 (all schedules for all concluded contracts have been sent to the Principal)
13 | [7 empty] | The Parties have approved Time Schedules of 0 and 1 levels as well as TS (level 2, initial period). Time Schedule (level 2) of implementation period hasn't been finalized. Time Schedule (level 2) of implementation period for the Principal's responsibility hasn't been provided | TS (level 2) within the Contractor's responsibility was submitted to the Principal. Finalization of TS (level 2) after provision of information by the Principal | Expert of project management directorate | 30.09.2019 |  | Consideration of schedule (level 2) of implementation period is possible only after submission of significant comments on deadlines and highlighting of such items by the Principal in the schedule (letter to the Principal No. 007/70/08/00239 dated 06.03.2020)
23 | 14 | 1.14 | For planning of detailed design development, a database was shown. Database of Detailed Design development is not comprehensive. | WP7.1.3 | detailed design for the CYB, CXW, GQU, JAJ | App. G to the Contract PMM | G.2.4 5.9 | Development and agreement upon schedule of issue and approval of DDD has not been finished | Schedules of issue and approval of DDD shall be developed and finalized in WG-1 with the Principal | Design Director Deputy design director Chief project engineer | 27.11.2019 | 2020-03-04 | Letter No. 007/BU2/02-01/01150 dated 04.03.2020 was sent to the Principal
24 | 15 | 1.15 | While two different Designers (NE AEP and Moscow AEP) are engaged in the design activities, There is no any link between the design documents development schedules( for TA, Basic Design and Detailed Design), i.e.: for development of Design documents, successors and predecessors have not been defined. Which one company (due to time and financial issues) may develop design documents, while it may not have received the input documents from previous stages for development of such documents. | WP7.1.4 | Two separate and deferent sheets for development of basic design and detailed design have been developed. | App. G to the Contract PMM | G.2.4 5.9 | Development and agreement upon schedule of issue and approval of DDD has not been finished | Schedules of issue and approval of DDD shall be developed and finalized in WG-1 with the Principal | Design Director Deputy design director Chief project engineer | 27.11.2019 | 2020-03-04 | Letter No. 007/BU2/02-01/01150 dated 04.03.2020 was sent to the Principal
25 | 16 | 1.16 | Design work progress report developed by AEP was shown, but for sample taken, the problems and delays was not evidenced. | NC7.1.11 | In the January Work progress report on 20.01.2019, no statement about delay in approval of reactor plant TA was evidenced | App. G to the Contract PMM | G.2 5.9 | Information in the Report isn't complete | Timely and complete information from Design Department shall be submitted for inclusion to the Contractor's Report | Design Director Deputy design director Chief project engineer Leading specialist of project management directorate | 27.09.2019 |  | Information will be taken into account in the report of the Contractor
26 | 17 | 1.17 | For development of detailed design documents, a database was shown but this was not comprehensive. | NC7.1.12 | Following systems were not reflected in the mentioned database. CYB, CXW, UGH | App. G to the Contract PMM | G.2 5.9 | Development and agreement upon schedule of issue and approval of DDD has not been finished | Schedules of issue and approval of DDD shall be developed and finalized in WG-1 with the Principal | Design Director Deputy design director Chief project engineer | 27.11.2019 |  | Letter No. 007/BU2/02-01/01150 dated 04.03.2020 was sent to the Principal
27 | 2 |  | 7.2 Scope Management - Design Management
29 | 19 | 2.2 | Technical characteristics for some of the items have not been stipulated. | WP7.2.1 | Item Nos. 24QKJ01AA184,32JNG66BB003 | Appendix L to the Contract | L.4.8 | [5 empty] | Since deletion of items takes place in the part of the sets to be develeped till agreement with the Principal, then procedure on changes is not applied.
35 | 25 | 2.8 | Since no organizational unit for review, technical check and acceptance of the Developed design documents by AEP has been established in the ASE organization structure for BNPP-2; therefore no such review technical check and acceptance are done on design documents before submission them to Principal; Hence, the Principal always receive some design documents with low quality or those documents which may not be fully in compliance with the contract requirements and agreements as per protocols. | NC7.2.3 | --- | Appendix L to the Contract | L.4.8 Functions of Design Unit |  | Control shall be enhanced | Ответственный блок проектирования: постоянный контроль |  | Fulfilled | Responsible Design Unit
41 | 31 | 2.14 | For sample taken, results of the design control on basic and detailed design was requested, While only the basic design documents, was presented after one day; results of design controls stipulated in MSP (D) were not evidenced. | NC7. 2.4 | Following records was requested for the Basic design and detailed design documents for “water supply and sewerage system of main buildings” and BU2.0130.0.0.AD.TB0001 and BU2.0130.20UQA.0.GR.TB0001, but they have not been evidenced:  Result of control on documents which have been used as input data for development of detailed design document;  control during designing;  output technical inspection;  metrological examination;  assessment of compliance with regulatory documents (normative control);  distribution control;  control over introduction of modifications  analysis;  review;  computational analysis;  Qualification test, Simulation and modeling, mock- up test, walkthrough analysis. | QAP (D) | 9 specially: 9.4.3, 9.4.7, 9.5, 9.7.2/3, | Audit was not conducted in design institute, but in the main office of the Contractor | These documents are available in information exchange | Design Unit: constant control | Design Unit: constant control | Fulfilled | These documents are available in information exchange
42 | 32 | 2.15 | While some changes were shown, but they have not been highlighted. | NC7. 2.5 | BU2.120.20UJA.0.KM.LC0097-CTB0005 | BU2.0130.0.0.PM.DC0001 BU2.0120.0.0.PM.DС0006 |  | Procedure was under correction | The revised procedure shall be submitted to the Principal for approval | department responsible for the procedure | department responsible for the procedure |  | Procedure BU2.0130.0.0.PM.DC0001 has been corrected and sent for approval to the Principal by letter 007/70/07/00213 dated 26.12.2019. An invitation was received to attend the meeting. Due to the complicated situation because of COVID-19, the meeting with the Principal will be scheduled later on.
74 | 5 |  | 7.5 Information Management System
75 | 62 | 5.1 | The Contractor has stopped to enter the information into the IMS software from November 2018. Some technical parts of the IMS (3D) as well as its licensing issue have not yet been solved. The IMS has not yet been running. Some related technical documents have been developed by the Contractor and accepted by the Principal. Therefore, the Contractor shall take necessary actions to solve the problems and obstacles. | NC7. 5.1 |  | … |  | In the course of implementation of IMS the Contractor faced several problems related to the status of the Principal. This was specified in several letters Nos. 007/70/07/00078 dd. 28.11.2018, 007/70/07/00162 dd. 26.07.2019 + letter about "confidential" mark. At that compensatory measures were proposed. They are specified in MoM of WG-9 dd. 18.12.2018 and in letters Nos. 007/70/07/00102 dd. 15.02.2019, 007/70/07/00162 dd. 26.07.2019 The Contractor set up IMS in accordance with the agreed documents and introduced information within its responsibility. However the Principal didn't introduced the respective information to IMS. Therefore IMS was used unilaterally. | Development of IMS on a Russian software. | IT department |  |  | The Contractor continues to develop IMS based on Russian software. The Contractor presented a comparative analysis of ENOVIA and T-FLEX software by letter No. 007/40/433 / BUSH-2/00054 dated 10.03.2020. Setting up IMS based on requirements of the Project by the Contractor’s experts will be continued after the Principal’s approval of DTAs for IMS.
76 | 6 |  | 7.6 Cost Management
78 | 64 | 6.2 | while contract with Advantage (Авантаж) company has been concluded and based on head of supply unit statement, its activities are supervised, but Objective evidences demonstration of payment to the that company for recent months of 2019, was not evidenced. | WP7. 6.1 | Supply portal showed in the head of supply office and Statement of chief expert from corporative issues division |  |  |  |  | Supply Director Expert of corporate affairs directorate |  |  | Payment for the shipped equipment under the contract No. 7717Б2/180597 with LLC Avantazh was made on 04.07.2019. The audit observation regarding the last months of 2019 is not clear.
81 | 7 |  | 7.7 Quality Management - Document and Record Management
82 | 67 | 7.1 | No mechanisms to control and manage the process of identifying, issuance and submitting of the necessary working procedures (safety related), in due time, to the Principal was presented. | NC7. 7.1 | --- | App. R to the Contract | 3.3.8 |  | Record of agreement and development of procedures is kept. Procedures are available upon request of the project participants. | Director for nuclear, radiation, industrial, fire safety, labor protection and environment - Inspector General |  | 2019-12-20 | The mechanism for monitoring and managing the process of determining, issuing and providing the necessary working procedures (related to safety) is regulated by the "Regulation on management of documented information", approved by order No. 40/1689-П dated 20.12.2019 (instead of order No. 40 / 1828-П dated 07.11.2017 "On the entry into force of STO 8841271.030-2017" Management of documented information ")
83 | 68 | 7.2 | Based on the existed objective evidences (such as not finalizing of the PMM, PM Procedures, Design Documents), implementation of the documentation management process to plan and dully develop and issue the documents, with consideration of all related risks, cannot be satisfactory. | OFI7. 7.1 | --- | QAP(G) | 6 | Lack of agreement upon these documents | The Contractor will consider the Principal's comments on these documents. The Parties will agree on these documents. | Head of Project Management Directorate | 2019-12-31 |  | The document was not approved due to the disruption by the Principal of the agreed meeting (letter No. 007/40/433 / BUSH-2/00050 dated 10.11.2019) and the Contractor's impossibiliy to assemble a group of qualified and authorized specialists as the dates of the meeting were not agreed by the parties.
86 | 8 |  | 7.8 Quality Management - Quality Assurance Program
87 | 70 | 8.1 | Due to approval of Appendix R to the Contract and with consideration of approval of the Appendix L to the Contract in closed future, the Contractor shall monitor the necessity revising of the QAP (G). | OFI7. 8.1 | --- | QAP(G) | 1.1.1. |  | As part of conduct of Internal Audit, an analysis of the QAP (G) was carried out for compliance with the requirements of the agreed Appendices R and L to the Contract. The results will be sent to the Principal as part of the quality analysis report in the prescribed manner. | Expert of Quality Assurance Directorate | 2019-11-04
88 | [8 empty] | Ensure the annual analysis of the QAP (G) in the prescribed manner. | Quality Director | 30.04.2020 | 2020-03-03 | Based on the results of the annual QAP (G) analysis, a letter No. 007 / UKS-07/09/00472 dated 03.03.2020 was sent to the Principal. The revision of QAP (G) and its internal approval by the Contractor will be completed by 30.09.2020.
89 | 71 | 8.2 | In spite of some improvement on the process of development and reviewing of the QAPs happened, but delay of the approval of the subcontractors QAPs and the relevant Management Procedures as well as the QPs for Manufacturing Process are still exist. Since, this issue directly led to negative affect on registration of the subcontractors, granting permits process and timely implementation of the Project activities, it is highly recommended to analysis the process and take necessary applicable measures to improve the process. The analysis process shall cover the subcontractor's effort that have the responsibility to develop their relevant documents with the high quality level and based on the requirements up to the Contractor's people who engaged to review the documents. In this regard, providing necessary training to the subcontractor's people and development of some guidelines by the Contractor for them can be useful. | NC7. 8.1 | --- | QAP(G) | 2 | 1) The requirements of the Principal on many issues constitute an “expert opinion”. 2) The actual time for consideration of documentation by the Principal exceeds the time limits specified in Appendix B to the Contract. | Conduct an analysis of the development and review of QAP and QP. According to the results of the analysis: 1) to form a base of requirements to QP and QAP, on the basis of which the documentation will be considered, and provide it to the developers of documents (manufacturers); 2) to develop, agree with the Principal and send to the subcontractors a checklist for checking QP of the subcontractors; 3) to develop and send to subcontractors general requirements to format and content of QAP. | Expert of Quality Assurance Directorate | 21.08.2019 | 2019-08-21 | Fulfilled. QP checklists and QAP requirements were sent to suppliers by letter No. 07-01/8334 dated 21.08.2019
90 | 9 |  | 7.9 Quality Management - Nonconformance Control, Corrective & Preventive Actions
91 | 72 | 9.1 | About the implementation of the Nonconformance Process in the scope of the Contract, it was stated by the Contractor that, collection of information and data, recording, analysis and management of the implementation of the necessary corrective and preventive actions for NCs during the Design Process are being carried out by the main designer and for the Construction Stage are performed by the ASE Directorate for Bushehr NPP Construction. The Contractor ASE Moscow relevant department is performing the same activities for NCs during the Manufacturing Process. | OFI7. 9.1 | No reports from the site are received | App. R to the Contract | R.2.6 |  | Issue an instruction to Quality Director which establishes the procedure for preparation of consolidated reports on quality analysis, including data on non-conformance in the framework of design, construction and manufacture | Head of directorate for non-conformances | 2019-12-20 |  | The order establishing the procedure for preparation of consolidated reports on quality analysis, including data on non-conformities in design, construction and manufacture, is under approval in internal system (EOSDO) (No. 40/50949-ПРОЕКТ-П dated 19.03.2020).
92 |  |  | Due to its importance and probable negative impact of NCs with each other, which can be revealed during Design, Construction or in the Manufacturing Processes, no documented mechanisms were observed to explain how the Contractor in Moscow organizes, communicates, gathers information and data, analysis and manages the implementation of the Nonconformance Process and also in order to ensure that the contents and requirements which are stipulated in MP "Non-conformance control, corrective and preventive actions" (BU2.0903.0.0.QM.QA0009), are being fulfilled by the AEP, Directorate for Bushehr NPP Construction and other manufacturers. So in this regard, development of the documented instruction or procedure is recommended. |  | AEP Report № in the frame of QAR to ASE: RP 4.01.02.09/37-17 MSD of ASE Regulation NCC for Design
94 | 10 |  | 7.10. Quality Management - Assessment
95 | 74 | 10.1 | Management of development of the Quality Analysis Report needs more attention. Reports for 2th and 3th Quarters of 2018 have not been submitted to the Principal. | NC7. 10.1 | No QARs are observed for 2018 second & third Quarters | QAP(G) | 14.1.5 | No responsible person was designated | The report on the quality analysis sent to the Principal includes data on the indicated reports for the 2nd and 3rd quarters with a cumulative total. The report was sent by official letter 007.UKS-07/09/00156 dd. 07.03.2019 | Expert of Quality Assurance Directorate | 2019-08-20 | 2019-03-07 | Performed. Responsible person was designated. The report was sent by official letter 007.UKS-07/09/00156 dated 07.03.2019
96 | [8 empty] | Issue an instruction to Quality Director which establishes the procedure for preparation of consolidated reports on quality analysis and their submission to the Principal | Head of directorate for non-conformances | 20.12.2019 |  | The order establishing the procedure for preparation of consolidated reports on quality analysis, including data on non-conformities in design, construction and manufacture, is under approval in internal system (EOSDO) (No. 40/50949-ПРОЕКТ-П dated 19.03.2020).
97 | [6 empty] | 14.1.6 |  | Check the availability of Quality Analysis Reports during the internal audits of BNPP-2 Project | Head of department for checking management systems | According to schedule of Internal Audit | 2020-03-02 | When conducting an internal audit in the divisions of the Directorate, it is mandatory to check availability of Quality Analysis Reports for the Project.
98 | 75 | 10.2 | There is no mechanism on the ASE BNPP-2 MS to implementation of the related activities to ensure of fully and timely fulfillment of QAP (G) and related MPs requirements. Therefore, no records were observed that the Contractor BNPP-2 Project Managers have analyzed the efficiency of QAP (G) requirements implementation. | NC7. 10.2 | --- | QAP(G) Related MPs | 14.2.1 14.2.2 | The deadline for assessing the effectiveness of QAP (G) has not come | Evaluation of the performance of the QAP (G) is carried out once a year, the results of the evaluation will be presented to the Principal in the report for the 1st quarter of 2020, in accordance with the established procedure. | Quality Director | 2020-04-30 |  | In accordance with the requirements of clause 7.3.13 of STO 8841271.031-2019 “Regulation. Internal audits of the integrated management system” in the course of the internal audit, verification of compliance with QAP requirements is conducted. Performance assessment of QAP (G) is carried out annually (after execution of Schedule for the internal audits of integrated management system for 2020). The results of assessment of effectiveness of QAP (G) can be sent to the Principal only at the end of 2020 (in the report for the 4th quarter of 2020).
99 | 76 | 10.3 | Internal Audit and Assessment Process has not been properly and effectively implemented. In addition, no records were presented that the implementation of the QAP (G) requirements were assessed. Site activities have not yet been assessed. Therefore, this process needs more attention. | NC7. 10.3 | Audit of ASE Representative in Iran and in Site not considered in the related 2018 Plan Internal Audit. | QAP(G) | 14.3 | The decision to postpone the audit was made by management | Include in the Schedule of internal audits of the integrated management system for 2020 an audit of the Representative Office of NPP Project 53, including an assessment of compliance with the requirements of the QAP (G). To approve the Schedule of internal audits of integrated management system for 2020. | Quality Director Head of department for checking management systems | 2019-12-31 | 2019-12-30 | Order of ASE EC JSC dated 30.12.2019 No. 40/1760-P on conducting of internal audits of integrated management system of ASE EC JSC, ASE JSC, Atomenergoproekt JSC and ATOMPROEKT JSC.
100 | [8 empty] | Information on conducted audits of the representative office and site of Project 53 NPP should be included in the quality analysis report. | In accordance with instruction of Quality Director | 2020-12-31
101 | 77 | 10.4 | No evidences were presented that the Contractor has assessed its Subcontractors' and suppliers' Management Systems requirements implementation. | NC7. 10.4 | --- | App. R to the Contract QAP(G) | 2.7 14.2.1 14.2.2 | When preparing schedules of audits, the need to conduct audits on Project 53 was not taken into account | Conduct an analysis of the need to verify compliance with the requirements of the quality assurance programs of subcontractors and suppliers in accordance with Project procedure BU2.0903.0.0.QM.QA0004. Include the necessary checks in the Schedule of audits of suppliers for 2020. | Director for quality of equipment and CIW Director for quality, support and development of Project manufacturing | 2019-12-31
102 | 78 | 10.5 | No evidence was observed that the External Audit of ASE's suppliers and subcontractors has been carried out effectively and comprehensively. Therefore, the Audit Team has not been convinced that the subcontractor's activities in the scope of the Management System and requirements have been controlled by the Contractor. | NC7. 10.5 | -Based on the presented explanations and some Audit Team related observations, it seems that activities related to ensure that all contractual requirements between the Contractor and its subcontractors, are not implemented in a systematic and planned manner and these have been done in the frame of External Audit only on the manager expediency or based on the request of other Project Office Units. | QAP(G) | 14.4 | When preparing schedules of audits, the need to conduct audits on Project 53 was not taken into account | 1. Include in Schedule of internal audits of integrated management system for 2020 an audit of JSC ASE Representative Office. When preparing Audit Program, one of the criteria shall be STO 48546926.032-2018 "Audits of suppliers" and during the audit the organization of work for conducting audits of subcontracting organizations shall be checked in the Representative Office. 2. To include in the Annual schedules of audit of the equipment suppliers, design and survey suppliers, construction and installation suppliers for 2020, performing work / services as part of the work on the construction Project 53, the activities of which may affect safety. | Director for quality, support and development of Project manufacturing Quality Director Director for quality of equipment and CIW | 2019-12-31 |  | 1. JSC ASE representative office for construction of the Project initiated the postponement of the internal audit due to the worsening epidemiological situation because of COVID-19 outbreak by letter No. 007 / 46-11 / 01-872 dated 25.02.2020. Now, amendment to the order on conducting internal audits (No. 40/32815-ПРОЕКТ-П dated 21.02.2020) regarding the postponement to October 2020 of conducting an internal audit of the Representative Office is under approval in internal system (EOSDO).
103 |  |  | For example AEP and Gidropress have not been audited and no request from the Project Team Units to audit of the project subcontractors, were received. |  | -External Audit schedules of sub-contractors have not been submitted to the Principal in advance (Quarterly).
104 |  |  |  |  | Not any record for carrying out the associated Quality Audits to assess the implementation of the safety requirements as well by the Contractor was observed.
105 | 79 | 10.6 | The Contractor has no plan to perform self-assessment on itself, subcontractors, and suppliers and consequently has no information about self-assessment results as well as about improvement plan and the results within the frames of the (annual) Quality Analysis Report have not been sent to the Principal. | NC7. 10.6 | --- | MP Conduct of M. S. Audits BU2.0903.0.0.QM.QA0004 | --- | Absence of procedure on self-assessment | Develop and approve procedure on self-assessment in the format of standard of organization (СТО ПР.8841271 4.23.06-2019) | Quality Director | 2019-09-30 |  | СТО ПР 8841271.4.23.06-2019 "Procedure. Self-assessment of activities for implementation of NPP construction projects" was approved and put into effect by the order of ASE EC JSC dated 06.09.2019 No. 40/1141-П
109 | 12 |  | 7.12 Organization and Project Team Management
113 | 84 | 12.4 | While audit plan had been forwarded to the Auditee one month in advance and in the audit plan has been clearly stipulated that departmental manual (положении по разделения) shall be presented to the audit team, but such documents were not evidence during the audit. | NC7. 12.2 | --- | PLN-4310- 001 | Page 6, item1 | It is not clear for which departments it is necessary to provide documents. | It is necessary to coordinate in advance to which departments of the Contractor it is necessary to send requests, as the Principal's own opinion about the audited department does not always correspond to the functionality of the Contractor's unit. | Head of Project Management Directorate |  |  | All structural divisions of the company have their own regulations
114 | 85 | 12.5 | Since, some of the Contractor's personnel who interviewed during the audit, were not really familiarized with the requirements stipulated in the QAP (G), Safety Policy and some Appendices of the Contract, related to their jobs and duties (such as personnel Management Unit & Safety Management Unit), the Audit Team was not convinced that training plan, refreshment and qualification upgrading for personnel engaged in the BNPP-2 Project, has been effectively and comprehensively implemented by the Contractor. Therefore, the Contractor (Project Team) shall organize and implement the effective training processes to cover all aspects of the requirements, which need to be trained. | NC7. 12.3 | -Personnel Management Unit & Safety Management Unit No documented procedure or plan for execution of the following issues was observed:  Quality Management Documentation;  PM Documentation;  TA for NPP Design;  Safety Analysis Report;  Construction Organization Plan. Quarterly schedule for monitoring of submission and approval of Project Documents was not evidenced. - A plan for development of the documents and submission them to the Principal Unit Dossier was not evidenced. - Evidences for Specifying and reflecting requirements for issuance of documentation, and procedure for making changes in the documents, (including preparation of notifications concerning change, issuance of new revisions of documentation), were not presented | QAP(G) App. B to the Contract | 4.4.15 2 2.2.3.6 2.2.4.2 2.4.1 | Long-term agreement of QAP (G). The Contractor did not have time to train all personnel with this document. | Training on QAP (G) will be organized for employees involved in the implementation of the project | Head of Project Management Directorate | 2 quarter of 2020 |  | Materials were sent to the project participants for self-study. Employees were identified who are ready to provide clarification on the QAP (G)
126 | 14 |  | 7.14 Stakeholder Management
127 | 94 | 14.1 | In spite of specifically written stakeholder issue in the Safety Policy of the Contractor for improvement of the safety subject, no records presented that the Contractor has measured the level of satisfaction of its Key Interested Parties (INRA, Principal, etc.). | NC7. 14.1 | --- | Safety Policy QAP (G) | 15 | [5 empty] | Request was sent to the Principal and response was received.
128 | 95 | 14.2 | No systematic process or developed document was designed and developed in the Contractor BNPP-2 Management System to identify, manage and organize its Stakeholders, their relations and fulfill Key Interested Parties satisfactions. | NC7. 14.2 | the following issues have not been planned and implemented: -Master list of the BNPP-2 Project stakeholders? - A mechanism for ensuring to fulfill the requirements of the Contract, Safety Policy and QAP(G), related to this section. - A mechanism for ensuring that the Principal as the main stakeholder is satisfied or not? Moreover, measuring the Principal's satisfaction level on yearly basis, reflected in the QAR. - The Contractor main strategy for Iranian potential suppliers as the Project Stakeholders - Development a procedure specified in R.A of Appendix R to the Contract in which describes Identification of stakeholders, Management of stakeholder, their Involvement and Monitoring of their involvement. A mechanism for ensuring to identify all possible stakeholders in the Project and present them in the registry, including the name of the organization, the role in the Project and contact details and their register are to be regularly updated during the Project. | App. R to the Contract QAP (G) PMM | R.A. 5.8.3 5.8.4 5.8.5 5.8.6 5.8.7 | The Parties did not agree on a schedule for development of procedures, including the one indicated. Therefore, this document has not been developed. | Agree upon schedule for development of procedures. Agree upon this procedure in accordance with the schedule | Head of Project Management Directorate | 2020 |  | The document is under development. The expected deadline for sending it to the Principal is 2 months after approval of R.A
129 | 15 |  | 7.15 Safety Management
131 | 96 | 15.1 | Due to not existence of following evidences, it can be said that generally, documents, records or objective evidences were not presented to the Audit Team to convince that the requirements stipulated in the Safety Management section of the Appendix R to the Contract, are being well fulfilled. Therefore, it is highly recommended to the Contractor to take necessary prompt corrective actions: | NC7. 15.1 | Knowing and reorganization of the Unit Manager about the document named PSAR and related requirements on development, finalization and fulfillment the stipulated requirements and finally it is not accepting yet. | App. R to the Contract | 3.3.18 |  | Conduct elaboration and unscheduled briefing on Appendix R3 to the Contract with officials of the General Inspector’s unit, Director for Quality of Equipment and CIW, construction site of Project 53 | Head of Representative Office - Director for construction of Project 53 JSC ASE Director for nuclear, radiation, industrial, fire safety, labor protection and environment - Inspector General |  | 2019-10-22 | The study and familiarization of experts of Inspector General with Appendix R3 to the Contract dated 11.11.2014 No. NPP-4100-5500-2.3 was carried out.
132 |  |  |  |  | Periodically Safety Assessment through the implementation of the followings and submitting the results of the implementation of improving plans related to Safety Issues to the Principal:  Assessment of safety requirements;  Quality audits;  Inspections;  Management review;  Review of safety culture;  Safety case review;  Reliability assessment. | App. R to the Contract | 3.4.1 |  | Include in the plan of annual inspections by the Central Office of Project 53 on all issues of safety assessment. Providing the Principal with inspection results upon request | Director for nuclear, radiation, industrial, fire safety, labor protection and environment - Inspector General. |  | 2019-11-28 | Issues of assesmnent for all types of safety are included in the annual inspection plan by the Central Office of Project 53 and are determined by the Rules "Organization and conduct of inspections of safety and quality for safety" RP 3.08.02 / 42-18, approved on 13.04.2018 (The consolidated inspection plan of the State Atomic Energy Corporation Rosatom was approved by No. 1/1295-дсп dd. 27.11.2019)
133 |  |  |  |  | Having any plan and method for ensuring that the Safety Management Process is applied throughout the Project for the following areas of the Safety Management:  Environment protection;  Labor Protection;  Industrial safety;  Fire safety;  Safety and physical protection;  Nuclear safety;  Radiation safety. | PMM | с 5.11.1 по 5.11.7 |  | Development and implementation of process group maps for all areas of Safety | Директор по качеству Director for nuclear, radiation, industrial, fire safety, labor protection and environment - Inspector General. |  | 2019-10-28 | In the central office of JSC ASE EС, JSC ASE, JSC Atomenergoproekt, JSC ATOMPROEKT" map of groups of Safety Management Processes STO KGP 8841271.3.03-2019 was developed and implemented for joint use. The actualization of maps of groups of processes at the construction site was not carried out due to the lack of complete information on the laws of the Principal's country in the field of labor protection and industrial safety, which entails the risk of non-compliance with the relevant requirements of the General Contract, and also complicates the control of execution of safety requirements and contracts for construction and installation work by local subcontractors on the construction site. Requests to the Principal: 1) Letter No. 007 / 46-10 / 02-1510 dated 25.05.2019 to the Principal 2) Repeatedly - Letter No. 007 / 46-10 / 02-1772 dated 19.06.2019"
134 |  |  |  |  | Performing suitable and sufficient assessment of the risks related to safety to ensure that risks are as low as reasonably achievable and the results of Risk Assessment taking into account in the respective safety-related activities and documents by the Contractor, Subcontractors/ sub-suppliers. Elaborating the methods for fulfilling the Risk Management | App. R to the Contract | 3.2.7 |  | The Contractor shall conduct periodic (annual) Risk assessments when preparing safety status reports by type of work | Cost management director |  | 2020-02-28 | The Contractor's conduct of periodic (annually) risk assessments during preparation of safety reports by type of work is regulated by: 1. Risk management policy of JSC ASE EC, approved by order No. 40/1083-П dd. 29.06.2018 2. Organization standard "Procedure for preparing the annual report on assessing the state of safety in engineering division of the State Atomic Energy Corporation "Rosatom" "STO 8841271.061-2017, approved on 11.12.2017 3. Development and approval of annual reports on assessing the state of safety in engineering division of the State Atomic Energy Corporation "Rosatom" (№40/194-П, dd. 08.02.2018, №40/141-П, dd. 07.02.20219, № 40/245, dd. 28.02.2020)
135 |  |  |  |  | requirements by the Contractor in the relevant procedures of the Project Management System and submitting the results to the Principal for consideration and acceptance. |  |  |  | The Contractor shall conduct periodic (annual) Risk assessments when preparing safety status reports by type of work | Cost management director |  | Постоянно | Risk management process is carried out under the approved risk management procedures: BU2.0130.0.0.PM.DC0005 BU2.0130.0.0.PM.DC0009 BU2.0130.0.0.PM.DC0010 BU2.0130.0.0.PM.DC0011 BU2.0130.0.0.PM.DC0012 BU2.0130.0.0.PM.DC0013 BU2.0130.0.0.PM.DC0014 Including risks from the "Safety" category. Detailed analysis of safety risks is being prepared by the safety and inspection control department. For an in-depth risk analysis (in accordance with clause R.3.1.3. Appendix R of contract No. NPP-4100-5500-2.3 of 11.11.2014), regulatory documents of the Principal's country are required. Relevant requests to the Principal were sent in a timely manner. 1) Letter No. 007 / 46-10 / 02-1510 dated 25.05.2019 to the Principal; 2) Repeatedly - Letter No. 007 / 46-10 / 02-1772 dated 19.06.2019; 3) Letter No. 007 / 46-10 / 01-1313 dated 14.05.2019 to the central office of JSC ASE; At the moment (12.03.2020) no response has been received. "
136 |  |  |  |  | Providing any plan for the Risk Assessment which shall be performed in terms of safety (for Safety Risks) by the Contractor or Subcontractors/ Sub-suppliers and submitting the said plans and results of their implementation to the Principal. | App. R to the Contract | 3.2.8 |  | Providing a plan for implementation of activities following the results of periodic Risk assessments | Cost management director
137 |  |  |  |  | Having any records to adherence to safety principles and requirements in Design, maintain the said principles and requirements in Construction and Commissioning period, in order to ensure the safe operation of the Plant during the entire Designed Service life and showing them to the Principal. | App. R to the Contract | 3.2.9 |  | Include in the plan of annual inspections by the Central Office of Project 53 issues of compliance with the requirements of WPP and QAP. Providing the Principal with inspection results upon request | Director for nuclear, radiation, industrial, fire safety, labor protection and environment - Inspector General Head of Representative Office - Director for construction of Project 53 JSC ASE |  | 2019-11-27 | Issues of assessing compliance with the requirements of WPP and QAP are included in the annual inspections plan by the Central Office of Project 53. The consolidated plan of inspection activities of Rosatom State Corporation was approved on 27.11.2019 No. 1/1295-дсп
138 |  |  |  |  | Controlling changes by the Contractor (including through establishing a database) to ensure consistency between and among Design principles and requirements, equipment manufacturing, construction, documents, and physical condition of equipment, systems and Plant. | App. R to the Contract | 3.3.20 |  | Include in the plan of annual inspections by the Central Office of Project 53 issues on checking compliance with design requirements to manufacturing of equipment, the existence of procedures for checking compliance, construction, and the physical condition of equipment. | Director for quality of equipment and CIW Quality Director |  |  | At the moment annual schedule for conducting audits of suppliers to verify compliance with QAP requirements is under development.