**Attachment No. 9 to the Appendix No. 5 to the Supplement No. 10**

Obligations of the Contractor and Requirements

For Equipment installation, adjustment and commissioning at the power unit No. 1 of Bushehr NPP the Contractor shall perform the following obligations and requirements:

1. Prior to Equipment installation, adjustment and commissioning of the Equipment at the power unit No. 1 of Bushehr NPP the Contractor shall perform preparatory works in the following scope:

* According to the Tie-in Design submitted by the Bushehr NPP designer, the Contractor shall allocate the areas intended for laying communication lines of the Equipment across the central hall space (cable trays, availability of free space in cable trays and cable circuits) directly on the power unit No. 1 site of Bushehr NPP;
* According to the Tie-in Design submitted by the Bushehr NPP designer, the Contractor shall allocate the areas for sealed passages and its modules needed for Equipment cables connection (signal and power supply cables) on the power unit No. 1 site of Bushehr NPP;

1. The Contractor shall carry out installation, adjustment and commissioning of the Equipment as per regulations and the rules effective in the Russian Federation (list of regulations and rules is given in Attachment No.10). At the Principal's request the Contractor shall submit some regulations and rules from the list given in Attachment No.10.
2. No later than 2 (two) months before the works start the Parties shall agree the documents required for obtaining a work permit (work licenses, certificates of competence, work permits for operation of lifting mechanisms, electrical safety, the system of permits).
3. The Contractor's specialists will perform installation, adjustment and commissioning of the Equipment, works according to the following schedule: 8-hour working day, 40 hours a week. The work period shall not exceed 30 (thirty) calendar days since the date of the Contractor's specialists arrival for work performance. Herewith, the Contractor's specialists shall follow the workday schedule established by the Principal for the Contractor's specialists within the power unit No. 1 site of Bushehr NPP, as well as internal work order rules (including access mode), safety instructions and other rules they will be familiarized with on the power unit No. 1 site of Bushehr NPP.
4. The Contractor's specialists shall buy at their own expense new kitchen utensils and dishware, if the kitchen utensils and dishware provided to them were damaged or lost.
5. The Contractor's specialists shall buy at their own expense for repair or, if required, shall replace at their own expense furniture, gas and electric equipment, if those provided to him/them were damaged or lost
6. The Contractor shall provide insurance of its specialists (medical insurance and industrial risk and accident insurance) for the period of the specialists residence in the Islamic Republic of Iran.
7. The Contractor's specialists shall observe and respect customs and traditions existing in the Islamic Republic of Iran, shall not participate in political events in the Islamic Republic of Iran, shall follow the rules currently in force in the Islamic Republic of Iran organizations, as well as internal work order rules, safety instructions and other rules they will be familiarized with in the organizations.
8. In case of epidemics, the Contractor's specialists staying in the Islamic Republic of Iran shall observe the instructions issued by state authorities and health authorities of the Islamic Republic of Iran.