**Attachment No. 11 to the Appendix No. 5 to the Supplement No. 10**

The Principal’s obligations on support the Contractor

1. Prior to Equipment installation, adjustment and commissioning of the Equipment at the power unit No. 1 of Bushehr NPP the Principal shall perform preparatory works in the following scope:

* Principal shall examine characteristics of the work station for installation, adjustment and commissioning of the Equipment in the central hall of the Bushehr NPP power unit No. 1 (location, geometrical dimensions, elevations), and inform the Contractor hereof no later than 3 (three) months before the works start;
* Principal performs the placement of the mast at the work site, deactivates the mast as well as to install scaffoldings in order to ensure the performance of work by the Contractor without dismantling the mast;
* Principal shall perform the connection of the cables to the sealed passage modules not later prior 2 (two) days before Equipment adjustment;
* Principal shall complete the work station arrangement in the central hall (scaffolding installation, laying of working fluid feed lines, installation of lighting fixtures, installation of power sources) no later than 2 (two) days before the works start.

1. The Principal will assist the Contractor's specialists who perform inspection, installation, adjustment, commissioning and training of the Principal’s specialists at the power unit No. 1 of Bushehr NPP under the Contract as follows:

* Receipt of an entrance visa to the Islamic Republic of Iran (by sending a letter of invitation to the Islamic Republic of Iran embassy in the Russian Federation);
* Transfer from Imam Khomeini International Airport (the Islamic Republic of Iran, Tehran) to the town of Bushehr, and to the place of residence of Contractor's specialists in Bushehr NPP settlement (or in another place at the Principal's option) and back;
* Provision of places at the residence Bushehr NPP settlement (or in another place at the Principal's option), as well as daily transfer of the Contractor's specialists from the place of residence to the power unit No. 1 site of Bushehr NPP and back. The residence will be fitted with furniture and electric appliances, bedroom accessories and kitchen utensils as well as bathroom accessories. Catering services for the Contractor's specialists in the Bushehr NPP settlement (or in another place at the Principal's option), and on the power unit No. 1 site of Bushehr NPP;
* As required, pursuant to the Contract provisions, granting access to international telephone and telefax communication, copying and printing appliances, providing the possibility of working with the computer on the power unit No. 1 site of Bushehr NPP for the Contractor's specialists subject to the terms agreed with the Principal;
* As required, administrative support to get emergency medical services for the Contractor's specialists in case of sudden acute diseases, states, aggravation of chronic diseases posing life hazard, as well as special emergency medical services rendered in case of diseases, accidents, injuries, intoxication and other states which require urgent medical intervention at medical institutions of the Islamic Republic of Iran;
* Should any Contractor's specialist die during residence in the Islamic Republic of Iran, all formal matters shall be resolved including repatriation of remains of the Contractor's specialist;
* Rendering of miscellaneous potential services related to the works performed by the Contractor's specialists;

The Principal shall pay for the above listed services (including utility costs related to residence in the provided apartments, and payment for such services as electric energy, water, housecleaning and cleaning the territory around the house, garbage and domestic waste disposal, etc). If payment is made by the Contractor, the Contractor is obliged to compensate the documented expenses to the Contractor. The compensation period is 1 (one) month maximum since the date of confirming documents submission by the Contractor to the Principal.

1. The Principal shall provide administrative support of Equipment inspection, installation, adjustment and commissioning as well as training on the power unit No. 1 site of Bushehr NPP as follows:

* Familiarizing the Contractor's specialists (prior to the works start) with safety rules and occupational safety rules effective on the power unit No. 1 site of Bushehr NPP, the workday schedule, internal work order rules;
* Accommodating the Contractor's specialists in sanitary inspection rooms;
* Granting access for the Contractor's specialists to NPP and the NPP areas allocated for the works, specifying designated walking routes on the power unit No. 1 site of Bushehr NPP, and provision of safe labor conditions for the Contractor's specialists so that they could meet their obligations under the Contract;
* Supervision of the working conditions by the Principal's specialists (and/or Bushehr NPP specialists);
* Provision of catering facilities for the Contractor's specialists at lunch time;
* Provision (on a temporary basis) of the necessary personal protection means (helmets, workwear, footwear, etc) and personal hygiene products by the Principal to the Contractor's specialists at their work stations according to the procedure effective on the power unit No. 1 site of Bushehr NPP;
* As required, provision of computers to the Contractor's specialists subject to the terms agreed with the Principal on the power unit No. 1 site of Bushehr NPP;
* As required, granting access for the Contractor's specialists to the technical documentation closely related to the works performed by the Contractor’s specialists.