## IRA2012_May 2017
IRA2012: Action Plan for implementation of Workplan activities in 2014-2017
as of 15.05.2017
Increasing NPPD's Capability in Planning and Implementing Activities Related to Design and Construction of Two New Pressurized Light Water NPP Units in Bushehr with Emphasis on Safety
No. | Activity | Input | Implementing Officers | Resource | Cost | Venue | Type | Funding | Budget | Budget Year | Date | Changed Date | Status | Priority | Comments
1.2 Conducting project review meetings
1 | 1.2.1 | Annual project review and planning meeting 2014 | IAEA: Gueorguiev, NPPD: Fatourechian | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM | FootNote | 39,195 | 2012 | Q1/2014 |  | Completed
2 | 1.2.2 | Annual project review and planning meeting 2015 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2015 |  | Completed, 15-17 February 2015 in Tehran
3 | 1.2.3 | Annual project review and planning meeting 2016 |  | 3 IAEA staff for 3 days |  | Tehran and Bushehr | EM |  |  |  | Q1 2016 |  | Completed 29 February - 2 March
4 | 1.2.4 | Annual project review and planning meeting will be joint with IRA/2012, IRA/2013, IRA/9023 and IRA/9024 Annual meeting. |  |  |  | Tehran | EM |  |  |  | Q1 2017 |  | Completed |  | 14-15 Feb 2017 as agreed date
1.5 IAEA field monitoring
5 | 1.5.1 | Reqular field monitoring and review missions | IAEA: Gueorguiev, NPPD: Fatourechian | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2014 |  | Completed
6 | 1.5.2 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2015 |  | Completed
7 | 1.5.3 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Tehran and Bushehr | Meeting |  |  |  | 2016 |  | Completed |  | 1-2 missions per quarter jointly with IRA2013
8 | 1.5.4 | Reqular field monitoring and review missions |  | 1 IAEA staff for 4 days |  | Vienna | Meeting | FootNote | 21,000 | 2012 | 2017 |  |  |  | 1-2 missions per quarter jointly with IRA2013
2.2 Spent fuel storage and waste management programs
9 | 2.2.1 | EM to assist in radioactive waste management programme, including scaling factor application | IAEA:Ormai/Dyck, NPPD:Sheikholeslami | 1 IAEA staff and 3 IEX |  | Tehran | EM | FootNote | 3,095 | 2012 | 27 Sept - 1 Oct 2014 |  | Jointly with IRA2011/1.17.3 Completed
10 | 2.2.2 | EM to assist in spent fuel storage | IAEA: C. Hill NPPD: Derakhahandeh | 1 IAEA staff and 3 IEX |  | TBD | EM |  |  |  | Q2/2018- Shifted to New Project |  |  | H | Follow-up mission under 2011. Postpone to New Project.NPPD will elaborate its need 2 months in advance.
3.1 Development of training materials for two new NPP projects
11 | 3.1.1 | EM to assist in review of selected/developed training materials for future operatorsfor two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | Q4/2017 |  | To be implemented on the developed materials provided by the supplier of two new units | H | Move to the new Project 2018-2019
12 | 3.1.2 | EM to assist in review of selected/developed training materials for future operators for two new NPP units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | FootNote | 16,725 | 2012 | Q4/2017 |  | To be implemented on the developed materials provided by the supplier of two new units | H | merged with 3.1.1, Move to the new Project 2018-2019
3.2. Risk management during preconstruction and construction phases of an actual nuclear power plant
13 | 3.2.1. | WS on knowledge and risk management during preconstuction and construction phase of PWR with focus on safety | IAEA: Kang, NPPD: Tajbakhsh | 1 IAEA staff and 2 IEX for 4 days |  | Tehran Bushehr | WS | HardCore | 21,000 | 2012 | 27-30 April 2014 |  | Completed
5.1 Safety and quality requirements in construction of new PWR units at Bushehr by participating local organizations
14 | 5.1.1 | WS To assist in development of the Local Industry Utilization Plan | IAEA: Kang NPPD: Derakhshandeh | 1 IAEA staff and 2 IEX for 3 days |  | Tehran | WS | FootNote | 21,000 | 2012 | 25-27 Nov. 2017 |  | In progress | M
6.1 Public information and awareness programmes development
15 | 6.1.1 | WS on public information and awareness programmes | IAEA:B. Pagannone/ NPPD:Rahnama | 4-6 NEX and 2 IEX |  | Tehran | WS | FootNote | 16,350 | 2012 | 28 Sept-1 Oct 2014 |  | Completed
16 | 6.1.2 | EM to assist on the establishment of public information and awareness centre | IAEA: M. Van Sickle, NPPD: Rahnama | 1 IAEA staff and 2 IEX |  | Tehran/Bushehr | EM |  |  |  | Q3/2017 |  |  | M | NPPD is requested to send the IAEA two months before the draft plan/status description for the Centre.
17 | 6.1.3 | EM to review results of Stakeholder Involvement Plan | IAEA: M. Van Sickl, NPPD: Rahnama | TBD |  | Tehran | EM |  |  |  | Q3/2017 |  |  | M | Additional request as follow-up of 6.1.1. New request. Merged with 6.1.2
| 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: M. Van Sickl, NPPD: Rahnama | 3NEX |  | TBD | SV |  |  |  | Q4/2017 |  |  | M | NFs will send by end of June.
| 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: M. Van Sickl, NPPD: Rahnama | 3NEX |  | TBD | SV |  |  |  | Q4/2017 |  |  | M | NFs will send by end of June.
18 | 6.1.4 | SV on benchmarnig on stakeholder involvement | IAEA: M. Van Sickl, NPPD: Rahnama | 3NEX |  | TBD | SV |  |  |  | Q4/2017 |  |  | M | NFs will send by end of June.
2.1 Seismic safety assessment
19 | 2.1.1 | EM to assist in seismic safety assessment | IAEA:Y.Fukushima, NPPD: Shirzadi/Derakhshandeh | 1 IAEA staff and 3 IEX |  | Tehran / Bushehr | EM | FootNote | 40,095 | 2013 | 1-4 october 2016 | 1-4 October, Planned Implementation | Completed | H
20 | 2.1.2 | WS/EM on seismic safety | IAEA:Y.Fukushima, NPPD: Tourafshan/Derakhshandeh | TBD ( 4 days) |  | Tehran | WS/EM |  |  |  | Q3/2017 |  |  | M | Considering the EMR on 2.1.1, NPPD will define the scope of needs for further proceed.
3.3 Corporate knowledge management
21 | 3.3.1 | EM on corporate knowledge management for BNPP - 2&3 with focus on safety | IAEA:Z. Pasztory NPPD:Rahnama/Sheikholeslami | 1 IAEA staff and 3 IEX, 4 days |  | Tehran | EM | FootNote | 7,805 | 2013 | 15-18 Nov. 2015 |  | Completed
22 | 3.3.2 | EM on Management and maintaining design basis information through life cycle of BNPP-2&3 | IAEA:J. de Grosbois, Kolomiets 1 IAEA staff and 3IEX | I IAEA + 2 IEX |  | Tehran | EM |  |  |  | 21-25 April 2016 (3 days) |  | Completed
3.4 Nuclear material accounting and control during preoperational phases of two new PWR units in Bushehr
23 | 3.4.1 | WS on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (cancelled) | [5 empty] | FootNote | 22,275 | 2013 |  |  | NPPD does not need further assistance
24 | 3.4.2 | SV on nuclear material accounting and control during preoperational phases of the two new PWR units in Bushehr (SG) | IAEA: M. Mishar, SG NPPD: NPPD:Amini | 3NEX |  | TBD | SV |  |  |  | 2016 |  | Cancelled | H | NFs to be provided timely in advance
4.4 Human Resource Development (HRD) and Work Force Planning (WFP) programmes for the two new PWR units in Bushehr
25 | 4.1.1 | EM to assist in evaluation of developed programmes for updation owner's training system for the two new PWR units | IAEA: Drury, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD | HardCore | 27,875 | 2013 | Q2/2017 |  |  | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. Jointly with 4.2.1 New task (Possible home based assignment), Move to the new project 2018-2019
26 | 4.1.2 | EM to assist in evaluation of developed programmes to update owner's training system for the two new PWR units | IAEA: Drury, NPPD: Rahnama/Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | HBA/EM TBD |  |  |  | Q2/2017 |  | To be moved to 2018-2019, new project | H | Specific needs to be provided by NPPD on the basis of the contract for two new units. New task
27 | 4.1.3 | Group Trainig programme on pre-construction management with focus on safety requirements | IAEA: Kang; NPPD: Fatourechian | 1 IAEA Staff, 20 NEX |  | ICTC, Beijing, China | WS |  |  |  | 24 Aug.-4 Sept. 2015 |  | Completed
28 | 4.1.4 | EM to assist in development of comprehensive model for effective project management of the two new NPP units (1 + 3 IEX) | IAEA: Pekka Pyy. NPPD: Rahnama | 1 IAEA Staff and 3 IEX |  | Tehran | EM |  |  |  | 8-11 Nov. 2015 |  | Completed
29 | 4.1.5 | Group Fellowship Trainig on construction and commissioning management with focus on safety requirements | IAEA: K. S. Kang NPPD: Fatourechian/Rahnama | 2 IAEA staff and 20 NEX. The cost for the WS is expected cca. 100 000 EURs. |  | S. Korea | Group fellowship training |  |  |  | Q4/2017- Q1/2018 |  |  | H
30 | 4.1.6 | EM to assist in the review of the developed Project Management System for units 2 and 3 of the new project. | IAEA: Pekka Pyy. NPPD: Fatourechian/Rahnama | 1 IAEA/3 IEX 4 days. |  | Tehran | EM |  |  |  | Q3 /2017 |  |  | H | NPPD combine it with 3.1.1
4.2 Review and evaluation of the developed programme for upgrading owner's training system for the new NPP units
31 | 4.2.1 | EM to assist in review and evaluation of the developed programme for upgrading owner's training system for the two new PWR units | IAEA: D. Drury NPPD: Fatourechian | 1 IAEA staff and 3 IEX |  | TBD | EM and HBA | FootNote | 13,365 | 2013 | Q2/2017 |  |  | H | Jointly with 4.1.1
Cancelled
Further clarifications needed
| Completed | [9 empty] | 10 active tasks
| Move to new project (2018-2019) |  |  |  | H=5,M=5