## RU
График устранения замечаний к документам, необходимых для лицензии
Schedule of resolving the INRA/NNSD comments on the documents required for obtaining the Bushehr-2 Unit 2 Construction License
№ п/п | Наименование документа |  | Замечания NNSD | Ответы на замечания NNSD
|  | Documents | NNSD comments | Contractor's answers
1 | ПООБ (PSAR) Глава 1 | Preliminary Safety Analysis Report (PSAR) Chapter 1 |  | Reply to the comments and implement the document upto 6 month after reciving comments
2 | ПООБ (PSAR) Глава 2 | Preliminary Safety Analysis Report (PSAR) Chapter 2 |  | Reply to the comments and implement the document upto 6 month after reciving comments
3 | ПООБ (PSAR) Глава 3 | Preliminary Safety Analysis Report (PSAR) Chapter 3 |  | Reply to the comments and implement the document upto 6 month after reciving comments
4 | ПООБ (PSAR) Глава 4 | Preliminary Safety Analysis Report (PSAR) Chapter 4 | comments have been received | Most of the NNSD comments are not replied. It should be considered to reply and implement the document up to 6 months after receiving construction license
5 | ПООБ (PSAR) Глава 5 | Preliminary Safety Analysis Report (PSAR) Chapter 5 |  | Reply to the comments and implement the document upto 6 month after reciving comments
6 | ПООБ (PSAR) Глава 6 | Preliminary Safety Analysis Report (PSAR) Chapter 6 | comments have been received | Some of the NNSD comments are not replied. It should be considered to reply and implement the documentto up to 6 months after receiving construction license
7 | ПООБ (PSAR) Глава 7 | Preliminary Safety Analysis Report (PSAR) Chapter 7 |  | Reply to the comments and implement the document upto 6 month after reciving comments
8 | ПООБ (PSAR) Глава 8 | Preliminary Safety Analysis Report (PSAR) Chapter 8 |  | Reply to the comments and implement the document upto 6 month after reciving comments
9 | ПООБ (PSAR) Глава 9 | Preliminary Safety Analysis Report (PSAR) Chapter 9 |  | Reply to the comments and implement the document upto 6 month after reciving comments
10 | ПООБ (PSAR) Глава 10 | Preliminary Safety Analysis Report (PSAR) Chapter 10 |  | Reply to the comments and implement the document upto 6 month after reciving comments
11 | ПООБ (PSAR) Глава 11 | Preliminary Safety Analysis Report (PSAR) Chapter 11 |  | Reply to the comments and implement the document upto 6 month after reciving comments
12 | ПООБ (PSAR) Глава 12 | Preliminary Safety Analysis Report (PSAR) Chapter 12 | comments have been received | Some of the NNSD comments are not replied. It should be considered to reply and implement the document upto 6 months after receiving construction license
13 | ПООБ (PSAR) Глава 13 | Preliminary Safety Analysis Report (PSAR) Chapter 13 | comments have been received | Some of the NNSD comments are not replied. It should be considered to reply and implement the document in 3 months after receiving construction license
14 | ПООБ (PSAR) Глава 14 | Preliminary Safety Analysis Report (PSAR) Chapter 14 |  | Reply to the comments and implement the document upto 6 month after reciving comments
15 | ПООБ (PSAR) Глава 15 | Preliminary Safety Analysis Report (PSAR) Chapter 15 | comments have been received | Reply to the comments and implement the document upto 6 month after reciving Construction License
16 | ПООБ (PSAR) Глава 16 | Preliminary Safety Analysis Report (PSAR) Chapter 16 |  | Reply to the comments and implement the document upto 6 month after reciving comments
17 | ПООБ (PSAR) Глава 17 | Preliminary Safety Analysis Report (PSAR) Chapter 17 | comments have been received | replies were submitted
18 | ПООБ (PSAR) Глава 18 | Preliminary Safety Analysis Report (PSAR) Chapter 18 | comments have been received | None of the NNSD comments are replied. It should be considered to reply and implement the document up to 6 months after receiving construction license
19 | ПООБ (PSAR) Глава 19 | Preliminary Safety Analysis Report (PSAR) Chapter 19 |  | Reply to the comments and implement the document upto 6 month after reciving comments
20 | ПООБ (PSAR) Глава 20 | Preliminary Safety Analysis Report (PSAR) Chapter 20 |  | Reply to the comments and implement the document upto 6 month after reciving comments
21 | ПООБ (PSAR) Глава 21 | Preliminary Safety Analysis Report (PSAR) Chapter 21 | comments have been received | replies were submitted
22 | Программа обеспечения качества при сооружения АЭС (ПОКАС(С)) и процедуры системы менеджмента, относящиеся к качеству и безопасности сооружения | Management system Programme for Construction | comments have been received | end of february
23 | Управление несоответствиями при выполнении СМР и оказании услуг по проекту | Non-conformances management at BNPP-2 Site upon construction - installation and commissioning works |  | Reply to the comments and implement the document upto3 month after reciving comments
24 | Несоответствия, корректирующие и предупреждающие мероприятия | Non-conformances, Corrective and Preventive Measures |  | Reply to the comments and implement the document upto3 month after reciving comments
25 | Выдача предписаний на остановку строительных и монтажных работ | Issue of prescriptions for stoppage of construction and installation works |  | Reply to the comments and implement the document upto3 month after reciving comments
26 | Обращение, хранение и транспортировка элементов | Handling, storage and transportation of elements |  | Reply to the comments and implement the document upto3 month after reciving comments
27 | Порядок выполнения и контроля работ по проверке средств измерения и испытательного оборудования | Procedure of implementation and verification of measurement instruments and test equipment |  | Reply to the comments and implement the document upto3 month after reciving comments
28 | Управление контролием и испытаниями при проведении СМР | Inspection and tests management during CIW implementation |  | Reply to the comments and implement the document upto3 month after reciving comments
29 | Идентификация и контроль | Identification and inspection |  | Reply to the comments and implement the document upto3 month after reciving comments
30 | Обеспечение сохранности оборудования в процессе производства СМР | Assurance of equipment preservation during CIW implementation |  | Reply to the comments and implement the document upto3 month after reciving comments
31 | Контроль специальных технологических процессов | Special process monitoring |  | Reply to the comments and implement the document upto3 month after reciving comments
32 | Требования к субподрядчикам, процедура проверки на этапе СМР | Requirements to subcontractors, procedure of their selection and check at CIW stage |  | Reply to the comments and implement the document upto3 month after reciving comments
33 | Надзор подрядчика за субподрядчиками на площадке сооружения АЭС на этапе СМР | The Contractor’ Supervision over subcontractors within the Bushehr-2 NPP Site boundaries and beyond it |  | Reply to the comments and implement the document upto3 month after reciving comments
34 | ТЗ по проекту системы физической защиты | Technical Assignment on design of physical protection system | comments have been received | Some of the NNSD comments are not replied. It should be considered to reply and implement the document up to 6 months after receiving construction license
35 | ВАБ Уровень 1 | PSA level 1 |  | Reply to the comments and implement the document upto 6 month after reciving comments
36 | ВАБ Уровень 2 | PSA level 2 |  | Reply to the comments and implement the document upto 6 month after reciving comments
37 | ВАБ – сейсмика | PSA on seismic |  | Reply to the comments and implement the document upto 6 month after reciving comments
38 | ВАБ по противопожарной защите | PSA on fire |  | Reply to the comments and implement the document upto 6 month after reciving comments
39 | Программа и график подбора, подготовки и аттестации персонала для эксплуатации и техобслуживания АЭС | Programme and schedule for recruiting, training and qualifying staff for Operation and Maintenance of Bushehr-2 NPP |  | Reply to the comments and impliment the document upto 6 month after reciving comments
40 | Описание полномасштабного тренажера | Description of full-scaled simulator |  | Reply to the comments and implement the document within 3 months after receiving Construction License
41 | Предварительное описание аварийной готовности и реагирования | Preliminary description of the Emergency Preparedness and Response | comments have been received | Some of the NNSD comments are not replied. It should be considered to reply and implement the document up to 3 months after receiving construction license
42 | Концептуальный план управления старением | Conceptual Plan for Ageing Management | comments have been received | None of the NNSD comments are replied. It should be considered to reply and implement the document up to 6 months after receiving construction license
43 | Концептуальный план техобслуживания, надзора и эксплуатационного контроля | Conceptual plan for maintenance, surveillance, and in-service inspections |  | Reply to the comments and implement the document upto 6 month after reciving comments
44 | Предварительный План по выводу из эксплуатации | Preliminary Plan for decommissioning |  | Reply within 3 months after receiving Construction License
45 | Учет в проекте крупномасштабных природных явлений/катастроф и террористических атак -аспекты сооружения | Design Considerations against Large Scale Natural Phenomena/Disasters and Terrorist Attacks -Construction aspects | comments have been received | Some of the NNSD comments are not replied. It should be considered to reply up to 3 months after receiving construction license
46 | Учет в проекте крупномасштабных природных явлений/катастроф и террористических атак -аспекты эксплуатации | Design Considerations against Large Scale Natural Phenomena/Disasters and Terrorist Attacks -Operation aspects |  | Reply to the comments and implement the document upto 6 month after reciving comments
47 | Учет в проекте потери конечного поглотителя тепла | Design Considerations against Loss of Ultimate Heat Sink |  | Reply to the comments and implement the document upto 6 month after reciving comments
48 | Учет в проекте потери электроснабжения. | Design Considerations against Loss of Electrical Power | comments have been received | april of 2020
49 | Конструктивные меры от тяжелых аварий, включая меры по подавлению распространения радиоактивных материалов, меры по предотвращению отказа корпуса контейнмента и меры по предотвращению повреждения активной зоны (постулированные множественные отказы). | Engineering Measures against Severe Accidents including measures to suppress radioactive materials dispersion, measures to prevent containment vessel failure, and measures to prevent core damage | comments have been received | april of 2020
50 | Конструктивные меры и реагирование в случае крушения коммерческого самолета | Engineering Measures and Response against Commercial Aircraft Crash | comments have been received | Some of the NNSD comments are not replied. It should be considered to reply and implement the document up to 3 months after receiving construction license

## Лист2
№ п/п | Наименование документа |  | Ответственный | Разработка | Передача документа Заказчику | Согласование |  |  | Утверждение
|  |  |  | Окончание разработки |  | Рассмотрение заказчиком | Устранение замечаний | Повторное согласование | Финальное оформление (бумажная версия) | Передача документа Заказчику
|  |  |  | дата | 2 дня | 21 день | 21 день | 5 дней | 7 дней | 7 дней
1 | Предварительный отчет по обоснованию безопасности (PSAR) |  | Подрядчик | 2018-02-20 | 2018-03-23 | 2018-04-21 | 2018-05-25 | 2018-06-01 | 2018-06-08 | 2018-07-06
2 | Документы по проекту системы физической защиты |  | Подрядчик | 2018-02-20 | 2018-03-23 | 2018-04-21 | 2018-05-25 | 2018-06-01 | Документ дорабатывается Заказчиком | 2018-09-30
3 | 4.1 | ВАБ Уровень 1 | Подрядчик | 2018-02-20 | 2018-03-23 | 2018-04-21 | 2018-05-25 | 2018-06-01 | 2018-06-08 | 2018-07-06
| 4.2 | ВАБ Уровень 2 |  | 2018-02-20 | 2018-03-23 | 2018-04-21 | 2018-05-25 | 2018-06-01 | 2018-06-08 | 2018-07-06
| 4.3 | ВАБ – сейсмика |  | 2018-02-20 | 2018-03-23 | 2018-04-21 | 2018-05-25 | 2018-06-01 | 2018-06-08 | 2018-07-06
| 4.4 | ВАБ по противопожарной защите |  | 2018-02-20 | 2018-03-23 | 2018-04-21 | 2018-05-25 | 2018-06-01 | 2018-06-08 | 2018-07-06
4 | Описание полномасштабного тренажера |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
5 | Предварительный План вывода из эксплуатации |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
6 | Учет в проекте крупномасштабных природных явлений/катастроф |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
- аспекты сооружения
| - аспекты эксплуатации |  |  | 2018-03-28 |  | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
7 | Учет в проекте потери конечного поглотителя тепла |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
8 | Учет в проекте потери электроснабжения. |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
9 | Конструктивные меры от тяжелых аварий, включая меры по подавлению распространения радиоактивных материалов, меры по предотвращению отказа корпуса контейнмента и меры по предотвращению повреждения активной зоны (постулированные множественные отказы). |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
10 | Конструктивные меры и реагирование в случае крушения коммерческого самолета |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
11 | Программа и график подбора, подготовки и аттестации персонала для эксплуатации и техобслуживания АЭС «Бушер-2» |  | Подрядчик | 2018-05-29 | 2018-06-20 | 2018-07-11 | 2018-08-02 | 2018-08-08 | 2018-08-15 | 2018-09-12
12 | Концептуальный план управления старением |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
13 | Концептуальный план техобслуживания, надзора и эксплуатационного контроля |  | Подрядчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | 2018-06-18 | 2018-07-18
14 | Отчет о ходе выполнения сооружения |  | Подрядчик | дата | 2018-09-15 | 2018-09-22 | 2018-09-25 | 2018-09-30 | 2018-09-30 | 2018-09-30
15 | Программа обеспечения качества при сооружения АЭС (ПОКАС(С)) и процедуры системы менеджмента, относящиеся к качеству и безопасности сооружения |  | Подрядчик | Выполенено | ПОКАС(С) на согласовании, указать дату | дата | дата | дата | дата | дата
15.1 | Управление несоответствиями при выполнении СМР |  | Подрядчик | дата | 2018-04-01 | 2018-04-30 | 2018-05-12 | 2018-05-15 | 2018-05-21 | дата
15.2 | Несоответствия, корректирующие и предупреждающие мероприятия |  | Подрядчик | дата | 2018-06-10 | дата | дата | 2018-07-25 | 2018-08-01 | дата
15.3 | Выдача предписаний на остановку строительных и монтажных работ |  | Подрядчик | дата | 2018-04-01 | 2018-04-30 | дата | 2018-05-15 | 2018-05-21 | дата
15.4 | Обращение, хранение и транспортировка элементов |  | Подрядчик | дата | 2018-04-30 | 2018-05-30 | 2018-06-10 | 2018-06-15 |  | дата
15.5 | Порядок выполнения и контроля работ по проверке средств измерения и испытательного оборудования |  | Подрядчик | дата | 2018-07-25 | дата | дата | 2018-07-30 | дата | дата
15.6 | Управление контролием и испытаниями при проведении СМР |  | Подрядчик | дата | 2018-09-10 | дата | дата | 2018-09-10 | дата | дата
15.7 | Идентификация и контроль |  | Подрядчик | дата | 2018-09-15 | дата | дата | 2018-10-30 | дата | дата
15.8 | Обеспечение сохранности оборудования в процессе производства СМР |  | Подрядчик | дата | 2018-07-25 | дата | дата | 2018-09-10 | 2018-09-17 | дата
15.9 | Контроль специальных технологических процессов |  | Подрядчик | дата | 2018-06-25 | дата | дата | 2018-08-10 | 2018-08-15 | дата
15.10 | Требования к субподрядчикам, процедура проверки на этапе СМР |  | Подрядчик | дата | 2018-04-25 | дата | дата | 2018-06-10 | 2018-06-17 | дата
16 | Предварительное описание аварийной готовности и реагирования |  | Подрядчик/Заказчик | 2018-03-28 | 2018-04-20 | 2018-05-13 | 2018-06-04 | 2018-06-10 | Документ дорабатывается Заказчиком | Требуется согласование с Заказчиком
17 |  |  | Заказчик
18 |  |  | Заказчик
19 |  |  | Заказчик
20 |  |  | Заказчик

## EN
Schedule for development and approval of documents for obtaining the Bushehr-2 NPP Construction License
№ | Documents |  | Principal's Comments | Contractor's answers | Principal's Comments to answers | Contractor's answers | Submission to INRA | Contractor's answers | Approval by INRA
1.1. | Preliminary Safety Analysis Report (PSAR) Chapter 1 |  | 4300-99738 dd. 22.09.2018 |  |  |  | 2018-12-09 |  | 2019-04-20
1.2. | Preliminary Safety Analysis Report (PSAR) Chapter 2 | [5 empty] | 2018-12-09 |  | 2019-04-20
1.3. | Preliminary Safety Analysis Report (PSAR) Chapter 3 |  | 4300-99052 dd 29.08.2018 4300-99862 dd. 24.09.2018 |  |  |  | 2018-12-09 |  | 2019-04-20
1.4. | Preliminary Safety Analysis Report (PSAR) Chapter 4 |  | 4300-95710 dd 03.06.2018 | №007/BU2/02-01/00206 dd 15.08.2018 | 4300-100637 dd 13.10.2018 |  | 2018-12-09 |  | 2019-04-20
1.5. | Preliminary Safety Analysis Report (PSAR) Chapter 5 |  | 4300-97993 от 04.08.2018 4300-102993 dd 09.12.2018 | 007/BU2/02-03/00335 dd 13.12.2018 | 4300-104046 |  | 2018-12-09 |  | 2019-04-20
1.6. | Preliminary Safety Analysis Report (PSAR) Chapter 6 |  | 4300-96476 от 25.06.2018 | 007/BU2/02-01/00248 от 20.09.2018 | 4300-101139 от 23.10.2018 4300-103648 dd 24.12.2018 |  | 2018-12-09 |  | 2019-04-20
1.7. | Preliminary Safety Analysis Report (PSAR) Chapter 7 | [5 empty] | 2018-12-09 |  | 2019-04-20
1.8. | Preliminary Safety Analysis Report (PSAR) Chapter 8 |  | 4300-96318 dd 21.06.2018 | 007/BU2/02-01/00306 dd 26.11.2018 | 4300-103993 dd 31.12.2018 |  | 2018-12-09 |  | 2019-04-20
1.9. | Preliminary Safety Analysis Report (PSAR) Chapter 9 |  | 4300-100865 dd 16.10.2018 | till 25.01.2019 |  |  | 2018-12-09 |  | 2019-04-20
1.10. | Preliminary Safety Analysis Report (PSAR) Chapter 10 |  | 4300-91374 4300-92394 4300-93503 4300-95913 | 007/BU2/40-41/00117 dd 03.10.2018 | 4300-104012 dd 01.01.2019 |  | 2018-12-09 |  | 2019-04-20
1.11. | Preliminary Safety Analysis Report (PSAR) Chapter 11 |  | 4300-95887 dd 11.06.2018 4300-101675 dd 10.11.2018 | 007/BU2/02-01/00262 dd 05.10.2018 007/BU2/02-01/00264 | 4300-101228 dd 27.10.2018 |  | 2018-12-09 |  | 2019-04-20
1.12. | Preliminary Safety Analysis Report (PSAR) Chapter 12 |  | 4300-96317 dd 21.06.2018 | 007/BU2/02-01/00256 dd 03.10.2018 |  |  | 2018-12-09 |  | 2019-04-20
1.13. | Preliminary Safety Analysis Report (PSAR) Chapter 13 |  | 4300-84839 dd 16.07.2017 4300-119615 dd 23.12.2017 4300-96120494 dd 07.03.2018 | 007/BU2/02-01/8474 dd 13.11.2017 007/BU2/02-01/00090 dd 09.04.2018 |  |  | 2018-12-09 |  | 2019-04-20
1.14. | Preliminary Safety Analysis Report (PSAR) Chapter 14 |  | 4300-96588 dd 27.06.2018 | 007/BU2/02-01/00307 dd 26.11.2018 | 4300-103191 dd 12.12.2018 |  | 2018-12-09 |  | 2019-04-20
1.15. | Preliminary Safety Analysis Report (PSAR) Chapter 15 |  | 4300-101101 от 23.10.2018 4300-102994 dd 09.12.2018 | till 25.01.2019 |  |  | 2018-12-09 |  | 2019-04-20
1.16. | Preliminary Safety Analysis Report (PSAR) Chapter 16 |  | 4300-99536 от 12.09.2018 4300-101614 от 06.11.2018 4300-104028 01.01.2019 | 007/BU2/02-01/00308 от 26.11.2018 | 4300-103050 dd 10.12.2018 |  | 2018-12-09 |  | 2019-04-20
1.17. | Preliminary Safety Analysis Report (PSAR) Chapter 17 |  | 4300-96120107 dd 05.02.2018 | 007/UKS-07/09/00057 dd 07.08.2018 |  |  | 2018-12-09 | 007/BU2/02-01/00378 dd 16.01.2019 | 2019-04-20
1.18. | Preliminary Safety Analysis Report (PSAR) Chapter 18 |  | 4300-94394 от 26.04.2018 | 007/BU2/02-03/00261 от 05.10.2018 | 4300-100638 от 13.10.2018 4300-103049 dd 10.12.2018 | 007/BU2/02-01/00367 dd 28.12.2018 | 2018-12-09 |  | 2019-04-20
1.19. | Preliminary Safety Analysis Report (PSAR) Chapter 19 |  | 4300-99305 dd 06.09.2018 4300-99744 dd 22.09.2018 |  |  |  | 2018-12-09 |  | 2019-04-20
1.20. | Preliminary Safety Analysis Report (PSAR) Chapter 20 |  | 4300-102246 dd 21.11.2018 | till 30.01.2019 |  |  | 2018-12-09 |  | 2019-04-20
1.21. | Preliminary Safety Analysis Report (PSAR) Chapter 21 |  | 4300-91288 dd 21.01.2018 4300-96589 dd 27.06.2018 | 15.05.2018 007/BU2/02-01/00109 26.07.2018 007/BU2/02-01/00176 |  |  | 2018-12-09 |  | 2019-04-20
2 | Management system Programme for Construction |  | 4300-96120629 от 18.032018 | 06.09.2018 №007/46-11/06-1667 |  |  | 2018-12-09 |  | 2019-04-20
2.1. | Management system procedures related to quality and safety for Construction |  | LTR-4300-97121681 от 17.06.2018 LTR-4300-97121988 от 08.07.2018 LTR-4300-97121987 | 06.09.2018 №007/46-11/06-1667 |  |  | 2018-12-09 |  | 2019-04-20
3 | Preliminary Plan for Security Arrangement | [5 empty] | 2018-12-09 |  | 2019-04-20
4 | Documents on design of physical protection system |  | 4300-102840 dd 05.12.2018 | till 30.01.2019 |  |  | 2018-12-09 |  | 2019-04-20
5.1 | PSA level 1 |  | 4300-93241 от 13.03.2018 4300-96093 от 14.06.2018 | 007/BU2/02-01/00081 от 12.04.2018 007/BU2/02-01/0166 от 20.07.2018 | till 30.01.2019 |  | 2018-12-09 |  | 2019-04-20
5.2 | PSA level 2 |  | 4300-93241 от 13.03.2018 | 007/BU2/02-01/00081 от 12.04.2018 |  |  | 2018-12-09 |  | 2019-04-20
5.3 | PSA on seismic |  | 4300-93241 от 13.03.2018 4300-97204 от 15.07.2018 | 007/BU2/02-01/00081 от 12.04.2018 |  |  | 2018-12-09 |  | 2019-04-20
5.4 | PSA on fire |  | 4300-92670 от 28.02.2018 4300-97204 от 15.07.2018 | 007/BU2/02-01/00074 от 05.04.2018 |  |  | 2018-12-09 |  | 2019-04-20
6.1 | Environmental Report | [5 empty] | 2018-12-09 |  | 2019-04-20
6.2 | Programme for Determining the Baseline Environmental Conditions | [5 empty] | 2018-12-09 |  | 2019-04-20
7 | The schedule of Bushehr-2 NPP Construction | [5 empty] | 2018-12-09 |  | 2019-04-20
8 | Site Progress Report | [5 empty] | 2018-12-09 |  | 2019-04-20
9 | Programme and schedule for recruiting, training and qualifying staff for Operation and Maintenance of Bushehr-2 NPP | [5 empty] | 2018-12-09 |  | 2019-04-20
10 | Measures proposed to comply with applicable Safeguards Agreement | [5 empty] | 2018-12-09 |  | 2019-04-20
11 | Description of full-scaled simulator |  | 11.06.2018 №4300-95891 | 007/UKS-03/04/00014 dd 21.08.2018 | LTR-4300-97123423 dd 21.10.2018 |  | 2018-12-09 |  | 2019-04-20
12 | Preliminary description of the Emergency Preparedness and Response |  | 4300-97123340 dd 15.10.2018 | 007/UKS-03/04/00029 dd 10.01.2019 |  |  | 2018-12-09 |  | 2019-04-20
13 | Conceptual Plan for Ageing Management |  | 4300-97123341 dd 15.10.2018 | 007/UKS-03/04/00030 dd 16.01.2019 |  |  | 2018-12-09 |  | 2019-04-20
14 | Conceptual plan for maintenance, surveillance, and in-service inspections |  |  | 007/UKS-03/04/00028 dd 13.12.2018 |  |  | 2018-12-09 |  | 2019-04-20
15 | Preliminary Plan for decommissioning |  | 11.06.2018 №4300-95891 | 07.08.2018 №007/UKS-03/04/00009 |  |  | 2018-12-09 |  | 2019-04-20
16.1. | Design Considerations against Large Scale Natural Phenomena/Disasters and Terrorist Attacks -Construction aspects |  | 11.06.2018 №4300-95891 LTR-4300-97123423 dd 21.10.2018 |  |  |  | 2018-12-09 |  | 2019-04-20
16.2. | Design Considerations against Large Scale Natural Phenomena/Disasters and Terrorist Attacks -Operation aspects |  |  | 007/UKS-03/04/00014 dd 21.08.2018 |  |  | 2018-12-09 |  | 2019-04-20
17 | Design Considerations against Loss of Ultimate Heat Sink |  | 11.06.2018 №4300-95891 | 007/UKS-03/04/00014 dd 21.08.2018 | LTR-4300-97123423 dd 21.10.2018 |  | 2018-12-09 |  | 2019-04-20
18 | Design Considerations against Loss of Electrical Power |  | 11.06.2018 №4300-95891 | 007/UKS-03/04/00014 dd 21.08.2018 | LTR-4300-97123423 dd 21.10.2018 |  | 2018-12-09 |  | 2019-04-20
19 | Engineering Measures against Severe Accidents including measures to suppress radioactive materials dispersion, measures to prevent containment vessel failure, and measures to prevent core damage |  | 11.06.2018 №4300-95891 | 007/UKS-03/04/00014 dd 21.08.2018 | LTR-4300-97123423 dd 21.10.2018 |  | 2018-12-09 |  | 2019-04-20
20 | Engineering Measures and Response against Commercial Aircraft Crash |  | 11.06.2018 №4300-95891 | 007/UKS-03/04/00014 dd 21.08.2018 | LTR-4300-97123423 dd 21.10.2018 |  | 2018-12-09 |  | 2019-04-20
Approved _______________________/____________________
Approved _______________________/____________________
Approved _______________________/____________________
Approved _______________________/____________________
Approved _______________________/____________________
Note on K4: Reza Nazari: Dates in this column shall be deleted because none of the documents will be approved by INRA (agreement may be receieved)